Annual Review - Summary Sheet

Title: Prosperity Fund Global Anti-Corruption Programme (GACP)
Programme Value: £45m		Review Date: November 2019
Programme Code: GB-GOV-50-PF-07-ACO (including GB-GOV-3-PF-ACO-921; GB-GOV-3-PF-ACO-912; GB-GOV-3-PF-ACO-913; GB-GOV-3-PF-ACO-911)	Start Date: Some project transitional activity started in April 2017 but the full programme started in December 2018 following Chief Secretary to the Treasury approval in October 2018	End Date: March 2022

Summary of Programme Performance
Year	2018[1]	2019
Programme Score	U	A
Risk Rating	U	Moderate
[1] A pre-programme annual review was undertaken of transitional project activity in August 2018, but the programme log frame was not reviewed as it was not fully developed at that point in time.

Summary of progress and lessons learnt since last review
The programme is now in full delivery mode following approval by Chief Secretary to the Treasury in October 2018 and was publicly launched by Minister Field at the Organisation for Economic Co-operation and Development (OECD) Anti-Corruption and Integrity Forum in March 2019. Eight of the nine projects in the programme are mobilised and delivering outputs. One project is currently being scoped to complement other projects in the programme.
At the output level, the programme has exceeded all of its targets over the last year. The programme has begun to deliver intermediate outcomes and outcomes, albeit some targets have been exceeded, some achieved and some missed. Intermediate outcomes and outcomes delivered to date include new legalisation reform, new anti-corruption strategies, company information on the OpenOwnership register, online systems for the disclosure of Extractives Industries Transparency Initiative (EITI) data, grand corruption law enforcement actions, potentially recoverable stolen assets identified, and users accessing new anti-corruption knowledge products.
Overall, the programme’s theory of change is still valid, with the log frame and programme architecture aligned to it. The theory of change has been enhanced since the business case to better explain the linkages within the programme and the steps between project outputs, a reduction in corruption and resulting primary and secondary impact. These changes build on the version within the business case and are consistent with it. The log frame has also been enhanced significantly (e.g. adding annual targets and milestones), as is expected for a programme as it moves from design to delivery, including expanded and updated assumptions. Again, the underlying approach and rationale for the programme remains as it was in the business case.
Regarding the value for money (VfM) position, the programme remains on track to deliver good value for money in line with the business case. Some aspects of the programme are likely to deliver results before others, and some aspects are likely to be more transformational than others. The biggest opportunity going forward for greater efficiency and effectiveness is coordination between the projects and more strategic prioritisation of resources in geographies and projects that are demonstrating greater cost-effectiveness. On equity, the programme has made good overall progress in identifying how gender and inclusion can be mainstreamed into projects, however additional gender and inclusion partner expertise is required to ensure plans are successfully implemented.
The phased mobilisation of individual projects, some pre-dating the mobilisation of the programme as a whole, resulted in some missed opportunities for synergies to be designed-in from the start. The programme team has focused on identifying where potential synergies exist and ensuring these are realised – this work should continue.
The overriding risk to the successful delivery of the programme, and the main determining factor in achieving the intended outcomes and impact, is the political will to implement reform, address corruption, repatriate stolen assets and charge those that have embezzled state funds. The programme’s approach is sufficiently alive to this, but will need to be kept under continuous review.
A number of key lessons have been captured over the last year, these include:
- Initiating selected projects before the programme began has resulted in missed opportunities
- Work to plan and realise synergies is important, takes time and needs managing
- Significant work has taken place to improve communications between projects, across projects and with Posts, involving both Whitehall project leads and delivery partners
- Although progress has been made, further work is required to ensure that all four Whitehall departments are actively managing activity as a single integrated programme.
List of recommendations for the next year
The key recommendations from this annual review are:
- By the of February 2020, the GACP programme team, in consultation with strategic partners, should review log frame milestones for accuracy and ambition, and indicators to ensure they are targeting the GACP’s value add. Furthermore, GACP should consider using indicative ranges if uncertainty is too high on deliverables.
- By the end of March 2020, the GACP programme team should facilitate a review of the comparative VfM and balance of investment across the projects in the portfolio to ensure that the programme’s overall impact and VfM is maximised, and table a paper to the GACP Strategic Board for endorsement.
- By the end of March 2020, the GACP programme team, in consultation with the Steering Group, should undertake detailed analysis, and potentially subsequent redesign, to further realise synergies within the programme, between projects in GACP and within countries of operation, but also across Prosperity Fund bilateral and thematic programmes. With a varied and complex programme, this will be an ongoing challenge, but there are specific examples from projects such as the OECD, GDS, BenOwn and UNODC, which should be addressed.
- By the end of March 2020, the GACP programme team, in consultation with DFID, should review whether the Extractives project would be better managed solely by DFID to reduce the administrative burden given its lack of strategic alignment with the GACP and Prosperity Fund, and table a paper to the GACP Strategic Board for consideration.
- By the end of May 2020, ALL project leads and partners should ensure that they have access to gender and inclusion expertise; and that gender and inclusion is fully embedded into reporting, project level implementation plans and delivery.

SRO Commentary
I am very grateful for the very thorough annual review that the team has undertaken.  This is the first substantial annual review of the programme with the vast majority of work now underway.  Having just taken on the role of SRO, I am reassured that the programme is beginning to bear fruit, with some elements performing extremely well.  I asked the team to focus on gender and inclusion in this review, and they have done a good job in considering this and providing recommendations for further work.  I support all of the recommendations to make the programme even more effective by testing that the funds are being spent in the best way across the various elements and that synergies between all parts are realised.
Louise Thomas
GACP SRO and Head of Global Economic Issues Department, Foreign and Commonwealth Office
JFU Commentary
We welcome the conclusion of this review and appreciate all its findings and recommendations. The review demonstrates great progress GACP has made over the past year in delivering a complex set of interventions that are high HMG political priorities and are often working in politically sensitive spaces. The effort put into developing M&E and programme management systems to knit together the programme’s varied portfolio of projects is evident. We also note with appreciation early results achieved by the programme, including in improving anti-corruption policies and extending the reach of international anti-corruption mechanisms. As the programme progresses, it is key that these reforms are facilitated through processes of implementation and the programme effectively navigates the political challenges encountered along these processes. We fully endorse recommendations made for exploring consolidating the programmes interventions to maximise its effectiveness and for cultivating deeper synergies with other PF programmes. We recommend that as part of this process the programme seeks to further build up its connections with processes of market development and inclusive growth, and the primary purpose and secondary benefits that arise from these.
Daniel Davis
Head, Prosperity Fund, Joint Funds Unit, National Security Secretariat, Cabinet Office

List of Acronyms
AML	Anti-Money Laundering
ASEAN	Association of Southeast Asian Nations
BenOwn	Beneficial Ownership
BODS	Beneficial Ownership Data Standard
CST	Chief Secretary to the Treasury
CTF	Counter-Terrorist Financing
DFID	Department for International Development
DIT	Department for International Trade
EA	East Africa
EU	European Union
EGPS	Extractives Global Programmatic Support
EITI	Extractives Industry Transparency Initiative
FATF	Financial Action Task Force
FCO	Foreign and Commonwealth Office
GACP	Global Anti-Corruption Programme
GDMP	Global Digital Marketplace Programme
GDS	Government Digital Service
GFAR	Global Forum on Asset Recovery
G&I	Gender and Inclusion
HMT	Her Majesty’s Treasury
HMG	Her Majesty’s Government
IACCC	International Anti-Corruption Coordination Centre
IFFs	Illicit finance flows
IRG	Implementation Review Group
JACU	Joint Ant-Corruption Unit
JFU	Joint Funds Unit
LF	Log Frame
MLA	Mutual legal Assistance
MoU	Memorandum of Understanding
MREL	Monitoring, reporting, evaluation and learning
M&E	Monitoring and evaluation
NCA	National Crime Agency
ODA	Official Development Assistance
OECD	Organisation for Economic Cooperation and Development
PF	Prosperity Fund
SAM	South America and Mexico
SEA	South East Asia
SOEs	State Owned Enterprises
SRO	Senior Responsible Owner
StAR	Stolen Asset Recovery Initiative
ToC	Theory of Change
UNCAC	United Nations Convention Against Corruption
UNOCD	United Nations Office on Drugs and Crime
VFM	Value for Money
WB	World Bank
XWH	Cross Whitehall

## A. INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/global-anti-corruption-programme
DevTracker Link to Log frame:	Not yet published

The programme directly delivers on specific UK commitments made at the London Anti-Corruption Summit in 2016 and supports the delivery of the UK’s Anti-Corruption Strategy.
The FCO-led Prosperity Fund Global Anti-Corruption Programme is deploying £45m to promote inclusive sustainable growth and increase global prosperity through tackling corruption – [insert hyperlink once published in December 2019]. The programme consists of eight projects delivered bilaterally, regionally and globally, with a final ninth being scoped. The bilateral investment, which is about 30% of the budget, goes to five out of the twelve Prosperity Fund priority countries: Colombia, Indonesia, Malaysia, Mexico and South Africa.
The objectives of the programme are to:
- Invest in introducing new policies, laws and regulations as well as strengthen existing ones
- Increase transparency across the public sector, on beneficial ownership and procurement systems
- Strengthen the ability to investigate and recover stolen assets
- Raise awareness of the causes and impacts of corruption, taking into account G&I considerations
- Identify, apply and disseminate good practice approaches.

In undertaking this Annual Review, covering the period August 2018 to July 2019, the review team undertook interviews with the HMG programme management team, HMG project managers (DFID, FCO, GDS, HMT and NCA), delivery partners, HMG staff at Posts, and beneficiaries/stakeholders from partner governments.
## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment
Primary purpose: the programme is on track for delivering against its three defined outcomes, with the fourth to be fully defined including baseline and targets. Due to the phasing of projects being initiated, progress against some outcomes is more mature than in others. Feedback from beneficiaries/stakeholders validates this conclusion, with tangible results being delivered, albeit it is understood that some of the projects are in an early phase of their delivery lifecycle. The programme’s theory of change (ToC), log frame (LF) and gender and inclusion (G&I) approach set out how inclusive growth, poverty reduction and gender equality are central to this fully Official Development Assistance (ODA) funded programme. These factors have been included with the design at both the programme and project level, with actions plans in place for G&I. The eight active projects deliver across the four outcomes to differing degrees:
Outcome One – improved policies, laws and regulations on anti-corruption (StAR, UNCAC, FATF projects): Of the two planned outcome milestones, both were exceeded. For the intermediate outcomes (countries demonstrating commitment to improve or adopt new anti-corruption policies, laws and regulations), two milestones were exceeded and one achieved.
Outcome Two – increased use of transparent systems (BenOwn, Extractives, GDMP projects): Of the one planned outcome milestone, it was exceeded. For the intermediate outcome (research undertaken and plans established to implement transparency systems), one was exceeded, one missed and one was not expected to deliver.
Outcome Three – increased success of anti-corruption law enforcement action (StAR, IACCC projects): Of the three outcome milestones, all were exceeded. For the intermediate outcome (increased number of anti-corruption investigations), one target was achieved and two (both IACCC) were exceeded.
Outcome Four – increased awareness of the causes and impacts of corruption including G&I; and knowledge and application of good practices/approaches to address corruption in priority countries (OECD, StAR, BenOwn, FATF, UNCAC projects): An approach to measuring progress at the outcome level is still being developed by the programme team, with baselining activity planned for later in 2019-20 financial year. This will involve ‘communities of experts’ to baseline and monitor GACP’s progress, as well as establishing the governance process to adapt and respond to the experts’ views. This is an untested and new approach in the Prosperity Fund (PF) for gauging progress at outcome and impact levels. The GACP should share findings of the approach across the PF. For the intermediate outcome (increased understanding of the causes and impacts of corruption and good practice approaches), performance is mixed with three targets exceeded, one being achieved and two being missed.
Secondary benefits (new economic opportunities for international, including UK business, and mutually beneficial economic relationships): the programme has developed a strong narrative explaining how the programme enables the delivery of wider secondary benefits (principally an improved business environment), and how secondary benefits and primary benefits are intrinsically linked and mutually reinforcing. Secondary benefits are explicitly included within the ToC which also sets out how the programme’s four outcomes lead to both primary and secondary benefits. Further work is currently taking place with DIT to align activity on tackling corruption in target markets and to ensure secondary benefits are maximised. The GACP programme team should consider how wider ‘soft power’ benefits can be realised and captured.
There are no significant changes to expected outcomes or impact compared to what was described in the approved business case, albeit the narrative explaining how they will be achieved and measured has been enhanced. This is as expected for a complex programme such as GACP as it moves from design into delivery.
Overall output score and description
Each of the four outputs is examined in the main body of the report. Good overall progress has been made against each of these outputs with all indicators being achieved or exceeded.
Key lessons
A number of key lessons have been captured by the programme over the last year, these include:
- Initiating selected projects before the programme began has resulted in missed opportunities e.g. the ability of projects to focus on common countries
- Work to plan and realise synergies is important, takes time and needs managing e.g. the link between the work on procurement transformation, behavioural science and beneficial ownership data
- Significant work has taken place to improve communications between projects, across projects and with Posts, involving both Whitehall project leads and delivery partners. This has resulted in improvements, but due to complex programme structure with four Whitehall departments, nine projects and 10 delivery partners, this needs to be kept under review
- Although progress has been made, further work is required to ensure that all four Whitehall departments are actively managing activity as a single and integrated programme.

The overall validity of ToC remains. The ToC has been enhanced since the business case to better explain the linkages within the programme and the steps between project outputs, a reduction in corruption and resulting primary and secondary impact. These changes build on the version within the business case and are consistent with it. The LF has also been enhanced significantly (e.g. adding annual targets and milestones), as is expected for a programme as it moves from design to delivery, including expanded and updated assumptions. Again, the underlying approach and rationale for the programme remains as it was in the business case.
The programme as a whole has captured lessons and shared these across Whitehall, and with delivery partners as appropriate. This includes with Joint Anti-Corruption Unit (JACU) who facilitate wider sharing as appropriate across HMG.
Key actions
The key recommendations from this annual review are:
- By end of March 2020, the GACP programme team should facilitate a review of the comparative VfM and balance of investment across the projects in the portfolio to ensure that the programme’s overall impact and VfM is maximised, and table a paper to the GACP Strategic Board for endorsement.
- By the end of March 2020, the GACP programme team, in consultation with the Steering Group, should undertake detailed analysis, and potentially subsequent redesign, to further realise synergies within the programme, between projects in GACP and within countries of operation, but also across PF bilateral and thematic programmes. With a varied and complex programme, this will be an ongoing challenge, but there are specific examples from projects such as the OECD, GDS, BenOwn and UNODC, which should be addressed.
- By the end of May 2020, ALL project leads should ensure that G&I is fully embedded into project level implementation plans.
- By the of February 2020, the GACP programme team, in consultation with strategic partners, should review LF milestones for accuracy and ambition, and indicators to ensure they are targeting the GACP’s value add. Many of the targets were over achieved this year. Furthermore, GACP should consider using indicative ranges if uncertainty is too high on deliverables.
- By the end of March 2020, the GACP programme team, in consultation with DFID, should review whether the Extractives project would be better managed solely by DFID to reduce the administrative burden given its lack of strategic alignment with the GACP and PF, and table a paper to the GACP Strategic Board for endorsement.
- By the end of March 2020, the GACP team in collaboration with cross-Whitehall partners, should develop future plans and funding options beyond the end of the programmes as currently planned, and table a paper to the GACP Strategic Board for consideration.
Summary of changes to the logframe since the last annual review
This is the first annual review undertaken of the programme since it was approved (October 2018) and publicly launched (March 2019). A pre-programme annual review was undertaken of transitional project activity in August 2018, but the programme LF was not reviewed as it was not fully developed at that point in time.

## C: DETAILED OUTPUT SCORING

Output Title	Improved assessments of country level anti-corruption systems and associated provision of technical support.
Output number per LF		One	Output Score	A+
Risk:		Minor	Impact weighting (%):	15
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
Number of additional FATF regional bodies and member countries supported to / I) Carry out quality AML/CTF assessments / ii) Improve knowledge of how to comply with FATF Standards through research/training	25	42: Due to GACP funding, the FATF Secretariat has had the resources to support the review processes of the following countries, in order to improve their quality and drive improved and faster implementation of the FATF Standards: Albania, Belarus, Benin, Botswana, Burkina Faso, Cabo Verde, Colombia, Cook Islands, Dominican Republic, DRC, Ethiopia, Haiti, Indonesia, Jordan, Malawi, Malaysia, Mali, Mauritania, Mauritius, Moldova, Morocco, Myanmar, Nicaragua, Pakistan, Palau, Panama, Peru, Philippines, Senegal, Solomon Islands, Tajikistan, Thailand, Tunisia, Uganda, Vanuatu, Zambia, Zimbabwe, Sierra Leone and Tanzania; and three assessor training events: Tanzania (April), Oman (February) and Senegal (March).
Number of technical assistance packages delivered to countries/ regions.	Total is 8. / SEA: Procurement: 1 (Vietnam), Investigations: 2 (Laos and Cambodia), Asset recovery: 1 (Malaysia) / EA: Procurement: 1 (Tanzania), Whistleblowing: 2 (Tanzania and Ethiopia) / SAM: Regional event: 1	8= / Identification of corruption risks in public procurement in rural areas in Vietnam’s central provinces and training of procurement officers to mitigate corruption risks (June). / Manual on conducting corruption investigations in Cambodia developed (May). / Training with state inspectorate and anti-corruption authority in Laos PDR on corruption and financial investigations (March)SE Asia Regional Workshop on Promoting Beneficial Ownership Transparency (July) / Creation of the national anti-corruption in procurement group in Tanzania (April) / Final draft of the whistleblowing protection regulation of Tanzania to be adopted during phase II of the in-country capacity building (May) / Support to Ethiopia to develop their whistle-blowing and witness protection systems (July) / South America and Mexico Regional Conference on Fast-Tracking UNCAC (May).
Number of concrete inputs into key global asset recovery events.	5	27 = / CARIN network meeting (05/09/2018, the Hague, Netherlands) / International Association of Prosecutors (12/09/2018 Johannesburg) / Security Council meeting to focus on corruption and conflict (10/09/2019, New York) / UNGA side event on IFFs (28/09/18, NY) / IACC Copenhagen (22-24/10/18) / International Corruption Hunters Alliance (25/10/18, Copenhagen) / StAR/UNODC Expert Group Meeting on legal professional privilege and beneficial ownership / UNODC Expert Group meeting on Vast Quantities of Assets, (3-5/12/18 Vienna) / ARIN-AP meeting, steering group, AGM, regional workshop (11/18) / International Law Institute Anti-Corruption Seminar, (11/18) / ARIN-CARIB (16-18/11/18) / G24 technical meeting in Lima on IFFS / Conference on 'concrete modalities of stolen assets restitution: the way forward” (co-organized by the French Senate and Transparency International France) / Closed half day session organised by Transparency International (22/03/19, Paris) / OECD Global Anti-Corruption and Integrity Forum (March 2019,Paris) / Frozen: How can the EU fight global corruption? (06/03/19, Brussels) / UNODC Expert Meeting on the return of stolen assets (7-9/05/19, Ethiopia) / OAS - Experts Group on Money Laundering Control (4-5/06/19, Washington DC) / Global Illicit Trade Summit (25/06/19, Ethiopia) / 10th Session of the UNCAC Implementation group (30/05/19, Vienna) / UNODC Expert Group Meeting on Corruption (12-14/06/19, Oslo) / UNDP Conference on Armenia's anti-corruption strategy (04/19, Yerevan) / International Cooperation to Combat Illicit finance(05/19, New York) / African Union Dialogue in preventing IFFs (05/19, Ethiopia) / RECO's 20th anniversary (05/19, Strasbourg) / IACCC has presented and influenced the Commonwealth Anti-Corruption Benchmarks Expert Review meeting held in London. In addition to providing technical assistance, IACCC referral for PEP grand corruption cases is now a recommendations under the Commonwealth benchmarks (May 2019) / IACCC presented and provided technical assistance to the Interpol 25th Global Programme on Anti-Corruption, Financial Crime and Asset Recovery workshop for west African states held in Accra, Ghana (July 2019).

Key Points
Overview: This output is covered by three projects. Implementing the United Nations Convention Against Corruption (UNCAC) (implemented by UNODC), which has met its milestones, and Strengthening Anti-Money Laundering Systems (FATF) and Supporting the Global Recovery of Stolen Assets (StAR) that have greatly exceeded progress milestones. As all output milestones have been exceeded, intermediate outcome milestones either achieved or exceeded, and the outcome milestone exceeded, this output is scored as ‘A+’.
Strengthening Anti-Money Laundering Systems (FATF): The 39 FATF country assessments completed this year supported by the GACP have produced national assessments of anti-financial crime measures, including efforts to tackle corruption, with corresponding recommendations. The project has improved the quality of these assessments and their recommendations, and ensured these reports are completed and published on time. Comprehensive reviews of national anti-financial crime efforts have provided a road map and entry point for other interventions aiming to improve capacity to tackle corruption by other GACP projects and other HMG or international actors.
Implementing the United Nations Convention Against Corruption (UNCAC): This output continues to support the ToC from the technical assistance by the UNODC. This year it has focused largely on follow up work to help implement the recommendations set at the regional conferences for Eastern Africa (Feb 2017) and South East Asia (Jan-Feb 2017) e.g., creating a manual on carrying out corruption cases in Cambodia and assistance provided to Tanzania to develop a whistleblowing law. This year also saw the launch of the platform for South America and Mexico (May 2019). This brought technical experts from the region together to draft a set of recommendations which were then debated and finalised by political figures. This process also involved civil society and business representatives.
Supporting the Global Recovery of Stolen Assets: This output concentrates on StAR’s work to make sure that asset recovery is an important consideration of global change-makers and that best practice is shared. StAR’s input to regional and global events also helps to ensure that there is common understanding with regards to asset recovery, helping to make processes more compatible. StAR’s involvement for the listed events varies, often including planning, leading discussions and moderating sessions. Often their role includes involving civil society in the panels, e.g. for the UNCAC Implementation Review Group (IRG) StAR organised a briefing with representatives of Transparency International’s national chapters as well as a side event on data collection. This work aligns with StAR funding provided by DFID under its I-ACT programme.
In interviews with FATF and StAR, both suggested the milestones needed to be reviewed and indicators need to more accurately reflect the quality of outputs, albeit difficult to measure. On FATF, this was about trying to capture the positive feedback loop the GACP support created in encouraging more participation, more attention to follow-up actions and quicker implementation, which simultaneously strengthens the regional bodies’ advisory role. On StAR, there needed to be a clearer distinction in the type of input and event, from those involving heavy lifting (e.g. co-organising) or limited effort (panel member), even if there is an agreed definition of concrete inputs as “both oral and written asset recovery policy contributions, such as: presentations, statements delivered, and papers presented.” Furthermore, given the unique role that StAR has in setting standards and approaches to facilitate asset recovery, there is a desire from StAR to shift towards knowledge products. While StAR’s role in supporting the events is important, reinforcing the global knowledge products on asset recovery may potentially be an even better fit with the wider aims of GACP and PF.
Summary of responses to issues raised in previous annual reviews (where relevant)
This was previously “improved anti-corruption & AML policies, legislation, and institutions”. The previous recommendation was to deliver more synergies, consult on the sustainability of outcomes/impacts and, with delivery partners, adapt timelines for milestones appropriately. In consultation with strategic and implementing partners, the LF was restructured so that the output level reflected the GACP’s direct support, distinguishing from the outcome-level indicators around the implementation of policies/laws. A workshop was used to explore synergies at June 2019’s (working level) Steering Group. From this, links between UNODC technical assistance in Ethiopia and StAR input to African Union events and the Global Illicit Trade Summit in Ethiopia were established.
Output One recommendations:
1. Strengthening Anti-Money Laundering Systems. Output and outcome indicators and milestones need to be revised. The value-add in country-level anti-corruption systems is the improved quality of the process in report production. This is different from the reports themselves (i.e. FATF outputs) which are captured in Output 4.
2. Supporting the Global Recovery of Stolen Assets:
  1. The “concrete inputs” is too vague and the events need to clearly distinguish between scale of effort.
  2. GACP should explore how to support StAR in shifting its focus to global knowledge products (with its unique expertise) from supporting input to global asset recovery events. Some further prioritisation will be needed on the latter, which should be done in consultation with other strategic and implementing partners and Embassies/High Commissions.
Output Title	Research undertaken and plans established to implement transparency systems.
Output number per LF		Two	Output Score	A
Risk:		Minor	Impact weighting (%):	40
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
Number of new procurement system developmental phases (pre-discovery, discovery, alpha, beta) completed in target countries, disaggregated by country and region.	10	12 = / August 18 – scoping visit completed in 3 countries / Feb 19 – inception missions completed in 4 countries / Discovery completed in all five countries.
Number of countries receiving technical / financial support for the development of EITI or BO roadmaps, commodity trading approaches, and undertaking mainstreaming activities that go beyond the EITI minimum standard (cumulative).	Beneficial ownership: 8 / Commodity trading: 5 / Mainstreaming: 5 (feasibility studies and online systems for disclosure of EITI data)	BO: 8 = / All countries have roadmaps (Afghanistan, DRC, Myanmar, Zambia, Ghana, Liberia, Malawi, Nigeria). / Specific support activities delivered in Ghana, Afghanistan, Malawi, Myanmar, and Nigeria) / Commodity Trading: 8 = / Cameroon, Colombia, Mauritania, Mozambique, Cote d'Ivoire, Republic of Congo are disclosing improved information on commodity sales in latest report. / Indonesia is working on scoping its second commodity trading report / The secretariat is also encouraging more countries to join the targeted effort, such as Iraq. / Mainstreaming feasibility studies: 13 = Armenia, Ghana, Liberia, Madagascar, Malawi, Mauritania, Mexico, Peru, Senegal, Sierra Leone, Ukraine, Mozambique, and Zambia.
Number of additional countries assisted to open national company beneficial ownership registers.	2	2 = / Continued support to Ukraine, Kyrgyz, Nigeria. / Technical assistance started with Armenia and Kenya.

Key Points
Overview: This output is covered by three projects. Supporting Global Digital Marketplace Platforms, which has met its milestones; Improving Transparency of Company Beneficial Ownership (BenOwn), which has exceeded its milestones; and Combatting Corruption in Oil, Gas and Mining Sectors (Extractives), which has achieved and exceeded its milestones. Although all output milestones have been exceeded and the one outcome milestone exceeded, at the intermediate outcome level one milestone was exceeded and one was one missed. This, together with a concern over the alignment of the Extractives project with the programme’s ToC, leads this output is scored as ‘A’.
Supporting Global Digital Marketplace Platforms: The GDS-led Global Digital Marketplace Programme (GDMP) has completed the five discovery reports, which include the findings from scoping and inception missions, for the five selected countries (South Africa, Mexico, Indonesia, Malaysia, Colombia) with recommendations. The project remains in an early stage but has demonstrated the GACP’s ability to seize opportunities when they arise (e.g. Malaysia). Given the innovative nature of the project, some adaptation has been needed to changing policy priorities and administrations. This has led to parts of the project being more advanced, e.g. Mexico, Indonesia and South Africa. There has been a learning curve for GDS in establishing the project and relationships with various, and at times changing, stakeholders. However, there is room for two further improvements to ensure the programme outcomes are deliverable. First, as a project delivering in-country where there is potential overlap with GACP projects, communication is key and the Embassies/High Commission and GACP team are critical facilitators in ensuring this is managed effectively to ensure that local buy-in is maintained, potential emerging risks are managed and delivery choices remain rooted in maximising opportunities. Second, one area with little progress is G&I. Although GDS is now including G&I elements as evaluation criteria in all its external procurements to support GDMP delivery, and is starting desk-based research on G&I in the procurement space (which will identify opportunities for GDS to embed G&I initiatives more directly into project activities - lessons from which will be shared across GACP, including downstream where actions are having an effect), consideration of the genderised implications of changing procurement needs to be factored from the start. The activity risks being gender blind if G&I is not a more central priority for GDMP.
Combatting Corruption in Oil, Gas and Mining Sectors (Extractives): The DFID transparency work with the EITI Secretariat (~£500k) contributes towards beneficial ownership by deepening its implementation in the vulnerable sector of extractives. The work is focused on running pilots in three areas:
- Developing beneficial ownership roadmaps
- Developing approaches to commodity-trading transparency
- Improving the mainstreaming of EITI standards in reporting, e.g. more concise, accuracy of date, etc.

Over the last year, the project has exceeded expectations against the LF milestones. An additional benefit is this supports the EITI Secretariat’s targeted effort to influence more countries to uptake in commodity trading transparency.
In addition under this project, GACP contributed £1m in April 2018 to the World Bank’s Extractives Global Programmatic Support (EGPS) Trust Fund. The Trust Fund has multiple aims, including governance and transparency, targeting resource-rich developing countries, so their extraction is used sustainably and transparently to reduce poverty and boost sustainable economic growth. The EGPS selects, funds and monitors both country-specific and global extractives sector-related activities that are implemented either by a WB team (Bank Executed—BE) or a client country that has received an EGPS grant under WB supervision (Recipient Executed—RE). Through EGPS support, the WB supported EITI implementation in 26 countries, which is more than half of the eligible EITI implementing countries. The agreed milestone with EGPS, which has not been included in the programme, was to support six new country grants. However, by August 2019, five grant proposals have been approved and endorsed by the Steering Committee (Madagascar, Chad, Ecuador, Dominican Republic, Senegal) and three more were approved based on the prior feasibility assessment. These results have not been independently verified. However, DFID is satisfied with the progress made, but recognise there is room for improvement on results reporting. There are no plans for new support of the World Bank EGPS under GACP.
However, the project benefits are primarily aimed at DFID priority countries, aside from Nigeria, Mexico and Colombia – PF priority countries – and extractives is not a PF priority sector. Therefore this project seems poorly aligned to the GACP ToC and LF outcomes.
Improving Transparency of Company Beneficial Ownership (BenOwn): The number of additional countries assisted to open national company beneficial ownership registers include Armenia (MOU signed w/c 27th October) and Kenya. OpenOwnership has continued to provide support to Ukraine, Kyrgyz and Nigeria. Technical information was provided to Ukraine to support their implementation of beneficial ownership. Implementation guidance for the Ukraine pilot has been updated with examples in line with the Beneficial Ownership Data Standard (BODS). New regulations for beneficial ownership transparency, to which OpenOwnership provided significant inputs, were approved by Kyrgyz Republic mining licensing authority and are on course to be adopted. More countries are likely to come on board as a direct result of the beneficial ownership leadership group that OpenOwnership convenes and the campaign that JACU is leading across HMG towards a global norm of beneficial ownership transparency. Currently most of the companies on the global register come from the UK.
Three areas for improvement: 1) The number of countries, as a result of EU regulation, is expected to significantly increase when reporting against the milestone in next year’s annual review, so this should be revised in line with expectations and ambition. 2) The countries contributing companies focus remains broadly outside GACP and PF country priorities. That said, there is strategic alignment with GACP and synergies with other GACP projects. Expanding the geographic coverage of the project should be assessed. 3) While this project is working actively on encouraging more countries to establish open registers (which are then included in the Open Ownership register), there is an opportunity to greater stimulate the demand-side (law enforcement, civil society, businesses, investigative journalists etc) to encourage the use and application of the Global Open Ownership register, this should be investigated with OpenOwnership.
Summary of responses to issues raised in previous annual reviews (where relevant)
The previous output related to this was ‘developing countries have robust systems in place to minimise opportunities for corruption to take place’. This had a recommendation “projects include follow up on implementation of standards and tools in their delivery plans to ensure return on investment (e.g. countries are not just signing up to standards/tools without application)”. In response, the programme LF has been re-structured to focus the output level on the necessary phases or assistance required to ensure that partner countries have the capacity and capability to implement new systems (outside the control of GACP) – the outcome indicator.
Output Two Recommendations
GDMP: To fully capitalise on opportunities, such as links between BenOwn and GDMP, GDS, Embassies/High Commissions and GACP, and where necessary other project partners, need to urgently:
1. Develop a genderised understanding of the procurement space
2. Develop a clear forward workplan and communications on visit plans and objectives.
1. Extractives: This project appears poorly matched in its country and sector focus with wider GACP and PF aims. The GACP Strategic Board should consider if it would not be more effective and efficient for DFID alone to be the sole HMG partner for delivering in the extractives sector.
2. BenOwn:
1. The focus on GACP countries of operation is limited. The GACP programme team, in conjunction with DFID, JACU and OpenOwnership, should explore the scope for prioritising GACP countries, considering political will and commitment to action.
2. As part of a longer term strategy, the GACP programme team should agree (if not already established), in conjunction with DFID, JACU and OpenOwnership, plans on how users can make best use of database to ensure the transparency impact of registers is being realised.

Output Title	Increased international capacity to undertake anti-corruption investigations.
Output number per LF		Three	Output Score	A+
Risk:		Minor	Impact weighting (%):	14
Risk revised since last AR?		n.a.	Impact weighting % revised since last AR?	n.a.

Indicator(s)	Milestones	Progress
Number of IACCC deployments and case-specific partnerships with other anti-corruption organisations and initiatives.	2 (1 deployment, 1 major coordination)	7 = / 5 deployments (2 in Q2, 3 in Q3) / 2 case-specific partnerships with ICAR.
Number of new referrals into the IACCC (cumulative).	16	35 (65 total cumulative)
Number of delegations received by the IACCC.	30	41 (71 cumulative total)
Number of IACCC members.	By March 2019 - the IACCC will have 9 participant agencies	9 participatory law enforcement agencies (AFP, RCMP, NZP, NZSFO, CPIB, NCA, FBI, HSI, INTERPOL).
Number of new IACCC cases involving co-ordination of multiple jurisdictions.	2	2 cases required multi-jurisdiction coordination between August 2018 and July 2019 (one supported the return of several billion dollars to the affected state).
Number of additional scoping visits carried out by StAR.	1	4 = Ecuador and Pakistan, Colombia, Malaysia.

Key Points
Overview: This output is covered by two projects. Supporting the Global Recovery of Stolen Assets (implemented by StAR) which has exceeded its milestone and Co-ordinating International Intelligence Sharing on Grand Corruption (IACCC) which has achieved two milestones and exceeded three. In addition, as all the intermediate outcome and outcome milestones have either been achieved or exceeded, this output is scored as ‘A+’.
Co-ordinating International Intelligence Sharing on Grand Corruption (IACCC): The IACCC has achieved a number of notable outputs in the last year, including:
- o £68 million worth of London property was served with forfeiture notices as a result of the IACCC’s support to a major international case involving five separate jurisdictions. This same investigation has seen the IACCC serve court summons on a global bank to face charges in foreign jurisdictions and continues to pursue additional London property identified by the IACCC.
- o Over $2 billion was returned to an affected state following the assistance of the IACCC as part of a complicated multi-jurisdictional investigation.
- o Approximately £2.5 million of stolen assets were forfeited in an affected state following IACCC support.
- o One public official suspected of corruption offences was arrested in an affected state following IACCC support. This brings a total of five Politically Exposed Persons (PEPs) arrested as a result of IACCC intelligence.

To demonstrate how IACCC supported cases are progressing beyond the intelligence collection and sharing stage, 14 Mutual Legal Assistance (MLA) requests have been submitted to IACCC member jurisdictions following IACCC support. MLAs are critical to convert intelligence into evidence and are a good indicator of case progression towards a judicial outcome. In May 2019 the IACCC attended the Commonwealth Anti-Corruption Benchmarks Expert Review meeting and as a result the IACCC is listed as a good practice example for international cooperation. In July 2019 the IACCC presented and provided technical assistance to the Interpol 25th Global Programme on Anti-Corruption, Financial Crime and Asset Recovery workshop for West African states held in Accra, Ghana. Interpol deployed to the IACCC in April 2019; their reach, network and standing within developing countries will help reinforce the IACCC’s mission and capabilities. The IACCC Governance Board endorsed the concept of expanding membership to smaller financial centres, with new associate members expected to join in early 2020.
Supporting the Global Recovery of Stolen Assets (StAR): the results of the scoping visits by StAR vary by country. For example, in Ecuador, StAR’s work following the scoping visit helped to facilitate the creation of a new inter-institutional asset recovery group (workshop help in November 2018).
Summary of responses to issues raised in previous annual reviews (where relevant)
The previous annual review recommended that the programme “consult with bi-lateral partners to agree how best to enhance and maintain relationships post events” and “completion estimates [for outcomes] for international corruption cases are consulted when drafting milestones”. In response, GACP’s LF has since been restructured in consultation with strategic and implementing partners. This remains an ongoing process and the GACP team will look to update indicators and milestones as new evidence emerges.
Output Three Recommendations
1. StAR: investigate how the work of StAR relates to other projects in the programme and how further integration can be achieved to help maximise the overall impact of the programme.
2. IACCC: investigate future funding options for the IACCC to ensure sustainability of their operations, and potentially expanding its operations to meet rising demand.
3. StAR / IACCC: given the over achievement of some targets this year, review future year targets to assess whether they are ambitious enough.

Output Title	Gathering and disseminating new evidence of anti-corruption good-practice.
Output number per LF		Four	Output Score	A
Risk:		Minor	Impact weighting (%):	31%
Risk revised since last AR?		n.a.	Impact weighting % revised since last AR?	n.a.

Indicator(s)	Milestones	Progress
Number of additional new knowledge products (e.g. reports/workshop outputs) created (including G&I and behavioural science). / Disaggregated by how many include gender & inclusion and by project.	StAR - 2 / UNODC (SEA-1, EA-3, SAM-1) / OECD - 1 Anti-Corruption & Integrity Forum (equal gender balance among speakers); 1 Auditors Alliance conference; 1 LA SOE Governance conference / FATF - 10 evaluation reports completed	StAR: 3 = / E-filing asset declarations: benefits and challenges (May 2019) / Financial Intelligence Units Working With Law Enforcement (September 2018) / International Partnerships on Asset Recovery: Overview and Global Directory of Network (January 2019) / UNODC: 7 = / SEA (2) / Publication of Handbook on Investigation of Corruption Cases in SE Asia (July 2019) / Roundtable with Malaysia anti-corruption commission on promoting beneficial ownership transparency (May 2019) / EA (4) / Translation of Tanzanian whistleblowing protection laws into French (July 2019) / Report on benchmarking exercises for the region (May 2019) / Library of best practices for East Africa on whistleblowing protection and financial investigation (July 2019) / SAM (1) / Outcome document following the regional conference and containing all the recommendations and commitments for the upcoming project’s implementation in the region (July 2019) / OECD: 4 = / Global Anti-Corruption and Integrity Forum (March 2019) / Auditor’s Alliance annual meeting (March 2019) / OECD Anti-Corruption and Integrity Guidelines for SOEs translated into Spanish (June 2019) / Latin American SOE network annual meeting Lima (June 2019) / FATF: 39 evaluation reports (see Output one for list of countries).
Number of new instances when projects have taken actions to become more gender and inclusion aligned (e.g. workshops, collecting disaggregated data, plans etc).	9	10 / Following a cross-Whitehall workshop on gender and inclusion (G&I) in February 2019, all nine projects created G&I action plans / OECD ACI forum session on gender and corruption.
Number of behavioural science projects (or phases) carried out. / Disaggregated by how many include gender & inclusion and by project.	1 Project in development: agree scope.	1: project strategy (approach and scope) documented and agreed. This included consultation with Posts, market research and a workshop between behavioural scientists and the GACP team.

Key Points
StAR, UNODC, OECD and FATF have exceeded their output milestones. However, as it is too early in the programme’s lifecycle to assess outcomes and achievement of intermediate outcomes performance is mixed, the score is reduced from ‘A+’ to ‘A’.
This is a wide-reaching and innovative output which involves all of the GACP projects.
OECD: over 2,000 participants from 120 countries (1/3rd government, 1/3rd business, and 1/3rd civil society) participated in the OECD Anti-Corruption and Integrity Forum 2019 called ‘Tech for Trust’, which focused on risks and opportunities of new technologies for anti-corruption and integrity. This included sessions on various topics including: blockchain, artificial intelligence, big data analytics, and civic technologies, as well as a G&I session.
The Auditors Alliance meeting also took place during this week, with 200 speakers and participants from 47 different countries. The focus was on the following themes: auditing in an age of digital disruption; strategic audit analytics for safeguarding integrity; snapshot of findings from the OECD’s survey on auditing of new technologies; innovations in auditing and the use of new technologies; and artificial intelligence and automating audit.
The OECD’s Guidelines on Anti-Corruption and Integrity in State-Owned Enterprises (SOEs) is the first international instrument of this kind. These guidelines help countries to ensure that SOE owners exemplify integrity in their conduct, that ownership arrangements are conducive to integrity, that SOEs adhere to good practices and that accountability mechanisms are integral to SOE sectors. The translation of this document into Spanish allows greater readership and wider application of these guidelines – in particular, in South America where the OECD is focusing its work as part of the GACP. These guidelines were used as the conceptual framework for discussion within the Latin American Network on Corporate Governance of SOEs, which met on 27-28th June 2019.
UNODC: the handbook on Investigation of Corruption Cases in SE Asia is a particularly useful tool for practitioners (lawyers, prosecutors, judges, police and others) as it improves the capacity to facilitate MLAs and extradition by assisting practitioners to understand cooperation frameworks. The handbook provides an overview of the ASEAN Treaty of Mutual Legal Assistance in Criminal Matters (AMLAT) as well as the legislative frameworks in each ASEAN country governing MLA and extradition, as well as application in practice.
The regional workshop on promoting beneficial ownership transparency in Southeast Asia (22-23rd July) was organised by the UNODC, StAR and the Malaysia Anti-Corruption Commission (MACC). Representatives of anti-corruption authorities, law enforcement authorities, market and financial institutions supervisory bodies, other relevant state organisations and the private sector from SE Asian countries met to discuss: regulations and monitoring mechanisms for the establishment of information disclosure of beneficial ownership; enforcement and control systems to ensure the compliance with and accuracy of disclosed and gathered information; preventing abuse of corporate vehicles and of the legal professional privilege; and the relevance of beneficial ownership for corruption investigations.
StAR: StAR’s report on E-filing Asset Declarations is a public resource for policymakers and practitioners, the recommendations within the paper are supported by the experiences of France, Ukraine and the United States in their respective transitions to a digital solution for asset declarations.
The ‘Financial Intelligence Units Working with Law Enforcement’ knowledge product was a joint publication between StAR, the Egmont Group and the UNODC. This document was created to support the implementation of the international anti-money laundering/countering financing of terrorism (AML/CFT) standard promulgated by FATF and other international organisations, therefore supporting the FATF strand of work within the programme as well as that of StAR and the UNCAC to minimise opportunities for the proceeds of corruption to be used by criminal entities and support prosecutions and asset return.
The Global Directory of Networks and International Partnerships on Asset Recovery presents possible strategies for international cooperation including both formal MLA and informal assistance. The directory also lists the asset recovery networks and information about their structure and operations, to help asset recovery specialists access the appropriate networks.
IACCC: the IACCC is one of the experts being consulted by the Commonwealth Secretariat on Anti-Corruption benchmarks for commonwealth nations, to be published later this financial year.
G&I: considerable work during the review period went into analysing the links between corruption and G&I and how the GACP projects can mainstream G&I considerations. There is a general lack of evidence on the link between G&I and corruption and this is acknowledged by anti-corruption professionals as an emerging field, with the G20 Anticorruption Working Group including a specific commitment on gender and corruption in their Action Plan at the end of 2018. The programme is contributing to addressing this evidence and practice gap, mainly by working with delivery partners to explore how G&I can be best incorporated within individual projects. Given that most projects have already been designed and begun delivery, this has required a degree of retrofitting. All projects have created G&I action plans.
The FCO’s Prosperity Fund Social Development Advisor has led working sessions with both the UNODC and the OECD, raising awareness, exploring how G&I (including poverty and citizen engagement) can be mainstreamed into their project activities and promoting better co-ordination with their own internal gender equality experts and units.
The participant understanding and satisfaction ratings of workshops and products (an intermediate outcome measure) is generally good with scores of 93%, 80% and 97% for OECD, UNODC and StAR respectively.
Summary of responses to issues raised in previous annual reviews (where relevant)
The previous annual review recommended that the programme support delivery partners to incorporate gender, inclusion and human rights considerations into projects. This remains an important priority for GACP but has not been fully implemented yet. Workshops with strategic and implementing partners have taken place, with actions plans developed. The programme and project level delivery teams need to implement them and ensure they have access to the requisite G&I expertise, with additional support from the FCO Social Development Advisor (0.1 full-time equivalent allocated to GACP).

Output Four recommendations
1. Project Leads: Embed the project level G&I actions plan into measurement of implementers’ delivery success. Where possible, share lessons across the programme on actions that are having an effect.
2. Project Leads: Ensure delivery partners have access to their own requisite G&I expertise to further build awareness; and develop, implement and monitor their G&I action plans.
3. GACP programme team: Arrange additional G&I workshops with project leads/delivery partners to help share experience, good practice and learning; and further adapt and implement G&I-sensitive project activities.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
Key cost drivers and performance
The programme is in full delivery and spend for 2018/19 was £9,333,342 against a budget of £8,804,465, resulting in an overspend of £528,877. This represents 106% spend against budget, primarily due to a request from the JFU to accelerate delivery and associated spend of the StAR project in order to balance the overall PF portfolio. Overall, this is deemed to be a small variance, with most components coming in close to budget. The programme is forecasting a very slight 1.1% underspend this financial year, equivalent to roughly £144,000. Within this, the main area of variance is the Behavioural Science project, forecasted to underspend by £400k, owing to delays in agreeing a programme of work with the new delivery partner which should be resolved by next financial year.
Financial spend in Financial Year 2018/2019
Project/Item	Lead Dept.	Budget	Total actual spend	Total underspend or (overspend)	Total FY spend %
UK Based staff costs	FCO	136,630	131,933	4,697	96.6%
Business case development1	FCO	187,062	219,722	(32,660)	117.5%
Non staff admin2	FCO	59,588	58,429	1,159	98.1%
Sharing Good Practice Approaches to Tackling Corruption and Enhancing Business Integrity (OECD)	FCO	1,013,370	1,006,370	7,000	99.3%
Implementing the United Nations Convention Against Corruption (UNODC)	FCO	680,000	681,017	(1,017)	100.1%
Supporting the Global Recovery of Stolen Assets – (StAR)	FCO	0	700,000	(700,000)	n/a
Changing Behaviours to Prevent Corruption / (Behavioural Science)	FCO	0	(19,964)	19,964	n/a
South Africa Ethical Leadership and Public Accountability3	FCO	43,350	40,603	2,747	93.7%
Combatting Corruption in Oil, Gas and Mining Sectors (EITI Secretariat & WB)	DFID	1,500,000	1,500,000	0	100.0%
Improving Transparency of Company Beneficial Ownership (OpenOwnership)	DFID	950,000	883,753	66,247	93.0%
Supporting Global Digital Marketplace Platforms (GDS)	GDS/CO	2,300,000	2,284,242	15,758	99.3%
Co-ordinating International Intelligence Sharing on Grand Corruption (IACCC)	IACCC/NCA	1,050,000	1,016,572	33,428	96.8%
Strengthening Anti-Money Laundering Systems (FATF)	HMT	884,465	830,665	53,800	93.9%
TOTAL	n/a	8,804,465	9,333,342	(528,877)	106.0%

1 Costs associated with external consultants supporting the development of the business case and mobilisation of the programme.
2 Costs associated with travel and ad-hoc costs such as hiring an external consultant to support the 2018 Annual Review.
3 Costs associated with a one-off project that was funded by the GACP.
Programme Financial Profile
(rounded to the nearest thousand)
FY 17/18	FY18/19	FY19/20	FY20/21	FY21/22
£4.8m	£8.8m	£13.2m	£13.4m	£4.9m

Last financial year, each HMG partner was responsible and accountable for its individual project spend. The major areas of underspend were the IACCC (due to some delays), anti-money laundering (due to reduction in planned spend with the FATF training institute) and beneficial ownership (largely due to the delay in recruitment of staff).
The financial profile shows a rising spend year on year up until FY19/20, before plateauing and trailing off in the last year of operation. This is a very typical profile for a programme of this sort and there is nothing to suggest that the forecast for future years in inaccurate or unfeasible. The main cost-drivers for the majority of the projects are implementation delays and currency fluctuations, though an in-depth assessment has not been conducted. It is recommended that each HMG delivery partner is requested to provide this information as part of its regular reporting by the time of the next Annual Review.
VfM performance
Economy
Eight out of the nine components have been delivered in line with the business case, with the majority of delivery partners administered through MoUs or Administrative Agreements due to the multilateral nature of the organisations or where delivery is in-house by parts of the UK Government (UNODC, OECD, StAR, EITI Secretariat, FATF, World Bank, GDS and IACCC). There is one Accountable Grant due to the delivery partner’s charity status (OpenOwnership). As set out in the business case, this delivery model was chosen against alternatives given the ‘track record, expertise, credibility and deep engagement with national governments’ that these organisations possess. The ninth component, Behavioural Science, is the only one to revise its delivery model following mixed results from pilot projects undertaken over 2017-18 using transition funding. Following approval from the SRO and Programme Board, the team are now considering alternative delivery partners which are expected to represent better VfM.
Given the number of components and type of agreements in place it is difficult to provide a comprehensive assessment of whether the programme overall is paying the right price, especially in the absence of a competitive tenders for the vast majority of programmes. A comprehensive appraisal of delivery options is outlined in the business case.
The admin staff cost last FY was 4.4% of total spend, calculated in line with JFU guidelines. The programme team expect the admin staff costs to average out at 4.5% over the lifespan of the programme, slightly below the 4.6% estimated in the business case.
This doesn’t however take into account the administration or overhead costs of delivery partners which vary between 5% and 17% as referenced in Section F. Based on anecdotal evidence from interviews, some projects of the GACP do have more expensive delivery models, particularly multilateral partners that have set staff rates. That said, the majority of funding bar StAR and the WB EGPS, is ‘earmarked’ allowing for close monitoring of costs against the delivery of outputs. Regarding the Multi Donor Trust Funds, it is far more difficult for teams to track where the funding goes given that these are core contributions.
To ensure greater control over costs it is recommended that the programme team consider the feasibility of benchmarking cost across projects, as well as encourage HMG delivery partners to identify and report cost-savings.
Efficiency
Overall the programme is well managed, despite the complexities of having four HMG departments managing nine components. There have only been minor delays in a couple of components (IACCC and OpenOwnership) as noted above, however overall the programme is on track. The programme has the right level and capability of staffing in place, and a Deputy Programme Manager has recently started. The FCO Global Head of Anti-corruption oversees the programme and provides a valuable link HMG anti-corruption policy.
One area that doesn’t appear to be particularly efficient is the funding that the Extractives project receives from both this programme and DFID. Given this, it’s unclear what value-add FCO PF funding provides vis-à-vis DFID funding. In addition, while reporting between DFID and the FCO is somewhat aligned, the EITI Secretariat are required to report on slightly different indicators for each department. As per the recommendation in Section C, it is recommended that the GACP Strategy Board consider before next FY whether it would not be more effective and efficient for DFID alone to be the sole HMG partner for delivering in the extractives sector.
More broadly, there is potential for greater efficiencies through more coordination and knowledge sharing between the nine projects. Knowledge of the issues each country faces and key stakeholder contacts held by any of the delivery partners is likely to benefit other components in achieving its objectives. While there is already sufficient coordination among HMG delivery partners, this is not happening systemically among delivery partners. For example, several of the delivery partners meet at conferences which is a beneficial forum for knowledge exchange, but there is currently no regularly or mandated coordination between them. It is recommended that the programme team identify within the next 6 months how best to promote coordination and knowledge sharing across the programme.
Effectiveness
The programmes ToC and LF have undergone considerable improvement over the last year to make it more accurate and effective. Across almost all components, partner government support is critical for the success of the programme, which has been built into the selection of the programme’s priority countries and the design of individual projects. Risks to achieving the objectives of the programme are monitored closely at both the programme and project levels.
A number of projects have considerably exceeded their LF milestones, owing in large part to milestones being overly conservative in the first place. As per Section C, it is recommended that these milestones are revised for subsequent years. There are early signs of outcomes being achieved, particularly in the area of asset recovery and an improvement in policies, laws and regulations on anti-corruption.
Based on the findings of this annual review, the programme is delivering in line with that set out in the Business Case and is therefore expected to deliver primary benefits in the estimated range of £33m-£232m. On secondary benefits, given the nature of the programme the Business Case estimated only £3m of commercial benefits, however interviews suggested considerable network benefits and political influence that have already started to be realised through this programme – see Section G for more detail. In particular, the programme is seen by several stakeholders to be carrying forward the momentum generated by the 2016 Anti-Corruption Summit that the UK hosted and which spawned this programme.
The programme overall consists of a range of types of activities across a wide spectrum of anti-corruption policy areas. This means that some activities are likely to delivery results sooner than others, and some that will be more transformational than others. For example, the successful return of assets through the support of StAR and IACCC would be a significant achievement, however what impact the returned assets will have won’t be seen for years to come. Similarly, beneficial ownership registers may grow rapidly, but are only likely to have impact if the information is useful in tackling corruption and activity used. It is therefore recommended that the programme team regularly reviews Theories of Change and consider how to support (whether financially or otherwise) those aspects of the programme that are deemed to be more cost-effective; a discussion on which should happen before budgets for the next financial year are agreed.
Equity
The GACP programme team and the FCO Global Social Development Adviser took the initiative to jointly produce a draft G&I and Human rights approach and vision paper, hold a workshop with project leads (February 2019) to identify entry points for G&I specific work, appoint G&I champions for all projects, and support drafting action plans of how each project will mainstream/target G&I within its activities. The Gender and Inclusion scorecard, which was subsequently completed, rated the programme ‘Amber’ overall, following which the programme team responded further by:
- Consistently raising G&I with project partners to ensure G&I is mainstreamed into their activities (e.g. specific agenda item at the OCED and UNCAC project boards) and querying access to expertise (e.g. with OECD, UNCAC)
- Ensuring the LF has disaggregated indicators by G&I where appropriate.
All of these activities have now been completed and it can be said that the programme does consider G&I as a priority and has taken steps to ensure it is mainstreamed throughout the programme, resulting in the programme being a global programme trailblazer on G&I within the PF. There is clear consideration of G&I in the LF through the use of disaggregated results, however in the year covered by this annual review there has been no reporting on disaggregated results. It is recommended that the programme team reiterate and clarify if necessary the expectations of delivery partners regarding G&I capacity and reporting disaggregated results.
From the interviews with delivery partners it was clear that each had a different understanding on what G&I meant for their work, but did largely reflect the importance of G&I within their respective organisation. For those where this was less familiar, their understanding on how G&I related to their work was less developed and will in part require cultural change which this programme is helping to drive, especially as G&I in the anti-corruption field is a relatively new topic. It’s also worth noting that delivery partners displayed a much stronger focus on gender, with far less mention of inclusivity, which is somewhat understandable as it’s often less visible though shouldn’t be overlooked. The priority for the programme team going forward is to implement G&I actions plans, ensuring delivery partners have access to their own dedicated G&I resource and facilitate cross-learning between projects. To help achieve this, it is recommended that the programme team repeat the G&I workshops in 2020 as referenced in Section C, Output 4.
According to its Gender Equality Marker (GEM) Score of 0 (i.e. not targeted), the programme is not specifically targeted at gender equality, but has the scope to move towards a score of 1 (significant).
To understand the distributional impact of the programme it will be important for the programme to have access to high quality evaluation, due to the long impact pathways between the programme’s activities and end beneficiaries. It is therefore recommended that the programme is one of the case-study examples in the upcoming JFU G&I evaluation.
Assessment of whether the programme continues to represent value for money
The programme is on track to deliver good value for money in line with the Business Case. Some aspects of the programme are likely to deliver results before others, and some aspects are likely to be more transformational than others. The biggest opportunity going forward for greater efficiency and effectiveness is coordination between the projects and more strategic prioritisation of resources in geographies and projects that are demonstrating greater cost-effectiveness.
The overriding risk to the successful delivery of the programme, and the main determining factor in achieving the intended outcomes and impact, is the political will to implement reform, address corruption, repatriate stolen assets and charge those that have embezzled state funds. The programme’s approach is sufficiently alive to this, but this is something that will need to be kept under continuous review.
Quality of financial management
The FCO internal financial reporting tool OBIEE is used to scrutinise FCO spend and for detailed reporting of monthly spend/forecasting to the FCO’s Global Programme Support Team and Prosperity Fund Delivery Unit and the programme SRO. A more high-level RAG rated financial breakdown of spend is provided to the Steering Group and Strategic Board. The programme team receives quarterly financial reports from multilateral delivery partners and they also commission and scrutinise monthly financial actuals/forecasting provided by XWH project leads. Some minor issues have arisen with the timeliness and accuracy of XWH forecasting and the reporting across a couple of the projects, largely due to stretched staff capacity, but these issues should be largely resolved in the coming year as teams return to full staffing. A comprehensive record of monthly expenditure by project is maintained by the programme team. The multilateral delivery partners are well established organisations in the anti-corruption field and have well established financial management frameworks in place. Invoices are checked against deliverables and audit arrangements are covered by standard internal FCO audit mechanisms. Where advance payments are made (FATF) or as part of core-contributions (StAR, WB EGPS), teams check delivery against the pre-agreed deliverables or outcomes. Neither FCO, HMT or DFID reported any financial management issues with their delivery partners.

## E: RISK

Overall risk rating: Moderate
Although the overall risk rating, defined as the average of the output level risks is classed as ‘minor’, the overall risk rating for the programme as a whole is defined as ‘moderate’. This is due to the ambitious nature of the programme and the reliance on partner country political will which can change. Outputs are typically technical assistance focused and broadly in the control of the programme team and its deliver partners, whilst outcomes are more politically focused and beyond the control of the programme.
Overview of programme risk
The programme team maintains a risk register covering key project and programme risks that are actively managed, 16 in total. They are RAG rated according to severity and the top seven are listed below:
- The inherent nature of corruption means the programme is unable to robustly capture and demonstrate impact – this is being mitigated through working closely with the experts across government to create a robust monitoring, reporting and VfM approach. Communities of experts will be created at Posts to help assess the outcomes and impact of the programme and shape its evolution. The programme itself aims to inform the international evidence base on effective anti-corruption activities and measures. The programme has and will continue to access external experts (e.g. U4, OECD etc) to inform and review the approach to data gathering and benefits (classified as a ‘moderate’ risk)
- The programme's complex delivery model and varying geographic coverage results in Posts lacking sight on all programme activities – this is being mitigated via implementation of a programme level communications strategy, working in close cooperation with policy colleagues, targeted communications with Posts e.g. quarterly video conferences, working closely with JACU and other government departments (classified as a ‘moderate’ risk)
- Programme or project staff are deployed to other areas of HMG and this has a resulting negative impact on Programme/Project work – this is being mitigated via closely monitoring the potential need for staff deployments, across projects and the programme and assessing the impact on projects/programme work. Utilise temporary staff as needed (classified as a ‘moderate’ risk)
- Negative HMG media publicity e.g. the ‘losers’ of corruption sharing misinformation about the programme – this is mitigated through close monitoring of media in London and at Post. Defensive lines have been developed. Liaison with the media office on a case-by-case basis (classified as a ‘minor’ risk)
- Bribery and corruption risk in delivery partner organisations and their supply chains – this is mitigated through no funds being provided direct to other government administrations. All external programme expenditure is dispersed direct by HMG to suppliers, helping to mitigate the opportunity for local corruption (classified as a ‘minor’ risk)
- Litigation risk related to publishing personal data on the OpenOwnership Register – this has been mitigated through OpenOwnership commissioning legal advice on this issue from a law firm that services open data projects. A legal defence has been prepared for any such challenges, and a privacy policy that sets out the legal basis for the processing of the data makes our obligations to data processors clear. There is also a clear process flow for handling data takedown requests (classified as a ‘minor’ risk)
- HMG staff and delivery partner security risk associated with working on a sensitive subject matter in sometimes unstable environments – this is being mitigated via all organisations involved in the delivery of the programme following their respective policies and guidance. This includes, for example, FCO Travel Risk Assessments, FCO foreign travel advice, Cabinet Office approved travel channels, United Nations Security Management System, OECD Convention etc. In addition, the programme team regularly liaises with individual HMG Posts to understand the nature and level of risk (classified as a ‘minor’ risk).

All cross-Whitehall project leads are required to formally report on risks in their monthly (quarterly for DFID) flash reports to the programme management team. In addition, a more detailed risk assessment is undertaken bi-annually, again reporting to the programme management team. Due to the cross-Whitehall nature of the programme, each project has its own governance arrangements to manage project risks. The programme management team reports monthly within the FCO on key risks and quarterly to the JFU. Risks are updated on both a spreadsheet and Prospero (the PF reporting hub). The top risks are presented to and reviewed by the Steering Group (quarterly) and the Strategic Board (bi-annually).
Overall, the programme and project teams appear to have a good awareness of risks, they are sufficiently captured and documented, and actively managed. The programme and governance boards have regular oversight of the risks.
Outstanding actions and recommendations from risk assessment
Recommendation – review the multiple ways risks are captured (project/programme/fund level) to improve management efficiency.
Recommendation – review the risk relating to partner country support for project activity to ensure appropriate mitigating actions are agreed.

## F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
The programme’s delivery is broadly in line with the planned timeframe. Eight of the nine projects are in delivery. The one remaining project, Behavioural Science, was always planned to lag the other projects so it could be designed to complement the other projects and they therefore needed to be up and running first. Of the eight projects in delivery, all are broadly on track. One project, anti-money laundering systems, has experienced two issues (one supplier related, one political) which resulted in delays. There have also been small delays in the GDS and the IACCC projects. In all cases, the project leads shared updates with the programme team and appropriate remedial actions were put in place, one resulting in small change in scope but not material to the integrity of the project or wider programme.
Performance of partnership(s)
The key partnerships are between Whitehall partners (DFID, FCO, GDS, HMT and NCA), with individual delivery partners (e.g. OECD) and with partner governments.
The partnerships across Whitehall are broadly strong, but in some cases, there is room for improvement that would help maximise synergies and overall impact. The partnerships with individual delivery partners are strong. The partnerships with partner governments are also broadly strong, this is especially the case for the five core countries.
Project governance arrangements vary by project but typically include an annual review/project board where progress is reviewed and lessons captured. This feeds into future project plans and is also shared at the programme level where appropriate (e.g. through monthly ‘flash’ reports and at programme boards).
Changes in the Delivery Plan
There has been one material change to the delivery chain. This relates to the Behavioural Science project where a decision was taken (by the programme’s SRO) to commission a multilateral partner. This was mainly due to additional information coming available about multilateral capability in this space and the enhanced sustainability they offer and ability to magnify impact.
The management fees or overhead costs are as follows:
Lead Department	Delivery partner	%
FCO	OECD	5.3%
FCO	UNODC	13.0%
FCO	StAR	17.0%
DFID	Extractives WB	17.0%
DFID	Extractives EITI secretariat	3.0%
HMT	WB	0%
HMT	FATF Secretariat	5.1%
HMT	FATF regional bodies	0%
DFID	OpenOwnership	9.0%

Asset monitoring and control
Two of the projects manage assets – beneficial ownership and IACCC, managed by DFID and NCA respectively. Both departments have asset registers for their respective project and regularly monitor and update them.

## G: BUSINESS ENVIRONMENT

How has the business community and business environment responded to the programme?
Direct engagement with the business community has not been the prime focus to date. This is an area still being explored, given where the programme is in its lifecycle. Although the programme has had initial discussions with the CBI and is considering using JACU’s business survey. Over the next year, it is recommended that the programme team explore further how it might raise awareness on the programme, including better complementing business needs (in conjunction with DIT), and establish a feedback mechanism for the UK business community.
The GACP’s contribution to UK soft power and spearheading the UK’s contribution to the global architecture of anti-corruption and preventing IFFs should be a central feature of the GACP secondary benefits. Throughout the Annual Review interviews, this was acknowledge by strategic and implementing partners and partner countries. By helping overcome technical obstacles through UK technical assistance, the GACP’s secondary benefits go well beyond the partner countries, including the UK’s soft power.
The programme is planning to create country-specific communities of experts next year, including with local business representatives. Where possible, the British Chambers of Commerce should also be included to gauge the impact of the programme and reshape activity as needed.
The programme has no non-ODA spend.

## H: MONITORING & EVALUATION
Evidence and evaluation
An evaluation readiness report is currently underway which is due to be completed in November 2019. This is the first time that the programme will have been evaluated. A full evaluation is scheduled to commence in August 2020. The ToC and LF has undergone extensive development over the last year through a number of workshops. This has primarily been to refine the impact pathways and design a programme LF that can capture and aggregate the activity of all nine projects, in addition to improving the individual project LFs. The programme had not previously assigned weightings for each of the four outputs, but has done so for the purposes of the AR based roughly on the spend associated with each output. It is recommended that the weightings are reviewed and agreed by the programme board.
There does not appear to have been any major change in the programme assumptions or evidence base, though it can be said to be expanding and evolving, in part due to the activities funded by this programme. One such example, is a study[2] published at the start of the year which documents the impact of the return of $322.5 million of stolen assets to Nigeria. The study shows how the return of stolen assets can have a disproportionate benefit on the poor and most marginalised groups when used in certain ways – in this case via a conditional transfer programme. The programme team has also recently commissioned research to collate what evidence exists on gender, inclusion and anti-corruption, which may provide new insights once completed.
[2] https://aneej.org/wp-content/uploads/2019/10/Mantra-Field-Report-final-compressed.pdf
Monitoring progress throughout the review period
Given the difficulties in quantitatively measuring changes in corruption, the programme has adopted a novel approach to measuring outcomes and impacts, drawing on experience from the UNODC. This approach consists of three pillars:
- Expert panels in each priority country, comprising of government official, academics, thought leaders, businesses, donors and multi-laterals. These panels will meet twice a year to baseline and track perceived changes in corruption in areas specific to programme activity;
- UK business community survey (included in the JACU process) applied annually to gauge corruption perception towards certain markets;
- Comprehensive review of all the data and evidence on anti-corruption.

The communities of experts will form the corner stone of the programme’s ability to measure progress towards the reduction of corruption, with the expectation that the communities will be established in each of the programme’s key countries by February 2020. Besides this, there will be regularly monitoring provided by the programme and individual project boards. The responsibility for monitoring, reporting, evaluation and learning (MREL) lies across several members of the programme and project teams. While this does have its benefits, the review recommends that the they meet more regularly to ensure coordination and effective delivery of the MREL framework.