Administration Costs Guidance

For most projects, the combined total of management fees, overheads and administration costs should not exceed 10% of the overall project budget (although UN agency admin costs may be higher, up to around 15%). Note that 10% is not a target, but a limit.

To ensure we are achieving best Value for Money, it is important to understand what is included in a project budget and whether the costs stated are reasonable. Understanding what is included will also help avoid double counting, i.e. you should check the Activity Based Budget carefully to ensure that the same items do not appear elsewhere in a different budget line or are hidden in several line items.

We do not accept ABBs with “contingency” or “risk” or “miscellaneous” costs.

Running costs associated with an implementers offices, such as office equipment, building reparation & repairs, fixing/maintaining boilers/generators etc should not fall to the project budget as separately itemised direct costs. These costs are associated with running the business, not delivering the project. They are part of the overheads of the organisation. As such they should be part of any indirect admin charge that the implementer adds to the direct costs of delivering project activities and outputs.

Management Fees should be reflected as a fixed sum and not as a percentage of the budget. Check that the cost is reasonable. If we are being asked to pay a Management Fee challenge any salary costs which may also appear in the Activity Based Budget.

Personnel costs: we can legitimately pay costs for implementing agency staff who are directly involved in delivering the project. These can be separate and in addition to the admin charge. But make sure that:

You receive a detailed breakdown of staff costs so that you know how many and which staff are assigned to the project

The salary costs are reasonable

The staff identified will actually be working on the project

The time allocated is reasonable – we should not be paying for two months work if one month is sufficient

We are not paying unnecessarily high costs when accommodating someone involved in the project – Embassy marker hotels should be the starting point when accommodating anyone who is involved in the project. Refer to Geographical Expenditure Guides on FCONet as a guide

The class of travel is correct – follow FCO travel policy guidance, but aim to use Economy or Premium Economy rather than Business Class where possible