Annual Review 2020 - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Prosperity Fund: Global Business Environment Programme
Programme Value: £30m		Review Date: November 2020
Programme Code: GB-GOV-50-PF-08-GBE (including GB-GOV-3-PF-GBE-911; GB-GOV-3-PF-GBE-913; GB-GOV-3-PF-GBE-921)	Start Date: November 2017	End Date: March 2022

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2021/22
Programme Score	B	A	A+
Risk Rating	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review
The programme has made good progress in the year under review, pivoting well to support partner governments address the economic fallout of COVID-19. The programme is likely to exceed its output and outcome targets, despite the operational disruption caused by COVID-19. GBE contributed to 28 reforms de jure, including several that are economy-wide. Five of these reforms are already benefiting firms and consumers; how the other de jure reforms affect businesses in the real economy will be assessed in the next 18 months. The programme has already exceeded 77% percent of its end-of-programme output targets, and shown good financial performance. Staff have also addressed 94% of last year’s Annual Review recommendations and improved their tracking of Value for Money.

List of recommendations for the next year
1. Gather data on how international firms respond to reforms that directly remove barriers to exports and investment. To strengthen the evidence that the programme contributes to greater exports and investment. [Responsibility: World Bank Group]
2. Gather data on the how UK firms benefit from reforms that directly remove barriers to exports and investment. To strengthen the evidence that the programme contributes to greater exports and investment. [Responsibility: HMG programme teams at Post, with DIT colleagues]
3. Seek to strengthen private sector participation in partner countries where it trails expectations, particularly in Nigeria and the Philippines (and to a lesser extent Malaysia although private vs public disaggregated data is not available here for the past year). [Responsibility: World Bank Group]
4. Deepen our understanding of whether major reforms benefit poor women and men. This could be done without much additional effort, based on qualitative as well as quantitative information. For example, by identifying companies that benefit from Brazil’s expanded Direct Investment Ombudsman and employ significant numbers of poor women and men. Or by identifying categories of goods and services targeted at poorer women and men that benefit from Brazil’s modified anti-dumping laws. [Responsibility: World Bank Group]
5. Carefully consider feasibility, sustainability and past agreements and guidance on gender and inclusion before requesting new or different gender and inclusion activities. [Responsibility: FCDO]
6. When validating relevant reforms, include in the sample micro and small businesses, and businesses owned by women and marginalised groups. The programme already plans qualitative research to capture the effects of reforms on women and social excluded groups. This recommendation is to reinforce the importance of doing this.[1] [Responsibility: World Bank Group]
  [1] This is one of several annual review recommendations that also features in the recent independent assessment of the programme’s processes to ensure gender and inclusion are adequately considered. See Prosperity Fund (2020) GBEP G&I scorecard: November 2020.
7. Building on the efforts made to increase dissemination of the valuable learning outputs, further improve dissemination of outputs to non-World Bank audiences. Many of the useful research papers are difficult to find, unless potential readers know the exact titles and where to look on the WBG website. Improved visibility on search engines would be useful. [Responsibility: World Bank Group]
8. Set more stretching dissemination targets for the Global Influence Window, for the remainder of the programme (subject to funding). [Responsibility: FCDO programme team and World Bank Group]
9. Continue to look for opportunities to save on administrative costs, without substantially undermining the quality of programme management. [Responsibility: FCDO]
10. Investigate why a significant minority of participants are not satisfied with programme events in its nine partner countries. Use findings to drive continuous improvement. [Responsibility: World Bank Group]
11. Continue to invest in building the capacity and evidence base to sustain reforms. [Responsibility: World Bank Group]
12. Continue to communicate proactively with FCDO staff at Post, to manage risks and expectations with host governments [Responsibility: World Bank Group]
13. Further raise awareness of Brazil’s Direct Investment Ombudsman among investors. [Responsibility: HMG programme team, with DIT, particularly among UK investors in Brazil]
14. Further develop what makes a reform count as “major”, with specific consideration to business impacts on the ground. Continue to record progress of the programme’s contributions to major reforms specifically. Whilst continuing to measure contributions to all reforms, including regional and process reforms. Using a similar definition to the Business Case would help future annual reviews to assess progress.[2] [Responsibility: World Bank Group]
  [2] In the business case, a major reform is defined as a reform that contributes around 0.114 % to a country’s GDP, or more. Given the practical impossibility of measuring the contribution of the reform to GDP, WBG would need to use expert (subjective) judgement to assess if a reform is major. Having a rough idea of whether a reform is ‘major’ is better than having no definition at all.
15. Continue to monitor the political economy and prioritise among remaining reforms, to maximise impact, particularly in the event of budget cuts. [Responsibility: World Bank Group]

SRO commentary
I am grateful to the work of the review team for their work on this Annual Review recognising the progress that the Programme has made in a difficult year. This progress is down to the hard work of the teams in FCDO in London and at post and World Bank colleagues. I endorse the recommendations made by the review and we will action them as required. We will also work to ensure that the activities of this programme also seek to maximise the synergies in the creation of FCDO and the continued impact of Covid-19 on business environments and trade.

Joint Funds Unit response to the annual review
This third Annual Review finds good progress is being made across the programme’s outputs. At the country level, there is evidence that the programme is supporting real improvements in the business environments of partner countries, some in a substantial way. At the global level, the programme enjoys excellent engagement across practitioner groups and is producing analysis and sharing insight of value to stakeholders.
JFU agrees with the recommendations made and suggests a particular focus on 1) further clarifying the ways in which poor men and women benefit from specific interventions and 2) at a management level, to continue to review programme structures to ensure cost efficient delivery.

List of acronyms

DIT – Department for International Trade
FCDO – Foreign Commonwealth and Development Office
DFID – Department for International Development
FDI – Foreign Direct Investment
FY – Financial Year
GBE – Global Business Environment Programme
G&I – Gender and Inclusion
HMG – Her Majesty’s Government
IBEP – Improving Business Environment Programme (another name for GBEP)
JFU – Joint Funds Unit
MNC – Multinational Corporation
N/A – Not applicable
OECD – Organisation for Economic Co-Operation and Development
PF – Prosperity Fund
SMEs – Small and medium-sized enterprises
SRO – Senior Reporting Officer
VfM – Value for Money
WBG – World Bank Group

## A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-50-PF-08-GBE
DevTracker Link to Log frame:	Not yet available

The Global Business Environment Programme (GBEP) is a Foreign, Commonwealth and Development Office (FCDO) Prosperity Fund programme, which works with governments to improve the business environment of partner Middle Income Countries (MICs), with the objectives of boosting business competition and catalysing shared prosperity. The World Bank Group (WBG) implement the programme. Total funding allocated is £30m over a 4-year period, of which £28.5m is managed by the WBG via a single donor trust fund. The programme operates through two main components: the Global Influence Window and Country Engagement Window. The program also features a gender and inclusion cross-cutting theme in its activities, as integral to supporting more inclusive growth, shared prosperity and poverty reduction.

The Global Influence Window (30% of the total budget for delivery) produces operationally relevant diagnostics and tools across the following pillars: analytics, reform toolkits, adaptive policy design, the Global Investment Competitiveness Report and regular events bringing together policymakers, businesses, global technical experts and academics. The core objectives of the global engagement work through the Global Influence Window are to use the World Bank’s global reach and analytical work to support the design and implementation of reforms in the focal countries:

1. Fill existing gaps in business environment data and research
2. Advance thought leadership by shaping frontier business environment topics
3. Reinforce the analytical foundation of various business environment reform areas
4. Strengthen the design and implementation of business environment reforms in MICs
5. Foster peer to-peer learning across a wide cross-section of reforming countries

The Country Engagement Window (70% of the total budget for delivery) supports business environment reforms in 9 MICs: Brazil, Indonesia, Malaysia, Nigeria, Pakistan, Philippines, South Africa, Turkey, and Vietnam. These reforms are expected to generate improved investor perceptions, private sector savings, increased investments and more open and competitive markets. At the country level, the objectives are to:

1. Strengthen business regulations and practices
2. Enhance business competitiveness
3. Catalyse shared prosperity through support to subnational efforts and equity

The primary impact and expected outcomes across the focal countries include between 9 and 25 major reforms which will enable businesses to grow, save on compliance costs, increase productivity and competitiveness, enabling more inclusive growth[3]. These outcomes aim to help host countries to attract foreign investment and spur economic growth and higher incomes, which will in turn generate secondary benefits for UK and international businesses, in the form of greater investment and export opportunities. Conservative estimates (set out in the business case) suggest that benefits to the UK alone could range from £50 to £170m over 10 years. Actions to realise secondary benefits are for HM Government (not the WBG). Other shorter-term secondary benefits will include enhanced UK soft power with host governments.
[3] The Business case highlights that this inclusive growth will take place both across national regions and population groups.
GBEP is part of the Prosperity Fund, and aims to contribute to 3 of its 5 intermediate outcomes – Trade; Financial and Economic Reform; and Ease of Doing Business.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
The business case states that the programme is seeking to achieve around 25 reforms over its lifetime, including 9 major, economy wide reforms. The programme has already contributed to 28 reforms being enacted de jure (not all of which are major), including 15 in the previous year. Highlights from the year under review include:
- New rules and policies to prevent anti-competitive practices in the Philippines and Indonesia.
- The Government of Nigeria passed its Companies and Allied Matters Act, updating the laws governing company registration for the first time in 30 years. Among other things, companies can now be registered by single person; Limited Liability Partnerships are legally recognised; Annual General Meetings can now take place online.
- The Filipino government streamlined how it issues permits for the construction of shared passive telecommunications towers, and allowed foreign investors to construct and operate mobile phone towers. These are important reforms, in a country seeking to improve mobile network coverage and connection speeds, as COVID-19 travel restrictions lead people to rely increasingly on digital data to work and communicate.
- The Filipino Food and Drug Administration’s launched its e-services portal, and made other changes that streamline and accelerate its approvals.
- Reforms in South Africa that should reduce the time it takes SMEs to pay taxes by at least 20%.

The programme contributed to each of the reforms mentioned above. Typically, through problem identification, the co-creation of solutions, by gathering and presenting evidence on the benefits of reform, stakeholder coordination or a combination of these.
The programme has so far validated that five early, economy-wide early reforms are already likely to be benefiting the real economy. These are:
- The expansion of Brazil’s Direct Investment Ombudsman to serve investors from all countries. The ombudsman helps foreign investors to resolve disputes with Brazilian government agencies. According to the Brazilian government, it has already resolved 18 disputes, involving investments with a combined value of $830 million.
- Following a WBG recommendation, the Brazilian government introduced legal reforms to ensure that anti-dumping investigators consider the public interest before imposing duties on imports. Brazil’s Department of Trade Defence and Public Interest has since recommended for reductions or suspensions of antidumping duties, to serve the public interest.
- Three Doing Business reforms in South Africa: The time taken to start a business has decreased from 40 days to 7.5 days, to complete a corporate income tax audit from 32 weeks to 17 weeks, the time to claim a VAT refund from 15 to 5 weeks, and the mandatory pre-shipment stacking period was changed from 72 to 24 hours.

In Section C we recommend that the programme gathers more information from businesses affected by these first two reforms. So that the programme can tell a stronger story about the types of workers whose jobs are likely to be protected, and the types of consumers likely to receive cheaper or better quality products, as a result.

In stakeholder interviews we heard that at least two other reforms are also already making a difference to businesses and consumers. Both are in the Philippines, and mentioned above: the streamlining of telecommunication tower permitting, and reforms to accelerate food and drug licensing.

Given the number of reforms enacted to date in GBEP’s nine focal countries, the additional reforms likely to be enacted by end of the programme, and the contribution of the Global Window to 22 further reforms, the programme appears on track to exceed its ‘number of reforms’ targets. Progress is commendable, and is possible in part due to the programme’s agile response to COVID-19.

The programme’s priority reforms seek to benefit the poor, women and marginalised groups in several ways:
- Targeting reforms particularly relevant to MSMEs. These include reforms in Nigeria that make it easier to register a business, and establish Small Claims Courts in the country’s two largest commercial hubs.
- By supporting reforms that generate economic growth. The programme assumes that poor women and men will be amongst those benefiting from increased productivity, jobs and/or demand in the economy.
- By enhancing consumer welfare. Programme-supported reforms in four countries are expected to improve the enforcement of competition rules, sometimes by reducing protectionism.[4] Indirectly, these reforms may also reduce inequality, by inhibiting the use of market dominance to concentrate wealth.
  [4] The four countries are Indonesia, the Philippines, Brazil and South Africa.
- Targeting the poorer regions of Brazil, Malaysia and Pakistan. Offering expert advice to improve the business environment and investment promotion in these regions.
- Supporting partner governments to gather and use gender-disaggregated data. The review team noted seven separate activities here, informing investment promotion, competition policy and business skills training, among other things.

Evidence that the poor, women and marginalised groups benefit from reforms should materialise in the next 1-2 years, as all reforms are enacted and validated. For more detailed analysis of gender and inclusion, see Section C (particularly Output 4).

Annual outcome assessment (Secondary Benefits – exports, investment, soft power)
Exports: Many of the reforms targeted by the programme will contribute to host country economic growth, if implemented.[5] All other things being equal, this growth will lead to higher incomes, a share of which consumers will spend on imports, some of which are UK exports. These assumptions, stated in the business case, still look logical. Despite significant effort, the search for a methodology that can validate these assumptions statistically, and credibly quantify the programme’s overall contribution to UK exports, has not yielded results. There is however an opportunity to gather data on the effects of reforms that directly remove barriers to exports.[6]
[5] This view is supported by World Bank analysis, and by FCDO and DIT staff interviewed at Posts.
[6] For example, in Brazil the programme has supported a reform which removes protectionist anti-dumping measures, where there is strong public interest case to do so. Meanwhile, in the Philippines, the programme has supported the Food and Drug Administration to improve its licensing of pharmaceuticals.
Investment: several GBE-supported reforms will make partner countries more attractive to UK and international investors. Notably examples include the removal of restrictions on foreign direct investment in Indonesia; the expansion of Brazil’s Direct Investment Ombudsman to serve investors from all countries; and the streamlining of food and drug licensing in the Philippines.
For reforms to spur greater investment however, UK and international businesses need to be aware that a reform has taken place. The Department for International Trade (DIT), through its extensive ongoing communication with UK businesses, can play a valuable role in informing British investors about reforms. FCDO staff at Post have been asked to make DIT colleagues aware when reforms happen, so that DIT can notify relevant UK firms. Many already do this and with little additional effort, it should become standard practice.
Soft power: as described above, the programme has made important contributions to reforms that free trade from non-tariff barriers, and encourage greater foreign direct investment in the programme’s partner countries. Indirectly, and whilst maintaining the WBG’s strict political impartiality, the programme has contributed to the UK’s trade and investment objectives.
The last annual review noted concerns from HMG at Post that host country government counterparts were sometimes unaware that the UK funded WBG's business environment technical assistance. WBG’s hesitance to highlight UK funding is often understandable, and even in the UK’s interest; by maintaining and demonstrating its impartiality, World Bank Group enjoys greater influence. At the same time, FCDO and WBG have reached a better understanding in the year under review of where UK support can be recognised without WBG’s impartiality being questioned. Global influence window research outputs acknowledge UK funding, for example, and UK officials have been invited to speak at events engaging partner country businesses.
Recommendations

- Gather data on how international firms respond to reforms that directly remove barriers to exports and investment. To strengthen the evidence that the programme contributes to greater exports and investment. [Responsibility: World Bank Group]
- Gather data on the how UK firms benefit from reforms that directly remove barriers to exports and investment. To strengthen the evidence that the programme contributes to greater exports and investment. [Responsibility: HMG programme teams at Post, with DIT colleagues]

Overall output score and description
The programme has exceeded 77% percent of its end-of-programme output targets, and is likely to meet most others by the end of the programme. This is despite the programme increasing several of its targets after the last annual review. The A+ score reflects this progress, which is above expectations, as is outcome-level progress.

Key lessons
- The World Bank Group enjoys long-standing relationships with business environment reformers in host countries, and in most cases has retained a strong in-country presence. Such relationships and local presence are key to progress during a pandemic, when in-person meetings and international travel are restricted.
- The widespread shift to online meetings can actually help to disseminate knowledge in middle-income countries. Most regulators, policy makers and business representatives in the programme’s partner countries have themselves shifted to online working; online events have been cheaper and easier to organise, and often more widely attended.
- One way to gain recognition for UK funding whilst protecting a multilateral’s reputation for impartiality is to make the UK brand more visible with certain types of audience, and less visible with others. For example, in some countries, when hearing about UK support for reforms, business audiences are more receptive than host government audiences.
- Delivery partners are likelier to commit to ambitious results measurement and gender and inclusion activities when agreement is sought early in the programme cycle, and advice thereafter remains broadly consistent. Delivery partners may otherwise feel that extra requirements are destabilising, and “shifting the goalposts.”
- To create clear and consistent expectations, FCDO Business Cases should mainly refer to the central scenario (most likely outcome) throughout the document. GBE’s Business Case uses a target of 9 business environment reforms as its central scenario. Unhelpfully, the Business Case also refers three times to the possibility of ‘up to 25 major reforms’, which is its high-case scenario. Whilst Business Case authors may wish to convey what is possible, frequent references to the high-case scenario create uncertainty about what counts as good performance.
- G&I sensitisation/awareness raising with policy-makers and other decision-makers can help to ensure that they value G&I-related diagnostics and reform work, increasing the likelihood of progress and sustainability.

Summary of changes to the logframe since the last annual review
Indicators remain the same. The following targets were increased following the last annual review, as they had already been achieved:
- In the Global Window, the target number of peer-to-peer learning and capacity building events rose from 60 to 80. The target number of participants at these events (cumulative) rose from 1,200 to 3,500.
- In the global window, the target number of programmes leveraging GBEP’s research rose from 70 to 90. The target number of countries leveraging GBEP’s research rose from 60 to 85.
- In the country engagement pillar, the target number of learning and capacity building events rose from 90 to 120. The number of participants in these events rose from 1,800 to 5,000.

Summary of responses to issues raised in previous annual reviews
The programme has acted on 21 of the 22 recommendations from the last annual review, although six of these remain work in progress. Highlights include:
- New and clearer plans to validate the effects of programme-supported reforms on the real economy;
- A due diligence report showing that all reforms are expected, at a minimum, to “do no harm” to poor women and men (the reforms will benefit poor women and men);
- Higher targets for outputs that were previously not stretching (see above for details);
- Improved relations between the WBG programme implementers in Nigeria, and relevant Government of Nigeria stakeholders.
- HMG programme staff at Post feeling clearer about their roles and more satisfied with WBG’s efforts to coordinate and keep them informed.

One recommendation, to add milestone indicators to the programme’s results scorecard, was rejected by the delivery partner. WBG prefers to continue using its own format for results reporting, which does not include milestone indicators. The absence of milestones means we relied on reviewers’ judgement to assess the likelihood of output targets being met by the end of the programme. Where this is uncertain, our assessment has been cautious.
## C: DETAILED OUTPUT SCORING

Output Title	Clients and stakeholders engaged in business environment reform
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Number of beneficiaries/entities that receive [technical] assistance[7]	70	98 (140%)
Number of workshops, training events, seminars, conferences, etc.	120 (increased from 90)	141 (118%)
Number of participants in workshops, training events, seminars, conferences, etc.	5,000 (increased from 1,800)	8,993 (180%)
[7] ‘Beneficiaries’ refers here to government institutions and business associations in partner countries. The indicator counts the number of institutions receiving technical assistance to engage in reforms, not the number of businesses that ultimately benefit from the reforms themselves (which would be far higher).

Key Points

- The programme has assisted more host country government counterparts than targeted. 98 government counterpart agencies (target 70), across the portfolio of nine country projects, have been engaged in substantive policy dialogue.
- The number of workshops, seminars and events organised by GBEP’s country engagement has also exceeded the programme’s end target. 141 workshops, seminars, training events and conferences have been held to present and discuss the results of diagnostics, build consensus with counterpart agencies, and chart out pathways towards reforms. Nearly 9,000 stakeholders, representing both the public and private sectors, have participated in such events.
- So far, 40% of participants in programme events and workshops have been women. This is higher than the target (35%).[8] However, in Pakistan there has been limited female participation.
  [8] 90% of participant data is gender-disaggregated, so the 40% figure should be reasonably accurate. Gender-disaggregated data is missing in a few cases, for previous years. Source: GBE Results Scorecard, October 2020.
- Overall private sector participation has also exceeded expectations. However, although not all data is disaggregated by stakeholder type, progress towards several country specific private sector participant targets may not currently be on track to be met at the end of the programme. More specifically, in the Philippines and Nigeria where the targets are 620 and 500 private sector participants, respectively. In Malaysia there is currently zero recorded private sector participants, although private versus public sector disaggregated data is unavailable from the past year and the target of 20 should be attainable.
- Interviewees have commented that the quality of relationships between World Bank staff and country governments remains high and that the programme has swiftly repositioned itself and worked with local governments and stakeholders to pivot towards C-19 responses in both its Global Influence Window and its Country Engagement Window.
- The Country Engagement Window in particular has demonstrated strong progress on stakeholder engagement. In the Philippines for example, the programme has influenced thinking at the highest levels of government and supported the Anti-Red Tape Authority (ARTA) in the development of COVID-19 response measures. Furthermore, in Malaysia for example, several of the project’s policy recommendations have been adopted by the government and implemented as part of Malaysia’s economic stimulus and recovery measures.

Recommendations

Seek to strengthen private sector participation in partner countries where it trails expectations, particularly in Nigeria and the Philippines (and to a lesser extent Malaysia although private vs public disaggregated data is not available here for the past year).

## C: DETAILED OUTPUT SCORING

Output Title	Evidence collection, evidence informed analyses, strategies and policies generated with support from the programme
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Number of databases/surveys/diagnostics for policy (disaggregated by gender)	50	45 (90%)
Number of policy reports (e.g. assessments, manuals, policy notes) completed (disaggregated by gender)	70	74 (106%)
Number of new strategies/ policies drafted or contributed to the drafting	35	34 (97%)

Key Points
The programme is on track to deliver the target number of evidence related outputs, and has already surpassed the target for policy reports. Building on the extensive evidence based analyses of the first year, the programme developed new databases, including databases on regulatory risk; competition, looking specifically at antitrust regulation; and on digital platforms. Existing databases were updated, including the global databases on tax incentives and investment laws.

There is a strong feedback loop between country and global windows (although British Embassy Indonesia noted that there could be further strengthening of the lesson learning from the global window). In additional to informing country work within GBE, analytical outputs contributed to 31 investment climate reforms supported by WBG in non-GBE countries.
An example of using a strong evidence base to drive reform is illustrated by work in Indonesia, where in consultation with the private sector, the team published a benchmarking study on port tariff setting in Indonesia vis-à-vis other countries—including relevant logistics costs and issues faced by manufacturing companies—to spur a roadmap for reforms. Proposed changes to port tariffs, based on this analysis, have attracted government support, as the findings showed the potential for new tariffs to drive much-needed investment in port operations.
As the programme moves into its final year, it would be useful if further efforts could be made to measure the impact of the reforms which have been supported. There has been initial work in Brazil and South Africa, validating reforms. This would help inform future strategy development of investment climate reform by providing clear evidence of the benefits of different types of reform in each country context. See Output 4 below for a recommendation on this.
Recommendations
None, but see Output 4 below.
## C: DETAILED OUTPUT SCORING

Output Title	Legal, regulatory and administrative recommendations produced for partner governments
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Recommendations to laws/regulations/amendments/codes or recommendations to improve regulatory and legal environment	25	26 (104%)
Recommendations on procedures to be improved or eliminated	15	15 (100%)
Recommendations on business-enabling standards	2	1 (50%)

Key Points
- The programme is on track against this output, having met or slightly exceeded targets on two of the three indicators and achieved 50% on the third.
- Since the last annual review, the programme has recommended 10 improvements in legal instruments and 6 procedural improvements, in response to partner government requests.
- On business enabling standards, no further recommendations have been made since the last review. However, such recommendations are relevant only to the programme’s work in one of the nine partner countries (Nigeria). The programme is reasonably likely to achieve its target in the coming year.
- Interviewees consistently told us that programme-funded advice on business environment reform delivered has been well-received by host country governments. Host country government partners we interviewed in Brazil and the Philippines were keen to receive more advice in future.
- All countries broadly agreed with the identified pillars of intervention in their respective markets. They are comfortable with WBG’s methodology and Theory of Change.

## C: DETAILED OUTPUT SCORING

Output Title	Activities informed by crosscutting themes or advocating them
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Number of gender and inclusion related activities	9	20 (222%)
Number of country projects addressing gender and inclusion	6	9 (150%)

Key Points
- FCDO and WBG have prioritised reaching agreement on the approach to and ambition on G&I, and designing G&I activities in the nine focal countries. The programme now has G&I-focused interventions in all 9 focal countries [9]
  [9] Improving Business Environment for Prosperity Program, Gender and Inclusion Update (November 2020)
- Examples of G&I activities include: improving environmental licensing in Ceara, an economically underperforming region of Brazil; advising the Government of Nigeria on gender-related provisions in bilateral investment treaties; and training businesses and public sector organisations in Vietnam on gender mainstreaming.
- The number of activities has substantially exceeded the target. Particularly impressive is the programme’s efforts to support partner governments to gather and use better gender-disaggregated data. The review team noted seven separate activities here, informing investment promotion, competition policy and business skills training, as well as a review of discriminatory regulations in Indonesia. There are also early signs of innovation. The partnership in Pakistan with a large business association, encouraging its members to disclose their performance on gender-inclusive employment practices, is novel.
- The programme has also sought to ensure that poor women and men, and socially disadvantaged groups benefit from reforms in other ways. Firstly, many priority reforms are particularly relevant to MSMEs, such as online business registration in South Africa, and the ability to register a firm as a single person in Nigeria. SMEs are also likely to benefit from reforms that strengthen competition policy, e.g. through lower-cost inputs, where greater competition would drive down input costs. Secondly, the programme helps to tackle regional inequality, by offering expert advice to improve the business environment in poorer regions of Malaysia and Brazil.
- Whilst the number of gender and inclusion-related activities is commendable, it is hard to predict how many poorer women and men will benefit from them. The programme does not forecast its outreach. Meanwhile, the Mid-Term Evaluation raised concerns about lack of local ownership over many of these proposed reforms, making them less likely to happen, and less likely to last.[10]
  [10] Oxford Policy Management (2020) Mid-Term Evaluation of the IBEP programme.
- The programme conducted a pre-intervention assessment of the likelihood of its activities posing harm to the environment or social excluded groups, and concluded that its activities pose low or no risk. The review team is pleased to see that for the reforms directly affecting businesses, the programme plans to continue monitoring this, by surveying businesses to find out how reforms actually affect them. When doing this, this review recommends including enough micro, small businesses, and women-owned businesses, in the sample.[11] To verify that these businesses benefit as intended, or any further action is required to ensure their inclusion. Likewise, to understand any unforeseen consequences of reforms – positive or negative.
  [11] With the exception of reforms that do not target these groups directly, such as the Direct Investment Ombudsman reform in Brazil.
- The programme has not planned to measure the extent to which major reforms benefit poor women and men. WBG can reasonably argue that such assessments go beyond what they agreed to deliver – WBG agreed to assess that major reforms do no harm to poor women and men. The World Bank Group also feel that it is reasonable to assume that the economic growth resulting from major reforms will benefit poor women and men, without spending money to prove this beyond doubt. However, the circumstances under which growth is good for the poor continue to be debated within HMG. The risk of not doing additional measurement is that the programme facilitates major reforms which do benefit poor women and men, among others, but these benefits go unrecognised and unappreciated. Additional measurement could not only provide an opportunity to tell a positive story; further evidence that big business environment reforms in middle-income countries benefit poor women and men would strengthen the case for future HMG programming in this area.[12]
  [12] Another way to avoid this “under-appreciation risk” would be for the World Bank to analyse which economic shifts would make the most difference to women’s empowerment, in each target country. Once analysis is complete, the programme could then indicate which of its priority reforms contribute directly or indirectly to any of driving forces behind women’s economic empowerment. That said, it is beyond the scope of this review to assess whether primary data is available to facilitate such analysis – without such data the programme is unlikely to have time and money available to pursue this option.
- Global Influence research benefits Least Developed Countries (such as Burkina Faso, DRC and Mozambique) as well as middle-income countries. Tools developed by the Global Influence Window also support reforms to increase gender equity in ten countries. Notably, in Pakistan, a regulatory assessment tool developed with programme funding has contributed an amendment of the Companies Act, which brings the business registration process for women in line with that for men.[13]
  [13] The ten countries are Somalia, Liberia, Sierra Leone, Ethiopia, Mauritania, Tanzania, Uganda, Jordan, Lebanon and Pakistan. Source: IBEP progress report, Year 2 Half 2.
- The WBG’s perception is that they have heard varied opinions from FCDO on what constitutes good performance on G&I. Whilst WBG have adapted and added activities to accommodate requests, there is frustration at what implementers perceive as changes in advice. For example, the FCDO’s (internal) Business Case committed the programme to G&I processes and activities that were not specified in FCDO-WBG GBE Partnership Agreement governing the programme.
- The WBG central team continues to support and encourage country teams on G&I matters. For example, WBG has made assistance available to country teams from its central Women, Business and the Law advisory team, via the programme’s Global Influence Window.[14]
  [14] IBEP Y2H2 TWG minutes

G&I activities, like other activities, have adapted to support COVID-19 response.[15] This includes making country teams aware of risks of increased exclusion of youth from the labour market as a result of the Covid 19 pandemic.[16]
[15] IBEP Y2H2 June 17 2020 partnership council minutes
[16] Y2H2 progress report

Recommendations

- Deepen programme understanding of how major reforms benefit poor women and men. This could be done without much additional effort, based on qualitative as well as quantitative information. For example, by identifying companies that benefit from Brazil’s expanded Direct Investment Ombudsman and employ significant numbers of poor women and. Or by identifying categories of goods and services targeted at poorer women and men that benefit from Brazil’s modified anti-dumping laws. [Action: World Bank Group].
- Carefully consider feasibility, sustainability, past agreements and guidance on gender and inclusion before requesting new or different gender and inclusion activities. [Action: FCDO]
- When validating relevant reforms, include in the sample micro and small businesses, and businesses owned by women and marginalised groups. The programme already plans qualitative research to capture the effects of reforms on women and social excluded groups. This recommendation is to reinforce the importance of doing this.[17] [Action: World Bank Group]
  [17] This is one of several annual review recommendations that also features in the recent independent assessment of the programme’s processes to ensure gender and inclusion are adequately considered. See Prosperity Fund (2020) GBEP G&I scorecard: November 2020.

## C: DETAILED OUTPUT SCORING

Output Title	New knowledge, tools and guidance developed, contributing to global knowledge sharing and programme effectiveness (global level)
Output number per LF		5	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
# of publications and other data- and policy-based outputs (datasets, scans, diagnostic tools, toolkits, case studies, policy notes, etc.)	300	359 (120%)
# of peer-to-peer learning and capacity building workshops, training events, seminars, conferences, etc.	60	94 (157%)
# of participants in workshops, training events, seminars, conferences	1,200	4237 (353%)
% of female participants in workshops, training events, seminars, conferences	40%	48%
# of unique users who download outputs co-financed by the program and available online for public use	30,000	23,876 (plus 37,500 blog views)
% of Global Influence Window event participants who report being satisfied with the event	80%	91%

Key Points
The Global Window pivoted quickly to Covid-19 related response. The publication of the flagship product Global Investment Competitiveness Report (GIC), co-funded by GBE and the Austrian Government, was delayed from March to June to allow for inclusion of Covid related response. Other initiatives included:
- 2 rounds of ‘pulse’ survey of MNC affiliates in developing countries.
- A tracker of subsidies/state aid in response to Covid 19, which covered 480 initiatives in 120 countries.
- A tracker of policy changes effecting FDI entry was also produced
- Report on IPA response
- Incentives and investment linkages

Efforts have been made to strengthen the dissemination strategy. A new website was developed for the GIC https://www.worldbank.org/en/topic/competitiveness/publication/global-investment-competitiveness-report-2019-2020. The report has been downloaded by 10,000 users across 140 countries, and 5 virtual dissemination workshops were held with over 500 participants. The report has also been cited in key EU publications. A range of blogs have been developed to promote uptake of key research outputs. The blogs have been viewed 37 500 times.
Peer to peer learning has moved to online events in the wake of Covid-19. 34 events have been held with over 1500 participants, 91% of whom reported being satisfied with the outcome. The flagship programme peer to peer event was due to happen in March 2020. Due to Covid 19 it did not take place. A range of other specific peer to peer learning events did happen, such as one to link Pakistan to Brazil to learn about the experience of developing the Direct Investment Ombudsman.

Recommendations
Building on the efforts made to increase dissemination of the valuable learning outputs, further improve dissemination of outputs to non-World Bank audiences. Many of the useful research papers are difficult to find, unless potential readers know the exact titles, and where to look on the WBG website. Improved visibility on search engines would be useful. [Responsibility: World Bank Group]
Set more stretching dissemination targets for the Global Influence Window, for the remainder of the programme (subject to funding). [Responsibility: FCDO programme team and World Bank Group]

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The table below shows key spending areas over the last year. To help readers better understand forecast and actual spending, the table also includes data from previous years. This is necessary because HMG pre-pays the World Bank Group to deliver the programme, and some of the money HMG advances is spent on delivery in a subsequent financial year.

Project/Component	Year 0 (Nov 2017 - Mar 2018)	Year 1 (Apr 2018 - Mar 2019)	Year 2 (Apr 2019 – Mar 2020)	Year 3 (Apr 2020-Mar 2021) Spend	Total / Spend
GBEP total budget	£6,736,145	£3,450,000	£6,121,846[18]	£5,645,375[19]	£21,953,366
FCDO payments to World Bank	£6,500,000	£3,800,000	£7,500,000	£3,300,000	£21,100,000
FCDO admin budget	£236,145	£300,000	£406,700	£470,375	£1,413,220
WB Spend	£2,377,600	£6,236,000	£6,392,800	£2,864,000[20]	£17,870,4007
Country Engagement Window	£1,005,600	£4,449,600	£4,409,600	£1,768,000	£11,632,800
Global Influence Window	£1,000,000	£1,463,200	£1,387,200	£847,200	£4,697,600
Other Management Fees	£24,000	£127,200	£225,600	£83,200	£460,000
Trust Fund Admin Fee (5%)	£348,000	£196,000	£372,800	£165,600	£1,082,400
FCDO Admin Spend	£85,053	£219,458	£426,376	£271,472[21]	£1,002,359
FCDO Admin Costs (Salaries/Travel/Training)	£85,053	£219,458	£321,034	£143,256	£768,801
FCDO Platform Charges	£0	£0	£105,342	£128,216	£233,558
FCDO Actual Total Spend (Payments to WBG and FCDO Admin spend)	£6,585,053	£4,019,458	£7,762,038	£3,571,472	£22,102,359
[18] £1,875,000 was accrued in March 2020 and charged to 2020/21 budget. Original total Budget reduced due to this accrual at the end of the FY.
[19] Includes £1.875 million that was advanced during 2019/20, to be spent in FCDO’s FY 2020/21 (Apr-Jun). This arrangement was necessary due to differences in WBG’s and FCDO’s Financial Years. Original budget was £7,950,000; this was reduced in the ODA reprioritisation exercise in 2020.
[20] This figure, and the four beneath it, are April-Sept 2020 spend figures.
[21] This figure, and the two beneath it, are April-September 2020 spend figures.

Overall, the programme appears to cost less than expected.[22] In the year under review, this allowed it to maintain most activities despite the need to cut calendar year spending as part of HMG’s ODA Reprioritisation. A £3.3 million advance was originally intended to cover activity until December 2020; it is now expected to cover activity until March 2021.[23] As of September 2020, £3.23 million advanced to WBG remained to be spent; the programme team are confident that 80% or more will be spent by the end of FCDO’s Financial Year (March 2021), based on spending patterns. The next Annual Review may wish to check on this.
[22] WBG has so far spent £17.9 million, out of the £22 million budget for years 1-3. This is probably mainly a sign of a cautious approach to budgeting, whereby those setting the programme budget wanted to ensure it gave the programme enough resources needed to succeed, but were uncertain about exactly how much money was needed. Such an approach makes sense for a programme like GBE, where we cannot know exactly how many inputs will be required, and when, until the programme is underway. Different reforms require different experts. Only after the programme begins does it become clear exactly which reform should be prioritised. Priorities continue to shift during implementation, in response to changes in the political economy.
[23] A second funding payment was planned for Jan 2021. Due to budget reductions this second payment is deferred until April 2021 and is subject to the Spending Round outcome.

The key cost driver remains World Bank expert time and other personnel costs, at 76% of total project disbursements.[24] This was anticipated in the business case. Spending on travel and events meanwhile have decreased, given the travel restrictions related to COVID-19. In FY 19/20, the World Bank Group’s admin and reporting costs represented 8% of funding received, the largest component of which is a 5% trust fund administration fee. This is considered the standard rate for agreements with IFC, and is lower than fees charged under some World Bank Group agreements. FCDO's in-house admin spend on the programme, excluding platform costs, was 4.1% of programme spending FY 19/20, down from 5.5% in the previous financial year. The programme’s overall HMG admin spend so far is 4.2%, and projected to remain at a similar level. Without savings, the programme may struggle to meet its target of spending no more than 3.5% on in-house administrative costs. It is important to note however that options here are limited. The FCDO nine-country spread of the programme, and the value FCDO attaches to hiring a part-time staff member in each country, raises staff costs (but also has important benefits).[25]
[24] World Bank Group (2020) Improving Business Environment for Prosperity (World Bank Reference 72874) - Single Donor Fund. Unaudited Trust Funds Financial Report.
[25] Benefits of the nine-country model include the relative ease with which the programme can reallocate funds between countries, as described in the Risk section.

Recommendations:
Continue to look for opportunities to save on administrative costs, without substantially undermining the quality of programme management. [Action: FCDO]

VfM performance compared to the original VfM proposition in the business case
Economy
Quality of inputs: The business case set high expectations on quality, stating that the World Bank offers the best value for money as delivery partner due to its global reach, expertise and influence. Stakeholders we interviewed attested that the quality of this expertise and global reach match our high expectations. As described in Sections B and C, the WBG’s influence has probably exceeded expectations.

Cost of inputs: It has not been possible to compare the cost the programme’s main input, expert time, with other programmes. This is because the World Bank protects data on staff and consultant earnings; the programme relies on the WBG’s internal financial controls to deliver Economy in this area.

For analysis of administration costs, see Key Cost Drivers and Performance, above.

The programme has saved money on travel and events by shifting technical assistance and research dissemination online, following Covid-19 travel restrictions. Interviewees felt that, on balance, the quality of inputs has remained similar. This owes in part to the World Bank’s strong presence in the programme’s target countries, which has allowed in-country programme staff to maintain strong relationships with partner governments, even whilst some technical assistance has shifted online. The shift to online events, meanwhile, has enabled more people to participate; it does however inhibit the less formal exchange of knowledge that is often a by-product of face-to-face dissemination events.

Efficiency
Encouragingly, the programme is on track to achieve or exceed all of its quantitative output indicators, as described in Section C. The program uses several of these to assess the efficiency with which the programme converts inputs into outputs.[26]
[26] Number of participants in workshops; share of participants reporting satisfied or very satisfied with workshops, trainings, seminars, conferences, etc.; number of recommendations to laws/regulations/amendments/codes or recommendations to improve regulatory and legal environment; number of recommendations on procedures to be improved or eliminated.

In line with the positive feedback above on quality of inputs, the feedback we received on the quality of outputs was almost universally positive. This matters: the quality of outputs probably contributes more to the achievement of business environment reforms than the quantity. That said, the share of participants who reported being satisfied with programme events in the programme’s nine partner countries was 63%. With 90% of participants in Global Influence Window events reporting satisfaction, there may be room for improvement at the country level. That said, it may be that many of those counted as ‘not satisfied’ were simply people who attended an event, but who did not provide feedback on their satisfaction with it.

The programme has had to find savings during the year under review. Notably, the GBP-USD exchange rate has been, on average, around 20% lower than assumed in the Business Case; WBG incurs many of its costs in US Dollars. Savings have often been made by re-prioritising which reforms to pursue, when changes in partner country politics make certain reforms more feasible, and others less. The programme continues to drop or downscale support for business environment reforms that no longer appear as feasible. The programme’s design anticipated this need for adaptability, and did not prescribe precisely which reforms would be delivered in which countries. So reprioritisation of reform has not affected the overall Theory of Change.

Recommendations:
Investigate why a significant minority of participants are not satisfied with programme events in its nine partner countries. Use findings to drive continuous improvement.

Effectiveness
The Business Case made several assumptions about outcomes and effectiveness. Below, we test these based on evidence gathered in the past year.

Number of reforms: in its central scenario, the Business Case assumes that the programme will contribute to 9 major (economy-wide) reforms. Given that not all reforms targeted will be happen, the World Bank are pursuing 73 reforms, with varying degrees of likelihood, many of which are economy-wide. 28 of these have already been enacted, on paper. 12 are national-level reforms that will benefit businesses if implemented; 5 subnational and 11 are regulatory and policy process improvements.[27] We therefore believe that the programme is on track to exceed its target of 9 major reforms, although, as anticipated in the Business Case, most reforms can only be validated in the final years of the programme. When we also consider that the Global Influence Window has contributed to 22 additional reforms beyond the nine focal countries, the programme appears on track to exceed expectations.
[27] Author's calculations, based on ‘Table 3. Reforms Attained, Validation Approach and Timeline up to the end of Year 3 Half 1’ in World Bank Group (2020) IBEP Progress Report Year 3 H1: April 2020-December 2020, draft, 13/11/20.

Impact of reforms on the real economy: The Business Case assumes that all nine major reforms will benefit businesses and generate growth in the real economy. Globally, there are concerns that some business environment reforms approved by governments make little difference to how business is actually done.[28] For each major reform passed, the programme should therefore survey businesses (as part of a wider measurement plan), to check that businesses benefit from reforms as intended, as recommended in Section C3. Two economy-wide reforms have so far been validated as delivering benefits to the real economy. Our interviewees in the Philippines shared evidence that two further reforms are also benefiting businesses and consumers already. Further validation of reforms is planned for 2021 and 2022.
[28] Hallward-Driemeier, Mary and Pritchett, Lant. (2011) How Business is Done and The 'Doing Business' Indicators: The Investment Climate When Firms Have Climate Control. World Bank Policy Research Working Paper No. 5563, Available at SSRN: https://ssrn.com/abstract=1759154

Contribution of the programme to reforms: The Business Case assumes that some reforms would happen anyway; the programme’s capacity building and influence leads to more, faster and better reforms. Whilst impossible to know which reforms would have happened at the programme not intervened, we heard widespread and credible evidence that the programme has made reforms likelier. The Business Case cautiously assumed that the programme would only boost the likelihood of a perform happening by 1% – our assessment, based only on qualitative evidence, is that the programme’s contribution is higher. In Nigeria, for example, programme support for inter-ministerial coordination played an important role in the passage of the Companies and Allied Matters Act. While in the Philippines and elsewhere, while technical assistance has central to the identification of regulatory bottlenecks and the design of digital solutions.

Sustainability (longevity) of reforms: The business case assumed that the nine major reforms would all stick, continuing to benefit host economies for at least five years. The World Bank's long-term presence in countries, it was argued, gives it a greater ability than commercial suppliers to support the continued implementation of reforms. The review team saw evidence of this; interviewees praised WBG’s long history of advising partner governments on business environment reform, and expected WBG to continue doing so beyond the programme. That said, continued WBG presence does not by itself guarantee that reforms will last. Analysis of global trends suggests that reversals are common.[29] We cannot assume that all programme-supported reforms will last five years or more, particularly if new administrations show less commitment to open economies. Reforms also depend on the capacity of host country civil servants to implement them. Building partner government capacity to implement and sustain key reforms will be important in the final years of the programme.
[29] For analysis and discussion of the frequency of Reform reversals, see Gareth Davies (2017) is a genuinely sustainable, locally led and politically smart approach to business environment reform possible? Lessons from 10 years of implementing ENABLE in Nigeria. Adam Smith international and the Springfield Centre.

Recommendations:

- Continue to invest in building the capacity and evidence base to consolidate and sustain reforms [Responsibility: World Bank Group]
- Recommendations 5, 7, 11, 13 and 15 on the summary sheet also aim to improve programme effectiveness.

Equity
The OECD Gender Equality Marker score for this programme is 0, with gender not being specifically targeted within the programme.

Section C, Output 4 discusses in detail the integration of gender and inclusion considerations in design and implementation of reforms, and inclusion of women and marginalised groups in the benefits of reforms. To summarise:
- The programme’s VFM scorecard (November 2020) assessed the programme’s processes in relation to equity as “good”. The Prosperity Fund’s independent evaluation and learning suppliers, in their November 2020 assessment, concluded that the programme meets all the PF’s G&I policy minimum standards. This is a significant improvement on the last assessment in December 2019, where it met the minimum standard in only two dimensions[30].
  [30] GBEP Cycle 1 Evaluation December 2019
- All programme activities are vetted to ensure that they ‘do no harm’ to the interests of poor women and men, and meet WBG’s social and environmental safeguards. This review did not uncover any concerns that reforms might harm the interests of poor women and men.
- 17 programme activities also go beyond ‘do no harm’, and aim to improve gender equality or social inclusion.
- The programme has pursued more reforms than expected that seek to benefit women, marginalised groups and the least developed regions of partner countries.
- The likelihood of these reforms passing is lower, on average, than other reforms. Particularly where donor-driven, not driven by demand from partner governments.[31]
  [31] Oxford Policy Management (2020) Mid-Term Evaluation of the International Business Environment Programme. (Note: this report refers to the Global Business Environment programme, by another name.)
- It is reasonable to expect that women and marginalised groups benefit from most or all of the major reforms pursued by the programme. At this stage the programme however, we have limited evidence on how much major reforms will benefit poor women and men.

Assessment of whether the programme continues to represent value for money
Our assessment is that the programme continues to represent value for money. Costs are slightly lower than expected; inputs meet expectations in terms of quality; outputs exceed expectations; outcomes are on track to meet or exceed expectations.

The evidence on which we base our value for money assessment has improved in the past year. Acting on a recommendation from the last annual review, the programme has developed value for money indicators, which have been helpful in conducting the above analysis. A value for money scorecard, prepared by the Prosperity Fund’s independent Evaluation and Learning contractors, has also been useful. The scorecard also noted improvements in the programme’s processes for assessing value for money.[32]
[32] Prosperity Fund (2020) Global Business Environment Programme – Value for Money Scorecard, November 2020.

Quality of financial management
Day to day, finances are managed to WBG standards and subject to internal controls, which have been vetted and approved by previous programmes. FCDO receives quarterly financial updates from the delivery partner. FCDO and WBG also review the finances, including financial risks, at six-monthly working-level and director-level meetings. That these meetings they also jointly agree shifts in funding between programme components and countries.

The HMG programme team consider that the financial reports they receive are adequate, in terms of forecast accuracy. Reports detail spending by programme component, and quantify administrative and other costs. Differences between forecasts and actual spending are explained in the reports, and the six-monthly Council meetings. Explanations funds moved between programme components are also recorded in six-monthly Progress reports and in minutes of the six-monthly meetings.  Reports have been submitted on time.

To reduce the likelihood of funding in advance of need, the programme has shifted from annual advance payments to six-monthly payments. Typically, FCDO releases further funding only when the World Bank Group has spent 80% of its previous prepayment. Payments are set against rolling annual work-plans, which ensures flexibility and higher confidence forecasts will be met.[33]
[33] Prosperity Fund (2020) Global Business Environment Programme – Value for Money Scorecard, November 2020.

The FCDO Programme Manager reports spending on FCDO team salaries, expenses and platform costs monthly, to FCDO Finance Managers.

The Joint Funds Unit received accurate financial forecasts from the FCDO programme team at Supplementary Estimates; the programme spent just under 99% of their post-Supplementary Estimates allocation for FY19/20.[34]
[34] The table in Section D shows the programme's budget before it was revised during Supplementary Estimates. This explains the difference between the 99% figure quoted here and the data in Section D, which shows a greater difference between budget and actual expenditure.

Date of last narrative financial report	Nov 2020
Date of last audited annual statement	N/A

## E: RISK

Overall risk rating: Moderate (assuming continued funding)

Overview of programme risk
The programme team keeps a comprehensive risk register. The risk register for this programme was revised in November 2020. It comprises 27 risks: 2 green; 9 yellow; 14 amber and 3 red. The review did not uncover any major risks falling outside of the current risk register. The key risks are outlined below, along with comment on how the programme is managing them.
Key delivery risks relate to COVID-19 and uncertainty over future funding. These are in the “Red” category of the risks identified.
Were COVID-19 to spread widely among target beneficiaries, or among the WBG and FCDO delivery teams, this could delay or even derail delivery of key reforms and other, supporting activities. To mitigate this risk, where possible, programme management and technical assistance has moved to virtual delivery. The shift to online working has happened quickly and effectively, but COVID-19 remains a key delivery risk for the foreseeable future. COVID-19 also poses a delivery risk in that it changes host country governments’ priorities. As described in Sections B and C, the programme has mitigated this risk well, adapting its prioritisation of reforms and research to stay relevant to COVID-19 and subsequent economic recovery. It is also worth noting that in many countries, COVID-19 has made the programme more relevant than ever – host country governments have seen business environment reforms as cost-effective components of their economic recovery.
The reduction in HMG’s ODA budget for 2020/21 and 2021/22 poses significant risk. At the time of writing, we do not know if GBE will see a reduction in available budget next year. Clarity is expected before the next disbursement, scheduled for April 2021. Budget cuts may lead to a range of responses, including the cancellation of some planned activities, the pursuit of fewer reforms, a narrower geographical scope or an earlier and-date. Ending the programme early, in particular, would undermine value for money, given that many major reforms are in the pipeline and require modest extra programme support for fruition, and a number of delivered reforms require consolidation. An early end-date could also curtail the programme’s plans to validate reforms already achieved, which would deprive HMG of information on the important contributions this programme has made to inclusive growth, trade and investment with partner countries. Depending on how they handled, budget cuts could also affect HMG’s relationship with the World Bank, and will require careful handling and a collaborative response.
Another delivery risk is that outputs or outcomes are delayed when host government ministers and senior officials change. The programme has managed this risk well in the year under review.
A further, important delivery risk is that reforms have unintended negative consequences for women, socially excluded groups or the environment. The WB delivery team assesses and minimises this risk through pre-intervention assessments, applying the IFC Policy on Environmental and Social Sustainability[35] and requiring government clients to apply IFC’s Environmental and Social Performance Standards[36].
[35] Web address: https://www.ifc.org/wps/wcm/connect/7141585d-c6fa-490b-a812-2ba87245115b/SP_English_2012.pdf?MOD=AJPERES&CVID=kiIrw0g
[36] https://www.ifc.org/wps/wcm/connect/topics_ext_content/ifc_external_corporate_site/sustainability-at-ifc/policies-standards/performance-standards
The key operational risk is the programme lacking enough staff in target countries. The Mid-Term Evaluation noted that the absence of in-country WBG staff in Turkey may have hampered progress there. Other than that, the review team found nothing that suggested this risk has materialised so far.
A contextual risk is that the political economy in each host country changes, making certain reforms less feasible over time. To mitigate this risk, the programme periodically reallocates resources to reforms that remain feasible. The ability to move resources between countries has been helpful when, in certain countries, political changes have reduced the overall likelihood of business environment reforms happening.
To manage fiduciary risk, the programme benefits from the World Bank’s internal controls and long-standing experience of trust fund management.
The final risk is reputational. Given the size and breadth of activities, there is always a chance that something will attract criticism. To mitigate this risk, FCDO at Post and the WBG team need to communicate effectively around risks, and leverage their relationships with partner governments. The frequency and quality of communication between FCDO and WBG teams in the nine partner countries has generally improved during the year under review; in some countries FCDO staff still feel that WBG could be more proactive in information sharing.

Outstanding actions and recommendations from risk assessment
Continue to communicate proactively with FCDO staff at Post, to manage risks and expectations with host governments [Responsibility: World Bank Group]

## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme has largely been on track in the past year, despite the challenges posed by COVID-19 and reduction of ODA budgets. WBG responded to the pandemic effectively, swiftly moving to a virtual delivery model, thus reducing impact on continuity. WBG also accommodated a delay in disbursement; the next disbursement is now scheduled for April 2021, and subject to the outcome of the Spending Round. FCDO and WBG are planning how to respond to possible budget reductions.

Performance of partnership(s)
The working relationship with the World Bank is progressing well. Both FCDO and World Bank teams are comfortable in their interactions and expectations, and WBG has responded well to most FCDO requests, such as for extra validation of reforms. As mentioned above, there remains room for improvement in co-ordination between the World Bank Group and FCDO in some countries, although this has seen a marked improvement since the previous Annual Review.

Changes in the Delivery Plan
The major change in delivery plan has been to move to a virtual model, where possible, considering COVID-19. WBG has continued to provide business environment diagnosis and advice online. This continuity is partly due to the strength of relationships WBG enjoys in partner countries, particularly with regulators and other technical experts in host country public sectors. As mentioned in Section E, the delivery plan may change again in the year ahead, in response to budget reductions.

Asset monitoring and control
The Programme is not generating any assets, nor expects to, going forward.

## G: BUSINESS ENVIRONMENT

How has the business community and business environment responded to the programme?
Across GBEP’s nine countries, businesses have been engaged by WBG team with the support of local posts. The programme’s Global Influence Window regularly engages with the private sector through gathering experiences and perceptions. This year, in addition to the usual publication of the Global Investment Competitiveness Report (which included a survey of more than 2,400 business executives representing FDI in 10 large developing countries), business leaders were interviewed as part of a C-19 FDI Global Pulse Survey to assess the implications of C-19 on businesses and to guide governments’ policy responses.

Although at this stage there is currently limited validation of major reforms and the impact on the business community, one of the reforms which has been validated, establishing the Direct Investment Ombudsman (DIO) in Brazil, has delivered real benefits to foreign investors. The DIO has resolved 13 disputes since April 2019 from international investors. However, given the size of the Brazilian economy, we heard feedback that the Ombudsman could be usefully support from investors, and that further work to raise awareness of the Ombudsman among investors would add value.

Furthermore, with GBE support, the Government of Brazil has introduced mesas executivas, a new series of public-private dialogues. These dialogues are expected to provide a priority list of actionable reforms to reduce regulatory and bureaucratic bottlenecks constraining the business environment in Brazil.

Feedback from businesses, gathered as part of the Mid-Term Evaluation, was positive. In Vietnam, the programme has helped the national government to build local firms’ capacity to meet the demands of multinational enterprises. One foreign investor interviewed confirmed that COVID-19 increased the relevance of this work. With COVID-19 restrictions disrupting international supply chains, maintaining operations and reducing costs has become more important.

Feedback from businesses on the programme will continue to emerge in the next year as more major reforms are validated.

What role has non-ODA spending played in promoting programme objectives?
The Programme has received no non-ODA funding.

Recommendation:

Further raise awareness of Brazil’s Direct Investment Ombudsman among investors. [Action: HMG programme team, with DIT, particularly among UK investors in Brazil]

## H: MONITORING & EVALUATION

Evidence and evaluation
This year, the programme needed a Mid-Term Evaluation, in line with WBG practices, for the period November 2017 - March 2020. This was conducted by independent evaluators (Oxford Policy Management) and concluded in November 2020. Owing to COVID-19 restrictions, the review was conducted remotely and through virtual interactions. The programme was evaluated through a six-point framework covering Impact, Relevance, Sustainability, Coherence, Efficiency and Effectiveness. To avoid duplication of effort, the Prosperity Fund agreed not to conduct a separate evaluation of the programme during the year under review. Instead, the Prosperity Fund’s evaluation experts checked that Oxford Policy Management evaluators asked the key questions they would have asked.

The evaluation findings were largely positive. The evaluators praised the programme’s adaptable response to COVID-19, and the collaboration between global and country teams. The programme’s contribution to gender equality and social inclusion was scrutinised; a key recommendation was to make sufficient gender and inclusion expertise available to in-country implementation teams. A further recommendation was to invite more private sector feedback on reforms, especially during measurement of reform achievements. It was further recommended to review the Theory of Change, particularly at country level, based on on-the-ground political economy analysis. Lastly, it was recommended to enhance the programme’s external dissemination strategy, particularly for Global Influence Window products.

This was the second independent evaluation of the programme. The first, in 2019, is summarised in the last Annual Review.

Monitoring progress throughout the review period
WBG gathers data to track the progress of outputs and outcomes, reporting these two FCDO via detailed six-monthly Progress Reports. FCDO and WBG hold six monthly technical discussions, as well as the six-monthly Partnership Council Meetings at Director-level. As well as detailing the achievements and challenges from the previous six months, progress reports outline plans for the following 6 months.[37]
[37] FCDO staff in the 9 focal countries of the programme further also produce a quarterly report and in country Risk Registers. These feed directly into the programme quarterly reports produced by the London Programme Team. Monthly catch-up meetings between FCDO Post country teams and the London Based Programme team have been set up to allow the exchange of information.
One concern from this review is that WBG’s plans to validate reforms often list businesses as a ‘potential source’ for validation. The review team understands that COVID-19 travel restrictions and budget constraints make surveys more difficult. Wherever feasible however, we agree with the findings of the mid-term evaluation, that hearing from businesses about how reforms have affected them is central. Not all reforms will be implemented as planned – setbacks do not mean the programme has failed; learning what works and what does not is essential to improve future value for money.
The programme has uploaded indicators, baseline data and year 1 and 2 results to Prospero, the Prosperity Fund’s internal management information system.

Recommendations

- Further develop what makes a reform count as “major”, with specific consideration to business impacts on the ground. Then record progress of the programme’s contributions to major reforms specifically, via the scorecard. Whilst continuing to measure contributions to all reforms, including regional and process reforms. Using a similar definition to the Business Case would help future annual reviews to assess progress.[38] [Responsibility: World Bank Group]
  [38] In the business case, a major reform is defined as a reform that contributes around 0.114 % to a country’s GDP, or more. Given the practical impossibility of measuring the contribution of the reform to GDP, WBG would need to use expert (subjective) judgement to assess if a reform is major. Having a rough idea of whether a reform is ‘major’ is better than having no definition at all.
- Continue to monitor the political economy and prioritise among remaining reforms, to maximise impact, particularly in the event of budget cuts. [Responsibility: World Bank]
## Annex A: Annual Review 2019 - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Prosperity Fund: Global Business Environment Programme
Programme Value: £30m		Review Date: November 2019
Programme Code: GB-GOV-50-PF-08-GBE (including GB-GOV-3-PF-GBE-911; GB-GOV-3-PF-GBE-913; GB-GOV-3-PF-GBE-921)	Start Date: November 2017	End Date: March 2021

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2021/22
Programme Score	B	A
Risk Rating	Moderate	Moderate

Summary of progress and lessons learnt since last review

Since the last review in December 2018 the programme has geographically diversified into 3 new countries: Philippines, Malaysia and Vietnam in January 2019. The diversification was originally agreed by the then SRO and JFU in late 2018 and change request papers were submitted and approved by the Portfolio Board in July 2019.

The Theory of Change for Country Engagements has been reviewed and a new Theory of Change for the Global Window Initiative was produced. This exercise in turn has produced both country and global window results frameworks, which in turn inform the programme scorecard that includes indicators. These were approved at the May 2019 Partnership Council meeting.

In March 2019 the programme held a peer to peer learning event in Johannesburg, which had a focus on gender and inclusion, and the project has made a concerted effort and good progress in integrating these themes at the global and country project levels. Given the diverse nature of the policy work under the country engagement window, teams have identified various channels to incorporate gender-informed and gender-targeted activities in the projects’ design, with scope to do more on wider aspects of inclusion.

The programme has achieved 8 reforms since the last annual review in Brazil, Nigeria, Philippines and South Africa. Validation of these reforms is now ongoing.

The 1st Cycle Evaluation report was submitted to the programme team on 14th November 2019 and is currently being reviewed by the programme team and SRO. The Evaluation included a deep dive into South Africa, including a country visit to meet key stakeholders. The programme has also been able to upload indictors, baseline and first year values onto the Prospero system.

List of recommendations for 2019-2020

1. It is important that the programme measures the difference reforms make to the real economy and not just on paper. The World Bank should set a baseline for their impact indicators and a methodology should be put in place for tracking progress and validating reforms achieved after the programme closes. [Responsibility: World Bank]
2. Building on its environmental and social framework, the World Bank should ensure it has a mechanism in place for assessing and tracking its interventions to ensure they do no harm. [Responsibility: World Bank]
3. Consider whether there is scope to surpass business case expectations on inclusion, by supporting more reforms that benefit large numbers of poor and/or socially excluded women and men. For example, by targeting reforms in sectors where poor women and men or other excluded groups are most commonly employed. [Responsibility: World Bank]
4. FCDO makes it part of the job description of its PF-funded staff at Post to share updates on the passage of reforms with DIT colleagues (where relevant to UK and international investors) and leverage soft power benefits for the programme [Responsibility: FCDO programme team]
5. Agree on the approach to categorisation of outputs and indicators for the remainder of the programme in conjunction with the Prosperity Fund evaluation provider. The arrangement will continue to allow annual reviews to assess progress against the business case and avoid any deviation to reporting frameworks. Reporting from the World Bank should be aligned to this approach. [Responsibility: World Bank and FCDO programme team]
6. Estimate how much each indicator in the programme scorecard will change, year-on-year. Projecting how much each indicator will change, year-on-year, will make it easier to track progress of the outputs and make decisions on how to adapt programming to ensure outcomes are met. [Responsibility: World Bank]
7. As many of the end of programme indicator targets have already been achieved or are exceeding expectations at this stage of the programme, the programme team and the World Bank should consider agreeing more stretching targets for the remainder of the programme (where appropriate) [Responsibility: World Bank and FCDO programme team]
8. The World Bank should consider the scope for strengthening cross-learning between countries and with other HMG programmes, following the positive examples in this review period. [Responsibility: World Bank]
9. The FCDO programme team should reinforce guidance on the roles and responsibilities of PF-funded HMG staff at Post [Responsibility: FCDO programme team]
10. Proactively notify posts about opportunities for the UK to be visible in its support for World Bank-implemented GBEP activities, where this visibility will not unduly compromise the real and perceived independence and impartiality of World Bank advice. [Responsibility: World Bank]
11. Strengthen relationships with key government of Nigeria stakeholders around business environment reform. [Responsibility: World Bank]
12. The World Bank should increase its communication and dissemination of outputs from the global influence window. Publishing or linking programme outputs to the programme website might be one way of doing this. [Responsibility: World Bank]
13. FCDO should agree with the World Bank when and where the UK Aid and Prosperity Fund logos should feature on Global Influence Initiative publications funded by GBEP to increase visibility of PF funding [Responsibility: FCDO programme team]

1. The FCDO programme team should establish value for money indicators and systematically monitor these and hold regular discussions with the World Bank to ensure value for money is being achieved. [Responsibility: FCDO programme team]
2. Improve communication with Post before and after key meetings with the World Bank. For example, give Posts at least a week to comment on World Bank Progress Reports before the GBEP London programme team meets the World Bank to discuss the report. Posts only had two working days to provide comment on the Y2H1 Progress Report before FCDO programme team met World Bank for progress meeting. Giving additional time would allow Posts to be able to fully feed in their views on the programme including the alignment of interventions to host government objectives. [Responsibility: World Bank and FCDO programme team]
3. The World Bank should ensure it demonstrates the linkages between business community engagements (through workshops for example) in its development of linked outputs (e.g. new strategies or policies) across all markets, using the best practices adopted in Indonesia.