Guidance for Departments / A guide to choosing which IPA Assurance Reviews to include in the integrated Assurance and Approvals Plan for your Major Project / v2
[July 2017]

[back of cover – for printed publications, leave this page blank]

Crown copyright 2016
Produced by the Infrastructure and Projects Authority
You may re-use this information (excluding logos) free of charge in any format or medium, under the terms of the Open Government Licence. To view this licence, visit http://www.nationalarchives.gov.uk/doc/open-government-licence/ or email: psi@nationalarchives.gsi.gov.uk

Where we have identified any third party copyright material you will need to obtain permission from the copyright holders concerned.

This information is also available on the IPA website: https://www.gov.uk/government/organisations/infrastructure-and-projects-authority

# Contents

Introduction	04
Major Projects	04
Further advice and information	04
IPA Assurance Review Options	05
Who commissions the review?	05
When should the review happen in the project lifecycle?	05
Characteristics of the project to be reviewed	06
Primary purpose/s of the review	06
How is the review arranged?	07
Standard review team	08
Format of the review	08
Who receives the review report?	09
Format of the review report	09
How is the report used?	10

# Introduction
#
This document is designed to assist project teams when they are developing Integrated Assurance and
Approvals Plans (IAAPs) for the projects[1] that receive assurance from the Infrastructure & Projects Authority (IPA). It supplements the IPA’s Guide to planning Integrated Assurance and Approvals, which can be downloaded from the IPA website: https://www.gov.uk/government/organisations/infrastructure-and-projects-authority.
[1] For simplicity, the word ‘project’ refers to both projects and programmes throughout this document.

The following pages outline the assurance review options available from the IPA for inclusion in an IAAP.
This guidance does not cover the range of support tools used in the Early Development Pool projects (EDP) or the Consequential Assurance tools that may be used by the IPA to provide further assurance, investigation or support to Major Projects that are in difficulty. As such, consequential assurance is always tailored to address the specific issues and requirements of the project concerned, it cannot be included in an IAAP.
Major Projects
A Major Project is defined as a central government funded project or programme that requires HM Treasury approval during its life, as set out in Delegated Authority letters, or is otherwise of special interest to the Government.
If your project does not fit this description, this guidance will not be relevant to you, as the IPA does not provide assurance to projects outside the Government Major Projects Portfolio (GMPP).
All Major Projects fitting this description should be registered with the IPA for inclusion in the GMPP.
Further advice and information
Your organisation’s Programme and Project Management (PPM) Centre of Excellence (CoE), Support Unit, or Portfolio Management Office (PMO) (or equivalent), will be able to advise you on local IAAP requirements and on how to arrange an assurance review from the IPA. They will also be able to put you in touch with the relevant Operations Lead in the IPA - this person supports your (parent) department on its implementation of integrated assurance and approvals for Major Projects and on GMPP reporting.
Other enquiries can be sent to IPA@ipa.gov.uk
More detailed guidance on the different types of assurance review available from the IPA, can be downloaded from the assurance toolkit page on the IPA website: https://www.gov.uk/government/organisations/infrastructure-and-projects-authority.

# IPA Assurance Review Options

Planned assurance reviews for inclusion in Integrated Assurance and Approvals Plans (IAAPs)
Review / characteristics	Project Validation Review (PVR) / (Note: this is primarily used for EDP projects, and see notes below)		OGC Gateway™ / Gate 0	OGC Gateway™ / Gates 1-5	Project Assessment Review (PAR)
Who commissions the review?	Senior Policy Owner (SPO) / OR / Senior Responsible Owner / (SRO) if appointed		Senior Responsible Owner (SRO)	Senior Responsible Owner (SRO)	Senior Responsible Owner / (SRO) or IPA or / Chair of the HM Treasury’s Major Projects Review Group (MPRG).
When should the review happen in the project lifecycle?	Early stage in the policy or / business change development cycle before delivery is underway, and often before the SRO is appointed. / Undertaken ideally before development of the Strategic Outline Business Case (SOBC). / PVRs can be repeated. / PVRs can be used if a major strategic change in direction is being considered for an existing project.		A strategic review that is scheduled within a programme’s IAAP at relevant points in its lifecycle, e.g. to inform HM Treasury approvals or decisions at key milestones in the programme’s lifecycle / Gate 0 is specifically designed for the assurance of programmes, so is not applicable to projects. / Gateway 0s are repeatable and can be blended with a Gateway 1-5 of one of its constituent projects if timings allow, shown as e.g. a Gate 0/2.	A series of reviews that are scheduled within the project’s IAAP at five generic progression points in the lifecycle of the project. / Each of the five reviews are repeatable.	A PAR can be included in the IAAP (following discussion with the IPA) in place of one or all of Gates 0 - 5, if bespoke terms of reference are required. / OR / If the project is scrutinised by the Treasury’s Major Projects Review Group, a PAR will be conducted to inform the MPRG Panel meeting, at any chosen point in the project lifecycle.
Planned assurance options for inclusion in Integrated Assurance and Approvals Plans (IAAPs)
Review / characteristics		Project Validation Review (PVR)	OGC Gateway™ / Gate 0	OGC Gateway™ / Gates 1-5	Project Assessment Review (PAR)
Characteristics of the project to be reviewed		A major policy initiative or business change that is likely to be delivered through the vehicle of a Major Project. / Can also be used at enterprise portfolio level, to review the overall change agenda.	A programme that fulfils the criteria for a Major Project, even though some or all of its component projects may not individually be considered ‘major’.	A Major Project that is being delivered using a standard methodology, with clear approval and progression points.	A Major Project requires a a tailored assurance review set out in bespoke terms of reference. / NB. Always speak to your IPA Project Specialist if you think your project requires a PAR.
Primary purpose(s) of the review		To explore the critical aspects required for setting up a project effectively, plus additional exploration as relevant to the individual initiative. / Provide support to the department on the options for delivering the policy or business change, with a focus on whether any emerging options/solutions will deliver the required outcomes. / Avoid reputational risk of undeliverable commitments being made to the public.	Assessment of Delivery Confidence / Provide findings and recommendations to the SRO / Provide an assurance report to inform investment board and/or HM Treasury approval point.	Assessment of Delivery Confidence / Provide findings and recommendations to the SRO / Provide an assurance report to inform investment board and/or HM Treasury approval point.	Provide a tailored but strategic analysis across a number of complex issues and/or cross government dependencies. / Provide findings and recommendations to the SRO. / Provide an assurance report to inform investment board and/or HM Treasury approval point. / AND/OR / Inform an MPRG Panel meeting discussion.

Planned assurance options for inclusion in Integrated Assurance and Approvals Plans (IAAPs)
Review / characteristics	Project Validation Review (PVR)	OGC Gateway™ / Gate 0	OGC Gateway™ / Gates 1-5	Project Assessment Review (PAR)
After initial contacts with IPA how is the review arranged?	Annex A of the Risk Potential Assessment (RPA) form submitted. / An assessment meeting is held between the IPA and the SPO/SRO to clarify the scope and timing before a Review Team can be booked. / The Review Team hold a planning meeting with the SPO/SRO to agree Terms of Reference for the review and to arrange logistics & schedules including attendees for workshops or interviews. / A limited set of key documents are provided to the Review Team as pre-reading. / The review will normally take place 6 to 8 weeks after the assessment meeting.	A Risk Potential Assessment (RPA) form is submitted to the IPA. / An assessment meeting is held between the IPA and the SRO to clarify the assurance, scope and timings requirements before a Review Team can be booked. / The Review Team hold a planning meeting with the SRO to agree Terms of Reference for the review and to arrange logistics including outline interview schedule. / Key documents are provided to the Review Team as pre-reading. / The review will normally take place 10 to 12 weeks after the assessment meeting.	A Risk Potential Assessment (RPA) form is submitted to the IPA. / An assessment meeting is held between the IPA and the SRO to clarify the assurance requirements before a Review Team can be booked. / The Review Team hold a planning meeting with the SRO to agree Terms of Reference for the review and to arrange logistics including outline interview schedule. / Key documents are provided to the Review Team as pre-reading. / The review will normally take place 10 to 12 weeks after the assessment meeting.	A Risk Potential Assessment (RPA) form is submitted to the IPA. / An assessment meeting is held between the IPA and the SRO to clarify the assurance requirements before a Review Team can be booked. / The Review Team hold a planning meeting with the SRO to agree Terms of Reference for the review and to arrange logistics including outline interview schedule. / Key documents are provided to the Review Team as pre-reading. / The review will normally take place 10 to 12 weeks after the assessment meeting.

Planned assurance options for inclusion in Integrated Assurance and Approvals Plans (IAAPs)
Review / characteristics	Project Validation Review (PVR)	OGC Gateway™ / Gate 0	OGC Gateway™ / Gates 1-5	Project Assessment Review (PAR)
Standard review team[2] (excluding assessment and planning meetings)	2 or 3 reviewers x 2 days	3 or 4 reviewers x 3-5 days	3 or 4 reviewers x 3-5 days	3 or 4 reviewers, x up to 5 days / This review team should include a departmental representative who is independent of the project team and able to provide understanding of wider departmental context, culture and strategic direction.
Format of the review	A workshop(s), supported by interviews, if required with policy team members and stakeholders. / Wash up meetings with the SPO/SRO at end of day. / A draft report submitted at the end of the on-site review period and agreed within a week of completion.	A series of confidential and non-attributable interviews with project team members, stakeholders and suppliers. / Daily progress meetings with the SRO. / A draft report submitted at the end of the on-site review period and agreed within a week of completion.	A series of confidential and non-attributable interviews with project team members, stakeholders and suppliers. / Daily progress meetings with the SRO. / A draft report submitted at the end of the on-site review period and agreed within a week of completion.	A series of confidential and non-attributable interviews with project team members, stakeholders and suppliers. Option to include a hour risks and issues workshop, / Daily progress meetings with the SRO. / A draft report submitted at the end of the on-site review period and agreed within a week of completion.
[2] These can be adjusted at IPA discretion, but are the standards used by the IPA for resource planning purposes, unless agreed otherwise by the relevant Operations Lead.

Planned assurance options for inclusion in Integrated Assurance and Approvals Plans (IAAPs)
Review / characteristics	Project Validation Review (PVR)	OGC Gateway™ / Gate 0	OGC Gateway™ / Gates 1-5	Project Assessment Review (PAR)
Who receives the review report?	SPO /SRO / IPA & Departmental Assurance Coordinator (DAC) / HM Treasury Spending Team / Wider circulation within the department by the SPO/ SRO. / The report may be shared by the IPA with other relevant interested parties at the centre, such as / Government Digital Service and/or the Government Commercial Services.	SRO / IPA & DAC / HM Treasury Spending Team / Wider circulation within the department by the SRO. / The report may be shared by the IPA, after discussion with the SRO, with other relevant interested parties at the centre, such as Government Digital Service and/or the / Government Commercial Service.	SRO / IPA & DAC / HM Treasury Spending Team / Wider circulation within the department by the SRO. / The report may be shared by the / IPA, after discussion with the SRO, with other relevant interested parties at the centre, such as Government Digital Service and/or the / Government Commercial Services.	SRO / IPA & DAC / Treasury MPRG Panel (if appropriate) / HM Treasury Spending Team / Wider circulation within the department by the SRO. / The report may be shared by the IPA, after discussion with the SRO, with other relevant interested parties at the centre, such as Government Digital Service and/or the / Government Commercial Services.
Format of the review report	Standard format covering the three mandatory topics, with some flexibility for tailoring. / No Delivery Confidence Assessment	Standard format template / Delivery Confidence Assessment	Standard format template / Delivery Confidence Assessment	Standard format template that allows a lot of flexibility for tailoring to reflect the bespoke Terms of Reference and meeting MPRG Panel requirements. / Delivery Confidence Assessment

Planned assurance options for inclusion in Integrated Assurance and Approvals Plans (IAAPs)
Review / characteristics	Project Validation Review (PVR)	OGC Gateway™ / Gate 0	OGC Gateway™ / Gates 1-5	Project Assessment Review (PAR)
How is the report used?	Informs departmental discussions about viability of the potential project. / SPO/SRO actions the findings and the recommendations to design, scope and develop a project. / HM Treasury Spending / Team will expect to see the report at the next approval point.	SRO actions the findings and the recommendations / HM Treasury Spending Team will expect to see the report at the next approval point. / A poor Delivery Confidence rating may as a consequence trigger further investigation, / support and/or intervention from the IPA	SRO actions the findings and the recommendations / HM Treasury Spending Team will expect to see the report at the next approval point. / A poor Delivery Confidence rating may as a consequence trigger further investigation, support and/or intervention from the IPA	SRO actions the findings and the recommendations / HM Treasury Spending Team will expect to see the report at the next approval point. / If the project is subject to MPRG Panel scrutiny, the report will inform MPRG Panel meeting discussions and lines of questioning. / A poor Delivery Confidence rating may as a consequence trigger further investigation, / support and/or intervention from the IPA