## Version control
V. no. | Changes made | Made by | Date
1.
2.
3.
4.
5.
6.
7.

## Guidance
Contract Management Planner - Guidance
1 | The purpose of the Contract Management (CM) Planner is to enable Contract Managers to map out and monitor all the required activities over the specific contract's life span. This guidance only covers the delivery period of the contract (i.e. from the day the supplier starts delivering the contracted provision to contract exit). Detailed guidance on Contract Management activities during procurement, mobilisation and implementation can be found in the Contract Management Standards Guidance, which is being developed by CCS (Crown Commercial Service).
2 | The CM Planner enables mapping of both routine and ad hoc contract related activities (e.g. such as regular supplier reporting and intermittent benchmarking), as well as key contractual dates (e.g. deadlines for provision and payment of invoices). The activities are grouped under main headings (e.g. review, comment, improve cycle for supplier quarterly KPI reports).
3 | This document is designed to supplement the practical and strategic guidance on contract management provided by the departments and the contract-specific CM Operations Manual (Tier 1 / 2 suppliers) and Process Maps (all contracts).
4 | As a starting point, the CM Planner template is already populated with the most common contractual activities. Contract Managers should review and customise the activity list provided in accordance with the specifics of the contract they manage, as follows: a. If the listed activity is included in the contract - add contractual reference, responsible party, frequency and the timing of the activity under relevant month/s b. If the listed activity is not in the contract, but required - agree frequency, responsible party, and dates with relevant internal and supplier stakeholders and update the CM Planner accordingly c. If the listed activity is not relevant to scope and nature of the contract - delete it from the CM Planner d. Add any contract-specific provisions, which are not on the provided list and which require scheduled activity from client CM team or the supplier
5 | As many CM activities overlap, and therefore can be listed under more than one heading, the following conventions are suggested for grouping activities: 'Governance' - Includes liaison (meetings), administration and update of governance documents 'Performance Management' - only includes client side activities. The supplier role is covered in 'Reporting' and 'Governance' 'Continuous Improvement' - includes elements of Supplier Performance Management (SPM)
6 | The CM Planner worked example illustrates how the template can be utilised in practice
7 | To ensure that all scheduled activities take place, use the CM Planner Monitoring template provided, which allows both Contract Managers and their line managers to monitor progress on scheduled activities. It can be used for a single or multiple contracts, depending on the remit of the Contract Manager/ team using it.
8 | The CM Planner Monitoring example provides detail on how the template can be populated, using a specific month from the CM Planner worked example for demonstration
9 | The CM Planner should be regularly updated, specifically when the following occurs: a. Changes made to the contract that impact on contract-related activities or frequency b. The Contract Management team is restructured or individuals named in the CM Planner change c. Contract Managers agree contract-related procedural/ operational changes either internally or with the supplier, which may not result in changes to the contract, but impact the activities in the CM Planner

## CM Planner - template
Contract Name: |  | [Insert Contract Name] | [6 empty] | Contract Ref.: | [Insert Contract Ref] |  |  | Contract Period: | [Insert contract period]
Contract type
Ref. No. | Category | Activity | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Detailed action | Contract Ref. | Responsible Party | Frequency | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Reporting | Performance reports | X | X |  |  | Ensure Performance Report provided by the supplier by contractual deadline
2 | Reporting | KPI dashboard | X | X | X | X | Ensure KPI report provided by the supplier (if separate from Performance report) by contractual deadline
3 | Reporting | Development plans | X | X |  |  | Ensure Service Development Plan provided by supplier
4 | Reporting | Client reports | X |  |  |  | Client side report on contract performance submitted to contract board/ SMT/ key stakeholders
5 | Performance Management | Performance reports review | X | X |  |  | Review the reports and escalate any underperformance issues via agreed routes
6 | Performance Management | KPI dashboard review | X | X | X | X | Review the KPI dashboard and escalate any underperformance issues via agreed route
7 | Performance Management | Improvement plan implementation | X | X |  |  | Review if benefits identified in suppliers development plan have been delivered by agreed deadlines
8 | Performance Management | Contractual milestones | X | X | X | X | [For works/ project/ phased contracts] Review if the relevant milestones were achieved by supplier and escalate any delays
9 | Performance Management | Site visits | X | X | X | X | [For works/ FM/ ICT etc. contracts which include tangible deliverables on client sites, e.g. cleaning, maintenance, IT support etc.] Attend site with supplier [end user/ stakeholder] representatives to: a. Ensure that all the contracted provisions have been delivered b. Ensure that the delivery is to contractual standard c. Gain feedback from end users
10 | Governance | Supplier performance/ operational meetings | X | X | X | X | Schedule/ attend/ administer meeting
11 | Governance | Board meetings | X | X |  |  | Schedule/ attend/ administer meeting
12 | Governance | End user/ stakeholder meetings | X | X | X | X | Schedule/ attend/ administer meeting
13 | Governance | Category/ departments CM meetings | X | X | X | X | [Add any regularly scheduled category/ departmental meetings relating to scope/ sub-category of the contract]
14 | Governance | Contract Management Operations Manual | X | X |  |  | Review and update Ops Manual with any changes to contract, processes or procedures
15 | Governance | Supplier handbook (service details for end users) | X | X | X | X | Review the handbook and ensure it is updated with latest contact details and any changes to KPIs/ Call-offs/ scope of service etc
16 | Governance | Change review | X | X | X | X | Ensure any changes made to the contract during previous financial year are reflected in: a. Contract documentation (with authorised change documents) b. Contract budget c. Supplier performance and provision
17 | Financial | Invoice payment authorisation | X | X | X | X | Ensure supplier invoice includes all required information and/or authorisations/ sign-offs from end users and authorise payment, within contractual timescales
18 | Financial | Annual budget review | X | X | X | X | Conduct annual contract budget review at the end of the financial year, to: a. Assess spend against projected costs for previous financial year, flagging up and escalating any significant increase/ decrease in spend and the reason for it b. Ensure any expected savings, rebates, credits and profit share for the financial year have been provided. Flag up and escalate if any of these haven't been provided or are not at expected levels c. Make any required budget adjustments for next year, to accommodate: 1. Indexation 2. Contractual changes 3. Changes to demand for call-off type provision 4. Changes to costs following benchmarking/ VFM review
19 | Financial | Benchmark report | X | X |  |  | Ensure benchmark reports provided by supplier or commissioned from third party, in accordance with contractual provisions
20 | Financial | Benchmark report review | X | X |  |  | Review and comment on benchmark report within contractual timescales
21 | Financial | Benchmark cost adjustment | X | X |  |  | Ensure adjusted costs agreed within contractual timescales, or escalation/ dispute/ exit invoked, if no agreement is reached
22 | Financial | Financial stability of the supplier | X | X | X | X | Conduct periodic check of supplier financial stability (eg Dun & Bradstreet)
23 | Risk | Risk Register | X | X |  |  | Review and update the risk register | bar: Nov
24 | Risk | Contingency plans | X | X | X | X | Review and update the contingency plan
25 | Insurance | Insurance renewals | X | X | X | X | Ensure relevant insurances and indemnities provided under, or linked to the contract are renewed prior to expiry of previous policies
26 | Continuous Improvement | Contract benefits review | X | X | X | X | a. Review and update the expected benefits, in line with the latest priorities of the contracting organisation, which are relevant to the contract b. Review if the contract scope, length, and provision methods are in line with the updated benefit expectations c. Recommend amendments/ amend the contract to align with the latest set of benefits
27 | Continuous Improvement | Supplier development plans review | X | X |  |  | Service Development Plans reviewed and agreed with supplier for implementation
28 | Continuous Improvement | CM governance review | X | X | X | X | [Task for the line manager of the Contract Management function or internal review team/ audit] a. Review that there is sufficient staff for the scope of CM work and that staff are adequately trained, appraised and have required commercial and contractual understanding b. Review that the IT resources and systems used for CM are fit for purpose and effectively used b. Confirm that risk, cost and performance are under control
29 | Continuous Improvement | Review of supply chain development | X | X |  |  | [For contracts with sub-contractors identified in the contract or specific SME support provisions] Review the management of sub-contractors with supplier, specifically in terms of (assuming open book accounting provisions included in the contract): a. Rates paid to sub-contractors b. Profit margins retained by main supplier c. Timescales for sub-contractor payments from payment of main supplier invoice by client d. SLA/ KPI targets set for sub-contractors e. Sub-contractor selection process f. Sub-contractor performance review process g. Sub-contractor training and development
30 | Exit | Alternative provision planning | X | X | X | X | [at least 6 months prior to contract expiry date] Agree with Category lead: a. Best route to market b. Strategies for market warming c. Required changes to scope and specification d. Required changes to SLA/KPIs
31 | Exit | Contract extension deadline | X | X | X | X | [If contract includes extension options, include the deadlines by which such extension should be authorised by the procuring organisation and confirmed to supplier, with advance notice period to give time for required authorisations to be obtained by deadline]
32 | Exit | Exit Plan/ handover information | X | X | X | X | Ensure Exit plan/ handover information is provided by supplier in accordance with contractual timescales/ prior to contract expiry
33 | Exit | Exit management | X | X | X | X | [include time dependent activities from Exit plan)

## CM Planner - example
*Worked Example for guidance only*
Contract Name: |  | Joint venture for provision of professional advisory services |  |  | Contract Ref.: | XXX |  |  | Contract Period: | March 2007 to Feb. 2017
Ref. No. | Category | Activity | Detailed action | Contractual Ref. | Responsible Party | Frequency | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Reporting | Performance reports / KPI dashboard | Quarterly reports on performance against 12 KPIs. contractor to provide supporting documentation on request. (See KPI worksheet for details of what and how monitored) | 7.1, 21A Schedule 2, 17 (KPIs) (Quarterly reports), Annex 9 (KPIs) | Contractor - provide reports Contract Manager - approvals or notice to issue improvement plan if KPI failed on 2 occasions in any 12 rolling months | Quarterly (February, May, August and November) | contractor/ Client query feedback received | Report due (Feb. 2012 will be first time improvement report is due if any KPI failed twice or more in previous 12 months) |  | contractor/ Client query feedback received | Report due |  | contractor/ Client query feedback received | Report due |  | contractor/ Client query feedback received | Report due
4 | Reporting | Business Plan issue | Draft business plan submitted no later than 6 weeks prior to end of Financial year. The plan to be agreed 2 weeks before end of Fin. Yr. | 9.2 (requirement); 9.3 (content) | Contractor - provide plans Contract Manager - approvals | Annual | Feb: 6 wks prior to end of Fin. Yr; Contract Period: Mar: 2 wks prior to end of Fin. Yr
5 | Reporting | Audited accounts provision | Provide audited accounts within 6 months of the relevant accounting reference date | 14.9 | Contractor- report Contract Manager - check audited accounts provided | Annual | March 2007 to Feb. 2017 Nov: X (within 6 months of audited accounts reference date)
6 | Reporting | Reports on undertaken work | Progress reports on works undertaken | 19.2 | Contractor- report Contract Manager - check reports provided and work of adequate level | Quarterly (February, May, August and November) | bar: Feb; March 2007 to Feb. 2017 May; March 2007 to Feb. 2017 Aug; March 2007 to Feb. 2017 Nov
7 | Performance Monitoring | Performance reports / KPI dashboard review | If KPI failed > contractor to provide programme for improvement of performance on the specific KPI within 20 days of notice issued by Client. Client has 20 days to confirm if the improvement programme is accepted. (if improvement is not achieved within timescales in the agreed programme, the contract may be terminated) |  |  |  | contractor/ Client query feedback received |  | Client queries submitted | contractor/ Client query feedback received |  | Client queries submitted | contractor/ Client query feedback received |  | Client queries submitted | contractor/ Client query feedback received |  | Client queries submitted
8 | Governance | Annual Performance review meeting | Annual review of the companies' performance over the past year | Sch. 2, 4.4 | Contractor/ Contract Manager- joint attendance | Annual | bar: Contract Period: Mar
9 | Governance | Supplier performance/ operational meetings | Meetings with Managing Director to review performance | 7.5 | Contractor - set up Category Manager - attendance | Bi-monthly | Jan: X; Contract Period: Mar: x (Annual meeting (see 8 above); March 2007 to Feb. 2017 May: x (Business plan review); March 2007 to Feb. 2017 Jul: X (profit share update; Hourly fees sign off); March 2007 to Feb. 2017 Sep: X; March 2007 to Feb. 2017 Nov: X
10 | Governance | Board meetings | Meetings between Category Representative and Managing Director | Sch. 2, 4.3 | Contractor/ Category Representative - joint attendance | Monthly | x (review of KPI query feedback from contractor) | x | x (review of Client KPI queries) | x (review of KPI query feedback from contractor) | x (Hourly fees review; Profit share review and sign off) | x (review of Client KPI queries) | x (review of KPI query feedback from contractor) | x | x (review of Client KPI queries) | x (review of KPI query feedback from contractor) | x | x (review of Client KPI queries) (audited accounts review)
11 | Financial | Hourly rates review | Review of adjustments needed to hourly rates on basis of criteria set in 14.2.1-3 | 14.2 | Contractor/ Contract Manager - joint review | Annual | March 2007 to Feb. 2017 Apr: 2011-04-01
12 | Financial | Profit share approval (Discount) | Parties agree a service Discount (profit share based on 50%/50%) for following financial year | 14.5 | Contractor - provide proposals Contract Manager - review and approve | Annual | March 2007 to Feb. 2017 Apr: 2011-04-01
13 | Financial | Profit share payments | Discount (see 6 above) paid in quarterly instalments | 14.6 | Contractor - payments Finance Manager - check relevant credit is provided in the monthly invoice | Quarterly (April, July, Oct. and Jan.) | Jan: 1 Jan.; March 2007 to Feb. 2017 Apr: 2011-04-01; March 2007 to Feb. 2017 Jul: 2011-07-01; March 2007 to Feb. 2017 Oct: 2011-10-01
14 | Financial | Profit share adjustment (Discount adjustment) | Discount (see 6 above) adjusted if actual profit is higher than the estimated profit, on 50%/50% basis | 14.7 | Contractor - payments Finance Manager - check relevant credit is provided in the monthly invoice | Annual | March 2007 to Feb. 2017 Jul: X (14 days from determination of Actual Operating Profit)
15 | Financial | Benchmarking | VFM review takes place 2011 and 2014, March-May. Both parties can agree extensions. If VFM not delivered, remedial programme to be put in place by contractor (schedule 4). Client to respond within 20 business days. If actions not achieved by deadlines contract can be terminated. | 3.2 and 8 Schedule 4 (VFM procedure) | Contractor - provide reports Contract Manager - approvals | 2011 and 2014 | Contract Period: Mar: 1 March 2011 1 March 2014 (Start); March 2007 to Feb. 2017 May: 1 May 2011 1 May 2014 (End)
16 | Risk | Risk register | A review of the Risk Registers | Internal procedure | Contract Manager | Bi-annual | bar: Contract Period: Mar; March 2007 to Feb. 2017 Sep
Etc.

## CM Planner Monitoring -template
Contract Name/ Ref. | Ref. No. | Category | Activity | Detailed action | Contract Ref. | Responsible party | Action deadline | Progress (choose from drop down menu) | Comments | Completed | Completed
[10 empty] | In progress | In progress
[10 empty] | Delayed | Delayed
[10 empty] | Not started | Not started

## CM Planner Monitoring - example
*Worked example of monitoring for guidance only*
Contract Name/ Ref. | Ref. No. | Category | Activity | Detailed action | Contract Ref. | Responsible party | Action deadline | Progress (choose from drop down menu) | Comments | Completed
Professional Services JV | 7 | Performance Monitoring | Performance reports / KPI dashboard review | If KPI failed > contractor to provide programme for improvement of performance on the specific KPI within 20 days of notice issued by Client. Client has 20 days to confirm if the improvement programme is accepted. (if improvement is not achieved within timescales in the agreed programme, the contract may be terminated) | 7.1, 21A Schedule 2, 17 (KPIs) (Quarterly reports), Annex 9 (KPIs) | Contract Manager - approvals or notice to issue improvement plan if KPI failed on 2 occasions in any 12 rolling months | 2014-04-30 | In progress | 01/5/14 - Reports provided, but two KPIs failed for 2nd time. Notice to Improve issued | In progress
Professional Services JV | 9 | Governance | Supplier performance/ operational meetings | Meetings with Managing Director to review performance | Sch. 2, 4.3 | Contract Manager - review of KPI query feedback from supplier | 2014-04-30 | Completed | 15/4/14 - meeting took place and KPIs reviewed, with follow up action agreed. However see action in 2 regarding latest report. | Delayed
Professional Services JV | 11 | Financial | Hourly rates review | Review of adjustments needed to hourly rates on basis of criteria set in 14.2.1-3 | 14.2 | Contract Manager - joint review and agreement on adjustments | 2014-04-30 | Delayed | 4/5/14 - supplier provided proposals, but there are is a dispute on two of the proposed amendments to hourly rates | Not started
Professional Services JV | 12 | Financial | Profit share approval (Discount) | Parties agree a service Discount (profit share based on 50%/50%) for following financial year | 14.5 | Contract Manager - review and approve proposals provided by client | 2014-04-30 | Delayed | 1/5/14 - Supplier yet to issue the proposed discount proposal. Chased and will chase again and escalate if not provided by 10/5/14
Professional Services JV | 13 | Financial | Profit share payments | Discount (see 6 above) paid in quarterly instalments | 14.6 | Finance Manager - check payment made | 2014-04-30 | Completed | 1/5/14 - Discount included in latest invoice as credit