FCO SPF PROJECT EVALUATION

Sections 1-3 to be filled out by Programme Teams / Post

Project Details
Project Number / (GB-3-xxxxxx ABC) / ABC = 3 digit country code from OECD	PHR COB 161401
Project Title	Risk Maps to track electoral irregularities in the 2014 Elections
Project Cost (total cost / cost to FCO if different)	Planned budget: £38,885 / Final Spend: £38,887
Project Start/End Dates	1 June2013 – 9 March 2014
Programme	Human Rights and Democracy Programme (HRDP)
Country/Countries	Colombia
Official Development Assistance Y/N	Y

Project Purpose (from proposal form)
Strengthening state institutionalism in order to guarantee transparency for the electoral process. Legislative elections will be carried out on 9 March 2014.

Project Background / Context including what the project set out to achieve (150 words max)
The project aimed to reduce electoral risks, including fraud, violence and other crimes, for the March 2014 legislative elections, given a history of massive and systemic electoral irregularities in previous elections. This negatively affects citizen participation (as voters or candidates) and trust in the results. It aimed to produce two main outputs. The first, an update of the implementer’s (Misión de Observación Electoral – MOE) electoral risk maps in order to identify those municipalities which were most likely to face challenges. This then allowed the electoral authorities to focus their resources accordingly. The second output was an update of MOE’s online tool which allowed citizens to report any irregularities, “Pilas con el Voto”. Whilst the government produced a similar tool, modelled on MOE’s tool, trust in the authorities is low. MOE passed the information gathered from the tool to the authorities who then undertook investigations and preventative action where possible.

Evaluation summary (150 words max)
This was a professional project by one of Colombia’s most respected civil society organisations. It was well-timed for the lead-up to the 2014 elections, and a good fit for the HRDP’s democracy priority, and British Embassy Bogotá’s country business plan. The project succeeded in delivering its main outputs, which represented excellent value for money. However, its overall purpose and some indicators were not within the implementer’s gift, and perhaps should have been expressed in a more measured way. It is also difficult to measure the “strengthening of state institutionalism”, although the government agencies involved and other stakeholders regarded the project as a success, believing that the electoral risk maps had focused attention on the highest-risk departments and thus helped prevent electoral irregularities. In addition, MOE’s electoral risk maps and virtual tool have been replicated in other countries, and are likely to have a long-term impact in Colombia and more widely.

Questions
Did the project achieve the project purpose?	Y
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Y
Was the project completed on time? (Y/N) / If not, why not?	Y
Were the Project benefits sustained after project completion?	Y

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green
Green		X

Guide to overall rating:
Green- project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
Implementers and Post should ensure that the project purpose and indicators are both within the gift of the implementer, and are not over-ambitious. / It is important to ensure that the failure to meet an indicator would not, in fact, be an indicator of the project purpose’s success. Or, if that cannot be avoided, then the implementer needs to explain clearly in the project completion report how these results could be interpreted. For example, failing to meet the target of 5,000 reports of electoral irregularities on the online tool could be a signal that the risk maps have had the desired effect of getting the relevant authorities to take appropriate action to prevent electoral irregularities. / Work with media organisations individually, rather than seeking to meet them collectively, since they want to believe that they have exclusive information. / Choosing the right implementer is vital. MOE is the most respected organisation in electoral matters in Colombia, and this guaranteed direct access to key decision makers in government, civil society, and the media. / Democracy projects can be extremely technical, and difficult for non-experts to understand. It is therefore important that both the implementer and Post take care to ensure that such project bids are expressed clearly. Post should also ensure that the use of English in the bid is easily comprehensible.

Recommendations for future projects

We were so impressed with this project as a model for future democracy projects, that we publicised it across our FCO human rights network as follows: / Example of Best Practice: Colombia Democracy Project / We know that it can be a challenge to develop good quality democracy projects with local implementers. However, HRDD has just carried out an evaluation of Human Rights and Democracy Programme Fund projects in Colombia; one of these was an excellent democracy project, which could perhaps be replicated elsewhere. Its two key outcomes were electoral risk maps and a website where citizens could report electoral irregularities (sites in Spanish, but graphics self-explanatory). The former allowed the authorities to send extra resources to those areas at high risk of electoral irregularities, thus helping to prevent such incidents. And the latter attracted almost 5,000 reports which were passed to the relevant authorities, thus helping to end the culture of impunity.