## PBA Milestone Chart
1
Public Bodies Act - Milestone Chart v1.0 September 2013 | [8 empty] | 2
Note - the steps in the checklist below may be taken in different sequence according to the situation and demands of the reform in hand. | [8 empty] | 3
Public Body | Schedule | Headline as at 16 March 2011 | Policy Lead | Net Admin Reductions £m | Commencement Date | Estimated Laid Date | Notes |  | 4
5
Milestone | Timings | Dependent Tasks and Estimated Timing | Schedule - Weeks | Progress | Date Started | Date Completed | Notes
Design | From Week 34 - To Week23 | Draft Order - 7 Weeks | 11
Explanatory Document Developed - 6 Weeks
Draft Impact Assessment - 6 Weeks
Draft Equality Assessment - 6 Weeks
DA Consultation (in parallel with general consultation) | From Week 30 - Week 25 | Dept Legal teams alerted to consider possible DA Consent Requirements | 5
Dept officials to work with Territorial Offices to agree possible DA Consent Requirements
Devolved Administration Informed of Dept view to DA consent requirements
Devolved Administrations agreement in principal to consent requirements
Advocate General / Scottish Ministers / Scottish Government
Welsh Ministers / National Assembly of Wales
Northern Ireland Ministers / Northern Ireland Assembly
Consultation on the proposal | From Week 27 - To Week 11 | Consultation Start and End Date - up to 12 Weeks | 16
Consultation pack to include policy reform proposal and Impact Assessment and may include Explanatory Document
Publish Consultation
Consultation Response Date
Territorial Offices alerted as to possible Consent Requirements
Inform Devolved Administrations
Secure appropriate Devolved Administration agreement to the level of consent required (LCM and/or Ministerial consent)
Brief Parliamentary Select Committee Clerks
Brief Secondary Legislation Scrutiny Committee Clerks
Brief Minister(s)
Pre Scrutiny Process | From Week 27 - To Week 13 | Draft Order to Parliamentary Counsel | 14
Draft Order to JCSI - 3 Weeks
JCSI Comments incorporated
Draft Explanatory Doc to CO for Comment - 1 Week
|  | Impact Assessment finalised | [5 empty] | Regulator Policy Committee review of Impact Assessment - upto 6 weeks
Regulator Policy Committee review of Impact Assessment - upto 6 weeks
|  | Reducing Regulation Cabinet Committee Review of Impact Assessment - 2 Weeks |  | Ongoing
Parliamentary Branch to contact clerks to arrange time for debate
Territorial Offices/Devolved Administrations agreement in principal to LCMs
Pre-Parliamentary Process | From Week 13 - To Week 10 | Briefing Ministers | 1
Laying the Order at Westminster
Laying the Order at Scottish Parliament - Day after laying at Westminster
Laying the Order at Northern Ireland - Day after laying at Westminster
Laying the Order at Wales - Day after laying at Westminster
Westminster Parliamentary Process | From Week 10 - To Week 0 | Debate / resolution 40 days | 7 - 10 Weeks
Debate / resolution 60 day
Responding to Parliamentary Committee recommendations; provide paper to support reforms and respond to challenges
Ministerial response to Committee Recommendations
Draft opening and closing speeches for the resolution debate to take place in both Houses
Parliamentary Branch to secure timing for final statement on floor of House
Order | Week 0 | Commencement Date
Completed
Ongoing
Outstanding

## PBA Outline Schedule
ACTION | Week 34 | Week 33 | Week 32 | Week 31 | Week 30 | Week 29 | Week 28 | Week 27 | Week 26 | Week 25 | Week 24 | Week 23 | Week 22 | Week 21 | Week 20 | Week 19 | Week 18 | Week 17 | Week 16 | Week 15 | Week 14 | Week 13 | Week 12 | Week 11 | Week 10 | Week 9 | Week 8 | Week 7 | Week 6 | Week 5 | Week 4 | Week 3 | Week 2 | Week 1 | Week 0
Drafting
EX Doc / EM developed
Parly Counsel scrutiny
JCSI scrutiny
Ministerial approval
Order laid
Scrutiny - 40 days
Scrutiny - 60 days
Debate/ resolution - 40 days
Debate/ resolution - 60 days
Key
Estimated Duration
Actual Duration

## Recess & Sitting Dates
WESTMINSTER
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Days
WESTMINSTER 2013 | Jan | [31 empty] | 24 | 24
| Feb | [31 empty] | 17 | 41
| Mar | [31 empty] | 26 | 67
| Apr | [31 empty] | 8 | 75
| May | [31 empty] | 22 | 97
| Jun | [31 empty] | 28 | 125
| Jul | [31 empty] | 30 | 155
| Aug | [31 empty] | 0 | 155
| Sep | [31 empty] | 0 | 155
| Oct | [31 empty] | 24 | 179
| Nov | [31 empty] | 25 | 204
| Dec | [31 empty] | 18 | 222
222
SCOTTISH PARLIAMENT
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Days
SCOTTISH PARLIAMENT 2013 | Jan | [31 empty] | 25 | 14
| Feb | [31 empty] | 20 | 34
| Mar | [31 empty] | 30 | 64
| Apr | [31 empty] | 16 | 80
| May | [31 empty] | 31 | 111
| Jun | [31 empty] | 29 | 140
| Jul | [31 empty] | 0 | 140
| Aug | [31 empty] | 0 | 140
| Sep | [31 empty] | 29 | 169
| Oct | [31 empty] | 16 | 185
| Nov | [31 empty] | 30 | 215
| Dec | [31 empty] | 21 | 236
247
NATIONAL ASSEMBLY FOR WALES
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Days
NATIONAL ASSEMBLY for WALES 2013 | Jan | [31 empty] | 25 | 14
| Feb | [31 empty] | 22 | 36
| Mar | [31 empty] | 25 | 61
| Apr | [31 empty] | 16 | 77
| May | [31 empty] | 27 | 104
| Jun | [31 empty] | 30 | 134
| Jul | [31 empty] | 22 | 156
| Aug | [31 empty] | 0 | 156
| Sep | [31 empty] | 8 | 164
| Oct | [31 empty] | 28 | 192
| Nov | [31 empty] | 27 | 219
| Dec | [31 empty] | 9 | 228
239
NORTHERN IRELAND ASSEMBLY 2013
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Days
NORTHERN IRELAND ASSEMBLY 2013 | Jan | [31 empty] | 25 | 14
| Feb | [31 empty] | 28 | 42
| Mar | [31 empty] | 23 | 65
| Apr | [31 empty] | 23 | 88
| May | [31 empty] | 31 | 119
| Jun | [31 empty] | 30 | 149
| Jul | [31 empty] | 6 | 155
| Aug | [31 empty] | 0 | 155
| Sep | [31 empty] | 29 | 184
| Oct | [31 empty] | 28 | 212
223
Westminster Sitting Dates @ 21st January 2013
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Days
WESTMINSTER 2013 | Jan | [31 empty] | 24 | 0
| Feb | [31 empty] | 18 | 0
| Mar | [31 empty] | 27 | 0
| Apr | [31 empty] | 9 | 0
| May | [31 empty] | 22 | 0
| Jun | [31 empty] | 28 | 0
| Jul | [31 empty] | 17 | 0
| Aug | [31 empty] | 0 | 0
| Sep | [31 empty] | 0 | 0
| Oct | [31 empty] | 24 | 24
| Nov | [31 empty] | 26 | 50
| Dec | [31 empty] | 18 | 68
213
Key
State Opening
Days Elapsed
Recess
Parliament Prorogued