## Sheet1
Progress towards delivery on time and to budget (Ratio of actual spend as percentage of anticipated final cost to percentage of actual progress of ODA programme).
Commentary This shows how much of the ODA capital budget has been spent at the end of the reporting quarter as a percentage of anticipated final cost divided by the percentage of ODA total capital programme completed. E.g. As of 31st December 2011, the actual spend on the ODA capital programme was £4.87bn and the Current Baseline Budget for the total capital programme, including post games transformation, was £5.24bn (93.0% of the budget). The percentage progress on the ODA total capital programme was 93.5%. Therefore the ratio of spend to progress was 93.0/93.5 = 0.995 (a figure less than one means that progress achieved is greater than actual spend).
Quarter up to
ODA total capital programme | March 2010 | June 2010 | September 2010 | December 2010 | March 2011 | June 2011 | September 2011 | December 2011 | March 2012 | June 2012 | September 2012
Percentage Spend | 52.6547 | 58.7408 | 65.2379 | 70.7698 | 75.8573 | 82.1381 | 89.6958 | 92.9936
Progress Percentage | 54.5231 | 60.8089 | 65.7831 | 71.9386 | 76.21 | 81.4902 | 89.8924 | 93.4815
Ratio | 0.96573 | 0.96599 | 0.99171 | 0.98375 | 0.99537 | 1.0079 | 0.99781 | 0.99478
Actual Spend | 2861924000 | 3187557000 | 3542273000 | 3842637000 | 4160095000 | 4469993000 | 4699429000 | 4871934000
Earned Value (progress achieved) | 2963479000 | 3299786000 | 3571877000 | 3906103000 | 4179437000 | 4434737000 | 4709731000 | 4897494000
Current Baseline Budget | 5435271000 | 5426482000 | 5429775000 | 5429773000 | 5484106000 | 5442048000 | 5239297000 | 5238997000
SOURCE: ODA Programme Performance Report
Note on A17: ANTONIADES PETER: Total Olympic Capital Programme (Codes 1, 2, 5 & 7) Actual Cost divided by Total Olympic Capital Programme CBB
Note on G16: As at end of 24th June 2011.