## Sheet1
Progress towards delivery on time and to budget (Ratio of actual spend as percentage of anticipated final cost to percentage of actual progress of ODA programme).
This shows how much of the ODA capital budget has been spent at the end of the reporting quarter as a percentage of anticipated final cost divided by the percentage of ODA total capital programme completed. A value below 1 demonstrates that percentage of progress is higher than the percentage spend.
E.g. At the end of the last quarter (March 2011), the actual spend on the ODA capital programme was £4.16bn and the Current Baseline Budget for the total capital programme, including post games transformation, was £5.484bn (75.9% of the budget). The percentage progress on the ODA total capital programme was 76.2%. Therefore the ratio of spend to progress was 75.9/76.2 = 0.996. (A figure less than one means the progress achieved is greater than the total amount of actual spend )
Quarter up to
ODA total capital programme | March 2010 | June 2010 | September 2010 | December 2010 | March 2011 | June 2011 | September 2011 | December 2011 | March 2012 | June 2012 | September 2012
Percentage Spend | 52.6547 | 58.7408 | 65.2379 | 70.7698 | 75.8573
Progress Percentage | 54.5231 | 60.8089 | 65.7831 | 71.9386 | 76.21
Ratio | 0.96573 | 0.96599 | 0.99171 | 0.98375 | 0.99537
Actual Spend | 2861924000 | 3187557000 | 3542273000 | 3842637000 | 4160095000
Earned Value (progress achieved) | 2963479000 | 3299786000 | 3571877000 | 3906103000 | 4179437000
Current Baseline Budget | 5435271000 | 5426482000 | 5429775000 | 5429773000 | 5484106000
SOURCE: ODA Programme Performance Report
Note on A18: ANTONIADES PETER: Total Olympic Capital Programme (Codes 1, 2, 5 & 7) Actual Cost divided by Total Olympic Capital Programme CBB