## Sheet1
Progress towards delivery on time and to budget (Ratio of actual spend as percentage of anticipated final cost to percentage of actual progress of ODA programme).
This shows how much of the ODA capital budget has been spent at the end of the reporting quarter as a percentage of anticipated final cost divided by the percentage of ODA total capital programme completed.
E.g. As of 24th June 2011, the actual spend on the ODA capital programme was £4.47bn and the Current Baseline Budget for the total capital programme, including post games transformation, was £5.44bn (82.1% of the budget). The percentage progress on the ODA total capital programme was 81.5%. Therefore the ratio of spend to progress was 82.1/81.5 = 1.008 (a figure greater than one means the total amount of actual spend is greater than the progress achieved). The ratio is greater than 1 on this occasion because of an earlier than expected project completion payment, a result of the fast rate of progress on site with over 88% of venues and infrastructure for the Games now complete.
Quarter up to
ODA total capital programme | March 2010 | June 2010 | September 2010 | December 2010 | March 2011 | June 2011 | September 2011 | December 2011 | March 2012 | June 2012 | September 2012
Percentage Spend | 52.6547 | 58.7408 | 65.2379 | 70.7698 | 75.8573 | 82.1381
Progress Percentage | 54.5231 | 60.8089 | 65.7831 | 71.9386 | 76.21 | 81.4902
Ratio | 0.96573 | 0.96599 | 0.99171 | 0.98375 | 0.99537 | 1.0079
Actual Spend | 2861924000 | 3187557000 | 3542273000 | 3842637000 | 4160095000 | 4469993000
Earned Value (progress achieved) | 2963479000 | 3299786000 | 3571877000 | 3906103000 | 4179437000 | 4434737000
Current Baseline Budget | 5435271000 | 5426482000 | 5429775000 | 5429773000 | 5484106000 | 5442048000
SOURCE: ODA Programme Performance Report
Note on A17: ANTONIADES PETER: Total Olympic Capital Programme (Codes 1, 2, 5 & 7) Actual Cost divided by Total Olympic Capital Programme CBB
Note on G16: As at end of 24th June 2011.