## Лист1
Communication campaign on raising awareness on the implementation of the Association Agreement including DCFTA and its impact in Ukraine
Action plan
Activities | 2013 | [9 empty] | 2014 | [11 empty] | 2015 |  | Budget | Implementation
| Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Research
Sector researches (8.6.1) | 2013 Mar: 10; 2013 Apr: 10 | 260000 | UK Embassy
Regional researches (8.6.2) | 2013 Mar: 3; 2013 Apr: 3
Activities for mass media
Trainings for regional journalists (8.1.2) | 2013 Apr: 4; 2013 May: 4; 2013 Jun: 2; 2014 Feb: 4; 2014 Mar: 4; 2014 Apr: 2 | 668000
Contest for journalists (8.1.1) | bar: 2013 May
Exchanges of journalists (8.1.5)
Press visits for journalists (8.1.3) | 2013 May: 3; 2013 Jun: 3; 2013 Sep: 3; 2013 Oct: 3; 2013 Nov: 3; 2014 May: 3; 2014 Jun: 3; 2014 Sep: 3; 2014 Oct: 3; 2014 Nov: 3 |  | Eastern partnership
Pen clubs (8.1.4) | bar: 2013 Dec; 2014 Apr; 2014 Oct
TV/radio programmes
Sector short films on national TVs (8.3.1) | [24 empty] | 280000 | bar: 2013 Jun; 2013 Sep; 2014 Feb; 2014 May; 2014 Oct; 2015 Feb
Features on national TVs (8.3.2) | 2013 Sep: 5; 2013 Oct: 5; 2013 Nov: 5; 2014 Feb: 5; 2014 Mar: 5; 2014 Apr: 5; 2014 Sep: 5; 2014 Oct: 5; 2014 Nov: 5; 2015 Feb: 5
Talk shows on regional TVs and radio (8.3.4) | 2013 Sep: 10; 2013 Oct: 10; 2013 Nov: 10; 2014 Feb: 10; 2014 Mar: 10; 2014 Apr: 10; 2014 May: 10; 2014 Sep: 10; 2014 Oct: 10; 2014 Nov: 10; 2014 Dec: 10; 2015 Feb: 10
Activities for general public
Road shows for general public (8.1.10) | 2014 Apr: 10; 2014 May: 10; 2014 Jun: 7 | 200000
Debates in universities (8.1.11) | 2013 Apr: 10; 2013 May: 10; 2013 Sep: 10; 2013 Oct: 10; 2013 Nov: 10; 2014 Mar: 10; 2014 Apr: 10; 2014 May: 10; 2014 Sep: 10; 2014 Oct: 10; 2014 Nov: 10
Activities in schools (8.1.12) | 2013 Apr: 10; 2013 May: 10; 2013 Sep: 10; 2013 Oct: 10; 2013 Nov: 10; 2014 Mar: 10; 2014 Apr: 10; 2014 May: 10; 2014 Sep: 10; 2014 Oct: 10; 2014 Nov: 10
Activities for expert/business community
Trainings for regional experts (8.1.9) | 2013 Apr: 4; 2013 May: 4; 2013 Jun: 2; 2014 Feb: 4; 2014 Mar: 4; 2014 Apr: 2 | 240000
National conferences (8.1.6) | bar: 2013 May; 2013 Sep; 2013 Nov; 2014 Mar to 2014 May; 2014 Sep; 2014 Nov
Info days for regional SMEs (8.1.7) | 2013 May: 4; 2013 Jun: 4; 2013 Sep: 4; 2013 Oct: 4; 2013 Nov: 4; 2014 Feb: 2; 2014 Mar: 2; 2014 Apr: 2; 2014 May: 2; 2014 Sep: 2; 2014 Oct: 2; 2014 Nov: 2
Regional round tables (8.1.8) | 2013 May: 4; 2013 Jun: 4; 2013 Jul: 4; 2013 Sep: 4; 2013 Oct: 4; 2013 Nov: 4; 2014 Feb: 4; 2014 Mar: 4; 2014 Apr: 4; 2014 May: 4; 2014 Sep: 4; 2014 Oct: 4; 2014 Nov: 4
Workshops with business associations | bar: 2013 Apr to 2013 Jun; 2013 Sep to 2013 Nov; 2014 Feb to 2014 Jun; 2014 Sep to 2014 Nov
Advertising
Information displays (8.3.6) | [24 empty] | 500000 | bar: 2013 Jun to 2015 Feb
Outdoor (8.3.8) | bar: 2013 Oct to 2013 Nov; 2014 Feb to 2014 Apr; 2014 Oct to 2014 Nov; 2015 Jan to 2015 Feb
Posters (8.3.7) | bar: 2013 Oct to 2013 Nov; 2014 Feb to 2014 Apr; 2014 Oct to 2014 Nov; 2015 Jan to 2015 Feb
TV/radio (8.3.9) | bar: 2013 Oct to 2013 Nov; 2014 Feb to 2014 Apr; 2014 Oct to 2014 Nov; 2015 Jan to 2015 Feb
Press (8.3.10) | bar: 2013 Oct to 2013 Nov; 2014 Feb to 2014 Apr; 2014 Oct to 2014 Nov; 2015 Jan to 2015 Feb
Internet (8.3.11) | bar: 2013 Oct to 2013 Nov; 2014 Feb to 2014 Apr; 2014 Oct to 2014 Nov; 2015 Jan to 2015 Feb
Online communications
Website (8.4.1) | [24 empty] | 60000
Social media (8.5)
Printed materials (8.7) | [24 empty] | 80000
Fact sheets | bar: 2013 Apr to 2013 May; 2014 Jan to 2014 Feb
Sector brochures | bar: 2013 Apr to 2013 May; 2014 Jan to 2014 Feb
Regional brochures | bar: 2013 Apr to 2013 May; 2014 Jan to 2014 Feb
Brochures for general public | bar: 2013 Apr to 2013 May; 2014 Jan to 2014 Feb
Magazine | bar: 2013 Jul; 2013 Oct; 2014 Jan; 2014 Apr; 2014 Jul; 2014 Oct; 2015 Jan
Guide for journalists | bar: 2013 Apr to 2013 May
Posters and leaflets | bar: 2013 Apr to 2013 May; 2014 Jan to 2014 Feb
Promo materials | bar: 2013 Apr to 2013 May; 2014 Jan to 2014 Feb
2288000