## Slide 1: PWVAPB (13/05)
Workstrand leads: Sam Cramond NHS CB & Joint Improvement Programme (LD Team Contact: John Crook)
Main Achievements
Next Period
Joint Improvement Programme
Chris Bull appointed, Sam Cramond, Ian Winter, Sarah Brown - other appointments to follow
1st two Joint Improvement Programme Board meetings – 31 Jan and 28 Feb
Supporting Commissioning (other)
Letter from Ian Dalton requesting information from Primary Care Trusts by 28 Feb - registers should be underway and transition to CCGs (NHS CB)
Be Bold published Dec 12
Key Actions this period | Lead | 
(13) Establishment of Joint Improvement Programme | NHSCB/ LGA | Green
(26) PCTs to develop registers of all people with challenging behaviour in NHS care and make clear to CCGs in handover | NHS CB | Amber
(42) Commissioners to review the care of all people in LD or autism inpatient beds and agree personal care plan. NHS CB to hold PCTs/CCGs to account for commissioning | NHS CB & JIP | Amber
(19) Develop service specifications for commissioning services for people with challenging behaviour | NHS CB, ADASS | Green
(20) Royal College of GPs and Royal College of Psychiatrists produce guidance on commissioning | Royal College JC Panel | Amber
(21) Produce guidance on use of different inpatient services | Royal College Psychiatrists | Amber
(25) Agree how Quality of Life principles should be adopted in social care contracts | DH, ADASS, ADCS, LGA | Green
(65) Identify barriers to reducing the need for specialist assessment and treatment hospitals and identify solutions for providing effective local services | NMDF/TLAP partnership | Green
Joint Improvement Programme Plans
Development of good practice on what a good review looks like for commissioners
Confirm arrangements for engagement, especially service users and families
Meeting of Concordat signatories
Care reviews completed and validated etc.
Other
NHSCB returns
PROGRAMME WORKSTRAND 1 : RIGHT CARE, RIGHT PLACE (February 2013)

## Slide 2
High level summary of aims:
Reviewing placements and supporting everyone inappropriately in hospital to move to community based support. Locally agreed plans to ensure quality care and support services based on the model of good care
What was delivered since last report?
This is the first report since publication of Transforming Care
What are the overdue delivery objectives, and why?
None overdue.
Royal College Joint Guidance now likely to be delivered in June.
Information gathered by the NHS Commissioning Board will begin to check PCT/CCG progress
What are the key milestones in the next six months?
Reviews completed
Publicly available update on progress
Start to put in place personalised plans
Risks and Issues
Developing this within the new NHS system, managing the handover from Primary Care Trusts to Clinical commissioning Groups has risks.
PROGRAMME WORKSTRAND 1 : RIGHT CARE, RIGHT PLACE (February 2013)

## Slide 3
Workstrand leads: William Vineall DH, Alan Rosenbach CQC
Main Achievements
Next Period
Key Actions this period | Lead | 
(29) CQC continued programme of inspections and enforcement action – ensuring model of care is part of inspection and registration | CQC | Green
(40) Examine how corporate bodies, Boards of Directors and financiers can be held to account for poor care including: regulatory and criminal sanctions, CQC powers, fit and proper persons test for board members | DH | Green
(68) Review regulatory requirements for criminal records checks and provider requests for criminal record certificates | DH | Green
  CQC to consider the new operation of regulatory model in view of the Francis recommendations and the creation of a Chief Inspector of Hospitals.
PROGRAMME WORKSTRAND 2: REGULATION, INSPECTION, CORPORATE ACCOUNTABILITY (February 2013)
Corporate accountability –
Continuing work on a new registration requirement on the fitness of directors, and on proposals to make it possible to prosecute providers for providing poor quality care.
In the light of the Francis recommendations we are looking at giving CQC powers to bring a prosecution under the Health and Safety at Work Act, and to review the CQC registration requirements to make them clearer.

## Slide 4
PROGRAMME WORKSTRAND 2: REGULATION, INSPECTION, CORPORATE ACCOUNTABILITY (February 2013)
High level summary of aims:
Strengthen accountability and responsibility of providers, and their management, for quality of care. Tightening the regulation and inspection of providers.
What was delivered since last report?
This is the first report since publication of Transforming Care
What are the overdue delivery objectives, and why?
None overdue.
Criminal records requirements - we are not planning to change the CRB check regulations. Providers will still be required to check the barred list for relevant activities, and will be able to take-up a criminal records check. The registration requirement is that providers must have effective recruitment procedures in place.
What are the key milestones in the next six months?
CQC models published
Consultation on any proposed regulatory changes, including fit and proper persons test
Risks and Issues
Francis Inquiry report – Further work to understand how the Post Winterbourne work fits with Francis recommendations

## Slide 5: PWVAPB (13/05)
Workstrand lead: Pam Nixon, DH
Main Achievements
Next Period
Key Actions this period | Lead | 
(44) Identify and promote good practice for people with learning disabilities across health and social care | DH with Forums, ADASS, LGA, NHS | Green
(24) National Quality Board to set out how the new system should operate to improve and maintain quality | NHS CB | Green
(7) Identify the key factors to take account of in commissioning advocacy for people with learning disabilities in hospitals so people in hospital get good access to information, advice and advocacy that supports their needs | DH | Green
(8) Drive up the quality of independent advocacy, through strengthening the Action for Advocacy Quality performance mark and reviewing the Code of Practice for advocates to clarify their role | DH | Green
(43) Provider organisations to set out a pledge or code based on Think Local Act Personal Making it Real principles | Providers | Green
(39) Embed the importance of Local Healthwatch involving people with learning disabilities and their families, engaging with existing Partnership Boards | DH, LGA, Healthwatch England | Amber/ Green
PROGRAMME WORKSTRAND 3: QUALITY & SAFETY – GOOD PRACTICE, STANDARDS & ADVOCACY (February 2013)
(44) A working group has looked at 87 projects and decided on a shortlist of 6 good practice projects
(7 & 8) Developing scopes for two advocacy projects with Action for Advocacy and Inclusion North.
(24) The National Quality Board guidance has been updated in the light of the Winterbourne View report (and will be updated again following Francis report).
https://www.wp.dh.gov.uk/publications/files/2013/01/Final-NQB-report-v4-160113.pdf
(44) Visit good practice projects in March to check. Ministerial meeting on 30 April.
(39) Local Healthwatch organisations start up w/c 1 April 2013
(43) Provider roundtable with Minister on 26 March. Providers consulting on draft code.

## Slide 6
PROGRAMME WORKSTRAND 3: GOOD PRACTICE, STANDARDS AND ADVOCACY (February 2013)
High level summary of aims:
Improving quality and safety so that best practice in learning disability services becomes normal practice. Ensuring good information and advice, including advocacy, is available to help people and their families.
What was delivered since last report?
This is the first report since publication of Transforming Care
What are the overdue delivery objectives, and why?
None overdue.
What are the key milestones in the next six months?
(44) Good practice project visits undertaken in March.
(44) NVFF, National Forum and Steering Group to feedback to Minister on 30 April.
(44) Good practice event with Joint Improvement Programme, planned for the Autumn to bring together all pieces of work on good practice
(43) Providers to have agreed and publicised pledge/code
(7 & 8) Work underway to take forward two pieces of work on advocacy: Action for Advocacy Performance Quality Mark and Code of Practice and work by Inclusion North on advocacy in hospitals.
Risks and Issues
Good practice not embedded across all areas. Need to make sure linked closely with Joint Improvement Programme work on what good looks like.

## Slide 7: PWVAPB (13/05)
Workstream leads: Zawar Patel DH, Sam Cramond, NHS CB/Joint Improvement Programme
Main Achievements
Next Period
Key Actions this period | Lead | 
(17) Commission audit of current services for people with challenging behaviour to take a snapshot of provision, numbers of out of area placements and lengths of stay. To be repeated 1 year on. | DH | Amber / Red
(37) Develop measures and key performance indicators to support commissioners in monitoring their progress | DH with NHS CB and HSC IC | Amber
(38) Implement a joint self-assessment framework to monitor progress of key health and social care inequalities and publish the results from local areas | NHSCB and ADASS | Green
(61) Develop a new learning disability minimum data set to be collected through the Health and Social Care Information Centre | DH | Amber/Green
(52) Monitor and report on progress nationally, including reporting comparative information on localities | NHSCB/LGA and Joint Implementation Programme | Amber
PROGRAMME WORKSTRAND 4 : INFORMATION & DATA (February 2013)
Work underway to develop local registers and review care plans
Joint health and social care self-assessment framework (SAF) almost finalised
Set up Data and Information Working Group to progress this work quickly
Agreed proposals to take forward which are in paper for Programme Board
NHSCB to:
Ensure WV commitments clearly identified as part of CCG assurance framework
Update Concordat signatories on progress against commitments.
Members of the Joint Improvement Programme Board will update Learning Disability Programme Board regularly on progress.
Commission work on audit, KPIs and minimum data set

## Slide 8
High level summary of aims:
Ensure transparent information and robust monitoring to deliver transformed care and support and to make sure the public, people with challenging behaviour and families know whether we are making progress.
What was delivered since last report?
This is the first report since publication of Transforming Care
What are the overdue delivery objectives, and why?
None overdue. Risk of slippage to following actions:
Audit – depends on ability to update SAF. Alternative would be to commission separately but this is slower.
KPIs and Minimum Data Set – relies on submission to commissioning group being agreed
What are the key milestones in the next six months?
Complete local registers and start reviewing care
Update Programme Board in July on Audit, KPIs and Minimum Data Set
Risks and Issues
Potential duplication – leading to poor compliance/excessive burdens on health and care organisations. Key partners working together to ensure alignment
Lead in times – where new work needs to be commissioned
Collect the wrong data – inability to give assurance on key issues
Potential gaps – lack of transparency on baseline data against which to measure progress and improvements
Need to ensure fits with other developments, e.g. Zero Based Review of adult social care data
PROGRAMME WORKSTRAND 4 : INFORMATION & DATA (February 2013)

## Slide 9
Workstream leads: Pam Nixon, DH and John Crook, DH
Main Achievements
Next Period
Key Actions this period | Lead | 
(45) Explore whether there is a need to commission an audit of use of medication for this group. As a first stage, commission a wider review of the prescribing of antipsychotic and antidepressant medicines for people with challenging behaviour | NHS CB with Royal College of Psychiatrists | Green
(51) Ensure medicines are used in a safe, appropriate and proportionate way and their use optimised in the treatment of people all ages with challenging behaviour. | Royal College of Psychiatrists, Royal Pharmaceutical Society | Green
(53) Publish guidance on best practice around positive behaviour support so that physical restraint is only ever used as a last resort where the safety of individuals would otherwise be at risk | DH | Amber
(53) Consider what further action may be needed to check how providers record and monitor restraint | DH/NHS CB/ NHS IC | Amber
PROGRAMME WORKSTRAND 5: QUALITY & SAFETY – RESTRAINT, MEDICATION, POSITIVE BEHAVIOUR (February 2013)
(45 & 51) Meeting on medication actions with all key stakeholders held on 13 February: agreement to gather good practice guidance and available data before decision on audit; agreement to pursue a collaborative for safe and appropriate medicines.
(53) Guidance on positive behaviour support and set of values; refresh of 2002 DH/DfE guidance; framework for commissioning training in restraint and PBS; identification of data and information needs on recording restraint.
(45 & 51) Meeting with providers on 18 March to obtain prescribing data. Meeting with all stakeholders to review progress late April/early May. NHS CB oversight of all actions
(51) Explore the setting up of a Collaborative with interested parties
(53) Commence work on guidance
(53) Skills for Care commence work

## Slide 10
High level summary of aims:
Improve quality and safety so that there is better understanding of how to use physical restraint properly and good practice on positive behaviour support and the environment so that challenging behaviour is reduced. Tackle over-use of antipsychotic and antidepressant medicines to ensure the best course of action for the patient.
What was delivered since last report?
This is the first report since publication of Transforming Care
What are the overdue delivery objectives, and why?
None overdue. Risk of slippage.
What are the key milestones in the next six months?
(53) Skills for Care (working with Skills for Health) consult on framework for commissioning training on physical intervention and positive behaviour support.
(53) Scope and commission guidance on positive behaviour support and set of values
(53) Commission update of 2002 DH/DfE guidance for people with learning disabilities and autism on restrictive physical interventions.
(53) Consider data and information needs on recording incidents of restraint with NHS CB and NHS IC.
(45) Clarity around whether an audit will be required
(51) Setting up of Collaborative
Risks and Issues
Finding the right organisations/people to undertake work in both areas.
PROGRAMME WORKSTRAND 5: QUALITY & SAFETY – RESTRAINT, MEDICATION, POSITIVE BEHAVIOUR (February 2013)

## Slide 11: PWVAPB (13/05)
Workstrand Leads: Anita Wadhawan (DH) John Crook (DH) and Pam Nixon (DH)
Main Achievements
Next Period
Key Actions this period | Lead | Current status
(14) Refresh Challenging Behaviour: A Unified Approach to support clinicians in community learning disability teams | Learning Disability Professional Senate (LDPS) | Amber
(15) Develop national minimum training standards and a code of conduct for healthcare support workers and adult social care workers | Skills for Health, Skills for care | Green
(16) Develop a framework of guidance and support on commissioning workforce solutions to meet the needs of people with challenging behaviour | Skills for Care | Green
(10) Produce key points guidance for social workers on good practice in working with people with learning disabilities who also have mental health problems | College of Social Work with BASW | Green
(12) Produce good practice standards for commissioners and providers to promote reasonable adjustments required to meet speech, language and communication needs of people | Royal College of Speech and language Therapists | Green
(23)Develop core principles on a statement of ethics to reflect wider responsibilities in the health and care system | LDPS | Amber/ Green
PROGRAMME WORKSTRAND 6 : QUALITY & SAFETY – WORKFORCE (February 2013)
(23) The College of Social Work, BASW and other key stakeholders are planning to issue key points by the end of April.
(10) Work began on 8 February to produce good practice standards for commissioners and providers.
(73) This action on whistleblowing is complete.
(15) Skills for Health and Skills for Care have delivered the minimum training standards and code of conduct for healthcare support workers and adult care workers in England.
(14) Refresh Challenging Behaviour: A Unified Approach to support clinicians in community learning disability teams guidance to be published in June 2013.
(28) HEE to take on duty for education and training across the health and care workforce from 1 April 2013 and will work with partners to improve skills and capability to meet the needs of people
(54) There will be a progress report on actions to implement the recommendations in Strengthening the Commitment the report of the UK Modernising learning disability Nursing Review.
(10) First draft of good practice standards sent to the National Forum, 22nd March. To be completed in November.
(15) National Minimum Training standards and code of conduct expected to be published.

## Slide 12
High level summary of aims:
Improve quality and safety through improving the capability of the workforce so that staff are properly trained in essential skills supported by good clinical and managerial leadership. Health and care professionals should understand and be supported in achieving minimum standards and aspire to best practice. Members of staff should feel it is safe to raise concerns when things go wrong and be listened to.
What was delivered since last report?
This is the first report since publication of Transforming Care.
What are the overdue delivery objectives, and why?
(14) Refresh Challenging Behaviour: A Unified Approach to support clinicians in community learning disability Team – this action by the Learning Disability Professional Senate (LDPS) was due at the end of December (2012) is undergoing consultation and is likely to be published in June.
What are the key milestones in the next six months?
(15) & (16) Publication of Skills for Care/NDTi guidance to ‘Develop a framework of guidance and support on commissioning workforce solutions to meet the needs of people with challenging behaviour’ being road tested with employers and others. Publication due in March.
(14) Refresh of the Challenging Behaviour: A Unified Approach to support clinicians in community learning disability teams guidance will be published in June 2013.
(23) The College of Social Work, BASW and other key stakeholders plan to issue key points by the end of April.
Risks and Issues
Need to make sure this is linked closely with work of Joint Improvement Programme on what good looks like.
PROGRAMME WORKSTRAND 6 : QUALITY & SAFETY – WORKFORCE (February 2013)