## Slide 1: Supplier transparency pilot
Progress to date: Many donors, CSOs and development finance organisations already publishing to IATI – now need to extend this to include private sector suppliers Transparency expectation included in DFID Statement of Priorities and Expectations for suppliers (SoPE – Annex 1) since January 2013 497 suppliers committed to the SoPE Supplier conference (June 2013) and British Expertise event (Sept 2013) – engaged suppliers on transparency and requested pilot volunteers 8 suppliers have agreed to participate in the pilot | Risks and concerns: Possible misperceptions regarding the level of disclosure required Possible challenges in applying IATI standards if DFID funding accounts for only a small amount of the supplier’s overall income Particular challenges for SMEs – burden of aligning publishing standards Need to ensure suppliers provide information in usable format Possibility that IATI language needs to be amended to align with supplier language Possible resistance to take-up from ‘for profit’ suppliers
Scope of the pilot: Potentially 8 suppliers (ASI, Crown Agents, Oxford Policy Management, British Council, Coffey, Integrity, HTSPE, DAI) accounting for 32% of direct proc spend Mix of SMEs and global organisations Pilot to be completed by end of Q4 2013 Review lessons learned from pilot in Q1 2014 and establish approach for remaining suppliers Commence roll-out to further suppliers in Q2 2014 (aiming for compliance from suppliers accounting for 80% of DFID direct procurement spend) | Next steps: Seek Sector Transparency Panel’s views on fields for suppliers to publish Introduce IATI minimum level of disclosure to suppliers (Annex 2) Work closely with IATI - workshops and one-to-one sessions for suppliers in support of both pilot and roll-out Agree implementation schedules with pilot suppliers Commence and run pilot Review publication compliance and lessons learned from pilot
Questions for the Panel: What are the Panel’s views on possible approaches for private sector suppliers? What information/data fields should suppliers be expected to publish? | 

## Slide 2
Commence roll-out to suppliers accounting for 80% procurement spend
Aid Transparency Challenge rolled out to all CSOs
SoPE – 497 suppliers now signed up
Complete pilot
Requested supplier engagement in Aid Transparency Challenge
Engaged with 8 suppliers to secure participation in pilot
Commence 8 supplier pilot
(30% procurement spend)
Review lessons learned from pilot and establish approach for roll-out
Process: steps and timescales
Oct 2012
Jan 2013
June 2013
Sept 2013
Oct 2013
Q4 2013
Q2 2014
Q1 2014