## Slide 1
ECO STEERING GROUP – 11 OCTOBER 2013
DECC ACTION PLAN TO ASSIST DELIVERY OF THE ENERGY COMPANY OBLIGATION

## Slide 2
  SWI Delivery/blending
    Issued call for evidence (closed 10 October)
    Asked companies for delivery plans
    Exploring options to increase uptake, including looking at cash back offer (end October)
  ECO Communications Plan
    Enhanced ECO presence on gov.uk
    ECO information leaflets – Affordable Warmth
    Ofgem FAQs
    Workshops with EnergyUK (early 2014)
    Workshops with NEA (Oct – Nov)
    Range of activities to raise profile and understanding of ECO
ECO Action Plan Workstreams

## Slide 3
  3. Managing Scheme Transitions/Promoting Jobs And Growth
    Held an insulation industry roundtable – series of actions agreed and being delivered e.g. working with Ofgem to address ECO operational issues/providing clarification on ECO delivery to NIA members
    Explore extending ESAS referrals (Oct/Nov)
    Consider expanding cash back (Oct/Nov)
    Addressed specific industry technical issues in conjunction with Ofgem
    Look to provide early clarity on ECO 1.2
  4. Local Authorities and ECO Delivery
    Green Deal Streets Competition
    Work with the LGA to drive LA engagement with ECO
    Share results of HECA
    Extend ESAS referrals to LA schemes (Oct/Nov)
    Share DECC data on remaining potential / housing stock
ECO Action Plan Workstreams

## Slide 4
  5. Ofgem Guidance/Regulations
    Established working group to simplify/standardise suppler reporting requirements ECO 1.1 addresses various technical issues
    Today call for specific changes / issues you would like to see changed and what with (to maintain robustness)
  6. Delivering to Vulnerable Customers
    Actively progressing data matching (Nov/Dec)
    Providing online lookup for CSCO areas, including rural (Nov)
  7. Understanding the ECO Delivery Profile
    Meeting all companies on a monthly basis for update on delivery and any problems
    Actively monitoring delivery – publishing monthly stats
    As above – energy companies have shared SWI delivery plans
ECO Action Plan Workstreams

## Slide 5
Do you agree with the workstreams/themes we have identified under which to take action?
Are there specific actions under the themes you think it would be helpful for us to undertake?
Are there actions you are taking, or could undertake, which would help support the workstreams set out?
Questions For The Steering Group