## Slide 1: EMR Capacity Market Implementation Coordination Update
Industry Implementation Forum – 23rd January 2013

## Slide 2: Items to cover in this update
National Grid’s role in implementing CM
Update on 15th January “Launch” Event
  Success
  Issues
  Plan
  Process
  IT Systems
Workshop Programme going forward

## Slide 3: National Grid’s role in implementing CM
National Grid (Delivery Body)
As the delivery body for the Capacity Market, National Grid will be responsible for:
Procuring and implementing core systems to support the running of capacity auctions and the pre-qualification process, and the implementation and maintenance of the capacity register
Designing and implementing business processes to support capacity auctions and pre-qualification, and producing supporting documentation/guides including the auction guidelines
Designing and implementing business processes to support the management of each delivery year i.e. contract management, spot testing
National Grid (Implementation Co-ordinator)
National Grid will also fulfil the role of ‘Implementation Co-ordinator’ for the Capacity Market:
Owning and maintaining the Capacity Market Implementation Plan
Co-ordinating implementation activities across delivery partners and potential capacity providers
Engaging with potential capacity providers on implementation issues and their readiness to participate in the Capacity Market
Collating, tracking and helping to resolve implementation issues
Passing any policy issues to Government if raised as part of implementation discussions

## Slide 4: What we need from Industry
Identify the additional NG/DECC/Delivery Partner implementation tasks & milestone detail you need to see to help plan your own tasks
Identify, plan and manage the implementation activities that you need to do within your own organisations
Share the high-level milestones as part of an “Industry Readiness” representation on the overall Implementation Plan
Develop internal capabilities and processes to ensure readiness
Engage in the coordination process to ensure successful delivery
Raise any implementation issues early enough in the process that they can be resolved – “No Suprises”
Collaborate with Delivery partners
  Future I.C. events
  Bilateral meetings

## Slide 5: Implementation Coordination Workshop plans
Implementation Coordination Launch Session
  Review of EMR to date (Policy to Implementation)
  Describe National Grid’s role & introduce the team
  Consider how we describe a successful implementation
  Consider the risks & issues to us achieving success
  High level view of the Implementation Plan, the CM Processes and the IS Systems strategy
Future sessions
  Review progress to plan
  Review & update issues
  Focus on a particular element of Implementation i.e. Pre-qualification
  Updates from other Delivery Partners (Ofgem, CMSB, Elexon)

## Slide 6: Workshop dates
When | Focus Subject
15th Jan (Full day) | Implementation Coordination Launch
12th Feb (1/2 day) | Pre-qualification
13th March (1/2 day) | Electricity Capacity report
10th April (full day) | Auction
End April | Potential additional workshop
15th May (1/2 day) | Pre-qualification
End May | Potential additional workshop
12th June (1/2 day) | Readiness
End June | Potential additional workshop
Venue: – Grand Connaught Rooms, Holborn

## Slide 7: Summary of the CM Implementation Success Factors identified at the workshop
Success | Description
Pre-qualification & the Auction happened on time | Planned dates were met / only moved under an agreed governance process The Auction ran and cleared in 2014 Capacity was procured for delivery year of 2018/19
Pre-qualification ran smoothly and all applicants had the best opportunity to successfully pre-qualify | Rules/Guidelines were finalised in time, available to everyone, simple to understand and delivered the results expected Procedures were explained, available to everyone, simple to understand and supportive (e.g. helping not blocking) NG Systems were simple to use; ready on time; seen, tested and understood by applicants in advance; worked as intended and gave the results expected Applicant Systems were ready on time and able to communicate with NG Systems as expected
The Auction ran smoothly and all bidders had the best opportunity to secure a capacity agreement | As above for Pre-qualification The Auction was “liquid”, included a diverse range of technologies/applicant sizes and offered best value to consumers The Auction Monitor approved the auction outcome
Settlement is on schedule for delivery | Smooth transfer of data from NG to Elexon Payment/Settlement systems implementation is on track Generators and Suppliers are confident of delivery of fit-for-purpose Settlement systems

## Slide 8: Some of the successes raised might be better described as successful outcomes of the CM Market
Success | Description
Secondary market is liquid and ready in time | Market was ready ahead of first delivery year and well supported by industry participants Participants had the best opportunity to participate (knowledge, system access, clear rules & procedures) Secondary Market supported delivery of physical capacity
Long-term market is stable and successful | Lights stayed on New capacity was ready on time Agreement holders were paid correctly and Suppliers were billed correctly LOLE was achieved at lowest cost to consumers Industry had broad knowledge of how the market works Robust forward look of the need for market solution Interim capacity arrangements no longer required

## Slide 9: We went into the workshop with a number of “NG Issues” identified in Collaborative Development
Notification process?
Opportunities for automation?
Trading
Timing – dates for demand curve, price maker/taker declaration & auction
Guidelines – Format & timing
IT Systems – early visibility, access, participant testing, training & “Mock Auction”
Pre-qualification
Timing - dates for opening , closing & everything that follows
Preparation - activities & participant readiness
Data submission - How will it work, opportunities for bulk transfer / portfolio submission & possible pre-population by NG?
IT Systems - Early visibility, training, access & User Trials
Information - Confidentiality, transparency, sharing with DECC/Ofgem
Auction

## Slide 10: We captured a number of Implementation Risks/Issues which will inform the agendas for future workshops
Issue | Detail
Potential timeline creep | Movement in the timeline and associated deadlines will undermine confidence in the process & lead to genuine loss from any delays
Industry representation | Are we involving the right people in the implementation process, how do we engage with “practitioners” who understand the details
Governance | Governance around the implementation process and development of the associated Rules is unclear
Participant readiness | What will happen if one participant (or a small number) are not ready? Will this be factored into the ‘Go Live’ readiness criteria?
Pre-qualification queue blockage | There is concern that pre-qualification will take longer than planned leading to delays in the auction
Auction system delay following pre-qualification | Delays to systems between pre-qualification and Auction could mean that pre-qualification data is no longer valid
Auction system security and confidentiality | It is not clear how security and confidentiality of pre-qualification and auction information will be protected
Auction is cancelled | There are concerns that the auction will be cancelled due to lack of liquidity, not clearing or that too much plant opts out
Supply side system development | In order to ensure participants can get paid on time, suppliers charging systems will also need to be ready.

## Slide 11: We also captured issues which, whilst impacting on Implementation, cannot be resolved entirely within this process
Issue | Detail
Lack of firm rules | Final rules and regulations will not be available until late June. The plan does not allow sufficient time for applicants to review the rules or regulations that have not yet been published.
State Aid impact | The State Aid process and impacts are unclear for applicants, what are the deadlines and how might go-live be impacted.
DSR delays | Further delays to the start of the DSR Transitional Arrangements will undermine confidence and reduce the willingness to sufficiently invest in advance of go live
Interconnection participation | It is not clear how interconnected capacity will be eligible to participate in the CM
Secondary Trading | Concern that a robust secondary trading arrangement will not be in place
Change in Law confidence | There is insufficient change in law protection leading to a lack of confidence and appropriate risk management
Confidence in long term view | Participants are not confident that there will continue to be a capacity mechanism to participate in
General Election impact | Will the election and it’s preparation lead to changes in policy or timescales

## Slide 12
 | 2013 | 2014 |  |  |  |  | 
 | Dec | Jan | Feb | Mar | Apr | May | Jun
Government |  |  |  |  |  |  | 
Ofgem |  |  |  |  |  |  | 
Delivery Body |  |  |  |  |  |  | 
Applicant |  |  |  |  |  |  | 
Capacity Market Settlement Body |  |  |  |  |  |  | 
Royal assent to Energy Bill
Government response to consultation published
Consultation closes
1
Delivery plan published
6
Informal auction guidelines
Electricity capacity modelling and analysis
2
Publish draft Capacity Market Rules change process
5
EMR Capacity Market Implementation Plan
Version 1.1
Publish final Capacity Market Rules change process
Publish appeals guidance
Code and licence changes
Analysing consultation responses, finalising policy and draft secondary legislation
4
Auction IT systems design and build
Implementation planning
Pre-qualification IT systems design and build
Implementation planning
Consultation on Capacity Market Rules change process
3
Capacity Market Settlement Body setup
Key
DECC
Delivery body
Ofgem
Applicant
Settlement body
Note: This is an indicative timeline. Depending on updates to the design of the Capacity Market and the draft legislation after the Oct – Dec 2013 EMR consultation closes, this plan may need to be revised.
E
E
E
E
E
E
E
E
E

## Slide 13
 | 2014 |  |  |  |  |  | 2015
 | Jul | Aug | Sep | Oct | Nov | Dec | Jan
Government |  |  |  |  |  |  | 
Ofgem |  |  |  |  |  |  | 
Delivery Body |  |  |  |  |  |  | 
Applicant |  |  |  |  |  |  | 
Capacity Market Settlement Body |  |  |  |  |  |  | 
8
01/08 Legislation and code / licence changes in force
14/07 Applicant access to National Grid pre-qualification IT systems
10
01/08 Publish "Formal" auction guidelines
21
20/10 Updated auction guidelines
and enable IT system access
11
04/08 Pre-qualification window open
12
15/08 Pre-qualification window closes
13
Capacity Market Settlement Body operational
14
26/09 Pre-qualification results day
03/10 Deadline for posting bid bond/ collateral
10/10 Appeal assessment complete and appellants notified
Update auction parameters
22
24/10 Initial
collateral verification
25 business days before the auction
25
14/11 Tier 2 appeals process complete
26
17/11 Successful appellants provided system access
27
18/11 Final Auction Guidelines & bidder details published
28
25/11 Mock Auction
29
02/12 Closing Date for Price Maker/Taker confirmation
30
05/12 Go/No Go
Decision
09/12 Start Auction
11/12 Complete Auction
33
12/12 Notification of provisional Auction results
34
18/12 Auction Monitor report to Government on auction
Verify Collateral
EMR Capacity Market Implementation Plan
Version 1.1
35
24/12 Auction Results Day
36
23/01 Issue Capacity Agreements
Within 24 hours of auction closing
Within 20 business days of Results Day
9
01/08 Publish auction determination and parameters
Pre-qualification prep
User Trials
Application
Assess applications
Consider
appeals
18
Appeal
Post
Collateral
Auction
15
16
19
20
31
32
7
17
Consider appeals
Must be within 8 business days of auction closing to allow Government to consider the auction monitor’s report
Participant Auction Testing
Participant Auction Testing
26/09
03/10
Appeal
10/10
17/10
23
31/10 Collateral re-posting deadline
Note: This is an indicative timeline. Depending on updates to the design of the Capacity Market and the draft legislation after the Oct – Dec 2013 EMR consultation closes, this plan may need to be revised.
24
4/11 Final collateral
verification
Key
DECC
Delivery body
Ofgem
Applicant
Settlement body

## Slide 14: Capacity Market Process End to End
1. Amount to Auction
2. Eligibility and Pre-Qualification
3. Auction
4. Capacity Agreement Management
5. Secondary Market
6. Delivery
7. Payment
8. Reporting
9. Change Control
10. Appeals

## Slide 15: Capacity Market Process End to End
1. Amount to Auction
2. Eligibility and Pre-Qualification
3. Auction
4. Capacity Agreement Management
5. Secondary Market
6. Delivery
7. Payment
8. Reporting
9. Change Control
10. Appeals

## Slide 16: The IT Systems Landscape
Focus
For Today
-
Amount to
Auction
Eligibility & Pre
qualification
Auction
Capacity
Agreement
Management
Secondary
Market
Delivery
Payment
Delivery
Plan
Settlement
Systems
Auction
Solution
SO
Systems
Admin
Systems

## Slide 17: We have established a number of Design Principles to ensure systems are both “fit for purpose” & accessible to all
Rules
Communicate
Secure
Web
Simple
Efficient
Audit
Validate

## Slide 18: How will we involve you?
Monthly briefings with IS items
On-line component demos aligned with development cycles
Early release of solutions for user familiarisation
Mechanisms for feedback
Mock-auctions for E2E testing

## Slide 19: IS Plan & Progress
  Progress to date
  We are currently in final negotiations with two solution providers for each product
  We expect to make decisions and place contracts by the end of January
  We expect to start work in early February
  We will use an “agile” approach to meet deadlines and track policy change
  The Auction solution will be based on existing proven auction service, configured to meet the CM rules

## Slide 20: Workshop dates
When | Focus Subject
15th Jan (Full day) | Implementation Coordination Launch
12th Feb (1/2 day) | Pre-qualification
13th March (1/2 day) | Electricity Capacity report
10th April (full day) | Auction
End April | Potential additional workshop
15th May (1/2 day) | Pre-qualification
End May | Potential additional workshop
12th June (1/2 day) | Readiness
End June | Potential additional workshop

## Slide 21: EMR Capacity Market Implementation Coordination Update
Industry Implementation Forum – 23rd January 2013