## Slide 1: EMR Industry Implementation Forum (IIF)
Thursday 23rd January 2014

## Slide 2: Agenda
Timing | Item | Lead
14.30 – 14:40 | Welcome and Introductions | Jonathan Mills (Chair), DECC
14.40 – 14.55 | Discussion on IIF Ways of Working | PWC
14.55 – 15.10 | Collaborative Development Deliverables Update | PWC
15.10 – 15.25 | CM Implementation Update | Chris Woodalll, National Grid (CM Implementation Co-ordinator)
15.25 – 15.40 | CfD Implementation Update | Ruth Herbert CfD Counterparty Company (CfD Implementation Co-ordinator
15.40 – 15.50 | Update on Additional DECC Engagement | Jack Thomlinson (DECC)
15.50– 16.00 | AOB | Jonathan Mills (Chair), DECC

## Slide 3: Proposed ways of working
The objectives of the IIF are for:
    DECC to keep industry updated on the overall implementation of EMR and progress towards delivery
    Implementation coordinators to report back on their engagement with industry and on progress against the respective Implementation Plans
    Industry to escalate significant implementation issues that cut across the Programme and to identify implementation matters to be brought to the IIF
    Industry to advise DECC on any cross-industry processes that need to be established to support implementation.
    The IIF is not designed to provide an opportunity for the industry to discuss emerging or agreed policy. Policy discussions will take place through other stakeholder engagement mechanisms.
3

## Slide 4: Proposed ways of working
Meeting frequency
    Every 6-8 weeks
Secretariat
    Provided by DECC
    Meeting papers issued at least 48 hours in advance of each meeting
    Minutes for each meeting published on DECC website
Membership
    Comprised of members from industry at Director of Operations level
    Membership to be kept to a "manageable" size
4

## Slide 5: Collaborative Development Deliverables Update
 | Capacity Market | Contracts for Difference
Delivered and published | Operating Model Operating Model Annex A – Process Maps Operating Model Annex B – Data Flows Implementation Plan | Operating Model Operating Model Annex A - Process Maps (subset)
Delivered to DECC | Customer Journeys | Remaining Process Maps Customer Journeys Policy Index(delivered through Counterparty Body work)
To be delivered to DECC by 7th Feb | Policy Index | 
On hold | CM Settlement Body Process Maps | Implementation Plan Customer Journeys Data Flows

## Slide 6: CM Implementation Co-ordinator
Chris Woodall
National Grid
23 January 2014

## Slide 7: CfD Counterparty and EMR Implementation
Ruth Herbert
CfD Counterparty Set up Team
23 January 2014

## Slide 8: Role of CfD Counterparty company
Private company, operating at arm’s length from Government and responsible for:
CfD:
Signing CfD contracts with projects agreed by Government or System Operator.
CfD contract management (generic and investment contracts transferred from DECC).
Forecasting supplier obligation levy rate, collecting collateral from suppliers.
Payment flows from/to generators and suppliers (via Elexon)
CfD Implementation Coordination
CM:
CM payment flows from/to capacity providers and suppliers, on behalf of the Capacity Market Settlement Body (CMSB)
Other activities (TBC) on behalf of the CMSB.
Notes: - To note that there are shades of grey here – e.g. in relation to CfD allocation and auction design.

## Slide 9: Implementation phase
  CfD Counterparty Company and Operations setup
Resourcing/Recruitment
Company set up
Business planning and finance
Accommodation
Project management
  CfD Counterparty Company IT systems setup
  CfD Implementation Co-ordination
CfD Operating Model ownership
CfD Business Design Authority
Implementation plan management
CfD systems testing oversight / coordination
CfD Contract management
CfD and CM Settlement
Supplier Obligation Forecasting
Internal HR and Finance
Notes: - To note that there are shades of grey here – e.g. in relation to CfD allocation and auction design.

## Slide 10
The CfD Operating Model
Components
Customer Journeys
Process maps
(partially published)
Traceability matrix
(work in progress)
User Interface definition documents
(work in progress)
What?
A reference document setting out how the Contracts for Difference (CfD) will operate and enabling change control to be applied.
For whom?
The Operating model will be used to inform the specifications / catalogues of requirements for system procurements.
It will also be useful for generators and suppliers, as it will include interface definitions, which will enable them to design their internal systems for CfD implementation/ participation.

## Slide 11
Maintaining the Operating Model
Stakeholder comments feed into Delivery Partner review of Operating Model and into impact assessment of changes
Updated process maps and impact assessments to the CfD Business Design Authority
Where policy intent or timelines may be impacted, EMR Design Authority decision requested
Modified maps published for industry review and comment
The collaborative process

## Slide 12: Procurement and engagement plan
Publication of business process maps
Sector show and tell sessions: business processes and customer journeys
Publication of settlement systems interface specification
Stakeholder participation in interface testing
Oct /Dec 2013
Jan/Mar 2014
Apr/Jun 2014
Jul/Sep 2014
Oct /Dec 2014
Jan/Mar 2015
Apr/Jun 2015
SETTLEMENT GO LIVE
Stakeholder trialling
Publication
Engagement
Publication of updated business processes, syncing with secondary legislation
Initial stakeholder meeting: CfD implementation and business process overview
Bilats: industry implementation
Design
DEVELOPMENT
ENGAGEMENT
Procure/design
Implement
Test
CfD Settlement system
CfD Contract management system (CMS)
Design/configure
Updates to business process maps
Business process issue groups (as required)
(TBC) Settlement systems consultation: interface for data exchange
DESIGN PHASE
BUILD PHASE
TEST
LIVEPHASE
CMS questionnaire: proposed data and portal solutions
Ongoing updates to operating model for continuous review and comment
CMS: publication of system and process

## Slide 13
QUESTIONS?

## Slide 14: Update on DECC engagement
Jack Thomlinson
DECC
23 January 2014