## Sheet1
FCO and British Council response to the Arab Spring
Recommendation | Accept/Partially Accept /Reject | Action | Impact of Actions | Target date | Update as of July 2014
Completed/ On-track / Off-track
1. The FCO should introduce explicit ‘theories of change’ into its country strategies to identify clearly what outcomes it hopes to achieve and how, particularly in the good governance area. It should then measure and report on progress towards outcomes, to produce a clearer picture of overall results. | Accept | 1. Country strategies were reviewed and updated over 3 months from January 2014. Posts were required to produce explicit 'theories of change' to complement their strategies, to capture their intended activity and objectives. DFID expertise was drawn on to provide guidance and support to posts during this process. | 1. All country strategies now have an explicit theory of change. Embassy staff were offered support, guidance and training in how to draft and update their theory of change. These lessons will be reinforced next year. The process of drafting resulted in more concrete deliverables being identified.
|  | 2. Posts are required to keep their theory of change up to date as part of the quarterly reporting process. This is completed in consultation with their lead in the London programme team. | 2. Posts have been asked to use a new quarterly reporting format, which will include an update of impact against the orginal theories of change. The first quarterly reporting period for 2014/15 completes next month, after | 2014-01-01 | Completed
which we will be able to follow up with posts to ensure their theory of change remains a living document. This will also increase the level of
engagement London programme team have in the reporting process and improve monitoring and evaluation.
2. For the next annual round of APPF grants, the FCO should introduce grant-making procedures that distinguish amongst partners with different levels of delivery and financial management capacity. | Partially Accept | 3. The FCO has reworked its extant Grant Contracts to make them more user friendly. The language and lay out is more accessible for those with whom we are implementing projects. The FCO has also developed a shorter, simplified version of the Grant Contract which can be used for projects costing less than £5,000. However, the FCO has to maintain its robust contractual and reporting requirements to ensure effective use of public funds. Programme Office also offer bespoke training on the use of grant contracts to our Programme Teams and provide detailed guidance and assistance | 3. Questions relating to contracts have reduced by as much as 80%. Since September 2013 there have been no requests for a contract for use with low value projects. | 2013-11-01 | Completed
3. During this financial year, the FCO should adapt its financial system to include new modules on programme management. It should support this with improved staff training and guidance material. | Partially Accept | 4.The FCO is updating the Prism financial management system. The new version will be rolled out in November 2014. However, as we have previously noted it is not possible to adapt the system to to meet all the specific requirements of Programmes. The system has to meet the business need of the whole organisation. However, the FCO is providing bespoke training on use of Prism for Programme activity. | 4. Too early to measure the impact of the roll out of the Prism upgrade | 2013-11-01 | Completed
4. The FCO should invest more effort into sharing knowledge and experience among partners and country office programmes. | Partially Accept | 5. The FCO Arab Partnership team has been re-structured over the past 2 months to bring together Arab Partnership and MENA Conflict Pool. The new Head of MENA Strategic Programming ensures that best practise is shared between the two programmes, utilises regional DFID, MOD and FCO networks and expertise and brings HMG funding into one strategic frameword. | 5. Duplication of work has reduced due to the increased strategic oversight, and lessons are more readily dispersed through the network. Whilst the full value of this restructure will be realised over the next twelve months, bringing the teams together is already improving standards of programme management, and ensuring efficiencies.
|  | 6. The Arab Partnership programme team in London have proactively engaged with partners and other actors to share knowledge and experience, and gain insight into other similar programmes. Efforts have focused on partners AP funds in multiple countries (e.g. Global Partners, Westminster Foundation for Democracy). | 6. Interaction with partners has increased the degree to which projects are in line with AP's strategic objectives. Increased engagement with other donors working in the same fields and space has reduced the amount of overlap (for example, advising the European Commission about areas AP operates in). Over the next three months the Arab Partnership programme team are convening partners working in the three thematic areas to review lessons learned and expectations for the next 12 months, and to collect feedback. | 2013-09-01 | Completed
|  | 7. The Arab Partnership network met in London in November 2013. The full range of actors across the AP network exchanged lessons and experiences during the event: post project officers, London programme office, and partners. Through a series of seminars important themes were explored. | 7. The network has grown stronger as a result of the network event. This has lead to more post-to-post communication and lesson sharing. This has been particularly valuable in improving value for money, saving on administration costs where posts are using the same implementer, and sharing experiences.
8. The new FCO intranet will be launched in Summer 2014. This will introduce new tools which AP will use to facilitate lesson-sharing across the region, including forums and notice boards on which staff can record their experiences.
5. The British Council should develop improved methods of measuring the institutional or social impacts of those projects that have broader goals beyond skills transfer to individuals. | Accept | 9. At the strategic level British Council has reviewed and updated the outcomes and the logic model for work across its three main business units - English, Education and Society and Arts. | 8. The review of outcomes across the three main business areas provides the strategic frame for our work and greater clarity on organisational impact for planning, delivery and evaluation. | Schedule of Evaluations agreed by September 2013 | Completed
|  | 10. At the programme level, business units have prioritised evaluations of their portfolios. Impact evaluations carried out on some of our main grant funded programmes in the last year have included: Brazil Transform, Premier Skills, Africa Digital Schools (Badiliko) Project, Social Enterprise (global); our major schools programme Connecting Classrooms, Active Citizens, UKIERI, English for Education Programmes across South Asia. | 9. Evaluations are being used to support planning and to strengthen delivery. As International Inspiration closes, the interim and end of programme external evaluation conducted by Ecorys are being used to conduct a formal Lessons Learning exercise to inform future sports programmes. External evaluation of our Skills for Social Entrepreneurs programme in East Asia over three years is being used to inform the design of a new global programme in Social Enterprise currently in design for roll out in 2015/16. An external evaluation of Active Citizens is being used to inform the design of stronger M&E tools for supporting the delivery of social action projects by participants. The evaluation of Brazil Transform has led to work to strengthen transparency and learning. 10. We are continuing to work at regional levels to strengthen evaluation planning and its link with corporate planning | Review of progress in undertaking evaluations by May 2014 | Completed
|  | 11. A review of how British Council evaluates impact across its society programmes is underway and a core set of impact outcomes across all society work has been identified. We are now mapping these indicators across all society programmes and developing our enterprise data system to enable global tracking and reporting. | 11. More standardisation of impact tracking and reporting. A global set of comparative Key Performance Indicators across all Society work enabling easier comparisons for driving efficiency and effectiveness. This will lead to a stronger understanding of impact delivered through our society programmes
|  | 12. Continued capacity building and professional development in impact evaluation for British Council project managers and senior managers across the global network. Working with external partners we provide accredited professional and academic qualifications in impact evaluation. | 12. Improved understanding of impact and its measurement across the organisation