## Nutrition (hidden)
DFID’s Contribution to Improving Nutrition
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. DFID should make long term commitments to maintain the pace and scale of its nutrition investments through it country programmes. | Accept | DFID will update and extend its Scaling Up Nutrition position paper (which expires in 2015) to cover the period up to 2020 in line with existing financial commitments. | 2016-03-01
2. DFID should implement nutrition interventions which have the greatest impact on stunting and cognitive development | Accept | DFID will provide professional development opportunities for relevant staff cadres to ensure that advisers working on nutrition programmes can use the latest evidence on interventions which deliver the greatest impact on stunting. | 2015-07-01
3. DFID should ensure that its interventions target better the nutritional needs of the most vulnerable. | Accept | DFID will provide guidance to staff to ensure new business cases, evaluations, theories of change and annual reviews of nutrition related interventions specifically consider the needs of the most vulnerable. | 2014-12-01
4. DFID should work with partners globally and in developing countries to ensure systems are in place to measure impacts of programme | Accept | DFID will support the launch of the first global nutrition report and, working with the European Commission, will develop options for supporting countries to strengthen information systems for nutrition and fill data gaps. | 2015-01-01
5. DFID should actively explore ways in which to engage the private sector in reducing undernutrition | Accept | DFID will review existing work with the private sector by developing an action plan on scaling up market based approaches to improving nutrition. | 2014-12-01

## Anti Corruption 2
DFID’s Approach to Anti-Corruption and its Impact on the Poor ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. DFID, in conjunction with the FCO and other UK Government departments, should articulate and implement a detailed plan setting out the level of ambition, commitment and positioning of the UK with respect to tackling corruption in its priority countries, including as experienced by the poor. | Partially Accept | DFID will agree with other Government departments its role in implementing a new UK Government Anti-Corruption Action Plan led by Cabinet Office once this is finalised. | 2015-03-01 | Complete
2.DFID should develop standalone anti-corruption country strategies and, in addition to its current activities, programming that explicitly tackles corruption and that extends over a 10- to 15-year time horizon with short-, medium- and long-term goals for reducing corruption, particularly with respect to the poor. | Partially Accept | DFID will review the value of its existing Anti-Corruption and Counter Fraud strategies in the light of experience and decide whether to refresh them to include longer time horizons, and to set out how we expect our interventions to affect corruption as experienced by the poor | 2016-01-01 | On track
3. DFID should include in its expanded anti-corruption portfolio many more programmes which specifically target the everyday corruption experienced by the poor and educate the population about the ill effects of corruption. | Partially Accept | DFID will continue to implement interventions which target corruption as experienced by the poor and will review how this is addressed in its service delivery programmes. | 2016-01-01 | On track
4.DFID should gather and publish targeted and dynamic feedback from the stakeholders of its anti-corruption work, including the intended beneficiaries, to allow DFID to ‘spot check’ and correct its existing programmes and to inform new programming. | Partially Accept | Within its country programmes and any new anti-corruption strategies, and in line with our Smart Rules, DFID will consider the best methods of gathering beneficiary feedback to inform programmes, including options for spot checking programmes where appropriate. | 2016-01-01 | On track
5. DFID should create an internal embedded centre of excellence explicitly to focus on anti-corruption and to gather evidence of effectiveness, disseminate lessons learned and cultivate expertise that will drive anti-corruption efforts globally. | Partially Accept | DFID will assess what additional research is needed to deliver operationally relevant evidence on tackling corruption and will expand its existing anti-corruption policy team to gather evidence, disseminate lessons and cultivate expertise. | 2015-03-01 | Complete

## Smart Rules
Rapid Review of DFID’s Smart Rules ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. DFID needs to continue to refine the Smart Rules to facilitate ease of use by teams in the field with a particular focus on clearer principles , focused technical guidance and examples of where discretion can be applied | Accept | 1. DFID’s Programme Cycle Committee will consider the recommendation and commission further work if necessary ahead of the next planned update of the rules. | 2015-07-01 | Complete
2. The Smart Rules need to be enhanced in key areas to meet critical challenges identified by ICAI *Be more explicit about beneficiary involvement; *Clarify the relationship between value for money , sustainability and impact; *Ensure a consistent approach to risk ,adaption and learning. *Enable mobilisation and increased realism in planning ; and *Make senior staff (such as heads of office) specifically accountable for continuous learning. | Partially Accept | 2. DFID's Programme Cycle Committee will consider the detail of the recommendation and commission further work if necessary ahead of the next planned update of the rules | 2015-07-01 | Complete
3. DFID needs to maintain the momentum of the change programme which has arisen from the End to End review and continue to engage all departments in a dynamic transformation focused on improving the impact of UK | Accept | 3. DFID will put in place complementary reforms and supporting measures to maintain momentum including continued training for Senior Responsible Owners , launching of "master classes" and continual professional development conferences and focusing on cultures and behaviours as well as processes. | 2015-05-01 | Complete
4. DFID leadership needs to define a compelling vision and mission for the organisation for the next decade , focused on reducing poverty for beneficiaries and use this to establish some explicit principles for the overall transformation ahead | Accept | 4. DFID leadership will continue to reinforce the Department’s vision and mission at every opportunity to both internal and external audiences. Our overall approach will be reviewed following both the 2015 UK General Election and the agreement of the Post 2015Development Agenda, and we will fresh the vision and mission as appropriate in the light of these. | 2015-12-01 | Complete
5. DFID needs to continue to leverage its leadership role in the global aid community to streamline overall system effectiveness and improve collaboration between partners | Accept | 5. DFID will continue to press the importance of development effectiveness principles in our engagement with all partners, in preparation for the next High Level Meeting of the GPEDC in 2016. | 2016-05-01 | On track

## ICF
The UK’s International Climate Fund | ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. The ICF should work through a wider range of delivery partners at the international and national levels, with a stronger understanding of their comparative advantages. | Accept | 1. ICF Secretariat to undertake a mapping of ICF delivery partners to identify delivery gaps and inform an ICF Board discussion on the strengths and risks of the current portfolio. | 2015-09-01 | Complete
2. More flexibility in the allocation of resource and capital expenditure is needed. DECC and Defra would benefit from more flexible and direct access to both resource and capital expenditure. | Accept | 2. The Government will consider as part of and/or in light of the next Spending Review. | 2015-09-01 | Complete
3. The ICF should develop a more differentiated strategy for working with the private sector focussed on the particular conditions and approaches required to attract different forms of private capital. | Accept | 3. DFID and DECC private sector advisers to review the ICF’s private sector strategy, including commissioning work to identify ways to increase private sector engagement in adaptation | 2015-11-01 | Complete
4. The ICF should deepen its engagement with developing country governments and national stakeholders, including through greater emphasis on capacity development. This is likely to require greater access to grant and technical assistance resources, including for middle income countries. | Partially Accept | 4. Identify opportunities to identify opportunities to increase ICF support for country level engagement and capacity building in new and existing programmes; for example by explicitly including capacity building as a selection criterion for future ICF projects and requests for project extensions. | 2015-12-01 | On track
5. The ICF should strengthen coherence across multilateral and bilateral delivery channels and programmes and implement a common, country level planning process and tracking system. | Partially Accept | 5. Whilst recognising the need to strengthen coherence the ICF seeks to support countries own systems to plan and track climate programming. To do so the ICF will identify and showcase systems that enable effective country level planning and use them to inform future capacity building support from the ICF. | 2016-01-01 | On track
6. The ICF should be more transparent and inclusive, publishing its strategies, activities and progress on an ICF website, in a coordinated reporting format in partnership with other climate finance providers | Accept | 6. Update the ICF "GOV.UK" website regularly with improved quality and transparency of public information on the ICF. | 2015-07-01 | Complete

## Fragile States
Assessing the Impact of the Scale-up of DFID's Support to Fragile States OFF TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. DFID needs to develop coherent guidance on working in fragile states, drawing on adaptions developed at country level , new research and learning and the evolved systems being developed in DFID centrally | Accept | 1. DFID will update it's peacebuilding and state-building guidance to support work in fragile states drawing on a wide range of evidence , including from country practice | 2016-03-01 | On track
2. DFID should ensure that country-level targets realistically reflect the challenges of scaling up and the longer-term timescales needed for lasting impact in fragile states and calibrate funding accordingly .The targets should reflect the entire country portfolio ,taking account of small as well as large programming through qualitative and quantative targets | Partially Accept | 2. DFID will review its target setting and performance monitoring framework later this year. As part of this, we will draw on emerging knowledge and lessons from the review and consider how best to cover the whole country portfolio. | 2016-03-01 | On track
3. DFID needs to provide guidance on the inclusion of targeted infrastructure components in development programmes to enhance sustainable impact in fragile states programming | Partially Accept | 3. DFID will consider updating its guidance on infrastructure in fragile states in the light of experience with the new policy framework | 2016-03-01 | On track
4. DFID needs clarity about its appetite for risk in fragile environments :there needs to be explicit alignment between the centre and the field about potential for failure and its consequences | Accept | 4. DFID will develop additional policy guidance. | 2015-10-01 | Off track DFID has developed a risk management and assurance framework which is being considered by DFID’s Audit & Risk Assurance Committee framework in December 2015. Underpinning this is guidance, examples of good practice and tools (including on articulating risk appetite in all contexts, including in fragile environments) which is work in progress and will continue to be developed throughout 2016.
5. DFID should leverage its learning about operating in fragile states and take a clearer global leadership role, in particular to work with the international community to advance thinking about how effectively to work in fragile states | Accept | 5. DFID will continue to play an active role in influencing the international community . This year we will use the Mid Term Reviews of the African Development Fund 13 And World Bank's International Development Association 17 commitments and the on-going DFID-led UN Portfolio Delivery Review process to help multilateral organisations and international financial institutions review experience with different approaches to fragile states | 2015-12-01 | On track

## OGDsODA
Official Development Assistance (ODA) spent by Departments other than DFID COMPLETE
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1.DFID should request ODA-spending departments to accompany their annual ODA returns to DFID with an information note describing, in simple terms , the main activities or types of activity claimed as ODA. DFID should include this information as an annex to its Statistics on International al Development , to enhance transparency. | Accept | 1. DFID will integrate the request into the commission which goes to departments in APRIL/May 2015 and include information provided in Statistics on International Development 2015. | 2015-10-01 | Complete

## Security and Justice
UK Development Assistance for Security and Justice OFF TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. DFID should adopt a new strategy for more focussed and realistic security and justice assistance that emphasises tackling specific security and justice challenges in particular and local contexts. This should include working in a cross-disciplinary way to address wider security and justice themes , such as gender equality (including working with men),labour rights and urban insecurity. | Partially Accept | 1. DFID will produce an updated and consolidated security and justice position paper including consideration of wider security and justice themes. | 2015-12-01 | Off track: we have drafted a Security and Justice Position Paper but will now need to ensure coherence with the Strategic Defence & Security Review and UK Aid Strategy commitments on building stability. New target date March 2016.
2.DFID should identify the key evidence gaps across its security and justice portfolio and tailor its investments in research and innovation to fill those gaps. It should develop guidelines on how to ground programme design in sound contextual analysis and evidence of what works and on how to strengthen programme oversight , including management of political risk. | Partially Accept | 2. DFID will map the key evidence gaps supporting the security and justice portfolio and assess whether additional investments in research and innovation are necessary to address any gaps. | 2015-09-01 | Complete

## Business in Development
Business in Development ON TRACK
Recommendation 5 Rejected No Action
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. DFID should translate its high level strategies for business engagement into detailed operational plans which provide specific guidance on business engagement with a focus on the poor. | Partially Accept | 1. Operational Plans will continue to provide the link between DFID’s high level strategies and our programmes. Once finalised, the full Inclusive Growth Diagnostics will address practical implications for economic development programming – including around business engagement. This will be reflected in future Operational Plans. | 2016-04-01 | On track
2. DFID should ensure better linkages between centrally managed programmes and country offices for business in development, including LEG | Partially Accept | 2. Private Sector Department will complete the drafting of a plan to strengthen the coherence of its portfolio, based on its experience of networks and other models for developing linkages between centrally-managed and country office programming. | 2016-04-01 | On track
3. DFID should pull together, synthesise and disseminate management information across all departments, including for LEG, to improve management and ensure learning is captured and used to improve performance | Partially Accept | 3. Following the approval of a Management Information Strategy in February 2015, DFID is strengthening its management information across the organisation with the aim of streamlining data collection and quality assurance. This will include reporting on development capital and other private sector instruments. 4. The Leading Task and Finish Group with the remit of driving forward a Learning Action Plan and integrated learning across DFID, will report later this year. 5. We will proceed with current plans to monitor our Development Capital portfolio. | 2016-04-01 | On track
4. DFID should add suitably experienced members to the Investment Committee to enable sufficient strategic oversight of all components of its LEG portfolio. | Partially Accept | 6. We believe the Investment Committee has the appropriate skills to oversee our current DevCap portfolio, but we will keep this under review. 7. Ministers will decide on the appropriate level of oversight and corporate governance for potential new Development Capital platforms. | 2016-04-01 | On track

## Impact
DFID's Approach to Delivering Impact ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. At the departmental level, DFID should develop a Results Framework that better reflects the range of impacts it seeks to achieve, capturing not just the breadth of its engagement but also its transformative impact, including successes in institution building and policy influence. To do so, it will need to look beyond quantitative indicators towards other ways of capturing the impact of UK aid. | Partially Accept | 1. DFID’s new Single Departmental Plan will provide the overarching performance framework for the Department. Beyond that, we are reviewing our future priorities for results reporting and will consider opportunities to improve how we measure and report the full range of impacts of our programmes. | 2016-04-01 | On track
2. At the country portfolio level, DFID’s Country Poverty Reduction Diagnostic (CPRD) should pay more attention to longer-term change processes, both looking backwards to understand the trajectory of achievements and forward towards potential long-term paths out of poverty and fragility. Its operational plans should contain stronger links between the analysis and programming choices, with more emphasis on how different programmes and sectors interact to produce wider impact. | Partially Accept | 2. As part of the strategic planning and resource allocation processes for the next Spending Review Period, CPRDs will continue to consider longer term change processes, and will directly inform resource allocation decisions. | 2016-04-01 | On track
3. At the programme level, DFID’s business cases should be more explicit about the route towards long-term impact, including policy and institutional change, setting out the building blocks and pathways required to achieve transformative impact over time. This includes looking beyond the life of the programme to the follow-up actions required and exploring how to work with other programmes and initiatives to achieve mutually reinforcing results. | Partially Accept | 3. DFID will consider this recommendation in the context of its next update of Smart Rules – the operating framework for programmes - and through ongoing work to introduce a more flexible and adaptive approach to programming. | 2016-03-01 | On track
4. Annual reviews should include an assessment of the assumptions and risks set out in the logframe and theory of change. DFID should work to tighten feedback and learning loops, to enable real-time adjustment of programmes. | Partially Accept | 4.DFID will consider this recommendation in the context of its next update of Smart Rules – the operating framework for programmes - and through ongoing work to introduce a more flexible and adaptive approach to programming. | 2016-03-01 | On-Track
5. DFID should engage with intended beneficiaries throughout the programme cycle, in design, delivery and monitoring. DFID should anchor its interventions in sustainable community structures that are integrated into wider governance systems. | Partially Accept | 5. We will strengthen our package of support on beneficiary engagement - including guidance materials, case studies and programme management training for DFID staff. | 2016-03-01 | On track
6. In its ongoing review of its risk-management processes, DFID should explore how to achieve an explicit and balanced risk profile in its country programmes, including high-risk programming with the potential for transformative impact. High-risk interventions should be identified as such from the outset, with the rationale for action clearly stated, and then be subject to appropriate risk management arrangements. | Accept | 6. As part of the ongoing work to improve risk management, DFID will complete the pilot testing of the draft risk-return tool across a range of business areas to ascertain how it can be used to inform portfolio strategy and programme selection in countries. | 2015-12-01 | On track
7. In its procurement processes, DFID should carefully consider both the merits of transferring outcome risk to implementers, particularly in high-risk environments and the likely impact on its objectives, its supplier base and its overall costs. It should work towards clear guidance on what forms of results-based contracting to use in which circumstances, so as to avoid needless rigidity in programming and unhelpful incentives that do not enhance actual impact. | Accept | 7. DFID will update and disseminate guidance setting out best practice for payment by results contracting. | 2015-12-01 | On track

## Multilaterals
How DFID Works With Multilateral Agencies To Achieve Impact ON TRACK
Recommendation 1 Rejected No Action
Recommendation 2 Rejected No Action
Recommendation 3 Rejected No Action
Recommendation 6 Rejected No Action
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
4. DFID should continue to press for greater transparency and accountability of multilaterals | Partially Accept | 1. DFID will continue to press for greater transparency and accountability of multilaterals including through the new MAR. | 2016-04-01 | On track
5. DFID should promote more integrated working amongst multilateral institutions at country level. | Accept | 2. DFID will continue to support better donor coordination; we will collect examples of effective integrated working and share the lessons from these examples across the country network. | 2016-04-01 | On track
7. DFID should communicate more effectively to taxpayers about the role, impact and importance of multilaterals. | Partially Accept | 3. DFID will work with multilaterals to increase their engagement with UK media and provide strong case studies explaining the impact of their programmes. We will do more to share stories and content. We will take stock of this work in December 2015 | 2015-12-01 | On track

## Follow Up
Follow up of ICAI Reports from Years 1, 2 and 3 OFF TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2015 Update
1. Education: DFID should intensify its support for governments to set targets and timelines which reflect realistically achievable rates of improved educational attainment, in other words, not just more but better education. This would include the scaling-up of teacher training. | Partially Accept | 1. Scaling up teacher education is one of several possible responses to poor learning outcomes. We will continue to consider support for teacher education on a case by case basis | 2016-12-01 | On track
2. Education: DFID should encourage governments to have clear goals aimed at limiting inequities in resource distribution, for example through linking funding to reductions in very high pupil: teacher ratios. | Accept | 2. DFID will continue to encourage partner governments to address inequities, and will facilitate the sharing of best practice between countries. | 2017-04-01 | On track
3. Education: DFID should intensify its support for local government to improve the use of data systems, quality control, analysis and performance review to support locally-determined actions for improving pupil learning. This should include key influencing factors, such as pupil and teacher attendance. | Partially Accept | 3.DFID programmes will look to strengthen government capacity to use data on key indicators to improve pupil performance, based on analysis of at which level of government there are bottlenecks. | 2017-04-01 | On track
|  | 4. DFID will draw on DFID’s new 8-year (2014-2022) research programme on education systems (RISE) to better understand how education systems work to deliver improved learning and to incentivise improved use of data at all levels. |  | On track
4. Learning: DFID should ensure that its learning improvement initiatives and plans are consistently driven forward, with realistic timescales for change. In particular that staff spend more time engaged more directly with delivery partners and beneficiaries and that specific incentives are put in place to reward managers for encouraging and using staff feedback | Partially Accept | 5. Lessons from the four pilots will feed into DFID’s Learning Strategy, which will be launched in Summer 2015. The strategy will aim to further embed learning across the organisation. | 2015-12-01 | Off track : First stage of delivery has addressed specific concerns from ICAI report , developing beacon of good practice approach led by a Learning Group and supported by a network of Learning Champions across the business and 2015 has been the Year of Innovation and Learning in DFID . Four pilots addressing key drivers of change in learning in DFID are helping inform a strategy for the whole business. Learning from these activities is being fed into the new strategy , which will now be launched in early 2016 to ensure maximum impact and uptake .
5. Child mortality in Kenya: There are risks to health outcomes in Kenya as a result of the pace and manner of DFID’s decision to exit malaria work. DFID should balance this decision with an appropriate focus on ensuring that alternative funding sources are available to continue the provision of basic health supplies, such as bed nets, and that a commensurate investment in health systems strengthening is made. | Partially Accept | 6. The Kenyan Government will circulate its draft Health Financing Strategy in August 2015, for consultation with development partners. We will to use our experience, evidence, and influence as a key member of the Health Sector Working Group, to try to ensure it is soundly based. We will also aim to influence the Global Fund to ensure that they give priority in allocating resources to malaria control and health system strengthening for Kenya. | 2016-04-01 | On track
6. Girl Hub: We recommend that DFID should consider in depth whether ongoing funding is merited and either reach a decision to cease funding or consider extending the project for a year to enable the evaluation to be completed. A condition for this should be that the governance issues be resolved and that Nike Foundation provides detailed information on its in-kind contributions. | Partially Accept | 7. DFID will commission a due diligence assessment to inform management of the accountable grant for Girl Hub Rwanda. This will include governance issues. | 2015-07-01 | Complete
7. Future follow-up: To improve the effectiveness of the follow-up process, DFID should engage directly with the ICAI team post publication to ensure that responses address the key issues raised; that there is greater consistency in how the terms ‘accept’, ‘reject’ and ‘partially accept’ are used; and that progress is tracked by DFID in a more rigorous and structured way. | Partially Accept | 8. DFID will work with ICAI to agree appropriate post publication protocols | 2015-10-01 | Complete