## Content
Standard Operating Procedures: Open
Contents
| Phase | SOP No: | SOP Title
Pre-procurement market engagement | Business need identification, baselining & market analysis | 1.1 | Analyse business need
|  | 1.2 | Conduct pre procurement market engagement
|  | 1.3 | Conduct benchmarking vs. current provision
|  | 1.4 | Write & publish a project specific P.I.N.
|  | 1.5 | Establish industry boot camp logistics
|  | 1.6 | Run an industry boot camp
|  | 1.7 | Write 1st draft of strategic outline business case
|  | 1.8 | Internal decision to "make or buy"
| Mobilisation | 2.1 | Establish a cross disciplined team
|  | 2.2 | Create a project performance hub
|  | 2.3 | Complete team skills assurance
|  | 2.4 | Establish & brief project board
|  | 2.5 | Establish what approvals will be required & when
| Sourcing strategy | 3.1 | Write procurement strategy & get approval
|  | 3.2 | Update business case (SOBC to OBC)
|  | 3.3 | Create bidders pack / invitation to tender (ITT)
|  | 3.4 | Write & get approval for OJEU notice
|  | 3.5 | Carry out assurance & obtain approval to proceed
Sourcing & Contracting | Supplier notification (OJEU) | 4.1 | Publish OJEU notice & issue ITT
| Supplier clarification | 5.1 | Set up & run an online / electronic Q&A facility
|  | 5.2 | Refine project & resource plans
|  | 5.3 | Brief evaluation team
| Execution of sourcing strategy through evaluation of tenders | 6.1 | Receive & sort tenders and conduct compliance check & clarification
|  | 6.2 | Evaluate tenders
|  | 6.3 | Write full business case
| Finalisation of contract | 7.1 | Obtain approval to award decisions
|  | 7.2 | Issue notification of standstill period & debrief suppliers
|  | 7.3 | Update the full business case
| Contract signature | 8.1 | Sign contract

## # 1.1
Date | 2015-02-10
Version | 8.1
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Ensure that you have a sound understanding of the business outcomes required | Create a concise statement of key outcomes and play back to the policy makers, your understanding of the high level requirements. Key risk that commercial team perceives the business need differently to the policy makers. Ensure that you have identified all of the key stakeholders who will own or be affected by the business outcomes. Make sure that you understand the impact of socio-economic and wider policy factors on the make up of the high level requirements. For example, there may be a requirement for any subsequent procurement to contribute positively to the UK economy, support indigenous supply chains etc. |  | Definitions of terms: Outcome, Output, Input The outcome of a project is the contribution it makes towards the goal(s) of the organisation Outputs are intermediary objectives that support the delivery of outcomes, e.g. improved IT systems are often outputs to projects. Inputs secure outputs and normally many inputs are needed to secure outputs, e.g. in an IT project inputs may include hardware, software, design of databases etc.
2 | Consider running stakeholder analysis boot camp to achieve Step 1 | If you have a large, diverse group of stakeholders, for example, a cross government group, consider running a stakeholder boot camp to agree your business outcomes & if appropriate, high level draft specification.
3 | If appropriate run stakeholder analysis boot camp | Use the visual management tools and techniques. Arrange a boot camp and ensure all the key stakeholders attend. Set expectations at the outset by making it clear that key decisions will be made at this session. At an appropriate time before the boot camp populate a customer needs statement (business outcome as you currently understand it) and circulate asking stakeholders to bring their thoughts on requriements to the boot camp. Use someone who is experienced in facilitating to manage the boot camp. Outline the etiquette for the day and clearly identify what needs to be achieved by the end of the session and what the next steps will be. Before closing the boot camp ensure that you have met your predefined objectives for the day & that key stakeholders are clear about the subsequent timeline for the procurement. Use the outputs of the boot camp to feed into your approach to market considerations and your project specific PIN. |  | LEAN Visual Management - Stakeholder Boot Camp
4 | Initial "make or buy" considerations | Based on your understanding of the desired policy outcomes consider and investigate existing in-house or in government capability to meet requirements. Give consideration to alternative business models such as Joint Ventures, Mutuals & Co-operatives. Decide on whether a regulated procurement is necessary, and set out options for the scope of what could be procured. Look for examples of similar activity elsewhere in government. Identify whether the requirement is covered by centralised procurement. (e.g. through the CCS and/or Procurement Centres of Excellence) or whether any other requirements exist for collaboration, use of national/international agencies etc. Consider the sustainability implications; can different kinds of products meet the business need (e.g. low emission vehicles)? Is a procurement required at all or could the need be met through working with other departments? The Regulations permit contracts to be reserved for Mutuals , whereby they are protected from competition for a period of three years. |  | Refer to the Procurement Route Decision Tree (in the Lean Sourcing Manual & the Standard Template Library)
Business models
CCS centralised categories
5 | Initial approach to market considerations | Evaluate the potential market approach for the identified options. Consider how any procurement might fit within the current ‘commercial landscape’ in government. Commercial team are unsighted on policy intent where new commercial vehicles may have been envisaged such as Joint Ventures or mutuals Market Knowledge in the team may be insufficient to ensure full consideration of all possible approaches Use quantitative evidence to underpin evaluation of options Use emerging market analysis to confirm that the correct procurement procedure is envisaged/being followed and refer to current government policy. Consider the role Small Medium Enterprises (SMEs) and or Voluntary Community and Social Enterprises (VCSEs) can play. Consider whether the requirement can be broken down in order to increase competition and create opportunity for SME and/or VCSE participation. Take into account the requirements of the Social Value Act 2012 (See SOP 1.2.3) and consider whether additional consultation with stakeholders and/or with the market is likely to be required.
1.1 Analyse Business Need

## #1.2
Date | 2015-02-10
Version | 5.1
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Carry out market research to establish whether there is a market for what you need | Research what the market has to offer, if anything, and establish whether there have been any significant developments since you last went to market. Use market specialists if appropriate. Use existing market knowledge, e.g. Lists of suppliers, known contacts, expressions of interest etc. Use this data to establish who the key suppliers might be and whether there are Small Medium Enterprises (SMEs) and or Voluntary Community and Social Enterprises (VCSEs) within the market place and to inform benchmarking against current provision (if applicable). Create a diverse list of suppliers, which includes SMEs, that you would like to invite to an industry boot camp. |  | Refer to SOP 1.6 for details of running an industry boot camp
2 | Hold informal discussions with potential suppliers | Contact the potential suppliers identified through research so far and arrange informal private discussions with them about your emerging requirements. Ensure that there is a meaningful two way exchange of information; simply holding an 'industry day' does not necessarily achieve this. Focus on potential suppliers' views of what is possible and desirable for them to provide. Include such factors as the key risks, the likely costs and socio economic factors such as potential supply chain and wider economic and social impact of various market approaches. Take a note of the key points discussed in each meeting to ensure that you have an audit trail in case you need to refer back to the discussions. Take care with reference to Regulation 41 not to distort competition through any pre procurement market engagement activity. |  | PPN - Procurement Supporting Growth - Myth busting factsheet
3 | Take into account the requirements of the Social Value Act 2012 | Consider whether there is a need to consult with both the marketplace and potential users on how the service required could bring added economic environmental and social benefits. The Social Value Act: One Year On provides useful guidance for commissioners explaining the implications of the Social Value Act as well as other resources and links. |  | Social Value Act: One Year On Report
PPN 10/12 The Social Value Act
1.2 Conduct pre procurement market engagement

## #1.3
Date | 2015-02-10
Version | 3.2
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Identify current provision | Identify any current contracts within the department which cover the scope of the intended procurement. Consider whether the requirement is new, or whether it replaces an existing service or product.
Identify information that needs sharing in order to ensure that all suppliers can bid on equal terms.
Begin the process of establishing 'due diligence' information. This should include identifying existing contracts and licences affected by any proposed new provision, assets that may be transferred and the numbers, identity, up to date records of each employee's terms and conditions, and employment history of staff potentially affected through TUPE regulations.
2 | Analyse/establish current spend | Collect data on the amount of time/resource used currently to deliver the service/product and the levels of service currently delivered and the history of the volume of supplies or services required. Identify the costs of current contracts, including the resource costs of managing existing services. Collect data covering an easily measurable time period – e.g. Monthly, per annum etc. Clearly label any assumptions made. Data collected may represent a different business model and therefore be misleading. Consider the total cost of ownership when assessing the costs of existing contracts.
3 | Establish current provision baseline | Use data collected to establish and record a baseline position regarding the costs of current provision.
Baseline data can be used to feed into the Strategic Outline Business Case.
There may be less value in undertaking the benchmarking exercise where you are looking for a new or innovative solution to your business requirement.
4 | Carry out comparative benchmakring | Using the data that you have gathered, carry out a comparative exercise to benchmark against your baseline.
1.3 Conduct benchmarking versus current provision

## #1.4
Date | 2015-06-19
Version | 4.3
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Write a project specific Prior Information Notice (PIN) | Write the project specific PIN to include requirements, scale and contract value as far as is known at the time. If possible try to keep your requirements outcome based so as not to restrict the response from the market. Consider the presentation and content carefully; effectively this is making a 'pitch' to the marketplace; use plain English to describe clearly the high level statement of need and potential opportunity. Include in the PIN details of the Industry Boot Camp and a contact for suppliers to confirm their attendance. Ask suppliers to identify whether they are a SME or VCSE when they confirm their attendance at the Industry boot camp. |  | Refer to SOP 1.6 for details of running an industry boot camp
EU Definition of an SME
2 | Publish the PIN | Use PIN template via eNotices As good practice you should additionally publish the PIN on Contracts Finder Your medium term procurement plan will have been published as part of your procurement pipeline. Therefore you must identify this procurement, with reference to the pipeline. Ensure that the relevant EU timescales and information associated with publishing a PIN are adhered to in order to take advantage of the shorter timescales for receipt of tenders. Ensure that any relevant internal approvals have been obtained before publishing a PIN.
3 | Advertise the requirements and the Industry Boot Camp | Consider whether the PIN is sufficient to alert the marketplace to your requirements, and to the Industry Boot Camp. Consider advertising in Trade journals, specialist publications etc. Ensure that any advertisements give the same amount and quality of information as the PIN, to show that equal treatment has been afforded to everyone in the potential marketplace.
1.4 Write and publish a project specific PIN

## #1.5
Date | 2015-02-26
Version | 2.1
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Book venue and facilities for the industry boot camp | Identify the number of rooms required, as a minimum: Main room Project room Surgery room(s) Refer to the Visual Management tools and techniques to make sure that the venue can meet your requirements. Main room should be large enough to host project team and all suppliers comfortably. Project room should be large enough to host the team with available wall space. If you are unable to use the walls you will need screens/flip charts. Surgery room(s) should be large enough to host the suppliers and nominated project team members. Arrange for availability of ICT, printers, telephony, security, photocopying, flip charts, whiteboards where applicable .
Refer to SOP 1.6 Run an industry boot camp
2 | Secure diary commitments and resources from all required stakeholders | Schedule all required sessions with stakeholders well in advance, including expected duration of each session. Avoid delays by confirming diary slots with stakeholders.
3 | Compile attendance list | Monitor the response to your advert in the PIN and/or any other adverts you placed in Trade journals, specialist web portals and/or publications etc. so that you have a clear idea of who (including how many SMEs and/or VCSEs) will be attending.
1.5 Establish industry boot camp logistics

## #1.6
Date | 2015-06-19
Version | 4.2
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Organise an industry boot camp (workshop) as part of your market analysis | To comply with EU procurement rules and avoid the potential for challenge, all potential bidders need to be given the same opportunity and be treated equally both prior to and within the subsequent competition.
http://www.contractsfinder.businesslink.gov.uk/
Use the Visual Management tools and techniques to setup the logistics for an industry boot camp.
Try to ensure that a full range of potential suppliers and relevant trade bodies are aware of and attend the workshop. Include SMEs and VCSEs or as a minimum the relevant trade bodies. If you expect strong interest (large numbers to attend) consider running more than one Industry Boot Camp.
Ensure all attendees have name badges and provide attendee lists to facilitate networking.
Present your ideas and business requirements to the suppliers and invite questions, feedback and discussion. Clear and consistent messages are important; consider scripting and rehearsing the presentations to suppliers. Consider whether the initial presentation e.g. by the SRO, CEO etc. could be provided in advance by Webinar, Podcast etc. This could ensure consistency and save time on the day.
Schedule 1-2-1s with suppliers to discuss individual queries and ideas confidentially. Organise breakout groups to encourage networking and partnering opportunities.
Capture the suppliers’ views on your requirement, on the viability, and on possible delivery options.
Facilitate meetings between suppliers to explore the potential for the establishing consortia, partnering arrangements and/or subcontracting opportunities.
|  | Encourage suppliers to advertise sub-contracting opportunities on Contracts Finder. |  | Contracts Finder
2 | Refine requirements and business case | Use the outputs from the industry bootcamp, particular suppliers views of their market, to inform your decision to ‘make or buy’ (SOP 1.8):
Refine requirements (including the shape of your requirement) to reflect increased understanding of market. Ensure that you do not distort competition (see Regulation 41) in taking account of the outputs from the boot camp.
Consider how appropriate it will be to use an outcome based specification.
Update your market analysis.
Gauge the level of supplier interest in fulfilling the requirement using the supplier interest tracker and through making follow up calls/e-mails.
Inform the likely timescales for procurement and resources required to deliver it.
Develop procurement strategy (if procuring), consider lotting strategy, as you will be required to indicate later on, the main reasons for any decision not to subdivide into lots.
Refine the business case.
1.6 Run an industry boot camp

## #1.7
Date | 2015-02-10
Version | 2.2
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Write first draft of Strategic Outline Business Case (SOBC) | The Strategic Outline Business Case (SOBC) provides the platform for the ‘initial agreement to proceed’. It establishes the case for change, the need for investment and provides a suggested way forward for the early approval of management. Senior Responsible Owners (SROs) need to look at the characteristics of their organisation and business objectives in order to determine the appropriate strategic approach: If there is confidence about the long-term goal, stability of the organisation and business objectives, and the outcome responsibility can be passed to the private sector, then there is scope for contracting for an outcome, using a partnering approach where appropriate. Where there is stability of requirement, but a relatively simple set of objectives and processes, then contracting for outputs is the most likely path. In some circumstances where there is low stability, frequent change, and new approaches are developing rapidly, contracting for inputs is the better option, and often such contracts should be limited in scale and duration. Start to ensure that senior stakeholders and approvers are sighted and content wih the direction of travel. Suggested content & structure for SOBC as follows: Strategic fit - Description of the business need and its contribution to the organisation’s business strategy Objectives - Why it is needed now, key benefits to be realised, critical success factors and how they will be measured. Options appraisal - High level cost/benefit analysis of (ideally) at least three options for meeting the business need, analysis of ‘soft’ benefits that cannot be quantified in financial terms, identify preferred option and any trade-offs. Commercial aspects - this section outlines the potential deal and will include: Proposed sourcing option with rationale for its selection and key features of proposed commercial arrangements (e.g. contract terms, contract length, KPIs, SLA, payment mechanisms and performance incentives) .The procurement approach/strategy with supporting rationale. Affordability - Statement of available funding and ‘ballpark’ estimates of projected whole-life cost of project including departmental costs and resources required to manage the contract. Achievability - High level plan for achieving the desired outcome, with key milestones and major risks and dependencies. Consideration of the risks and dependencies might include: Interfaces with other projects, crtical dependencies e.g. expiry of current services and related transition arrangements, ministerial commitments. Outline contingency plans e.g. to address failure to deliver the service on time. Identify major risks alongside robust countermeasures. Resources, skills and experience required. Consider and identify any legislative requirements, for example the Energy Efficiency Directive. |  | If appropriate use the HMT Green Book Templates:
Green Book Templates
1.7 Write 1st draft of Strategic Outline Business Case

## #1.8
Date | 2015-02-26
Version | 4
Procedure | Open
Stage | 1
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Decide whether procurement is necessary. | Referring to the initial ‘make or buy’ decision (SOP 1.1), refine this as a result of your market analysis and discussions with suppliers during pre procurement market engagement; take the final decision on whether a procurement is necessary, i.e. whether to ‘make or buy’ to fulfil the requirements. Note: The term 'make or buy' is typically used in procurement to refer to the decision as to whether to use in house resources (make) or to contract externally (buy) to fulfil a requirement. Where there are serious concerns about the level of bidder interest you should consider delaying the start of the formal procurement process. You may need to change the parameters of the project to make it more attractive, to reduce perceived barriers to entry or involvement, or to undertake other market creation/stimulation activity.
1.8 Internal decision to "make or buy"

## # 2.1
Date | 2015-02-10
Version | 1.2
Procedure | Open
Stage | 2
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Establish a cross disciplined team at the start of the project | Identify what resources the project requires as set out in the strategic outline business case (SOP 1.7) and the skill sets these resources will need.
Formalise the appointment of the identified resources. Notify those required later in the project when they need to be available.
The team will typically consist of:
A Senior Responsible Owner
Commercial lead
Technical lead
User/business representatives / subject matter experts – these should include policy representatives
Legal support
Project/Programme manager
Project management office & admin support
Where possible, the future contract manager
Note – depending on the scale and nature of the project, individuals may be fulfilling multiple roles.
Ensure any gaps in resource/capability are highlighted on the risk log. Identify potential evaluators and ensure that they will be available at the planned times for tender evaluation; ensure that business stakeholders understand the time and resource required from evaluators and that they are committed to providing this.
The team may require additional skills to lead on specialist areas that cannot be provided in-house. Such resource costs need to be accounted for.
2 | Hold Project Team Kick-off Meeting | Arrange and hold a Project Team Kick-off & Strategy Meeting to review the procurement strategy, the activities to date and focus on preparation of documentation, Governance and approvals; reaffirm the working practices for the procurement in going forward. Ensure that the contract management team are identified and involved from the outset
2.1 Establish a cross disciplined team

## #2.2
Date | 2015-02-26
Version | 3.2
Procedure | Open
Stage | 2
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Identify and obtain a space to host a performance hub | Obtain a space to use as the project performance hub that is large enough to display project documentation on walls, screen panels and host meetings with stakeholders.
Ensure that the room is large enough to host the team. This space will also benefit from conference facilities (telephone/video conferencing). Resources may not allow for a dedicated room; consider whether portable boards or displays could be used; consider setting up virtual hubs using collaborative working ICT tools particularly if the team is on multiple sites.
2 | Create a performance hub | Use the Project Performance Hub Guidance visual management pack to create the team hub.
Display and deploy a product set contained within the library of standard documents or your own existing corporate template library. This will typically include a Team Implementation Plan (TIP) based on the standard template – which sets out the activities to be carried out throughout each stage of the project. Ensure that the plan from publication date of OJEU notice through to contract award decision date is within 120 working days. The standard document set can be used and adapted flexibly to fit in with your departments' established processes, e.g. for Project Management, Stakeholder Communications etc. It is not intended to be entirely prescriptive.
Plan out the utilisation of the resources and develop a detailed understanding of the costs to deploy them.
Develop a staged resource plan aligned to the activities in the TIP which identifies the planned utilisation of the cross disciplined team and the associated costs of doing so.
Identify sources of management information (MI) that will provide data to measure project turnaround times using the standard set of Key Performance Indicators (KPIs) and also assist with the completion of Cabinet Office reports such as the Quarterly Data Summary. This data will help to drive continuous improvement in future sourcing projects.
3 | Operate a performance hub using the standard document set | Use the standard document set (on a daily basis) to run project activities in line with the plan and ensure that you are on target to meet the 120 working days procurement turnaround target. Manage risks and the delivery of benefits through performance measurement.
2.2 Create a project performance hub

## #2.3
Date | 2015-02-10
Version | 2.2
Procedure | Open
Stage | 2
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Carry out skills assessment | Identify what skills and capabilities are required for each role within the team to ensure successful project delivery (see 2.1). It will be crucial to determine what specific technical skills will be required – e.g. data security, change management, legal expertise alongside general project management and procurement capabilities.
Assess the skills and capabilities of each individual within the team.
Identify gaps between current and required levels of skills and capability of individuals within the team. Identify any potential 'single points of failure' and consider contingency plans.
Document individual skill levels in the skills matrix within team performance hub.
2 | Fill key capability gaps | Identify training requirements for individuals and/or recruit capability where short term requirements cannot be met through training/coaching. |  | Lean Sourcing Training
Details about the courses are available from Crown Commercial Service by phoning the customer service desk on 0345 410 2222 or by emailing training@ccs.gsi.gov.uk
Develop capability levels through training/coaching/knowledge transfer.
Ensure that team members have been enrolled on/attended LEAN sourcing training.
Re-assess skills at agreed frequencies.
3 | Confirm that team skills assurance has been completed. | Update the skills matrix in the performance hub to reflect capability uplift.
Monitor performance of individuals where capability has been developed through training/coaching.
2.3 Complete team skills assurance

## #2.4
Date | 2011-06-14
Version | 1
Procedure | Open
Stage | 2
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Establish a project board to oversee the delivery of the project | Confirm who the SRO for the procurement project is and agree with them the appropriate membership of the project board.
Establish the terms of reference.
Set frequency of meetings and agree requirements for progress reporting and assurance reviews.
2 | Fully brief project board members | Provide an overview of the scope, objectives, deliverables and milestones of the project and the role(s) that project board members are to play in delivering the project.
Ensure board members fully understand the intended outcomes of the project.
If project board members do not fully understand the aims and objectives of the project and how it will be run (lean and visual management) there is a risk that decision making will be delayed.
3 | Appraise Project Board on progress and decisions required | Use key performance hub products (e.g. Team Implementation Plan, Risk log, KPIs, weekly reporting dashboard etc.) to appraise the project board of progress and to inform any decisions that need to be made by the project board.
4 | Keep project board members aware of progress. | Use the weekly report to provide the project board with an update on progress.
2.4 Establish and brief the project board

## #2.5
Date | 2014-05-27
Version | 2.1
Procedure | Open
Stage | 2
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Establish the internal and external approval and assurance processes | Establish the internal and external approval processes and build the approval points into your project plan.
Do the same with assurance processes whether internal or external (e.g. Gateway Reviews).
|  | Check whether your project will be subject to the central moratoria e.g. ICT |  | Spending controls
|  | Departments must operate a presumption that individual ICT contracts or projects should be less than £100m over the lifetime cost. |  | PPN - Guidance on ICT contracts less than £100m
|  | Identify whether HMT approvals are required. |  | Major Projects Authority
Establish whether the project is on the Government Major Projects Portfolio.
Check with Finance that you have picked up all the approvals that will be required.
|  | Establish whether the Crown Representative needs to be sighted on the procurement. |  | Refer to Guidance on Actions & Processes or contact strategic.suppliers@cabinet-office.gsi.gov.uk
2 | Create an approvals plan | Document a plan to ensure that requirements for approvals and assurance are met in a timely manner.
Having sight of approval points in advance will reduce the risk of delay to the project.
2.5 Establish what approvals will be required & when

## #3.1
Date | 2015-06-26
Version | 5.3
Procedure | Open
Stage | 3
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Identify appropriate procurement route. | You are currently using the SOPs for the Open Procedure, and at this point you need to make the final decision on the procurement route that you use. |  | Refer to the Procurement Route Decision Tree.
Use the Procurement Route Decision Tree.
Choosing the wrong procurement route can result in:
|  | Unnecessary costs to both suppliers and buyers |  | The Explanatory Note published by the European Commission gives some further analysis of what is meant by technical, and legal or financial, complexity.
Restricting the market and stifling innovation
Unnecessarily shutting out SMEs and VCSEs.
|  | Legal challenge |  | Explanatory Note
There is a government commitment to move towards greater use of the Open Procedure and there is currently a presumption against the use of the Competitive Dialogue procedure. If you are considering switching to the Competitive Dialogue procedure, the explanatory note explains the circumstances under which it can be used.
2 | Write procurement strategy | All options need to be considered and assessed, best Value for Money is the fundamental test. |  | *Procurement Route Decision Tree to be added once available*
Explain how the procurement will deliver the business or policy goals.
The Procurement Strategy (and/or the Commercial Strategy where departments make a distinction) needs to answer the following questions as a minimum:
Is a new contract required, or can this procurement use existing contractual arrangements/vehicles e.g. Frameworks, centralised procurement arrangements available through the Crown Commercial Service for use across government?
Are the requirements best delivered through a single or multi supplier contract? Consider whether division into Lots is appropriate. If so, develop the strategy for this. If not, remember you will need to explain the decision not to Lot and record this and the reasons why.
Have considerations for SMEs and VCSEs been made (if the supply market reflects them)?
What is optimum contract duration, size and value (contract value is a key determinant for SME and VCSE engagement) - Could the requirement be delivered by consortia?
What is optimum contract duration, size and value (contract value is a key determinant for SME and VCSE engagement) - Could the requirement be delivered by consortia?
Is there enough market capacity?
Use the output from SOP 2.3 (Complete team skills assurance) to verify and document the availability of capable resources.
Are there sufficient capable resources to manage the procurement? Use the output from SOP 2.3 (Complete team skills assurance) to verify and document the availability of capable resources.
What are the key contractual risks, who should manage them?
Which terms and conditions are required? Use standard terms and conditions of contract where these exist. For example the CCS Model Services Contract. Consider whether you need legal support in preparing the contracts.
In addition the strategy will include:
Your defined outcomes, how these will be reflected in/achieved through the contract.
The evaluation strategy including selection criteria and methodology; award criteria (including weightings) and methodology (see step 3 below).
|  | The contract and relationship management strategy. |  | https://www.gov.uk/government/publications/procurement-policy-note-0415-taking-account-of-suppliers-past-performance
3 | Write evaluation strategy and criteria | Write the evaluation strategy; this gives an overall structure for evaluation, including the high level criteria and weightings, the key evaluation points in the process, the criteria & methodology. The design of the evaluation strategy may require input from senior stakeholders from the business. Ensure that all business stakeholders have been consulted in formulating the evaluation criteria. Take care to ensure that the evaluation strategy reflects the outcome requirements as informed through pre procurement market engagement and as reflected in the expected benefits set out in the business case. Consider the time and resource required for evaluation and ensure that the strategy is planned to take account of these needs; consider using evaluation panels and how e-procurement systems can be used to save time and effort. Check that allocated resources remain committed and available. If the total anticipated value of the intended contract is anticipated to exceed £20 million (excluding VAT) you must include the provisions of PPN Action Note 04/15 - Taking Account of Bidders' Past Performance- in your evaluation strategy.
4 | Obtain approval | Schedule time in diaries early to ensure no delays are added waiting for senior stakeholders to become available with time to review the procurement strategy.
3.1 Write procurement strategy and get approval

## #3.2
Date | 2011-06-14
Version | 1
Procedure | Open
Stage | 3
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Update business case (status is changed from strategic outline to outline business case) | Reflect additional data on cost, benefit, risk, resulting from supplier discussions and market analysis work. |  | If appropriate use HMT Green Book Templates:
|  | Checklist: |  | Green Book Templates
Is the business need still valid and confirmed?
Cost options on a Net Present Value (NPV) basis.
Will the proposed solution meet the needs of key stakeholders and contribute to your organisation’s overall objectives?
Are the risks, costs and benefits listed for each of the options?
For major service contracts, revisit and update your business case as further information on costs and risks becomes available during the development of your requirements.
If appropriate, have energy efficiency and responsible disposal costs been considered in your options appraisal?
3.2 Update business case (SOBC to OBC)

## #3.3
Date | 2015-06-24
Version | 7.1
Procedure | Open
Stage | 3
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Create bidders pack including the invitation to tender (ITT) | All the information that is necessary for the bidders to respond to the OJEU notice including your ITT needs to be compiled into the bidders pack.
Key components include:
Criteria for mandatory & discretionary exclusion (under Regulation 57 in the Public Contract Regulations 2015)
|  | Specification (output/outcome based) |  | Outcome based specification - SME PPN
|  | Terms & Conditions Timescales / Project Plan Evaluation strategy & criteria Scoring methodology & weighting Compliance Instructions (including a clear statement of what will lead to a tender being rejected, e.g. Failure to meet mandatory requirements) |  | Procurement Pledge
|  | For contracts likely to exceed £20 million in value, you must specify in the ITT and OJEU Notice the minimum standards relating to past performance. |  | https://www.gov.uk/government/publications/procurement-policy-note-0415-taking-account-of-suppliers-past-performance
|  | For all contracts you must include in the procurement documentation the requirement for information supplied to the Authority as part of the bidding process to be shared across government; see PPN 01/14 for drafting |  | PPN 01/14 Information Sharing Within Government
|  | For contracts likely to exceed £5 million in value you must include the questions on tax compliance in the ITT as specified by PPN 03/14 |  | PPN 03/14 Promoting Tax Compliance
|  | Departments must comply with Government Buying Standards when procuring the following types of goods and services: Buildings Contruction projects Cleaning products and service Electrical goods Food and catering services Furniture Horticulture & park services Office ICT equipment Paper & paper products Textiles Transport Water & Wood using products |  | Government Buying Standards
|  | Departments are required to comply with the Common Minimum Standards (CMS) for the procurement of built environments in the public sector (unless it can be demonstrated that one or more of them fall outside of the set criteria). |  | Common minimum standards for construction
|  | Departments are required to follow measures set out in Government's Construction Strategy when procuring construction across all categories. |  | Government Construction Strategy
|  | Departments are required to comply with Government's ICT Strategy when procuring ICT goods and services. This includes complying with the following prinicples that arise from the ICT Strategy: Compliance with the Green ICT Strategy Compliance with the Open Source policy - where approrpiate departmens should procure open source solutions; When specifying ICT requirements departments should use open standards where available and appropriate; Procurements should align to apprpriate End User Device standards to enable users to access their applications; Departments should comly with Reference Architecture; Departments should comply with the Public Service Network (PSN) mandate. |  | Government ICT Strategy Resources
|  | When developing your terms and conditions, ensure that current policy is considered such as the policy on Prompt Payment. For construction, 5 working days has been extended down to tier 3 (sub-contractors). |  | PPN requirement to include 30 day payment clause
Construction - MCO speech
Tips for evaluation strategy:
Don’t test for information that is not directly relevant or useful
Keep the financial assessment as simple as possible and directly relevant to the purpose of your requirements
Explain how selection decisions will be made
2 | Check evaluation panel requirements | Refer beck to Team Skills and Resource Plans (SOP 2) to ensure that the evaluation panel is sufficiently resourced.
· Identify evaluation panel members - considerany questions that require specific evaluation skills
· Confirm that panel members are available for release
· Confirm that panel members do not have any conflict of interest
Failure to create evaluation panel requirements at this stage can jeopardise the procurement's success.
3.3 Create bidders pack/ITT

## #3.4
Date | 2011-10-19
Version | 3
Procedure | Open
Stage | 3
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Carry out any required internal or external assurance | The OJEU notice must reflect business needs and priorities, it must achieve a realistic balance between a scope that is wide enough to encourage innovation and a statement of business need to which the market can make a meaningful response.
Use OJEU contract notice template via eNotices:
Be clear & concise about your requirements & specify using outcomes where appropriate
Be clear on which parties can use the contract
Your notice should make it clear what outputs or outcomes are required, so that suppliers can understand the requirements, and the skills and capabilities needed to deliver these.
2 | Get legal assurance for OJEU notice | Ensure that there is a balance between clarity of requirements and breadth of scope to avoid being overly prescriptive or overly vague.
The risk of being too vague is that the supplier will not understand what is required and the procurement could be open to future challenge.
The risk of being too prescriptive is that you will limit the scope of what can be legally provided within the procurement potentially stifling innovation.
3 | Get approval to OJEU notice scope and content | Ensure timely approval of OJEU notice. Approval of scope and content is likely to involve Legal, SRO, senior customer/user.
3.4 Write and get approval for OJEU notice

## #3.5
Date | 2014-05-27
Version | 2.1
Procedure | Open
Stage | 3
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Carry out any required internal or external assurance | Plan for and prepare required documentation for internal and external reviews and scrutiny.
Participate in reviews, agree issues to address, plan and action these promptly.
Plan early for planning review and assurance activity.
Failure to complete all required procurement documentation before the OJEU is published will cause delays later on in the process leading to unnecessary costs.
2 | Obtain approval to proceed to OJEU | Schedule time in diaries early to ensure no delays are added waiting for senior stakeholders to become available with time to review the procurement strategy & bidders pack. Consider whether the size and nature of the procurement means that external approvals (e.g. Cabinet office, HM Treasury) will be required.
Cabinet Office spending controls
3.5 Carry out assurance and obtain approval to proceed

## #4.1
Date | 2015-06-23
Version | 4.3
Procedure | Open
Stage | 4
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Publish OJEU notice & bidders pack including ITT | Publish the OJEU notice via Tenders Electronic Daily. |  | PPN Transparency
Publish the bidders pack including your ITT at the same time via web link or access to the relevant e-procurement system. This is a legal requirement.
Contracts Finder on GOV.UK
Publish the details of the web based/electronic Q&A facility, including electronic links where appropriate.
Publish the OJEU on Contracts Finder.
|  | Ensure that you provide unrestricted and full direct access free of charge to the procurement documents from the date of the publication in the Official Journal. |  | http://www.legislation.gov.uk/uksi/2015/102/regulation/53/made
Consider advertising in trade journals, specialist web portals and/or publications etc. These advertisements should only appear once the OJEU notice has been published by the EU Publications Office. Any such advertising is in addition to, and not a substitute for, advertising in OJEU and Contracts Finder.
4.1 Publish OJEU notice and issue ITT

## #5.1
Date | 2015-06-23
Version | 1.2
Procedure | Open
Stage | 5
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Establish an on-line/electronic facility for suppliers to ask questions and for responses to be posted for all suppliers to view | Prepare and configure the organisations e-sourcing system for use by the project team. |  | E-sourcing systems include: (not an exhaustive list)
Bravo solutions
Emptoris
BIP
Upload documents that will be used to support the Q&A facility – e.g. bidders pack along with user instructions to support the Q&A.
See SOP 3.3 for details of Bidders Pack
Test that the system is ready for use.
2 | Notify suppliers that the Q&A facility is available | Send notification to suppliers that the facility is available and request confirmation that they are aware of:
How the system will be used, including wherever possible confirmation that any questions will be circulated on an anonymised basis.
Duration of operation
Hours of operation
Response times to questions asked
3 | Actively manage the facility | Monitor the facility daily and provide answers to the questions posed within stated timescales. Ensure that you provide bidders with any additional information and answers to questions no later than 6 days before the final date for receipt of tenders (See Regulation 53 (6)). Ensure that you have clearly nominated team members with the authority to respond to questions.
http://www.legislation.gov.uk/uksi/2015/102/regulation/53/made
Capture the audit trail for all questions received and responses given, include the log of all Q&As on the system so that it is visible for all suppliers.
Close the facility for new postings at the end of the designated period of operation, which should be no later than 6 days before the final date for receipt of tenders.
5.1 Set up and run an online / electronic Q&A facility

## #5.2
Date | 2011-10-19
Version | 2
Procedure | Open
Stage | 5
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Update project plan | Make sure the project is still on track.
If there are going to be any significant changes to the timescales that will affect suppliers make sure you notify them and re-issue the timetable. Although the project plans are likely to be under continuous ongoing review, this is a timely point at which to carry out assurance.
2 | Revisit resource plan | Check the availability of the evaluation team.
If any team members have left or are no longer able to be part of the evaluation, identify replacements.
Make sure any new team members fully understand the agreed business outcomes.
5.2 Refine project & resource plans

## #5.3
Date | 2011-09-21
Version | 2
Procedure | Open
Stage | 5
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Brief evaluation team members | Set up a meeting or a teleconference for all the evaluation team members.
Distribute the requirement, evaluation strategy and criteria in advance of the meeting.
Brief the team on the following:
How to apply the criteria
Scoring templates or electronic system
Roles and responsibilities
Timescales including deadline for completion of individual evaluation
Date for the consensus / moderation meeting
The importance of not speaking to suppliers during the process
Consider scoring a couple of questions as a group to practice and ensure a joint understanding of the criteria and methodology.
The role of each evaluator should be reiterated and subject matter expertise understood so that the key components of each tender will be evaluated by an individual with appropriate levels of technical or specialist knowledge.
Assign specialist evaluators to focus on specialist questions and avoid assigning an individual to evaluate all responses in a tender.
5.3 Brief evaluation team

## #6.1
Date | 2015-06-23
Version | 4.1
Procedure | Open
Stage | 6
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Receive & sort tenders | Open the tenders after the deadline has passed.
Allocate a unique reference number & create a tender receipt summary. The process for receipt and opening of tenders may in some cases be handled by a separate 'tender board' within the commercial or finance function.
Note: If using an electronic tendering system, this process will be automated and seamless.
2 | Conduct a compliance check | Check that the tenders comply with your instructions, for example, are in the correct format.
Check that there is no key information missing, for example, no questions have been missed out.
If you have given yourself discretion to do so and there are discrepancies, you may check with the supplier and give them an opportunity to correct any errors that do not materially alter the tender.
6.1 Receive & sort tenders and conduct compliance check & clarification

## #6.2
Date | 2015-06-23
Version | 3.3
Procedure | Open
Stage | 6
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Assess the tenders against the selection criteria | Apply the mandatory & discretionary exclusion criteria first in order to identify which tenders will undergo a full assessment by the evaluation team against the evaluation criteria.
This will prevent subject matter experts evaluating tenders unneccessarily.
|  | Regulation 58 (15)to(18) of the Public Contracts Regulations 2015 (technical and professional ability) should be used with care. Regulation 58 is a backward looking test and may act as a barrier to new market entrants. Try to focus on testing current capability by evaluating the value being offered (tendered) by suppliers. You can do this through using award criteria which test how the supplier will use its skills and experience to meet your actual requirements. |  | http://www.legislation.gov.uk/uksi/2015/102/regulation/58/made
2 | Distribute the tenders to the evaluation team | Only distribute tenders that have not been excluded on mandatory &/or discretionary terms.
Remind team members of the deadline for individual evaluations & the date of the consensus/moderation meeting.
Nominate a clear single point of contact for queries on the procedure & completion of score sheets.
3 | Evaluate tenders | Evaluate the tenders using the agreed criteria and scoring methodology.
Evaluate the technical and commercial elements of the tenders separately, with the results of these separate strands brought together at the end to form a consolidated assessment.
Each tender should have a technical score, a commercial score, and an overall consolidated score.
4 | Moderate the evaluation assessments | Convene a moderation/consensus meeting to ensure consistency of marking in the technical and commercial strands and to discuss anomalies and resolve any opposing views amongst the evaluators.
Collect individual scoring sheets in advance and create a summary of scores to enable you to easily see the variations.
Agree and record consensus scores.
Evaluators must include comments with their scores as this is essential for the effective moderation and subsequent debriefing of suppliers.
Identify winning bidder(s) and consolidate outputs of the evaluation to feed into the evaluation report.
5 | Create evaluation report | The evaluation report must contain the scores and all associated comments for all bidders still in the process.
The final recommendation on the winning bidder must be based on the tender that is most economically advantageous based on the published award criteria and evaluation methodology.
6.2 Evaluate tenders

## #6.3
Date | 2011-12-01
Version | 2
Procedure | Open
Stage | 6
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Write the full business case (FBC) | The Full Business Case sets out the recommendation for an affordable solution which continues to optimise VFM, and includes detailed arrangements for the successful delivery of goods and implementation of services from the recommended supplier. |  | Refer to HMT Green Book Templates:
Green Book Templates
The content should build on the earlier Outline Business Case and include the additional commercial and financial information.
Suggested content:
Executive summary
Economic case
Financial case
Strategic case
Commercial case
Management case
Plus details of:
Economic appraisals
Financial appraisals
Benefits register
Risk register
Risk potential assessment (RPA)
Letter of commissioner/ stakeholder support
Strategic business plans
Proposed contract
Contract award notice
6.3 Write full business case

## #7.1
Date | 2011-06-14
Version | 1
Procedure | Open
Stage | 7
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Obtain approval to award | The formal decision to award a contract must be signed off according to the governance arrangements set up for the procurement.
|  | For major projects, involving HMT/Cabinet Office scrutiny, additional assurance is required by the Major Projects Authority. |  | Major Projects Authority
Avoid delays by pre-arranging when senior officials/Ministers will be required to consider proposals to award contract and provide pre-briefing material.
7.1 Obtain approval to award decision

## #7.2
Date | 2015-06-23
Version | 5.1
Procedure | Open
Stage | 7
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Send all bidders the intention to award letter & offer further feedback | Issue the 'intention to award letters' (formally called a Regulation 86 Notice) to the successful and unsuccessful bidders in accordance with Regulation 86(1) Ensure that you send the notice to all bidders at the same time by electronic means; using any other method will affect the duration of the Standstill Period. |  | http://www.legislation.gov.uk/uksi/2015/102/contents/made
|  | Include feedback that explains clearly, in relation to each criterion, why the particular mark was awarded, and where they scored less than successful bidders, the reasons why. |  | Remedies Guidance Part 3
In the letter, offer additional feedback; this may be via telephone or face to face.
Keep a record / audit trail of all feedback.
Quality feedback enables suppliers to understand how they might be successful in the future.
2 | Observe standstill period | As required under Public Contract Regulations, leave at least 10 calendar days between notification of the contract award decision (i.e. sending out the Regulation 86 Notice) and the point when the contract is formally entered into with the winning bidder.
If the standstill period ends on a non working day, then standstill ends at 23:59hrs on the next working day.
Unsuccessful bidders may challenge the procurement decision during the standstill period leading to a delay in confirming the award and signing the contract.
A legal challenge during the standstill period leads to the automatic suspension of the award process until either the court decides to end the suspension or the challenge is dealt with by the court in proceedings.
7.2 Issue notification of standstill period & debrief suppliers

## #7.3
Date | 2011-06-15
Version | 1
Procedure | Open
Stage | 7
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Update full business case (FBC) | Update the FBC with the final contract and OJEU award notice.
7.3 Update full business case

## #8.1
Date | 2015-06-24
Version | 3.3
Procedure | Open
Stage | 8
Process Step | Operation |  | Key Points: Risks Quality Ease | Examples/References
1 | Prepare contract for signature | Compile documentation and confirm correct version control
Get internal legal review/QA
Obtain project board sign off
2 | Sign contract | Contract to be signed by individual with appropriate authority on both sides.
Ensure that a copy of the signed contract is safely stored and can be accessed when needed; use your established data management and storage systems as appropriate.
3 | Publish contract award notice on TED and publish contract on Contracts Finder | Publish contract award notice on TED, ensure you complete the fields required for the purposes of the Cabinet Office 120 day procurement turnaround measurement. |  | https://www.gov.uk/contracts-finder
|  | Redact signed contract and publish on Contracts Finder within 20 days of completion of the standstill period (contract award). Redaction must be undertaken in accordance with the principles set out in "The Transparancy of Suppliers and Government to the Public" published in 2015. |  | https://www.gov.uk/government/publications/transparency-of-suppliers-and-government-to-the-public
8.1 Sign contract