SCHEDULE 6.2

CHANGE CONTROL PROCEDURE

**VERSION CONTROL**

|  |  |  |
| --- | --- | --- |
| **VERSION NUMBER** | **DATE** | **COMMENT** |
| 0.1 | 27 July 2016 | Preliminary draft template version made available for general comment |
| 0.2 | 2 September 2016 | Uplifted draft, following feedback, made available for final comment |
| 0.3 | 25 October 2016 | Uplifted following local body and supplier feedback |
| 1.0 | 16 November 2016 | Baselined Version 1.0 |

**CONTENTS**

1 BACKGROUND 1

2 CHANGE REQUESTS 1

3 CHANGE IMPACT ASSESSMENT 2

4 AUTHORITY'S RIGHT OF APPROVAL 3

5 SUPPLIER'S RIGHT OF REJECTION 4

6 FAST-TRACK CHANGES 5

7 COSTS 5

8 EXECUTION OF CHANGE AUTHORISATIONS 6

9 PROGRAMME RELATED CHANGES 6

APPENDIX – CHANGE FORM 7

**SCHEDULE 6.2 – CHANGE CONTROL PROCEDURE**

1. BACKGROUND
   1. Subject to Clause 39.2, this Schedule 6.2 sets out the procedure for dealing with Contract Changes.
   2. Changes to the Project Plan are not subject to the Change Control Procedure (unless such change would also involve a change to any other aspect of the Contract) but are subject to the provisions of Schedule 4.1 (Implementation) paragraph 5, with each Party responsible for its own costs and expenses incurred in connection with the agreement of such changes to the Project Plan.
2. CHANGE REQUESTS
   1. Subject to the remainder of this paragraph 2.1, either Party may issue a Change Request to the other Party at any time during the Term by completing Part 1 of the Change Form set out in the Appendix. Save where such a requirement would reasonably involve undue delay in progressing the Contract Change concerned, proposed Contract Changes (proposed by either Party) should be subject to reasonable consideration through the governance arrangements provided under Schedule 6.1 (Governance) prior to issue of a Change Request.
   2. If the Supplier issues a Change Request, it shall also provide a Change Impact Assessment (by completing Part 2 of the Change Form set out in the Appendix) to the Authority as soon as reasonably practicable but in any event within five (5) Working Days of the date of issuing the Change Request. The Supplier shall provide such further information and revised versions of each Change Request and/or Change Impact Assessment and within such timescales as the Authority may reasonably require.
   3. Subject to paragraph 2.4, if the Authority issues a Change Request, the Supplier shall provide a corresponding Change Impact Assessment to the Authority within ten (10) Working Days from receipt of the Change Request by the Supplier or such longer period as specified by the Authority within the Change Request. If the Supplier requires any reasonable clarification in relation to a Change Request before it can deliver a Change Impact Assessment, it shall as soon as reasonably practical notify the Authority and the Authority shall respond to the request for clarification as soon as is reasonably practicable (a reasonable corresponding extension of applicable timescales under this Schedule 6.2 shall apply in those circumstances, which as a maximum shall be equivalent to the number of Working Days taken by the Authority to respond to the clarification).
   4. If the Supplier considers (acting reasonably) that a Change Impact Assessment in respect of an Authority issued Change Request would require:
      1. more than five (5) FTE Working Days of Supplier Personnel time to prepare; and/or
      2. a longer period than that provided pursuant to paragraph 2.3,

the Supplier shall (within five (5) Working Days of receipt of the Change Request) propose to the Authority in writing:

* + 1. the reasonable cost for preparing and providing the corresponding Change Impact Assessment; and/or
    2. an extension of time reasonably required for provision of the Change Impact Assessment (which may not exceed an additional fifty (50) Working Days),

together with reasonable supporting explanation and data for the above proposals (in the absence of such supporting explanation and data, the timeframe for response under paragraph 2.3 shall continue to apply). If, subject to any refinement of the Supplier's proposal under paragraph 2.4, the Authority wishes to proceed with that proposal:

* + 1. it shall inform the Supplier in writing;
    2. the Supplier shall provide the Change Impact Assessment within the timescale determined in accordance with this paragraph 2.4;
    3. the Authority shall be liable to pay the reasonable additional cost indicated by the Supplier (being the incremental cost beyond five (5) FTE Working Days of Supplier Personnel time), subject to provision of reasonable supporting evidence of the incurrence of those costs.
  1. The Supplier acknowledges and agrees that, without prejudice to any other right or remedy the Authority may have for failure by the Supplier to comply with the timeframe requirements in this paragraph 2, any failure to provide a Change Impact Assessment to the Authority (consistent with the requirements of paragraph 3) within twenty (20) Working Days from the date of delivery for the Change Impact Assessment determined in accordance with this paragraph 2 shall constitute a material breach by the Supplier.
  2. The following principles also apply to the above processes:
     1. the Authority must act reasonably in the frequency of Change Request submissions, including seeking to avoid iterative submission of a number of separate Change Requests concerning the same subject matter where reasonably practical and taking reasonable account of any Programme Authority Change Requests that may at the time be in the process of being implemented across the Broadband Delivery Programme;
     2. the Supplier shall not be entitled to recover the costs identified in accordance with paragraph 2.4 in the event that the Change Request concerns the deployment of additional or enhanced Network coverage.

1. CHANGE IMPACT ASSESSMENT
   1. Each Change Impact Assessment shall include:
      1. a descriptive summary of the proposed Contract Change;
      2. proposed drafting changes to this Contract necessary to give effect to the Change (including any and all corresponding changes to the Speed and Coverage Template, Implementation Plan, Project Plan, Milestone Payments table and the Project Model), provided that the Supplier shall take into account any proposed drafting changes set out in the Change Request where submitted by the Authority (the Contract Change should reflect these Authority proposals, save to the extent it would be unreasonable to require use of the drafting concerned);
      3. details of the impact of the proposed Contract Change on:
         1. the delivery and receipt of the Deployed Services;
         2. the Supplier Solution;
         3. the Supplier's ability to meet its other obligations under this Contract; and
         4. any other matter requested by the Authority at the time of the assessment, or considered by the Supplier to be relevant;
      4. details of how the proposed Contract Change will ensure compliance with any applicable Change in Law;
      5. a reasonable level of justification and evidence for these Changes and the above noted impact, including sufficient supporting detail to enable Authority assessment. In the case of changes to the Supplier Solution, this must include:
         1. detailed supporting financial information covering any changes to Milestone Payments, Supplier NGA Network Build Investment and any other aspect of the Project Model;
         2. identification of changes in numbers, build classification and/or Speed Categories for End User Premises;

at least equivalent to that which would be provided as part of the M0 process described in Paragraph 8 of Schedule 4.1 (Implementation);

* 1. If the proposed Contract Change has no impact of the kind described in paragraph 3.1.3 the Supplier shall provide a statement of this fact in the Change Impact Assessment.
  2. The Authority shall review each Change Impact Assessment and as soon as reasonably practicable shall respond to the Supplier in accordance with paragraph 4. The Supplier must comply with reasonable requests for further clarification in respect of the Change Impact Assessment if requested by the Authority.

1. AUTHORITY'S RIGHT OF APPROVAL
   1. The Authority shall review each Change Request and/or Change Impact Assessment and as soon as reasonably practicable shall do one of the following:
      1. approve the proposed Contract Change, in which case the Parties shall follow the procedure set out in paragraph 4.2;
      2. reject the Contract Change (providing reasons for the rejection), in which case it shall notify the Supplier of the rejection. The Authority shall not reject any proposed Contract Change to the extent the Contract Change is necessary for the Supplier or the Deployed Services to comply with any Change in Law;
      3. require the Supplier to modify the Change Request and/or Change Impact Assessment in which case the Supplier shall, as soon as practicable, submit a modified proposal for consideration by the Authority which takes the Authority's comments into account. The Authority shall have the approval rights set out in this paragraph 4.1 in respect of each modified Change Request and Change Impact Assessment and any subsequent version required by the Authority.
   2. If the Authority approves a Contract Change pursuant to paragraph 4.1.1 and it has not been rejected by the Supplier in accordance with paragraph 5, it shall notify the Supplier and the Parties shall sign a Change Authorisation (by completing Part 3 of the Change Form set out in the Appendix) within three (3) Working Days. Upon signature by both Parties, a Change Authorisation shall constitute a binding variation to this Contract.
   3. Until such time as a Change Authorisation has been signed by both Parties in accordance with paragraph 4.2, unless the Parties (acting reasonably having regard to the nature of the proposed Contract Change) agree otherwise in writing and subject to paragraph 5.3, the Supplier shall continue to supply the Deployed Services in accordance with the existing terms of this Contract as if the proposed Contract Change did not apply.

1. SUPPLIER'S RIGHT OF REJECTION
   1. The Supplier shall be entitled to reject a proposed Contract Change only if, following a Change Impact Assessment, the Supplier reasonably believes that the proposed Contract Change would:
      1. require the Deployed Services to be performed in a way that infringes any Law; and/or
      2. subject to paragraph 5.2, materially and adversely impacts:
         1. the Supplier's ability to fully deliver the Deployed Services; and/or
         2. the commercial and/or financial risk profile underpinning the Deployed Services,

provided the Supplier can demonstrate and evidence in writing to the reasonable satisfaction of the Authority that such impact cannot be addressed by the Parties as part of the relevant Contract Change,

in which case the Supplier shall provide written notice to the Authority which sets out the Supplier's rationale and supporting information for its proposed rejection.

* 1. Paragraph 5.1.2 shall not permit the Supplier to reject any proposed Contract Change to the extent the Contract Change is necessary for the Authority to comply with any change in Law (recognising that in respect of Specific Changes in Law, reasonable commercial terms shall be agreed by the Parties in order to account for such change).
  2. The Supplier shall not, in any event and without limitation to paragraph 5.2, be entitled to reject any Authority proposed Contract Change directing de-scoping of any part of the Network, provided that the de-scoping arises in respect of another operator’s verified (such verification taking place between the Authority and Programme Authority, applying a reasonably comparable standard of verification to that applied when classifying the original ITT intervention area applicable for the Project, with confirmation being provided to the Supplier by the Authority that this verification process has been conducted) coverage plans and/or to ensure compliance with Law.
  3. If the circumstances of de-scoping described in paragraph 5.3 above apply, the Parties shall work together to ensure the Deployed Services, Speed and Coverage Template, Milestone Payments table, Project Model and other relevant Contract components are correspondingly amended to reasonably reflect the de-scoping (including ensuring the Supplier is compensated for any wasted or stranded costs of the Supplier which would result from the de-scoping, on a basis consistent with the principles set out in paragraph 5.6 below). Where an Authority Change Request directs a de-scope of part of the Network, if required by the Authority the Supplier shall as soon as reasonably practical (in any event within five (5) Working Days or such longer period (as agreed in writing between the Parties, such consent not to be unreasonably withheld) save solely in respect of those close-down activities necessary to be performed for health and safety purposes, to physically secure and protect the Network sub-components concerned or otherwise to ensure compliance with Law), cease any work in progress and not commence any further Network Deployment in respect of the corresponding part of the Network being de-scoped.
  4. It is acknowledged that:
     1. a requirement to cease work pursuant to paragraphs 5.3 and 5.4 represents a Relief Event but solely in respect of that part of the Deployed Services which cease due to this direction and to the extent of any resulting interference such de-scoping might have on other Network build activities;
     2. the de-scoped part of the Network shall be removed from the scope of the corresponding Milestone(s) and the Supplier shall be entitled to claim Achievement of the remaining scope of the Milestone(s) provided and once the remaining scope and associated requirements of the Milestone(s) have been satisfied in accordance with the terms of this Agreement;
     3. the Authority shall reasonably consult with the Supplier to consider whether the funding represented by any reduction in Milestone Payments due to the de-scoping could be used to otherwise extend coverage under this Agreement. Any such extension of coverage would be subject to the Parties reaching agreement in accordance with the Change Control Procedure and subject to the Authority obtaining the prior approval of the Programme Authority to proceed (and that, inter alia, this will involve consideration of compliance with the requirements of the Commission Decision).
  5. Where a de-scoping is required pursuant to the above provisions of this paragraph 5, as part of the corresponding Contract Change the following cost principles shall be applied regarding the Supplier recovering wasted or stranded costs arising from that de-scoping:
     1. As a result of another operator’s coverage plans (save where also falling within paragraph 5.6.2 - the Authority shall pay the Supplier's wasted or stranded costs;
     2. To ensure compliance with Law – responsibility for wasted or stranded costs shall be allocated between the Parties on an equivalent basis to cost responsibility for Changes in Law as provided under Clause 13.

The Parties shall specify within the Contract Change the overall maximum amount of wasted or stranded costs payable by the Authority. The Supplier may only claim such wasted or stranded costs:

* + 1. provided the costs were incurred within the parameters of paragraph 5.4;
    2. where they are evidenced on the same basis as Milestone Payment Claims; and
    3. provided the Supplier has used its reasonable endeavours to mitigate such costs.

1. FAST-TRACK CHANGES

The Parties acknowledge that in order to ensure operational efficiency there may be circumstances where it is desirable to expedite the processes set out in this Schedule 6.2. If the Parties agree in writing that such circumstances apply in relation to a proposed Contract Change then the Parties shall agree an accelerated timetable for the steps described in this Schedule 6.2 in order to affect the Contract Change.

1. COSTS
   1. Subject to:
      1. those costs for preparation of a Change Impact Assessment payable by the Authority pursuant to paragraph 2.4 (which is itself subject to paragraph 2.6.2); and
      2. paragraph 7.2,

each Party shall be responsible for its own costs and expenses incurred in compliance with this Schedule 6.2 including the preparation and assessment of all Change Forms.

* 1. Without prejudice to any right a Party may have to recover costs incurred in respect of an Indemnified Claim, a Party's reasonable costs incurred in respect of any use of this Change Control Procedure as a result of any Default by the other Party shall be paid for by the Party in Default.

1. **EXECUTION OF CHANGE AUTHORISATIONS**

The Parties acknowledge that Change Authorisations may be signed in any number of counterparts. Such signature shall be effective when the signing Party delivers its signed Change Authorisation to the other Party by email in scanned PDF format or by hand, post or fax.

1. **PROGRAMME RELATED CHANGES**

From time to time the Authority may raise a Programme Level Change Request at the request of the Programme Authority. The Parties shall manage the Programme Level Change Request through the process set out above.

**APPENDIX – CHANGE FORM**

**PART 1: CHANGE REQUEST**

|  |  |
| --- | --- |
| **CHANGE REQUEST** | |
| **CONTRACT NO:** | *[Please state]* |
| **CHANGE NO:** | *[Please state]* |
| **DESCRIPTION OF THE PROPOSED CHANGE:**  [*Please state*] | |
| **FAST-TRACK PROPOSED IN RELATION TO CHANGE?** | *[Yes/No]* |
| **PRELIMINARY CHANGE ASSESSMENT TO BE PROVIDED?** | *[Yes/No]* |
| **PROPOSED DATE FOR CHANGE:** | *[Please state]* |
| **SUBMITTED TO:** | *[Please state]* |
| **REQUESTING PARTY:**  **SIGNED:**  **NAME:**  **DATE:** | *[Please state]* |
|  |
| *[Please state]* |
| *[Please state]* |

**PART 2: CHANGE IMPACT ASSESSMENT**

|  |  |
| --- | --- |
| **CHANGE IMPACT ASSESSMENT** | |
| **CONTRACT NO:** | *[Please state]* |
| **CHANGE NO:** | *[Please state]* |
| **SUPPLIER'S CHANGE IMPACT ASSESSMENT:**  *[Please refer to paragraphs 2 and 3 of Schedule 6.2 (Change Control Procedure)]* | |
| **SUBMITTED TO:** | *[Please state]* |
| **SUPPLIER:**  **SIGNED:**  **NAME:**  **DATE:** | *[Please state]* |
|  |
| *[Please state]* |
| *[Please state]* |

**PART 3: CHANGE AUTHORISATION**

|  |  |
| --- | --- |
| **CHANGE AUTHORISATION** | |
| **CONTRACT NO:** | *[Please state]* |
| **CHANGE NO:** | *[Please state]* |
| **ON BEHALF OF THE SUPPLIER**  **SIGNED:**  **NAME:**  **DATE:** |  |
| *[Please state]* |
| *[Please state]* |
| **ON BEHALF OF THE AUTHORITY**  **SIGNED:**  **NAME:**  **DATE:** |  |
| *[Please state]* |
| *[Please state]* |