SCHEDULE 4.3

RELIEF EVENTS

**VERSION CONTROL**

|  |  |  |
| --- | --- | --- |
| **VERSION NUMBER** | **DATE** | **COMMENT** |
| 0.1 | 27 July 2016 | Preliminary draft template version made available for general comment |
| 0.2 | 2 September 2016 | Uplifted draft, following feedback, made available for final comment |
| 0.3 | 25 October 2016 plus 11 November 2016 minor edits | Uplifted following local body and supplier feedback |
| 1.0 | 16 November 2016 | Baselined Version 1.0 |

**CONTENTS**

1 BACKGROUND 1

2 RELIEF EVENTS 1

3 QUALIFYING PERIOD 1

APPENDIX – RELIEF EVENTS 2

**SCHEDULE 4.3 – RELIEF EVENTS**

1. BACKGROUND

This Schedule 4.3 sets out details of the Relief Events and should be read in conjunction with Clause 19.

1. **RELIEF EVENTS**
   1. Subject to Clause 19, an event shall qualify as being a Relief Event only where and to the extent it both:
      1. concerns an Authority activity or responsibility relating to this Contract upon which the Supplier is dependent in order to provide the Deployed Services or which otherwise directly impacts the Deployed Services; and
      2. is described in the Appendix to this Schedule 4.3 or is otherwise expressly identified as a Relief Event in the Contract (excluding any Relief Event only identified within the Supplier Solution).

1. **QUALIFYING PERIOD**

The Supplier shall not be eligible to apply for relief in accordance with Clause 19 if and to the extent the relevant Relief Event occurs outside of the relevant qualifying period set out in the table in the Appendix to this Schedule 4.3.

**APPENDIX – RELIEF EVENTS**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **ID** | **RELIEF EVENT DESCRIPTION** | **QUALIFYING PERIOD (e.g. duration of Term, Network Deployment phase only)** | **EXPECTED IMPACT OF RELIEF EVENT** | **EXPECTED SUPPLIER MITIGATION / WORKAROUND (IF APPLICABLE)** |
| 1 | Any legal challenge, action and/or formal investigation relating to the Network Deployment which is commenced and/or upheld prior to the completion of the Network Deployment and which is brought:  (a) before the EU General Court or a national court or by the European Commission under the EU State aid rules including against the Authority; or  (b) against the Authority for breach of statutory duty including the duty owed under Regulation 89 of the Public Contracts Regulations 2015,  which materially affects either the delivery of the project and/or the viability of the public funds (in whole or part as appropriate) used to help pay for delivery of the project. | Network Deployment | Suspension of Network Deployment implementation and provision of related Deployed Services (in whole or part as appropriate) by the Supplier for the Coverage Area or the part of the Coverage Area materially affected by such Relief Event. 'Material affected' means any risk arising of impact on the validity of payments for deploying the whole or part of the Network or undertaking other Deployed Services. | The Parties shall within three Working Days of becoming aware of such matter convene a Governance Board meeting to discuss:   1. the potential materiality of such legal challenge, action and/or investigation; 2. the potential impact of the same on the Contract; and 3. likely relief options to be applied (if any are available),   following which a Relief Notice (if still required) will be provided by the Supplier to the Authority as soon as reasonably practicable (in accordance with the format set out in Clause 19.2). The Parties will then, for the avoidance of doubt, apply the process set out in Clause 19.3 to Clause 19.7 of the Contract. |
| 2 | Where:  (a) a Local Planning Authority or Local Highways Authority within the Coverage Area fails to provide any relevant consent, decision or response within the statutory or published time period; and  (b) the Authority has (and had at the relevant time) the ability to manage and control the processing of such consent, decision or response within such time period,  provided that the Supplier ensured that the application was submitted in a timely fashion, was of an accurate and high standard and was presented in such a way as to allow prompt determination. | Term | Change in timescales  Reduction in coverage  Reduction in broadband speed  Increased cost | The actions set out in Clause 19.3 of the Contract. Further steps to mitigate in accordance with Good Industry Practice. |
| 3 | Strike by Authority and/or Other Beneficiary personnel, which directly delays surveying, planning, or deployment. | Term | Change to timescales  Increased cost | The actions set out in Clause 19.3 of the Contract. Further steps to mitigate in accordance with Good Industry Practice. |
| 4 | Without prejudice to the operation of Clause 5, any requirement for permits, consents or notices from the Authority (or anyone acting on the Authority’s behalf) where details were provided as part of the ITT but have subsequently changed from what was provided including:  (a) any classification of works as major works under the Construction (Design and Management) Regulations 2015; and/or  (b) any classification as traffic sensitive, Road Category 0-2, or major works pursuant to any permit scheme under the Traffic Management Act 2004,  provided that the Supplier has taken reasonable steps to ensure that applications under the relevant permit, consent and/or notice applications (as applicable) are submitted in a timely fashion, are of an accurate and high standard, and presented in such a way which will allow prompt determination of the relevant application/request. | Term | Change in timescales  Reduction in coverage  Reduction in Speed  Increased cost | The actions set out in Clause 19.3 of the Contract. Further steps to mitigate in accordance with Good Industry Practice. |
| 5 | Authority delays and/or refusals in granting wayleaves on reasonable terms (being consistent with those terms the Authority otherwise sets for commercial deployments) where the wayleaves are required from the Authority, provided that the Supplier has taken reasonable steps to ensure that requests for wayleaves are submitted in a timely fashion, are of an accurate and high standard, and presented in such a way which will allow prompt determination of the relevant request. | Term | Change in timescales  Reduction in coverage  Reduction in Speed  Increased cost | The actions set out in Clause 19.3 of the Contract. Further steps to mitigate in accordance with Good Industry Practice. |
| 6 | Acts or omissions of third parties directly impacting delivery of the project, where these are: (i) under the direct control of the Authority; and (ii) not under the control of the Supplier, save where such acts or omissions reflect steps being taken by the Authority to comply with Law and/or its duties as a public body. | Term | Increased cost  Reduced coverage  Reduced broadband speed  Change to timescales | The actions set out in Clause 19.3 of the Contract. Further steps to mitigate in accordance with Good Industry Practice. |