## Anti Corruption
DFID's Approach to Anti Corruption OFF-TRACK
Recommendation | Accept/Partially Accept /Reject | Action | Target dates | Autumn 2014 update
Completed/ On-track/ Off-track
1. In any country assessed as having a high risk of corruption, DFID should develop an explicit anti-corruption strategy, setting out an integrated programme of activities and dialogue processes. | Accept | 1.New strategy guidelines are under development by the Anti-corruption policy team, in collaboration with the Risk and Control Unit and Internal Audit, drawing on existing good practice from country offices. These will be tested and piloted in a selection of country programmes, ready for dissemination by April 2012. | 2012-04-01 | Completed
|  | 2. Central scrutiny team established to review all strategy documents to ensure that they meet minimum requirements and provide a consistent assessment of corruption across the programme. | 2012-02-01 | Completed
|  | 3. Anti-corruption strategies will be developed for the first batch of countries by July 2012 with coverage of all eligible DFID country programmes by July 2013. | 2013-01-01 | Completed
2. DFID should review the structure and nature of its UK counter-fraud and anti-corruption resources, to develop a more co-ordinated approach to risk assessment, risk management, anti-corruption programming and fraud response. | Accept | 4.Identification of a Board level champion to lead and drive work in this area and support the work of the Fraud Risk Management Group, which will expand its role to co-ordinate all work on fraud and anti- corruption. | 2011-12-01 | Completed
|  | 5. Deputy-Director led review (reporting to the Management Board) of the nature and structure of DFID’s existing counter fraud and anti-corruption work. This will encompass functions, capacity and capability to take this agenda forward in line with ICAI recommendations. The review will identify;i) How to improve cohesion and co-ordination across the Department. ii)Whether and where additional resources are required iii)How increased capability can be disseminated across the organisation.iv) How to improve lesson learning and communication. | 2012-04-01 | Completed
|  | 6. Implementation of the Treasury sponsored ‘Managing the Risk of Financial Loss’ programme, commencing with eight key areas: Multilateral payments; Bilateral Aid; grants to Civil Society Organisations; Humanitarian/Emergency aid; Loans; procurement Payroll and Travel and subsistence and overseas programmes. | 2012-03-01 | Completed
3. DFID should develop more articulated processes for managing the corruption risks associated with particular aid types and invest more resource in due diligence and on- the-ground monitoring of delivery partners | Accept | 7. Due diligence products will be developed to explicitly cover engagement at the country level with multilateral and other partners. This will complement the work already undertaken on Fiduciary Risk assessments (which cover Financial Aid) and on UK based Civil Society. | 2012-12-01 | Completed
|  | 8. This extended suite of due diligence products will enable DFID to assess the financial competence and the accounting and reporting capabilities of different organisations in advance of funding commitments. | 2012-12-01 | Completed
4. While continuing to invest in the legal and institutional framework for fighting corruption, DFID should focus on supporting more robust law enforcement activity to build transparency and accountability. This should include innovative forms of beneficiary monitoring and community mobilisation. | Accept | 9. The anti-corruption strategies will explicitly consider additional actions covering both law enforcement and beneficiary monitoring and community mobilisation. | July 2012 | Completed
|  | 10. DFID will work more systematically across Whitehall to ensure that country programmes can access key technical resources from across Government. The feasibility of building on existing cross Government arrangements is being explored. This will systematise and deepen existing working relationships with relevant UK agencies, such as the National Audit Office, Serious Organised Crime Agency, Serious Fraud Office, Crown Prosecution Service, and the Metropolitan Police & City of London Police. This will enable country programmes and partner countries to access relevant technical skills where appropriate. | 2013-05-01 | Off Track. Process on-going. Target date revised to May 2015. In the last report, DFID was exploring whether the iFUSE programme (aimed at improving the conditions for economic development in country) would be a suitable vehicle for accessing the expertise of other government departments on corruption. This proved not to be the case as OGDs had no spare capacity to provide relevant technical resources to DFID country programmes. However, since the last report, HMG has developed the National Action Plan (NAP) on Corruption as part of the Open Government Partnership. The NAP facilitates more systematic working across HMG on anti-corruption. Under the NAP, DFID and the FCO are developing a ‘Toolkit’ for country offices and posts to enable more co-ordinated working in country; and better access to technical expertise. In addition, existing framework agreements with the Metropolitan Police, City of London Police and Crown. Prosecution Service (CPS) and the National Crime Agency to tackle international corruption affecting partner countries are in place.
|  | 11. Using established information platforms (new Empowerment and Accountability resource network and the existing anti-corruption resource centre), we will garner and consolidate best practice on community level beneficiary monitoring, including undertaking new research and evidence gathering, and making this available to country offices. | 2012-04-01 | Completed
5. DFID should invest more in intelligence collation and analysis of corruption risks in particular sectors and countries, to inform a more strategic approach to fighting corruption. | Accept | 12. Pilot Strategic Intelligence Threat Assessments: at country level to inform our programmes of major threats. This will contribute to our country level corruption assessments. Our learning from this pilot will inform how useful this approach is; resources needed; and how to institutionalise the process with our partners. | 2012-05-01 | Completed
|  | 13. Pilot a name verification system: to assess whether our partners have recorded links with organised crime or have outstanding fraud related issues at country programme level through using ‘Know Your Partner’ approaches. | 2012-06-01 | Completed
|  | 14. Development of Information Sharing Agreements with international development partners and key UK organisations (e.g. Charities Commission) to share counter fraud related case material and intelligence on sectors/targets. | 2012-02-01 | Completed
|  | 15. Creating intelligence/ learning from our fraud cases/control failures to inform our risk control systems: we are currently undertaking a lesson learning process exercise on all our closed cases covering the last three years and introducing a new information management system for case management and intelligence appraisal/analysis. | 2012-05-01 | Completed

## Climate Change Bangladesh
DFID's Climate Change Programme in Bangladesh COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed/ On-track / Off-track
1. DFID should ensure that organisations implementing UK aid are selected competitively and managed according to clear performance targets, set out in a service level agreement. | Accept | 1. We will review our agreements with partners on the Climate Change Programme in Bangladesh. Where performance targets are not sufficiently focused, we will sharpen them to ensure accountability for delivery is fully measurable. We will also set in place systems and appropriate internal staffing structures to track administrative costs and overheads more closely. | 2012-12-01 | Completed
|  | 2. At Headquarters level, discussions will continue on improving World Bank Trust Funds as a mechanism for country delivery, to increase effectiveness, accountability and value for money. | On-going | Completed
|  | 3. We will further strengthen staff skills for effective management of programme partners and programme delivery. | 2012-12-01 | Completed
2. DFID should ensure that all UK resources that support Bangladesh’s response to climate change are managed in a co-ordinated and integrated manner | Accept | 4. DFID will actively use its role as co-chair of the Local Consultative Group on Environment and Climate Change to ensure better integration across all key Climate Change and environment programmes in Bangladesh. | On -going | Completed
|  | 5. DFID Bangladesh will proactively facilitate improved programmatic integration between the Comprehensive Disaster Management Programme (CDMP) managed by UNDP, and the Bangladesh Climate Change Resilience Fund (BCCRF) administrated by the World Bank. We will also ensure better links with centrally funded initiatives through the World Bank (i.e. Pilot Programme for Climate Resilience) and UN (i.e. Global Environment Facility). | 2012-12-01 | Completed
|  | 6.DFID Bangladesh will increase its engagement with donor partners particularly around the annual review process to encourage better integration of all programmes. As new interventions are planned by DFID and others, we will encourage consolidation of existing funding mechanisms as a first choice. | On -going | Completed
|  | 7. DFID Bangladesh is reviewing its staffing and will increase staff to manage the Climate Change portfolio. As well as improving accountability of partners on delivery schedule and quality, this will also improve the focus on integration of programmes. | 2012-08-01 | Completed
3. DFID should support monitoring by local and international civil society organisations of the activities and achievements of the Bangladesh Climate Change Strategy and Action Plan. | Accept | 8. DFID endorses this recommendation but recognises that this work will be outside the remit of any single climate change supported programme (e.g. the BCCRF). The achievements of the Bangladesh Strategy and Action Plan will be an accumulation of efforts including GoB’s own Climate Change Trust Fund, the Pilot Programme for Climate Resilience, CDMP and many other projects and programmes. However, we will raise the issue within the GoB/Donor/Civil Society Coordination body – the Local Consultative Group on Environment and Climate Change (LCG). Through the LCG we will seek opportunities to establish the recommended monitoring body. Possible funding could be allocated within the next commitment of Climate Change funding – the full shape of the future programme will be designed during 2012. | 2012-06-01 | Completed
|  | 9.DFID will negotiate with the Government of Bangladesh and donors co-funding the BCCRF programme and agree an action plan for improved monitoring, including a transparent mechanism for reporting progress of fund allocation and implementation. | 2012-07-01 | Completed
4. DFID in Bangladesh should use the programme to fund research and activities to address migration caused by climate change over the next 20-30 years. It should support building capacity to deal with such effects of climate change. | Partially Accept | 10. DFID will monitor closely the outputs from both CDKN (Climate and Development Knowledge Network) and BCCRF studies to ensure application of results in current and future decision making processes. | On -going | Completed
|  | 11. DFID will engage with the UN International Organisation on Migration (IOM) to better understand migration issues in Bangladesh and see where programmatic work can be strengthened | 2012-04-01 | Completed
5. DFID should plan more explicitly for what will happen at the end of the programme. In particular, more effort is needed to build capacity within government to enable activities and administration to be led by local, not international, institutions. | Accept | 12. DFID will review the work plans of both key programmes (BCCRF and CDMP) to ensure work plans clearly include capacity building within the relevant Government of Bangladesh (GoB) ministries to take forward climate change activities, and exit strategies. This includes not only the host ministries (Ministry of Environment and Forests for BCCRF and Ministry of Food and Disaster Management for CDMP) but also other key line ministries. | 2012-07-01 | Completed
|  | 13.For BCCRF in particular, clear criteria for national capacity to manage the funds will be developed during 2012. This will enable GoB and development partners to track progress in developing these capacities to enable a full handover of management of the BCCRF to GoB. | 2012-07-01 | Completed

## Zimbabwe Health Sector
DFID's Support to the Health Sector in Zimbabwe COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed / On-track /Off-track
1. As noted by the International Development Committee, DFID should support the Zimbabwe Ministry of Health to strengthen its capability to manage the health system | Accept | 1. DFID will work closely with other funding partners and with the Ministry of Health and Child Welfare (MOHCW) to ensure the newly launched Health Transition fund (HTF) strengthens the capability of the Ministry | 2013-03-01 | Completed
|  | 2. DFID will consider with others the options for providing further technical assistance within HTF to strengthen the capability of the MOHCW. | 2013-06-01 | Completed
2. DFID should plan to address the risk of falling value for money if funding is scaled up further. This should include identifying the major value for money risks and specifying how they will be managed and monitored. | Accept | 3. DFID will produce a detailed Value for Money Strategy which will enable it to effectively prevent falling value for money in any of its projects. | 2012-04-01 | Completed
|  | 4. Value for money will include agreeing measures to mitigate the risks of corruption taking into account those to be agreed by DFID in response to the ICAI review of DFID’s approach to Anti-corruption. | 2012-06-01 | Completed
3. DFID should continue its effort to promote the removal of user fees for pregnant women and children under five and ensure that this is a core objective in future support to maternal health. | Accept | 5. DFID officials will seek ministerial approval for financial support to the Implementation of the Health Transition Fund (HTF). | 2012-03-01 | Completed
|  | 6. DFID will work with partners during implementation of the Health Transition Fund to continue to press for the removal of user fees as soon as possible | On-going | Completed
4. DFID should ensure more comprehensive reporting across the delivery chains, with clearer linking of funds provided with performance delivered | Accept | 7. DFID will continue to support efforts to monitor and track user fee charges through the Vital Medicines and Health Survey (VMAHS) and will also monitor this through accountability initiatives currently being designed as part of DFID’s Operational Plan for Zimbabwe. | 2013-09-01 | Completed
|  | 8. DFID Zimbabwe’s new Value for money Strategy will ensure a more consistent and systematic approach to collecting data on our projects which will strengthen monitoring of results delivered against funding provided. | 2012-04-01 | Completed
|  | 9.The focus of the Annual Review and Project Completion templates on Value for money will help support this process. | Jan 2012 onwards | Completed
5. DFID should take the lead in the donor community to agree a common definition of administrative costs and require implementing partners to report administrative costs on that basis. | Accept | 10. DFID Zimbabwe will work with other bilateral agencies in Zimbabwe to seek to agree a common definition of administration costs and identify a suitable mechanism for regular reporting. | 2013-03-01 | Completed

## World Bank Engagement
The Effectiveness of DFID's Engagement with the World Bank COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed / On-Track/ Off-Track
1. DFID should improve its oversight of World Bank trust funds it is financing and develop a corporate strategy for allocating resources to trust in line with UK government aid objectives within 12 months | Accept | 1.DFID Management Board signs off on the Corporate Strategy and Implementation Plan for Trust Funds to deliver: i)greater policy and donor coherence ii) consolidation and rationalisation iii)consistant and high quality monitoring and evaluation iv)stronger focus on VFM | 2012-11-01 | Completed
|  | 2. First report to DFID Top Management on progress by DFID in implementing the Corporate Strategy and Implementation Plan. | 2012-09-01 | Completed
2. DFID should work with the World Bank during the remainder of IDA16 and through IDA17 to improve service delivery cost-effectively in fragile and conflict-affected states, including through further decentralisation of staff. | Accept | 3. Exchange best practice with WB on innovative and cost-effective approaches to delivery in difficult contexts (having identified approach and priority areas by September 2012). | 2013-03-01 | Completed
3. DFID should review the principal factors influencing the success of IDA projects. It should then assess how to extend the measures and increase the stretch in targets in the IDA Results Measurements System (RMS). DFID should use this work to improve performance and value for money through the IDA17 replenishment negotiations | Accept | 4. DFID to draw on existing Bank material, particularly the Independent Evaluation Group’s (IEG) annual report, to identify the ‘influencing factors’ driving project performance and improving value for money. DFID to then use this as the basis for an assessment of the IDA16 Results Measurement System, establishing how stretching the existing targets are and whether there are any gaps in the Results Measurement System. | 2012-07-01 | Completed
|  | 5. DFID will share this assessment with other donors in advance of the IDA16 Mid Term Review | 2012-10-01 | Completed

## Afghanistan
DFID Programme Controls and Assurance in Afghanistan COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed / On-track / Off-Track
1. DFID should make explicit in its funding decisions how it is assessing and taking into account the risk of leakage and balancing that risk against the benefits the programmes are designed to deliver. | Accept | 1. A DFID Task Team will visit Kabul by end April to develop an Action Plan to further reduce the risk of leakage or fraud. DFIDA is already considering the use of third party verification and continuous audit. Specific responsibilities and resourcing needs will subsequently need to be agreed, including with DFID central departments. | 2012-06-01 | Completed
|  | 2. DFIDA will develop a new portfolio management tool to monitor and manage risks and results; and add a risk on partner financial systems to its existing risk register. | 2012-06-01 | Completed
|  | 3.DFIDA will undertake an annual scenario planning exercise to test strategy and enhance portfolio risk management. | 2012-09-01 | Completed
|  | 4. DFID’s Finance Division will develop guidance to assist spending departments in their assessment and management of fraud. This will guide new due diligence assessments of all partner organisations. DFIDA will implement this guidance and take a more comprehensive approach to risk analysis. | 2012-09-01 | Completed
|  | 5. DFIDA will use the findings from its on-going programme-wide Fiduciary Risk Assessment to identify additional actions to further address risk in new project business cases | 2012-08-01 | Completed
|  | 6. DFIDA will develop an Anti-Corruption Strategy, building on its existing work and central guidance. | 2012-09-01 | Completed
2. DFID needs to deploy people with more financial and procurement skills to improve its financial grip and reduce risk. It should focus its financial resources on improving its understanding and reporting of cost throughout the delivery chain. | Accept | 7. The new Finance Manager and Commercial Adviser posts will be filled as soon as possible. The Action Plan (recommendation 1, action 1) is likely to have additional staffing implications which DFID will take forward. | 2012-09-01 | Completed
3. DFID should strengthen its managing agent agreements by specifying the levels of controls and assurance that it expects to be in place and monitoring whether or not these standards are met. | Accept | 8. The Task Team (recommendation 1, action 1) will assess how managing agent agreements should be further strengthened. Depending on the outcome of the Action Plan, DFID will review managing agent agreements (multilateral, government, NGO and private sector) for all delivery partners | 2013-09-01 | Completed
4. DFID should ensure that its office in Afghanistan implements outstanding NAO and PAC recommendations regarding fraud and corruption. | Partially Accept | 9. On quantifying leakage DFID's Finance Division will develop guidance to assist spending departments in their assessment of fraud and leakage in each Business Case (see Recommendation 1 Action 1). The guidance will draw on recent research undertaken on options and methods to measure fraud. On risk management new actions that DFIDA will undertake are set out in Recommendation 1 above. On financial management new actions that DFIDA will undertake are set out at Recommendation 2 above. | 2012-09-01 | Completed

## Girl Hub
Girl Hub : a DFID and Nike Foundation Initiative COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed / On-track / Off-track
1. Girl Hub should be reconfigured to focus more sharply on how it will make a difference to girls, with detailed country and programme plans. It needs to measure both the success of each programme and how effectively programmes are linked to each other and to wider initiatives. | Partially Accept | 1.Rather than ‘reconfigure’ the Girl Hub, DFID’s standard Annual Review system will examine and make recommendations to ensure clarity of focus and further strengthen the logframe. | 2012-04-01 | Completed
|  | 2. The monitoring and learning plan will be finalised in July. | 2012-07-01 | Completed
|  | 3. Normal programme management processes require DFID to undertake a final progress review of the project as it approaches completion. This will be conducted independently in the first quarter of 2013. It will assess how the different activities (or programmes) in the log frame have combined to deliver the overall project objectives. It will consider and make recommendations on options for support beyond the project end date in 2013. | 2013-04-01 | Completed
2. Girl Hub should implement comprehensive and robust risk, governance, financial and performance management policies and processes. Girl Hub, DFID and Nike Foundation should ensure that their messaging is clear and consistent and that the roles and influences of each organisation are transparent and accountable. | Accept | 4. Annual Review will identify forward plan for next 6 months. | 2012-04-01 | Completed
|  | 5. Clear governance structure and risk management framework, including country programmes, approved by DFID-Nike Foundation Senior Strategic Collaboration Group. | 2012-07-01 | Completed
|  | 6. Girl Hub financial and performance management policies and processes approved by DFID-Nike Foundation Senior Strategic Collaboration Group | 2012-07-01 | Completed
|  | 7. Further assurance will be provided for DFID monies allocated through audit certificates. The Nike Foundation Annual Audited Statement for FY 2011/12 (June to May) will provide audit discharge for DFID’s global grant to Girl Hub. | 2012-11-01 | Completed
|  | 8. DFID-Nike Foundation Senior Strategic Collaboration Group will recommend how each organisation can clarify their roles and ensure this is clearly communicated | 2012-06-01 | Completed
3. DFID should assess the options for Girl Hub's future in the light of the evidence to date. | Accept | 9. DFID’s standard Annual Review system will identify a forward action plan for next 6 months | 2012-04-01 | Completed
|  | 10. The standard final progress review in first quarter 2013 (as noted in Action 3 for Recommendation 1) will make recommendations for options for support beyond project end date. | 2013-04-01 | Completed
4. DFID should reflect on the Girl Hub experience and the findings of this report in order to learn how it can promote innovation internally in a way that manages risk, including how partnerships with the private sector and private foundations should be implemented. | Partially Accept | 11. Lessons learned from Girl Hub (e.g. through annual reviews) will be fed into future activities to inform DFID’s future policy on innovation. We will continue to place emphasis on being able to work with the Private Sector in new and creative ways which manage risk effectively but avoid stifling innovation through bureaucracy. | 2012-09-01 | Completed
|  | 12. DFID will commit to updating information on its external website about its work with foundations. DFID will mirror this on its internal website and run Insight articles and seminars, to highlight to DFID staff what we can learn about foundations’ approaches to innovation and risk and ways of partnering with them. | 2012-09-01 | Completed
|  | 13. Work has already commenced and guidance will be available by the end of May with a progressive roll out across the organisation in 2012 | 2012-12-01 | Completed

## UNDP
Evaluation of DFID's Electoral Support Through UNDP OFF-TRACK
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed / On-track / Off -track
1. DFID should actively cultivate alternative delivery channels suitable for implementing electoral support. This means seeking out alternative or additional implementing partners where feasible, in order to complement and compare with UNDP and to provide additional resources for capacity-building. | Accept | 1. Comprehensive information & capability statements from non-UNDP providers to be made available to DFID staff, including areas of comparative advantage, geographic expertise and presence, and lessons / evaluations from previous programmes. | 2012-10-01 | Completed
2.1 DFID should immediately engage with the UN at headquarters and local levels to improve performance. This should form part of the 2013 update to the Multilateral Aid Review of UNDP by DFID. | Accept | 2. DFID will continue to support UNDP’s reform agenda, particularly those relating to human resources and cost control. DFID will engage with the UN 5th Committee, through the UK Mission to the UN to ensure greater UN system effectiveness on Human Resource issues. DFID will also work towards and support measures which will improve UN performance as set out in the Quadrennial Comprehensive Review. | 2012-12-01 | Completed
|  | 3. DFID will establish a stronger evidence base on the performance of DFID-funded UNDP election support, using UNDP’s own monitoring and evaluation and an Annual Survey of DFID staff based on the ICAI survey of Governance Advisers on UNDP electoral assistance. | 2012-11-01 | Completed
|  | 4. Closer engagement by DFID at Executive Board and working level, with UK Mission in NY, on follow-up to UN-led review processes, to support reform and performance improvement. | 2012-07-01 | Completed
2.2 [DFID] should encourage the UN to resolve differences in approach to elections between UN agencies. | Accept | 5. DFID will work with UNDP to identify UNDP’s comparative advantage on elections and democratic governance in the new UNDP Strategic Plan (2014 to 2017). (Executive Boards and Strategic Plan discussions). | June, Sept ’12, Feb, June and Sept ‘13 | Completed
|  | 6. DFID will engage with the follow-up to the review of integrated election assistance. | 2012-09-01 | Completed
|  | 7. Annual Review of the Department of Political Affairs (DPA) programme in 2013. | 2013-06-01 | Completed
3.1 DFID should place greater emphasis on ensuring value for money in electoral assistance. This means encouraging more realistic budget processes and advocating appropriate electoral systems and technologies | Accept | 8. DFID will work with UNDP to develop a new methodology for assessing value for money in electoral assistance, taking into account electoral systems, technologies, delivery context, and the need for greater budget and resource transparency | 2013-05-01 | Off-track/ongoing. DFID has been working with the UN to develop detailed shared guidance on value for money in elections. This is a UN-led process and timetable. A concept note has now been finalised.
3.2 DFID also needs to improve its identification of the costs of different aspects of electoral systems in difference countries, to enable better cost control. | Accept | 9. DFID will commission new analysis, data and guidance on comparative electoral costs in consultation UNDP and other providers | 2013-05-01 | Off-track/ongoing. As an interim measure, to support country programmes, DFID has developed summary internal technical guidance on costs and value for money. UNDP is currently scoping analytical work required to provide new data and guidance on costs in electoral assistance. This will be shared with DFID advisers once available.
4.1 DFID should strengthen governance arrangements over UNDP-managed programmes. This includes (i) separating political dialogue from technical oversight and (ii) making more use of third-party monitoring that will act to challenge and hold UNDP better to account for performance. | Accept | 10. New DFID-FCO guidance will be prepared on options for programme governance arrangements, based on best practice lessons, and to be adapted to local requirements | 2012-10-01 | Completed
|  | 11. The joint How To Note on electoral assistance will be amended to reflect the value of sourcing additional resources to monitor and advise staff during election operations. Where feasible, this could be done through EU coordination processes. | 2013-01-01 | Completed
4.2 Risk management arrangements to cover these issues should be fully integrated into the design of assistance through UNDP. | Accept | 12. DFID will work with UNDP to adopt a common approach to risk management (assessment, mitigation, reporting). This will be tested in at least 3 DFID-funded UNDP elections programmes. | piloting from 2013 | Completed
4.3 Where possible, programmes and basket fund arrangements should be maintained through the electoral cycle. | Accept | 13. New, internal online portal launched for DFID staff with resources (analysis, tools, data sets) covering all aspects of the electoral cycle and broader democratic governance. New work detailed here (on suppliers, vfm, costs, risk) to be housed on new portal. | 2013-05-01 | Completed
5. DFID should ensure that each example of electoral support is anchored in a strategy for democratic development. This should include how the elections assistance relates to governance objectives beyond the timeframe of a specific election. It should also include active engagement with a wider range of national stakeholders and political institutions. | Accept | 14. Joint How To Note on electoral support to be updated to reflect issues that should be specifically addressed in business cases and approval submissions. These include wider democratic objectives to which the support will contribute, and links to the strategic objectives for DFID’s Operational Plan in each country | 2012-11-01 | Completed

## Budget Support
The Management of UK Budget Support Operations COMPLETED
Recommendation 6 -rejected - no action
Recommendation 8 -partially accepted -no action
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed/ On-track / Off- track
1. DFID should determine the amount of budget support to provide based on an assessment of how much poverty reduction can realistically be achieved through expanding public expenditure given the quality of national policies and institutions. | Accept | 1. DFID will require all Business Cases for budget support to include a clear rationale for the volume of budget support being proposed | 2012-11-01 | Completed
2. DFID should build its general budget support operations around the possibility of higher and lower levels of funding, with a substantial increment between them, to send clear signals on performance and free up resources from non-performing operations. | Accept | 2. DFID will review each DFID budget support programme to assess the feasibility of introducing a Results Compact. Where feasible DFID will set out steps for the development and incorporation of a Results Compact into the programme. | 2013-01-01 | Completed
|  | 3. DFID will disseminate lessons learnt from evidence and international best practice of performance-based disbursements of budget support. | 2012-11-01 | Completed
3. DFID should set clear targets for progress on public financial management (PFM) reform and anti-corruption for each of its budget support operations and link future funding levels to progress achieved. | Partially Accept | 4. DFID will strengthen guidance on supporting PFM reform including on monitoring progress with measurable indicators. | 2013-03-01 | Completed
4. DFID should strengthen its approach to managing short-term fiduciary risk in its budget support operations through more active measures to address specific risks identified in Fiduciary Risk Assessments. | Accept | 5. DFID will require all Business Cases for budget support to consider the need for, and design of, safeguards in direct response to issues and risks identified in the FRA. | 2012-11-01 | Completed
|  | 6. DFID will establish a ‘community of interest’ on fiduciary risk and safeguards among budget support countries to share and discuss good practice. | 2012-09-01 | Completed
5. Both general and sector budget support operations should include explicit strategies for tackling constraints on efficient public spending and ensure that these are addressed systematically in policy dialogue and reform programmes | Accept | 7. DFID will require all Business Cases for budget support to include an assessment of the constraints to efficient public spending and propose measures to address these | 2012-11-01 | Completed
7. DFID should look for every opportunity to promote national accountability, including through sharing information on recipient government performance generated within budget support operations with parliament and other national stakeholders. | Accept | 8. Based on a review of the implementation of the 5% commitment, DFID will update guidance to country offices with case studies, good practice, and advice on further strengthening work on local accountability. | 2012-12-01 | Completed
|  | 9. DFID will ensure that Performance Assessment Frameworks (PAFs) and related performance data are made publically available in a timely & locally accessible way | 2012-10-01 | Completed
|  | 10. DFID will require all Annual Reviews of budget support programmes to say how we are using information from non-government systems including from beneficiaries in budget support dialogue. | 2012-10-01 | Completed

## India Health and Education
Evaluation of DFID's Support for Health and Education in India COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed /On-track /Off-track
1. Beginning with its work in Bihar in education and health, DFID should identify and monitor what are the particular benefits provided by UK aid in order to focus its activities where it adds most value | Accept | 1. DFID India will use the Annual Review reporting format to capture more systematically the results of the knowledge it shares, policy it helps generate and relationships it develops in India. | 2013-03-01 | Completed
|  | 2. DFID India and the World Bank will commission a 10 year review of their engagement in basic education, assessing the particular results, strengths and weaknesses of development partners’ funding, policy advocacy and technical support activities. | 2013-09-01 | Completed
|  | 3. DFID India will commission a value for money assessment of health sector support which will further examine the impact of our financial and technical assistance. | 2013-03-01 | Completed
2. DFID should clarify its forward strategy in Bihar to enable delivery partners to plan sustainable programmes for the future. | Accept | 4. A strategy to succeed the current Operational Plan (2011-15) will be announced in due course. | 2013-03-01 | Completed
3. DFID should increase even further the contribution it makes through technical assistance in India, which transfers skills and knowledge, because this is where it adds most value | Accept | 5. DFID India programmes in design under the Operational Plan emphasise the transfer of knowledge and know-how through technical assistance, including: - A collaberation with the UK Open University and Indian partners reaching 1 million teachers with improved learning materials - A pilot conditional cash transfer supporting 240,000 disadvantaged girls to go to secondary school in Odisha, offering a potential lessons for national action. - A new technical assistance project boosting NGO and government performance in Water, Sanitation and Hygiene emphasising community led approaches in Madhya Pradesh and Odisha. - Expansion of support for investment climate reforms in Bihar | 2013-03-01 | Completed
4. DFID’s planned anti-corruption strategy should include strengthening ties with local law enforcement bodies and establishing a whistle-blower hotline. | Accept | 6. The DFID anti- corruption and counter fraud strategy for India is in development and will be complete by November 2012. As part of this, we will renew risk assessments and mitigation measures across the India portfolio. 7. DFID India will advertise the current fraud hotline more widely through country office communication sites. DFID will enhance the profile of whistleblowing further and with more country context appropriate advertising. | 2013-03-01 | Completed

## Education 3 EA Countries
DFID's Education Programmes in 3 East African Countries COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed /On-track /Off-track
1. DFID should revise its 2010 strategy for education to ensure that learning outcomes are at the heart of its support through all levels of the education delivery chain. | Partially Accept | 1. In accordance with the Secretary of State’s stronger focus on quality of learning, DFID will develop and publish a Position Paper which will provide the detail on our approach to improving the quality of education (instead of revising the 2010 strategy). | End of 2013 | Completed
2. DFID should revise its pilots on results-based aid by working with ministries of education to introduce a results focus into national funding for schools. | Reject | 2. We accept the spirit of the recommendation that district and school level incentives are important. The existing pilots are already up and running and it would be poor value for money to redesign them now. However, DFID will explore the scope for a new pilot in Tanzania which would introduce a results focus into national funding for districts and schools, as ICAI propose | End of 2014 | Completed
3. DFID should continue to expand its support for communities to enable them to monitor and promote education, so as to encourage accountability, the widest possible participation and public debate. | Accept | 3. DFID will consider further options to enable communities to monitor education expenditure and outcomes. | 2012-10-01 | Completed
4. DFID should strengthen its capacity building in ministries of education to improve the value for money of their education systems. This should involve enhanced analysis (including tracking funds and comparing in-country unit costs and learning outcomes), evaluation ,forecasting and application of international good practice | Partially Accept | 4.DFID will offer capacity building for education ministries and respond to all reasonable requests for it . The precise arrangements in each case will be agreed with the relevant Ministry of Education | 2013-04-01 | Completed

## Asian Development Bank
DFID's Engagement with the Asian Development Bank COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed/ On-track/Off-track
1. Where DFID is co-financing projects with ADB, it should be clear about the relative contributions of each partner, strengthen its initial risk assessment and resource accordingly and improve its real-time monitoring and evaluation. | Accept | 1. DFID will provide country offices working with the ADB with specialist knowledge and advice on the relative contributions of ADB and DFID. | 2013-04-01 | Completed
2. As a shareholder, DFID should concentrate its influence on improving the impact of ADB and ADF projects , in particular by strengthening project design , implementation and independent evaluation on the ground. | Accept | 2. The UK will use discussion of the ADB Results Framework (2013-2016) to ensure that the choice of indicators and the proposed targets stretch the bank to improve its performance and enable shareholders to assess progress. | 2012-12-01 | Completed
3. Ad-hoc discussions between DFID country offices, DFID HQ and the UK representative at ADB should be formalised in quarterly strategic reviews for the five DFID focus countries where ADB activity is significant. | Accept | 3. Quarterly policy and programme meetings will be established between IFID, the UK representative in Manila and Asia Division staff. | 2012-10-01 | Completed
4. DFID needs to ensure that it always has the right information to make choices about when and how to work with ADB.If DFID wishes to use the MAR for this purpose, then future MARs should consider the capabilities of multilateral agencies on-the-ground across a range of countries, capabilities and project types | Accept | 4. Future MAR assessment will have a greater focus on delivery on the ground in a range of countries, using evidence from regular DFID office monitoring of multilateral performance and targeted country visits. | 2013-04-01 | Completed

## Horn of Africa Emergency
DFID's Humanitarian Emergency Response in the Horn of Africa OFF-TRACK
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed /On-track/ Off-track
1. DFID should work towards a cohesive early-warning system, with triggers for action pre-agreed with other key organisations and governments. It should engage with key organisations on this issue within six months. | Accept | 1. DFID will work with selected partners in Kenya, Ethiopia and Somalia to agree triggers for early action. | 2013-03-01 | Off Track This has been completed in Ethiopia and Somalia. DFID Somalia has worked with OCHA to develope a triggers mechanism that will be presented to the Humanitarian Country Team for approval before the year end. Agreement has already been reached with partners on the detailed indicators to be used in monitoring the situation and what thresholds will be used to determine whether a response is necessary or not. The process is now in the hands of OCHA and the cluster lead agencies and outside of DFID control. Work to establish triggers in Kenya will not be completed until early 2015. DFID Kenya has completed the first phase of its support to the National Drought Management Authority in designing a system for triggering a scale-up of the Hunger Safety Net Programme (HSNP) as a safety net in May 2014. The GoK is launching a Livestock Insurance Fund (LIF) and has paid its Africa Risk Capacity (ARC) premiums for the coming season. Work is ongoing and DFID is engaging closely with GoK on this and seeking to influence the design of LIF and any future ARC contract. They are also in discussions with the GoK and ARC about the possibility of designing a new product to focus exclusively on HSNP counties and an earlier season pay out.
|  | 2. DFID will complete a new risk modelling product to help prepare for natural disasters, and share this with the UN Office for the Coordination of Humanitarian Affairs and other key humanitarian partners | 2013-03-01 | Completed.
2. DFID should build on existing good practice to develop, within six months, a new model for flexibly addressing recurring crises in the Horn of Africa. This model should address three key areas: | Accept
2a. Funding: flexible funding mechanisms are needed to improve responsiveness | Accept | 3. DFID will review its procedures and produce internal guidance on more responsive and flexible multi-year funding mechanisms to address chronic crises. The guidance will include consideration of pre-approved contingency budgets and automatic triggers, within the parameters of responsible financial management and proper accountability. This guidance will be shared with other donors and partners | 2013-03-01 | Completed.
2b. DFID should consider how best to use and bolster its personnel during a crisis | Accept | 4. DFID will formally review how it recruits and deploys humanitarian advisers, and refresh its protocols for managing the demand for extra staff during prolonged surges in crises. | 2013-03-01 | Completed
2c. Partner selection: DFID should consider how best to use NGOs and CSOs in a crisis, to achieve objectives and build capacity | Accept | 5. DFID will develop further multi-year funding arrangements with NGOs, both at country level (E.g. in Kenya on livelihoods support in the arid lands) and at a global level (E.g. through a new Global Resilience Action Programme to build international and local capacity to anticipate and respond to natural disasters). | 2013-03-01 | Completed
3.DFID should build on its existing engagement with host governments and key agencies to develop lasting solutions. It should target key areas such as infrastructure development that are needed to address chronic poverty. It should use its expertise and experience to tackle challenging areas such as the sustainability of pastoralism and refugee camps. This should be incorporated into DFID’s plans for 2013-14. | Accept | 6. DFID will review support to activities supporting resilience and lasting solutions to chronic vulnerability in its refresh of country operational plans for 2013-14. | 2013-04-01 | Completed
|  | 7. DFID will embed disaster resilience in 8 pilot country programmes (including Kenya and Ethiopia) using a central checklist of agreed minimum standards, to inform later roll-out to all country programmes. | 2013-03-01 | Completed.

## Conflict Pool
Evaluation of the Inter-Departmental Conflict Pool OFF TRACK
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed /On-track/Off-track
1. The Building Stability Overseas Board should develop a clearer strategic framework specifically for the Conflict Pool, to clarify its comparative advantage alongside DFID (particularly in regional programming) and identify how it will intergrate defence, diplomacy and development into a multi disciplinary approach to conflict prevention. | Accept | 1. The Conflict Pool Secretariat will develop a Conflict Pool Strategy for the BSOB’s approval by the end of 2012. | December 2012 | Completed
2. By the next Conflict Resources Settlement (starting in 2015-16), the three departments should simplify the management structure for the implementation of Conflict Pool activities, while retaining a tri-departmental approach to strategy setting and funding allocation. | Accept | 2. In the context of preparing for the next Spending Review, we will consider what other management arrangements and structures would be appropriate and optimal for the Conflict Pool. | Autumn 2013 | Off-track - target date revised to April 2015 due to creation of CSSF. This was taken forward at the Spending Review for FY 15/16 which created a new, £1bn Conflict, Stability and Security Fund (CSSF). The CSSF Joint Secretariat is currently considering what management arrangements and structures are most appropriate, taking on board lessons from various reviews of the Conflict Pool. Revised governance arrangements will be in place before the Fund’s launch in April 2015. We will ensure that this is carried forward into the next Spending Review.
3. At the next spending review, the three departments should work with the Treasury to reduce volatility in the Conflict Pool budget. | Accept | 3. In the context of preparing for the next Spending Review, we will consider what further measures could be appropriate to reduce volatility in the conflict resources settlement. | Subject to timing of the next spending review | Completed
4. To maximise its impact, the Conflict Pool should match its funding model to its specific objectives, balancing a proactive approach to identifying partners for larger-scale activities with a flexible and responsive grant-making process for promising local initiatives and paying more attention to leveraging other resources to take pilot activities to scale. | Accept | 4. We will develop new programme guidelines to address this. | Autumn 2013 | Off-track - target date revised to April 2015 due to creation of CSSF. Programme guidelines for the new Conflict, Stability and Security Fund (CSSF) are currently being developed and will be agreed in time for the Fund's launch in FY 15/16.
5. The Conflict Pool should adopt guidelines on risk management and conflict sensitivity. | Accept | 5. The guidelines referred to in action 4 will address this. | Autumn 2013 | Off-track - target date revised to April 2015 due to creation of CSSF. Programme guidelines for the new Conflict, Stability and Security Fund (CSSF) are currently being developed and will be agreed in time for the Fund's launch in FY 15/16.
6. The Conflict Pool should develop a balanced monitoring and evaluation system which encompasses both strategic resource management and real-time assessment of the outcomes of specific projects. | Accept | 6. We will issue improved guidance on monitoring and evaluation for the Conflict Pool. | March 2013 | Completed

## Pakistan
DFID's Bilateral Aid to Pakistan COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed/On-track/Off-track
1. DFID Pakistan should ensure that conditions for scaling up its programmes are clearly articulated | Accept | 1. DFID will seek bilateral aid talks with the Government within six months of the election (expected spring 2013), to review progress on results, discuss policy developments in the four key areas, and agree actions going forward. | 2013-09-01 | Completed
1b. DFID should retain the flexibility to reallocate funding away from under- performing areas. The country programme should also be better balanced across government and non-government delivery channels. | Accept | 2. DFID in Pakistan will track risk and performance across the portfolio (including delivery channels), and the results will be discussed regularly at the programme board to ensure a balanced portfolio. | 2013-03-01 | Completed
2. DFID should increase its support for promoting affordable and equitable private sector delivery of health and education services to poor communities. It should focus on building government capacity to regulate the private sector, improve standards and monitor delivery | Accept | 3. DFID will ensure that its new health and education programmes (currently in design) include dedicated financing for private sector delivery of services and help build government capacity to regulate the private sector, improve standards and monitor delivery | 2013-03-01 | Completed
3. Building resilience to natural disasters at the household and community levels should become a core element of the DFID Pakistan programme. | Accept | 4.DFID will take account of ICAI recommendations as we establish a new programme to build community level disaster risk management, enhance preparedness, and improve disaster response. Both the resilience and the multi year humanitarian programmes are approved. | 2013-03-01 | Completed
4. DFID programmes should include agreed standards for budget integrity as a condition for scaling up. There should be a major emphasis on promoting transparency and accountability in budget processes and on increasing the amount of beneficiary involvement in the delivery and oversight of programmes. | Partially Accept | 5. DFID will continue to ensure all major programmes involving financial aid to government include clear measures to safeguard public money, ensure additionality of DFID funds, and promote transparency and accountability, including through more systematic beneficiary involvement | 2013-03-01 | Completed
|  | 6. Together with the World Bank DFID will offer help to the Governments of Punjab and Khyber Pakhtunkhwa to undertake Public Expenditure Reviews as the basis for agreeing benchmarks to improve expenditure policy and budget integrity. | 2013-03-01 | Completed

## Nigeria Education
DFID's Education Programmes in Nigeria COMPLETED
Recommendation 1 - Rejected -no action
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed /On-track/Off-track
2. DFID should work with its partners and each participating state to secure a clear agreement about the policy changes and financial contributions required to improve enrolment and learning and to introduce effective financial management and resource planning into education. There should be regular reviews of performance with states based on school level data | Accept | 1. GEP3 plans to sign State MoUs outlining policy and financial commitments needed from States. They will be in place by the first full Annual Review. | 2013-09-01 | Completed
|  | 2. State-by-State performance comparisons will be available by end of the academic year. DFID will review the results of a new monitoring tool recently put in place to track State budget release and utilisation against annual budgets. This will be reported to DFID on a quarterly basis to inform lobbying efforts. | 2013-06-01 | Completed
3. DFID should work with UNICEF to achieve significant improvement in performance of GEP3 over the next 12 months against agreed targets with a review of progress by DFID after six months | Accept | 3. A decision on the shape and scale of continued DFID support to UNICEF will be taken after the first full Annual Review. | 2013-09-01 | Completed
4. DFID should address implementation issues that are limiting the impact of the two programmes in relation to the female trainees teacher Scholarship Scheme, School- based Management Committees and Qur’anic Schools | Partially Accept | 4. DFID will identify ways of further supporting FTTSS graduates, and review progress on support to SBMCs by UNICEF in the next full Annual Review. | 2013-09-01 | Completed

## EU
DFID's Oversight of the EU's Aid to Low Income Countries COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed/On-track/Off-track
1. DFID should set out clearly what action is needed and how long it will take to deliver the same level of assurance on its contributions to the EU as it achieves elsewhere. This should include improvements to the performance management of EU aid and better access to EU information | Partially Accept | 1. We will update our Multilateral Aid Review on the European Development Fund and European Commission Budget instruments which will reassess their value for money and compare performance against other multilateral organisations, including the World Bank. | 2013-11-01 | Completed
|  | 2. Request a clear timetable for implementation of an improved EU results framework from EuropeAid | 2013-03-01 | Completed
2. DFID should give better guidance to DFID country offices on how they should contribute to EU country strategies and to existing coordination forums, so as to ensure a better combined impact from UK and EU funds and a greater focus on actual EU performance. | Accept | 3. Roll-out Europe Department communications strategy across DFID. | 2013-05-01 | Completed
|  | 4. Review and have implemented guidance on engaging with the EU delegations where no DFID country office is present, including through embassies where possible | 2013-12-01 | Completed
3. DFID should ensure that the EU secures on-going inputs from intended beneficiaries and effective intelligence on what is needed on the ground, in order to inform and challenge dialogue with recipient governments. | Accept | 5. Press for guidance to be issued to EU delegations on implementing the European Commission’s communication on civil society organisations in country. | 2013-12-01 | Completed
4. DFID should engage more actively on developing and driving through the EU’s planned improvement of its risk management processes, given the potential this has for improving the impact of EU aid. | Accept | 6. Push for the revised Development Cooperation Instrument (DCI) and European Development Fund (EDF) regulations, being negotiated as part of the Multi-annual Financial Framework, to enable greater responsiveness in the programming cycle. | 2013-12-01 | Completed

## Sudan WASH
DFID's Water, Sanitation and Hygiene Programming in Sudan COMPLETED
Recommendation 2-Rejected -no action
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed/On-track/Off-track
1. DFID should produce a detailed strategy and results framework for transition from emergency WASH programming in Darfur towards more sustainable investments in infrastructure. | Accept | 1. DFID in Sudan will develop a new Business Case for support to the water sector in Darfur. This will include a transition strategy and results framework. | 2013-09-01 | Completed
3. DFID should ensure that lessons from the Darfur Urban Water Supply (DUWS) project are integrated into business cases for future water programmes in Sudan and elsewhere. | Accept | 2. DFID in Sudan will develop a procurement plan for the East Water business case | 2013-06-01 | Completed
4. At the corporate level DFID should ensure that its WASH policy framework prioritise early planning for transition from emergency assistance through early recovery to development programming in the context in protracted and chronic crises. | Accept | 3.Based on the outcome of the pooled funds research, DFID will review, and if necessary, develop new financing instruments for delivering basic services in protracted and chronic contexts. A policy note and operational guidance will be available by June 2013. | 2013-06-01 | Completed
|  | 4. DFID will produce guidance on multi-year approaches to humanitarian planning to improve the effectiveness of its work in protracted crises. | 2013-09-01 | Completed

## Nepal Peace and Security
The Effectiveness of DFID's Peace and Security Programme in Nepal COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed/On-track/Off-track
1. To maintain and build on beneficiary impact achieved to date , DFID Nepal shoul within six months , develop an analytically based, forward looking governance and security strategy. This should link to a measurable results framework , with ambition consistant with the level of spending | Accept | 1. DFID in Nepal will undertake a comprehensive strategic review of the peace and security programme, drawing on recent analysis and mapping out the future programme direction. | 2013-07-01 | Completed
|  | 2. The results targets in the peace support log frame and in the Nepal Results Framework related to peace and security will be assessed as part of the comprehensive strategic review | 2013-07-01 | Completed
2. To ensure projects deliver value for money throughout their life cycles, DFID Nepal should ensure compliance with DFID procedures. It should, within six months, update its project information and planning systems and ensure that these are maintained. | Accept | 3. DFID in Nepal will conduct a full review of all our project documentation, and ensure these are accurate and up-to-date. We will ensure all required information is uploaded to the website. | 2013-05-01 | Completed
3. To deliver value for money, DFID Nepal should develop greater visibility of the end-to-end costs of delivery. This requires a more sophisticated consideration of administrative and programme costs at the design stage. At a corporate level, DFID should consider standardising its approach to this analysis. | Accept | 4. DFID Nepal will pilot a revised approach to analysing the costs of delivery, in our planned Security and Justice Business Case. This will be used as a model for all future Business Cases, as well as informing existing programming. | 2013-08-01 | Completed

## Western Odisha
Review of DFID's Livelihoods Work in Western Odisha COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed/On-track/Off-track
1. It is particularly important for livelihoods and other climate resilience programmes that DFID enables long term planning and budgeting. DFID staff should be made aware that departmental budgeting cycles should not constrain effective planning. This is especially the case where an intervention’s success depends on community participation and ownership. | Accept | 1. DFID will issue a communication to staff on how programme planning can take place within the constraints of the departmental budget cycle | 2013-06-01 | Completed
2. Exit and sustainability matter. There should be a specific mandatory workstream in all projects, from inception, that plans for exit and sustainability. DFID needs to manage livelihoods projects actively right through to the end. | Partially Accept | 2. DFID will prepare a sustainability strategy for the transition of its programme in India. | 2013-07-01 | Completed
|  | 3. DFID/NAO stocktake of Annual Reviews (AR) will consider whether the AR has sufficient focus on sustainability of outputs and outcomes | 2013-09-01 | Completed
3. The project emphasises the benefits of transparency to and involvement of beneficiaries. DFID should continue to develop greater transparency at all levels, including in respect of project results. | Accept | 4. DFID in India will refresh its guidance on transparency standards for project delivery partners | 2013-07-01 | Completed
|  | 5. DFID will launch a new open data platform for UK aid making aid information more accessible to stakeholders, and create a DFID ‘community of practice’ on beneficiary monitoring to improve cross departmental lesson learning. | 2013-09-01 | Completed

## UNICEF
DFID's Work Through UNICEF COMPLETED
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2013 update
Completed/On-track /Off-track
1. DFID should manage its relationship with UNICEF as a strategic delivery partner, by maintaining regular oversight of its UNICEF portfolio as a whole and managing UNICEF relationships with a greater focus on results and value for money. | Accept | 1. DFID will set up regular review meetings with UNICEF to oversee the whole DFID UNICEF portfolio and manage the relationship with an even greater focus on results and value for money. | 2013-10-01 | Completed
|  | 2. DFID will update its MAR assessment of UNICEF’s value for money for UK aid, by assessing UNICEF’s progress in implementing the agreed reform priorities. | 2013-12-01 | Completed
2. DFID should negotiate an updated global Framework Arrangement with UNICEF, which reflects current best practice in management of the partnership, clarifies procurement charges and is aligned more closely with DFID’s approach to managing commercial contractors. | Accept | 3. DFID will formally open negotiations with UNICEF on updating the Framework Arrangement by May 2013. | 2013-05-01 | Completed
3. DFID should strengthen its management of UNICEF’s local programme delivery, building on good practice seen in some DFID country offices and reflecting approaches used to manage other types of service delivery partner. | Accept | 4. DFID will disseminate to its country offices a good practice note specifically on working with UNICEF as a delivery partner. | 2013-05-01 | Completed

## Use of Contractors
DFID's Use of Contractors OFF TRACK
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed/On-track /Off-track
1. DFID should support its devolved delivery model with strategic guidance, informed by its sectoral experts, on when and how contractors of different sizes and specialisms can deliver most effectively. This should include a strategic partnering model for how best to use its major and SME contractors | Accept | 1. DFID will complete its review of strategic choices the department makes in its use of contractors. This will include a fundamental look at when the department should be delivering in-house and when and how it should bring in suppliers to maximise results and value for money | 2013-12-01 | Completed
2. DFID should prioritise its commercial reforms, so that PrG can support more strategic decision-making on the use of contractors and develop more productive relationships with them. | Accept | 2. DFID will prioritise its commercial reform programme and focus on a smaller number of key areas. | 2013-07-01 | Completed
3. DFID should update its bid evaluation process, strengthening the role of the programme’s designers during procurement, to enable a more sophisticated and balanced assessment of costs, timings, risks and results. | Partially Accept | 3. DFID will review its bid evaluation practice to identify how to improve early market engagement and how to strengthen the role of programme designers during procurement. | 2013-12-01 | Completed
4. DFID should develop a resourced plan for its programme management capability, to ensure end-to-end accountability for programme delivery and minimise disruption from staff rotations. | Accept | 4. DFID has made strengthening programme management a top priority in our Departmental Improvement Plan for the coming year and the Head of Profession will develop a detailed plan to implement this. | 2013-11-01 | Off-track - DFID has established for an initial 12 months the Better Delivery Team to take forward the programme management reforms. Work has commenced to evaluate the futre vision/sustainable model of this reform post 2015. Expected output April 15
5. DFID should strengthen learning from contractor-delivered programmes, to feed into the design, procurement and delivery of other programmes. | Accept | 5. As part of its effort to develop stronger relationships with its contractors DFID will ask them to propose practical ways to bring their insights and learning from programmes back into DFID and to share these across programmes. | 2013-11-01 | Completed

## PPAs
DFID's Support to CSOs through PPAs COMPLETED
Recommendation 2- Rejected -no action
Recommendation | Accept/Partially Accept /Reject | Action | Target date | Autumn 2014 update
Completed /On-track/Off-track
1. If DFID decides to continue with PPAs, or a similar grant-making instrument, it should use the intervening period to develop a more strategic, transparent and fair process for selecting CSOs and allocating funding. DFID should consider, both for this round and for any future rounds , extending the PPAs to more than three years to allow the strategic and innovative aspects of this unrestricted funding to develop. | Accept | 1. DFID’s adjusted PPA Evaluation strategy reflects the need to produce evidence on the optimum duration of PPA type grants and programme design characteristics to maximise the value of strategic funding. | 2013-11-01 | Completed
3. DFID should design the monitoring and evaluation system for PPAs so that it is less cumbersome and better suited to the long-term strategic nature of this funding. | Accept | 2. DFID will complete the review of the PPA evaluation strategy; adjust the approach to take account of lessons learnt as well as the experience of PPA agencies and the decision to extend the PPAs to March 2016. Updated guidance will be issued to PPA agencies | 2014-01-01 | Completed
4. DFID should strengthen the role of the Learning Groups in order to ensure that lessons learned are shared more widely within DFID ansd with Civil Society partners. | Accept | 3. DFID will design and implement a PPA Learning Group communications strategy. This will include tools designed to track learning uptake by PPA agencies, DFID and more widely. | 2013-07-01 | Completed

## Burma
DFID's Health Programmes in Burma OFF TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed/ On-Track/Off-Track
1. DFID should leverage its relationship with the Ministry of Health in Burma to date to focus the in-flows of health aid and accelerate the building of a more robust health system , including better intergration of the for-profit sector. | Accept | 1. DFID funds priority actions to strengthen health systems, in particular financial management systems through 3MDG Fund. | 2013-12-01 | Completed
2. DFID should work with other donors and the Ministry of Health to capture better quality information about the health sector in Burma and to create stronger and more robust monitoring systems and data baselines across key health programme areas. | Accept | 2. Data collection for baseline survey underway in 3MDG Fund implementation areas | 2013-12-01 | Off-track Following discussions with the Ministry of Health the 3MDG Baseline Survey was combined with the National Household Survey on Demographic and Health in order to streamline surveys, and make best use of existing resources. Initial preparatory steps have been started, data collection will commence by December 2014 and data will be available from August 2015 onwards.
3. DFID should work with all parties to ensure the potential risks of the 3MDG Fund programme are identified and addressed, including management of the UNOPS contract, to ensure that the Fund is mobilised, executed and monitored effectively. | Accept | 3. Risk matrix reviewed quarterly by the 3MDG Fund Board, and mitigating actions taken forward. The next two risk reviews in 2013 are critical for the first full year of operation of the 3MDG Fund. | September and December 2013 | Completed
4. DFID should ensure that, at this crucial time in developing its health programme in Burma, the impact of key personnel changes in the DFID office is minimised, including the timing of staff transfers and the development of a robust plan to ensure that key relationships are maintained. | Accept | 4. The new Team Leader for Basic Services in post following a structured programme of induction. | 2013-08-01 | Completed

## Montserrat
DFID's Support to Capital Projects in Montserrat OFF TRACK
Recommendation 1- Rejected -no action
Recommendation 2- Rejected- no action
Recommendation 4 -Rejected-no action
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed/On-Track/Off-Track
3.DFID should work with the Government of Montserrat to increase the engagement of the people of Montserrat in its projects. This is both to understand their perspective and to manage their expectations. | Partially Accept | 1. DFID will continue to engage the people of Montserrat in projects that matter to them. In particular we will:
|  | Consult the Opposition at the mid-year review of budget aid. | 2013-10-01 | Completed
|  | Work with the Government of Montserrat to ensure local people are consulted on planned developments, e.g. improvements to the ferry; the next phase of geothermal energy. | 2013-12-01 | Completed
|  | Ensure the participation and active involvement of the islanders so the hospital and health care project meets their needs, e.g. all primary school children will be involved in interactive health awareness; and registered diabetics will participate in self-management training. | March 2014 50% by Dec 2014 | Off Track - Although the child health awareness component of this Action has been completed, the diabetes target is off track. The view is that this target is too ambitious and is currently under review as part of our Hospital Project AR

## OPTs
DFID's Support to Palestinian Refugees through UNRWA ON TRACK
Recommendation | Accept/ Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed /Off-Track /On Track
1. DFID should carry out an urgent assessment to determine the level and nature of support UNRWA will require, to enable it to address effectively the challenge of reform and the widening gap between the demand for and supply of UNRWA services. The assessment should be conducted in close consultation with UNRWA, other donors and host governments and authorities and provide a significant input into the upcoming Medium Term Strategy process for 2016-21. | Partially Accept | 1. We will continue to work closely with hosts, donors and UNRWA to identify the Agency’s strategic priorities in the run up to the Advisory Commission meeting in November 2013. We will discuss with UNRWA the priorities for immediate support, in particular for the planning process. | 2014-01-01 | Completed
2. DFID should use its influential position to urge donors and hosts to provide unified political, technical and operational support to drive UNRWA’s reform activities. DFID should provide substantive support to the implementation of reform in the priority areas within UNRWA’s poverty alleviation, health and education programmes. | Partially Accept | 2. We will take an active role in the Sub-Committee (currently as Vice-Chair) in order to help provide unified support for UNRWA’s reform activities, including through the Medium Term Strategy process. | Ongoing | On track
|  | 3. In preparing a business case for DFID support for UNRWA from 2015 onwards, we will carry out an assessment of whether additional support for reform at an operational level would be useful and in which sector. | 2014-12-01 | On track
3. DFID should encourage UNRWA to engage more actively and to communicate more effectively with refugees as part of the reform process. DFID should consider providing technical support in this area. | Accept | 4. We will carry out an assessment (with UNRWA) of whether technical support to help UNRWA improve its engagement with refugees would be useful. | 2014-01-01 | Completed

## Empowerment and Accountability
Empowerment and Accountability ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed /On-Track/Off-Track
1. Promoting constructive community engagement with government around the delivery of public services and development programmes should be the principal focus of DFID’s social accountability programmes and a shared goal with its sector programmes. When scaling up successful social accountability initiatives direct grants to national CSOs to work with local communities are likely to be more effective than competitive grant making. | Partially Accept | 1. DFID will review evidence of the effectiveness and impact of social accountability initiatives, update the empowerment and accountability Theory of Change and communicate across DFID business units an updated version and revised summary of current evidence. | 2014-07-01 | Complete
2. DFID support for CSO advocacy and influencing at the national level should be more targeted, with smaller portfolios, longer partnerships and more tailored capacity-building support. | Partially Accept | 2. See actions in Section 1 and 3 (updated evidence summary and new 5 year research programme). | See dates in Section 1 and 3. | N/A
3.Future social accountability programmes should designed with the flexibility to test different approaches and scale up successful initiatives. DFID’s central policy team should guide this process of structured learning and ensure the continuous sharing of lessons among country offices and managing contractors and with relevant sector programmes. | Accept | 3. In addition to the evaluation, DFID will develop a multi-year, multi-country research programme. This will consider how to promote constructive community engagement in service delivery, and what social accountability initiatives work in different contexts. Evidence will enable scaling up of successful initiatives. | Programme to be approved by 2014 | On track

## Agriculture
DFID's Support to Agricultural Research COMPLETED
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed/On-Track/Off-Track
1. DFID should ensure its agricultural research and development programmes collaborate better to deliver research outputs to farmers as quickly as possible and at scale to maximise the benefits for poor people. | Accept | 1. In collaboration with the two RED regional Research Hubs, we will undertake a stocktake of the demand for agricultural research findings within DFID country programmes in order to improve the uptake of research by country programmes | 2014-03-01 | Completed
2. DFID should develop explicit ‘theories of change’ to map out the steps and partnerships needed to ensure research outputs lead to improved food security and nutrition for poor people and women. | Accept | 2. We will review the agricultural research programme priorities paper to ensure that we have the right balance between investments and partnerships to develop new technology and those needed to get technology into use. | 2014-03-01 | Completed
3. DFID should aim to increase agricultural productivity, while minimising negative environmental impacts. It should focus strongly on environmentally sustainable intensification of agriculture. | Accept | 3. The Agriculture team will develop a new Business Case in 2014 to support targeted research on sustainable intensification in Africa, leveraging other funder’s research investments in Africa Rising and Vital Signs. This will help governments and development partners to better understand the conditions and institutions that will support sustainable intensification and the complex trade-offs faced in promoting this as an objective. | 2014-06-01 | Completed

## Southern Africa Trade
DFID's Trade Development Work in Southern Africa OFF TRACK
All recommendations need to be read in the light of the decision to close the TMSA programme
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed /On-Track/ Off- Track
1.DFID should continue to take swift action, as it started to do when we raised our concerns, to ensure effective management of TMSA, including financial oversight, procurement, target setting and monitoring. | Accept | 1. As the TMSA programme winds down in March 2014 DFID will maintain strict oversight of TMSA activity and progress. | 2014-03-01 | Completed.
2. DFID should urgently work to raise awareness of the results of TMSA’s recent economic modelling to countries of the Tripartite, undertake further analysis and support poorer countries to address potential negative impacts of trade growth. | Accept | 2. DFID will disseminate the recent TMSA economic modelling work via DFID country offices and FCO posts in the region as part of our continued support to the Tripartite agenda. | 2014-02-01 | Completed
3. If DFID decides to continue with its support to regional integration in Southern Africa, it should identify a more suitable mechanism to deliver technical assistance to the Tripartite, with a focus on accelerating progress and drawing, as appropriate, on international expertise | Accept | 3. DFID is assessing how best to continue to support trade and regional integration in Southern Africa drawing on the work now in hand in the region and also from other trade programmes operating elsewhere. | 2014-06-01 | Off Track with work on-going. DFID Southern Africa has closed the TMSA programme in line with SoS decision and taking into account ICAI's requirements for tight controls . DFID Southern Africa has consulted widely on its future programme including both SADC and COMESA plus other donors and other DFID Country Offices . DFID SA is now seeking bidders to help with consideration of a number of options and to design a new regional trade and intergration programme. This process will be informed by the ICAI and other reviews of TMSA , international best practice and programmes operating elsewhere.Subject to a satisfactory procurement and scoping stage, a new programme will be in place in 2015.
4. As a prerequisite of any future trade development programme, DFID should undertake comprehensive analysis of the impact on trade and the poor both at the outset and throughout implementation and build in mitigating action to alleviate any negative effects. | Accept | 4. We will ensure that any trade programme tracks impacts on poverty and considers the case for mitigating actions. | 2014-06-01 | On track/met. DFID's Chief Economist has circulated internal guidance on how to assess the poverty impacts of trade programmes and made clear that this standard framework should now be applied in the development of all future trade programmes. This guidance will be used to inform and shape the design of the new regional trade and integration programme in Southern Africa.

## Afghanistan Livelihoods
DFID's Bilateral Support to Growth and Livelihoods in Afghanistan COMPLETED
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed / On-Track/Off-Track
1. DFID should formally review current and future projects to focus its portfolio more firmly on reducing poverty using evidence-based interventions. This should be completed within six-months using a consultative and evidence-led process. | Partially Accept | 1. Within the CPRD process DFID will review current and future projects against constraints, gaps and opportunities, in differing scenarios, to focus specifically on reducing poverty. This will include assessment of opportunities to address the key barriers to an exit from poverty and eventually from aid dependence. | 2014-08-01 | Completed
2. DFID should ensure that intended beneficiaries are, as far as practicable, directly consulted when new projects are being designed, so that their needs are clearly addressed and their ownership is enhanced | Partially Accept | 2. DFID will develop a full list of Afghan research and development organisations with the expertise to undertake beneficiary consultation. This will enable strengthening of DFID’s beneficiary consultation during project design and implementation. Further activity to strengthen research and development institutions will also serve to strengthen DFID’s capacity to undertake beneficiary consultation during project monitoring. Where delivery is through arrangements such as Multi-donor Trust Funds, DFID will work with the multilateral partners to strengthen their approach to beneficiary consultation | 2014-11-01 | Completed
3. DFID should enhance its approach and commitment to independent monitoring in order to assess current and future project performance and to allow it to assess the impact of its programme. | Partially Accept | 3. DFID Afghanistan’s programme-wide monitoring strategy will be published by August 2014. This will set out how DFID will strengthen independent monitoring by providing additional resource to undertake independent monitoring across the portfolio, build the capacity of DFID staff and implementing partners to monitor our programmes better, and provide a cross-portfolio analysis to aid strategic decisions about the shape of DFID’s programme in the future. | 2014-08-01 | Completed

## Philippines Emergency
DFID's Humanitarian Response to Typhoon Haiyan in the Philippines ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed/On-Track/Off-Track
1. In the Philippines, DFID and the Foreign and Commonwealth Office should support the Philippine Government’s reconstruction plan in strategic areas, such as climate change resilience. | Accept | 1.DFID, working with the FCO, will continue to engage with the Government of the Philippines on their reconstruction plans including considering a contribution to the multi donor trust fund. DFID investment will be focused on building back better and longer term climate resilience | 2014-09-01 | Completed.
2. DFID should build on the successes of this response to strengthen its leadership within the global humanitarian response systems and specifically of its stock-piling and logistics capacity. | Accept | 2. DFID will publicise its commitments on the drive for improved performance by the UN and wider humanitarian system. | 2014-06-01 | Completed.
|  | 3. In line with previous planning, DFID will start to increase its stockpile holding to meet the needs of 75,000 people (from 38,000), including a review of the most appropriate non-food items, including hygiene kits, with a particular focus on the needs of women and girls. | 2015-09-01 | On-track.
3. DFID should use learning from this response to develop a clear strategy for humanitarian engagement where it has no in-country presence. | Accept | 4. DFID will set out clearly how it responds where it has no in-country presence. This will incorporate lessons from the Haiyan response. | 2014-12-01 | On-track.

## Child Mortality
DFID’s contribution to the reduction of child mortality in Kenya ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed/On-Track/Off-Track
1. DFID centrally should specify its policy on equity more clearly and DFID in Kenya should focus systematically on the quality of – and access to –maternal, neonatal and child health services for remote and hard-to-reach populations. DFID should routinely use beneficiary feedback in its programme design. | Accept | DFID Kenya will draw on emerging good practice to appropriately integrate beneficiary feedback into programme cycle including design | 2015-03-01 | On- track
2. DFID should develop a clear exit strategy for funding basic supplies in Kenya (such as bed nets) and focus instead on achieving a long-term and coordinated approach amongst development and financing agencies, including GAVI and the Global Fund, for health systems strengthening. DFID should develop criteria for resuming direct financing to the Government of Kenya. | Partially Accept | DFID Kenya will work with key partners to consider the implications and rationale for funding basic supplies in Kenya to inform future strategy | 2015-03-01 | On-track
DFID should engage with emerging county government structures in Kenya to mitigate the risks and to expand the opportunities of devolution for health outcomes and to help develop information systems and financial management tools that will rapidly identify and address any negative impacts. | Accept | No action given | No date given | On- track

## Learning
How DFID Learns ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed/On-Track/Off-Track
1. DFID needs to focus on consistent and continuous organisational learning based on the experience of DFID, its partners and contractors and the measurement of its impact, in particular during the Implementation phase of its activities. | Accept | The Department will intergrade lesson learning and knowledge sharing into DFID's operational framework | 2014-12-01 | Completed
2. All DFID managers should be held accountable for conducting continuous reviews from which lessons are drawn about what works and where impact is actually being achieved for intended beneficiaries | Accept | DFID is already creating a new role in relationship to programme management – the Senior Responsible Owner (SRO). Part of their role will be to share learning from live programme reviews, including lessons learnt from intended beneficiaries. | 2015-01-01 | On-track
3. All information commissioned and collected (such as annual reviews and evaluations) should be synthesised so that the relevant lessons are accessible and readily useable across the organisation . The focus must be on practical and easy-to -use information . Knowhow must be valued as much as knowledge. | Accept | The Department will identify exemplar case studies that illustrate practical lessons learned and innovative approaches capable of wider application across DFID programmes, starting in October 2014. | 2015-10-01 | On-track
4. Staff need to be given more time to acquire experience in the field and share lessons about what works and does not work on the ground | Accept | All offices will consider how best to ensure their staff spend enough time in country. We will also consider how to deepen the field experience of staff working in hostile environments and in HQ | 2015-05-01 | On track
5. DFID needs to continue to encourage a culture of free and full communication about what does and does not work .Staff should be encouraged always to base their decisions on evidence , without any bias to positive. | Accept | The Permanent Secretary will issue a reminder on the Civil Service Code and the need for objectivity in use and presentation of evidence | 2014-07-01 | Completed

## Private Sector Development
DFID's Private Sector Development ON TRACK
Recommendation | Accept/Partially Accept/Reject | Action | Target Date | Autumn 2014 Update
Completed/On-Track/Off-Track
1. DFID should clearly define and articulate where it can add most value in PSD relative to other stakeholders. It should be more realistic in its ambitions and the impact it seeks to achieve. | Partially Accept | Building on initial work, DFID is developing a results framework for economic development. This includes defining key economic development indicators linked to DFID’s priorities which match ambition, resources and comparative advantage. By late 2014 Ministers will take an internal view on the results framework, but this will require further due diligence. | 2015-07-01 | On-Track
2.DFID should provide clearer guidance to its staff on how to design a coherent and well-balanced PSD country portfolio that matches its goals for an end to extreme poverty through economic development and transformational change. | Partially Accept | DFID will launch a new network to provide country offices with access to dedicated economic development advice from HQ, offering strategic support across portfolios and on programme design and helping ensure alignment with policy objectives. | 2014-09-01 | Completed
3. DFID needs better to calibrate and manage the risks associated with PSD and so innovate in a more informed fashion. | Partially Accept | As part of wider efforts to strengthen programme management capability, DFID is revising its pilot training on financial instruments, covering risk management and governance issues relating to private sector financing structures. | 2014-10-01 | Completed
4. DFID needs to work harder to understand the barriers and business imperatives faced by the private sector in participating in development. Wherever it operates, DFID needs to be clear how and where its interventions can address these barriers. | Accept | DFID will roll out a corporate relationship management approach to strengthen development relationships with selected private sector partners for development. | 2014-10-01 | Completed