## EE
ACTIVITY BASED BUDGET TEMPLATE
Act | Activity | Details | YEAR 1 | [11 empty] | Total (£)
|  |  | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
|  |  | APR | MAY
1.1 | Terms of Reference | 1 BR full time senior consultant @ £300 per day for 48 days | YEAR 1 APR: 6000; YEAR 1 MAY: 6000; YEAR 1 JUN: 2400 | 14400
|  | 2 part time analysts (co-funded) | YEAR 1 APR: 0
1.2 | Mission to the UK to learn best practices | 3 international round-trip airtickets - BSB/LON/BSB @ £1250 per ticket | YEAR 1 SEP: 3750 | 8030
|  | Accomodation in London for 3 people for 6 nights @ £180 per night/person | YEAR 1 SEP: 3240
|  | Subsistence for 3 people for 7 days @ £40 per day/person | YEAR 1 SEP: 840
|  | Transfer airport/hotel/airport @ £200 for the group | YEAR 1 SEP: 200
2.1 | Final project event, followed by a workshopto discuss and disseminate results | Venue and coffee break (co-funded) | YEAR 1 JAN: 0 | 1910
|  | International round-trip airtickets for 1 UK expert @ £1250 per ticket | YEAR 1 JAN: 1250
|  | Accomodation in London for 1 person for 3 nights @ £180 per night | YEAR 1 JAN: 540
|  | Subsistence for 1 person for 3 days @ £40 per day | YEAR 1 JAN: 120
| Monitoring costs | Logistics costs | YEAR 1 JUN: 800 | 800
Total |  |  | 6000 | 6000 | 3200 | 0 | 0 | 8030 | 0 | 0 | 0 | 1910 | 0 | 0 | 25140

## Sheet2
Ex. Rate: 2.7 (TBC by Dri) | £ | R$
Junior Consultancy UK | £ 300 per day | R$ 810 por dia
Senior Consultancy UK | £ 500 per day | R$ 1350 por dia
Simple Consultancy | £ 100 per day | R$ 270 por dia
Senior Consultancy | £ 300 per day | R$ 810 por dia
Interpreters | £ 440 per day per interpreter | R$ 1200 por dia por interprete
Translation equipment | £ 430 per day | R$ 1160 por dia
Junior Instructor UK rates | £ 300 per day | R$ 810 por dia
Senior Instructor UK rates | £ 500 per day | R$ 1350 por dia
Junior National Instructor rates | £ 300 per day | R$ 810 por dia
Senior National Instructor rates | £ 100 per day | R$ 270 por dia
Travel Costs to deliver capacity building course: air tickets, subsistence rates, transport and accomodation | £ 6000 for 3 days | R$ 16800 para 3 dias
Preparation of Support Material for capacity building course | £ 7000 for 5 days work | R$ 18900 para 5 dias de trabalho
Coffee Break | £ 7 per person | R$ 20 por pessoa
Economy International air ticket | £ 1100-1300 per person | R$ 3000-3500 por pessoa
Business International air ticket | £ 1500-1800 per person | R$ 4000-5000 por pessoa
National air ticket | £ 295 per person | R$ 800 por pessoa
Hotel London | £ 150 per day | R$ 400 por dia
Hotel Brasilia | £ 150 per day | R$ 400 por dia
Hotel Rio | £ 220 per day | R$ 600 por dia
Hotel SP | £ 185 per day | R$ 500 por dia
Subsistence Rate London | £ 40 per person per day | R$ 110 por dia
Subsistence Rate Brazil | £ 20-30 per person per day | R$ 60-80 por pessoa por dia
Venue (avoid using) | £ 400 per day | R$ 1080 por dia
Visits Team LO | £ 145 per day | R$ 392 por dia
Project Coordinator | £ 2220 per month | R$ 6000 por mês
Project Assistant | £ 1040 per month | R$ 2800 por mês
Graphic Design for publications | £ 2900-3700 | R$ 8000-10000
Printing of publications | as from £ 3700-7400 | a partir R$ 10000-20000