## Sheet1
GIZ Programme Framework and Finance for Private Sector Development in Tajikistan (FFPSD) | [6 empty] | Date: 02.05.2017
Recommendations of the GREAT Final Evaluation (21.03.2017)
Unit | Indicator | Recommendations by Evaluators | ACCEPTED |  |  | Comment/reasons for partial or lacking acceptance | situation under the successor programme TRIGGER
|  |  | yes | in part | no
Recommendations for successor TRIGGER Programme
1. Addressing Rural Economic Growth and Inequality |  | Poverty
c) An action plan for sustainability of the CC/PG model must also be developed, although (compared to Sarob) a combination of differences of approach and the foreshortened time scale for the development of this CI model will need to be more flexible and consider that it is at a lower point on the learning trajectory than Sarob.
|  | b) Design for any successor programme must include an action plan for Sarob’s transition into a fully autonomous, self-funding organisation within the life of any new programme, an action plan that clearly identifies and puts in place the resources required for this implementation. This will allow the continuation of the CI approach and the inclusion of small farmers in Sarob’s extension programme. |  | x |  | From the very beginning and even before the set-up of Sarob its business model was a key topic. Sarob had and has a business plan with the aim of becoming a fully autonomous, self-funding organisation. The programme supported implementation of the plan. As experience under GREAT showed, inclusion of small farmers in Sarob's extension programme can conflict with Sarob's commercial approach. This is why a village advisory model was developed to reach out to groups of small-holder farmers. | A business and a capacity development plan defining necessary inputs from the programme are available. A village advisory model was developed and is currently under implementation to reach out to groups of small-holder farmers.
|  | c) An action plan for sustainability of the CC/PG model must also be developed, although (compared to Sarob) a combination of differences of approach and the foreshortened time scale for the development of this CI model will need to be more flexible and consider that it is at a lower point on the learning trajectory than Sarob. | x |  |  |  | For the successor programme a producer group approach was developed. During the design stage of the approach it was clearly defined which parts are "programme investments" and which elements can be built on a business model which can work without programme funding in the future.
Gender
|  | A gender strategy, together with the relevant methodological instruments and mechanisms, including timely reporting should be developed and implemented for subsequent programmes. | x |  |  |  | Gender Analysis for the overall programme and specifically for value chains have been drafted. They form the basis of the programme's gender strategy.
2. Linking Local and National Action to Improve the Business Environment |  | a) A new partnership for action that combines national and regional organisations (especially CCIC, key central Departments such as Tax Committee and Economy, but also oblasts, Chamber of Commerce). International partners such as IFC / World Bank, EBRD and DFID should also take part. This Business Environment Action Partnership should have an ability to assemble resources for implementing agreed actions. A further requirement for success will be political support to ensure tangible results are possible. The CCIC Secretariat can play a facilitating and monitoring role in articulating an agreed action programme and managing the implementation process. |  | x |  | It is important to have a proper engagement between development partners and governmental actors on different levels. The donor coordination council (DCC) in Tajikistan was reformed in the beginning of 2017. The interaction with government gained more importance and improving the business environment and investment climate is one of two thematic areas in the private sector development working group. | The successor programme provides the deputy chair of the Economic and Private Sector Development Cluster within the DCC. Policy dialogue is mainly taking place at cluster level. | The successor programme provides the deputy chair of the Economic and Private Sector Development Cluster within the DCC. Policy dialogue is mainly taking place at cluster level. | The successor programme provides the deputy chair of the Economic and Private Sector Development Cluster within the DCC. Policy dialogue is mainly taking place at cluster level.
|  | b) The transformation of Business Associations into membership bodies with parallels with Chambers of Commerce. A vital start-up task will be to assist Business Associations to turn their experience of business issues into analysed proposals for reform that can have a chance of implementation. That type of initiative will need appropriate support, along with a management capability to act in partnership with the proposed Business Environment Action Partnership or others in regional and national administrations. Business Associations should discuss with the national Tajikistan Chamber of Commerce opportunities for fruitful collaboration. | x |  |  |  | The importance of the task is seen and sectoral analyses by business associations were supported in 2016. However, due to a clear value chain focus of the successor programme this rather broad and longer term task can only be addressed to a limited extent.
|  | c) GREAT’s successor to become a facilitator of capacity-building in the business environment process, and for connecting with partners locally, regionally and nationally. A partnership with AMFOT could widen the base of knowledge for defining possible reforms given the practical experience of business environment issues that is available through MFIs. |  |  | x | The successor programme has a "Business Enabling Environment" component. However, it cannot facilitate and support capacity development in the whole business environment process including the micro-finance sector. Given the results logic of the successor programme, attributable changes in the business environment are supposed to have an effect on programme target groups in selected value chains. The proposed objective is too broad to be covered under the successor programme. | Becoming a facilitator of capacity-building in the business environment process is not an objective of the successor programme.
3. Including Inclusiveness in the Logframe |  | The inclusiveness objective of GREAT was inadequately incorporated into Programme design and hence the logframe, as growth appears to have been conflated with poverty alleviation. The twin aims should have separate baselines, targets and indicators. | x |  |  |  | The successor programme aims at inclusive value chain development. On one hand it works with lead companies and supports them to develop, introduce or adapt inclusive business models. On the other hand it works with small holder farmers and supports formation of producer groups. Logframe indicators cover programme results on enterprise and individual level.
4. Integrated Programme Management |  | The structure of GREAT Programme management, with different teams responsible for each output, is not conducive to a holistic approach to Programme implementation. A more integrated approach is needed for any successor programme. | x |  |  |  | In the successor programme a matrix structure is introduced in which teamwork across "outputs" is happening. The results logic also requires joint efforts on output level to achieve common objectives on outcome level.
5. Value for Money – Agreeing and Monitoring VFM Indicators |  | a) Programmes should identify and rigorously maintain a focus on, and monitor, a set of agreed VFM indicators that reflect clear links between the cost of inputs of an activity and its related monetised outputs. Activity-level VFM indicators need to be clearly identified in the text and annexes of programme documentation to support better visibility and accountability for VFM. |  | x |  | Monitoring VFM indicators on activity level does not seem to be the right choice. It is very difficult, only seemingly accurate and/or very costly to link singular activities with results on different levels. However, VFM indicators on intervention level are important for managing, steering, and communicating efficiency of the programme. | The successor programme monitors VFM indicators on intervention level. Interventions are the unit above activity and below output/component level to which a monitoring plan is systematically linked and for which costs are monitored.
|  | b) Key programme documents that need to guide more detailed VFM analysis and reporting are the Business Case, MoU signed with DFID Manager, Inception Report. |  |  |  |  | DFID is not funding the successor programme. This is why the set of documents is not applicable.
|  | c) Activity-based accounting data need not apply to all programme activities, but where identifiable monetised output benefits are anticipated it is essential to be able to evaluate the related input costs. This is particularly so for an economic development and income generation programme. |  | x |  | see above on activity-based VFM indicators
6. Addressing Unexpected Outcomes of GREAT |  | In the successor programme, outcomes which at the time GREAT was designed were unexpected, but which during implementation and evaluation have emerged as actual, should be considered. Two issues should have priority in terms of programme monitoring. a) The first is the emergence of spin-offs, as in the case of the emergence of a beehive manufacturing industry in areas where GREAT and its partners have promoted honey as a commodity for the CC/PG model. | x |  |  |  | Copying and crowding in is covered in the monitoring system of the successor programme.
|  | b) The second is the issue of policy conflict, as in the case of local authorities acting in contravention of national policies such as freedom to farm to the detriment of farmers trying to take advantage of market opportunities. The implication is that monitoring in any successor programme should extend beyond Programme activities, identify such second-generation issues, and promote actions to promote positive spin-offs and counter negative spin-offs. |  |  | x | A risk monitoring mechanism going beyond programme activities and covering policy conflicts was implemented under GREAT. | A risk monitoring system covers the programme and the economic sector level.
7. Identifying Opportunities for Import Substitution |  | Any successor programme should explicitly take cognizance of the fact that that an important component of boosting demand for Tajik products is import substitution. When identifying demand for crops that can be recommended for adoption by farmers, opportunities for import substitution should be identified and promoted, but only where they result from efficiency gains that give domestic produce a competitive edge on the domestic market and/or from raising public awareness of the advantages of the local product. | x |  |  |  | The successor programme contributes to the implementation of Tajikistan's export promotion and import substitution promotion programme. Some of the selected agricultural value chains contribute to import substitution.
8. Agri-Processing – Addressing Industry Wide Constraints |  | Any additional effort to help realise the potential of F&V agri-processing should engage explicitly with industry-wide constraints in the sector (lack of storage, poor quality certification, lack of knowledge and expertise in export marketing) linked to the agricultural value chain. It should take into consideration the activities of other related programmes (especially the EU’s Enhanced Competitiveness of Tajik Agribusiness Project (ECTAP), and F&V projects in neighbouring countries) to facilitate remedial actions, with a special focus on exporting opportunities for Tajik products and / or import substitution. This would also highlight opportunities that extend business activity from primary production into processing. | x |  |  |  | The chosen value chain approach helps identifying and tackling sector-wide constraints.
9. Energy Efficiency –Identifying Further Development Opportunities |  | Given the success of the efficient energy products components (commercial self-sufficiency led to an expansion of beneficiaries, product development and diversification) a consequent recommendation is to redeploy any remaining energy efficiency development resources from GREAT to successor programmes. Maintaining a light monitoring of the component (e.g. seek data returns from a sample of crafts enterprises) for a limited period will help ensure that any further development opportunities in this sector are identified. | x |  |  |  | Further development in the energy efficient housing sector is monitored. The successor programme is currently reviewing further support to the development of energy efficient housing products.
10. Support for the Micro-Finance Industry |  | Closer working with AMFOT is recommended to help take the organisation to the next level of capability as a major player in national and regional policy debates on government, donor and commercial actions that will affect the microfinance industry. This strengthening will be essential for the sustainability of the organisation. |  |  | x | Due to a shift of focus micro finance sector development is not an own objective any more. Facilitation of access to finance for target groups in the selected agricultural value chains is still a task, but organisational capacity development of AMFOT goes beyond that. | Further organisational development support to AMFOT is not foreseen.
11. Improving Financial Products |  | Currently, MFI clients are being offered (with few exceptions) short-term and high interest bearing loans. a) Alleviation of this situation could be helped by assisting MFIs provide more extensive grace periods for loans. b) Consideration might also be given, for example, to the establishment of pilot schemes to provide equity stakes in suitable small enterprises. Potential initiatives, especially on a pilot or temporary basis initially, should be discussed informally with EBRD and EU. They might also be put to the DCCT to seek their inputs to the design of action proposals, and to assemble support and resources. Ideally a multi-organisational approach to the above issues and problems would be initiated. |  | x |  | Coordination with other development partners is actively sought. The role of the successor programme in working with MFIs, however, still has to be found. The issue of short-term and high interest bearing loans can hardly be solved with technical support only. | There is a close coordination with other development partners to faciliate access to finance for target groups in the agricultural value chains.
12. Diversification of Financial Products |  | Establish a programme to help the extension of rural credit unions by linking them to sources of start-up capital. These institutions inherently encourage savings and enhance financial literacy. |  | x |  |  | The successor programme is analysing options to faciliate this link. However, it is too early to say that a programme will be established.
13. Cross Border Revenue – Establishing a Multi-Organisational Effort |  | a) Ensure the sustainability and further development of the cross-border trade infrastructure of administrative arrangements and physical facilities, allowing also for the possibility of the future opening of additional cross-border trade points e.g. with China and – in principle – with Uzbekistan. The realisation of that objective will require governments (Ministries of Trade) in affected countries to maintain the Inter-Government Working Group. In turn that arrangement should support Cross-Border Bi-lateral Commissions, which in turn will need to manage the maintenance of operational structures including Cross-Border Support Centres, Business Groups to help ensure the continuation of matchmaking, physical market maintenance and development. |  |  | x | The successor programme does not have a specific cross-border trade focus, but uses a value chain perspective to identify markets. Export markets in neighboring countries and beyond play an important role. Physical cross-border markets and their operations cannot be supported in the future due to an amended programme focus and limited financial resources. | The Cross-Border Support Centres are still implementing partners of the successor programme. Business/Producer Groups are still supported as well as matchmakings.
|  | b) Provide better documentation, especially on legal rights and obligations for those involved in trade. This might be allied to further training on contracting and legally managing the process of trading across borders. |  | x |  | This is a topic for trade in general, not only for cross-border trade. It is addressed in cooperation with GIZ's regional programme "Trade Facilitation in Central Asia". | Information for enterprises on export procedures are provided in cooperation with GIZ's regional programme "Trade Facilitation in Central Asia".
|  | c) Commission an assessment into the situation of the free trade zones to clarify their physical extent, the types of activity that can be undertaken within them, whether there is a need or capacity for physically enclosing the Zones to protect their integrity as locations where a special legal and regulatory regime applies. In that last context, to clarify the scope and options for the variation in (for example) taxation, regulatory control, access rules for potential users / processors. |  |  | x | The situation of the free economic zones is well known. There is no need for a separate assessment. | The successor programme monitors and assesses potential of free economic zones to contribute to achievement of programme objectives.
|  | d) Consequently, consider a pilot project to develop one of the existing but undeveloped free trade zones on the border of Tajikistan and (probably) Kyrgyzstan. Trade patterns and volumes indicate that there could be advantages in turning some trading into new enterprises as markets have developed e.g. for clothing making-up/sewing, and aspects of agri-processing. The free trade zone could be of more general business and economic development interest where the regulatory environment is not absent but operates in a less intrusive and costly fashion. |  | x |  | Developing a free trade/economic zone is far beyond the scope and the financial possibilities of the successor programme. | The successor programme monitors further development of free economic zones and potential for possibilities of enterprise development based on close trade links.