## £20m workstream update
£20m Workstream Update - 02/12/2016
| 8 Point Plan Workstreams | Activity L1 | Financial Overview £m |  |  |  | Activity Subset | [6 empty] | Activity to Date | Further Activity
|  |  | Budget | AFC | Auth | COWD | Activity L2 |  | Start Date | End Date | Budget | AFC | COWD
| 1 | Unknown delay Jointly undertake the investigation and analysis of unknown delay on the network and agree performance improvement actions. | 0.4 | 0.054 | 0.4 | 0.034 | ü | Arcadis Analysis of Unknown Delay | 2016-08-26 | 2016-12-16 | 0.054 | 0.054 | 0.034 | - Arcadis commissioned to give an independent review into sub-threshold delay - Interviews and observations held - Final report produced outlining short, medium and long-term recommendations | - Arcadis findings to be handed over to the Performance team. - Action plans to be created and implemented based on review, pending feasibility study
[7 empty] | ü | Joint Performance Teams | 2016-08-26 | 2017-02-10 |  |  |  | - Engagement with GTR, Southeastern and NR to plan joint performance teams. | - Logistics (locations, system requirements) to be agreed for joint performance team - Staff to be aligned within the joint team organisation - Pilot of joint performance team to go live - Post pilot benefits review and 'go/no go' decision to continue with joint teams
| 2 | On Time We will improve on time arrival & departure through investing an additional funds in improved train driver diagram scheduling, train crew facilities, depot layout and additional platform staff. | 5.9 | 0.694 |  | 0.014 |  | Project Management | 2016-10-17 | 2017-04-14 | 0.1318 | 0.1318 | 0.0142 | - Project Manager and Project Management Office resource dedicated to the On time workstream - 6 month contract in place | - Ongoing Project and PMO resource in place until April 2017. Extensions to be agreed in February.
[8 empty] | Victoria Station Train Crew Accommodation | 2016-10-24 | 2017-11-27 | 0.15 | 0.15 |  | - Requirements gathering complete - Architect and principle contractor engaged to draw up accommodation plans and plan for surveys to be undertaken in the next 6 weeks to cover GRIP 1-4 | - Initial design of accommodation and layout produced for consultation - Development of a full business case - Lock down of scope and seek authority for GRIP 5-8
[7 empty] | ü | Dispatch - LEAN review | 2016-11-23 | 2016-12-20 | 0.017 | 0.017 |  | - Stations identified for review - Lean specialist appointed and out on the route undertaking analysis of the equipment to identify areas where performance is impacted | - Complete station reviews and consolidate outcomes - Cost schemes and agree works and timescales for delivery
[8 empty] | Selhurst Depot | 2016-10-24 | 2017-05-22 | 0.39563 | 0.39563 |  | - Kick off meeting undertaken - Principle contractor engaged and commencing optioneering work | - Review options post optioneering review - Agree next steps and the GRIP 4-8 delivery
| 3 | Reduced Seasonal Delay We are investing an additional funds to improve autumn and winter resilience preparation at known high risk vegetation delay locations to reduce the risk of performance delays. | 3.5 | 3.399 | 3.399 | 2.557 | ü | Vegetation Clearance | 2016-08-08 | 2017-03-31 | 3.222 | 3.222 | 2.54 | - Have surpassed the original target of 100 miles of vegetation clearance in 10 weeks (including herbicide spraying). Total now stands at 150 miles cleared | - Development of a Vegetation Strategy (applied Autumn standard) - Continued clearance of vegetation across priority 1/2/3/4 sites
[7 empty] | ü | Leaf Fall Teams | 2016-08-08 | 2017-01-27 | 0.177 | 0.177 | 0.017 | - 10 rail head inspection and treatment teams in place for the next 8 weeks
| 4 | Asset Resilience - Renewals We are accelerating specific renewals focussing on assets which have the biggest impact on improving performance including re-railing tunnels and road vehicle bridge strike protection. | 2.9 | 2.9 | 2.9 | 0.51 |  | Project Management |  |  | 0.04 | 0.04 | 0.01 | - Authority for the workstream was granted on 11th November 2016 to proceed with the workstream deliverables | - Raising several contracts with various delivers and ongoing project governance
[7 empty] | ü | Balcombe Tunnel Re-Railing & Con Rail | 2016-10-03 | 2017-01-27 | 0.9 | 0.9 | 0.5 | - 100% of UP road re-railed and 80% of DN road | - DN road to be complete in early Jan-17 and resourcing teams to clear excessive build up of ballast around con-rail to prevent future corrosion & lamintation
[7 empty] | ü | Balcombe Tunnel Shaft Refurbishment Detailed Design | 2016-12-05 | 2017-03-31 | 0.25 | 0.25 |  | - Remit produced and Contract strategy agreed with sponsor. Early engagement held with delivery Contractor and price agreed for delivery of remitted works | - Contract being raised to deliver the Design Works. Aim to request implementation funds at the South East Authority Panel on 3rd March 2017
[8 empty] | Camberwell Grove Tunnel cable management | 2016-12-05 | 2017-03-31 | 0.25 | 0.25 |  | - Remit produced and engaged with a Contractor to price up the works | - Tag and trace survey to identify and remove redundant cables - Provision of management system for remaining to reduce train shoe strikes on loose cables
[7 empty] | ü | Vehicle Incursions - Bridges | 2016-12-05 | 2017-03-31 | 0.85 | 0.85 |  | - Permanent electronic signage installed at Thurlow Park Bridge to reduce bridge strikes - Thurlow Park Bridge strike protection beams in place - Remit produced and Contract strategy agreed with sponsor. Early engagement held with Works Delivery to establish delivery programme | - Carry out implementation works to the high risk bridge strike areas as chosen by the Structures RAM team
[7 empty] | ü | Thurlow Park Bridge Reconstruction Feasibility Study | 2016-12-05 | 2017-04-28 | 0.2 | 0.2 |  | - Remit produced and Contract strategy agreed with sponsor. Early engagement held with delivery Contractor and price agreed for delivery of remitted works | - Contract being raised to deliver Feasibility Works. Aim to request design (and possibly implementation) funds at South East Authority Panel on 31st March 2017
[7 empty] | ü | Contingency and other schemes | TBC | TBC | 0.41 | 0.41 |  | - Contingency and for further works at Balcombe Tunnel as yet to be identified | - Ongoing discussions with the Route Team (Darren Fairley) on tunnel resilience strategy inc. any further works at Balcombe Tunnel
| 5 | Asset Resilience - Removal of unplanned TSRs We will reduce the unplanned TSRs by investing a £2.5m in a proactive predict system & preventative maintenance interventions to remove defects. | 2.5 | 2.5 | 2.5 | 0.474 |  | Project Management | 2016-10-17 | 2017-03-31 | 0.053 | 0.053 | 0.008 | - General project management costs for the delivery team
[8 empty] | Clearance of 57No Legacy TSRs | 2016-10-27 | 2017-01-09 | 0.121 | 0.121 | 0.106 | - TSR to PSR conversions at Sevenoaks, Catford and Otford. Trial Track Quality Gangs at London Bridge DU's | - Ongoing trails with Track Quality Teams in London Bridge
[8 empty] | BAU | 2016-10-27 | 2017-04-28 |  |  |  | - Initial discussions with the DU's to understand current process for BAU | - Develop training programme for ORBIS tool top support DU's to predict TSR's. - Understand current process of implementing TSR's and align with Area Directors
[7 empty] | ü | Predict & Prevent | 2016-10-27 | 2017-06-16 | 1.272 | 1.426 | 0.36 | - Wet bed gang deployed at Ashford DU, Rerailing at Mitre Bridge - 3 No. Crossings procured for Balham and New Points at 3No. Crossings at PTS872 Courthill Junction - Undercutting works carried out at Oxted | - Installation of Crossings at Balham, Ballast undercutter works at Banstead (80 No. Wet beds being removed)
[7 empty] | ü | Purchase Additional Tamper | 2016-11-28 | 2016-12-09 | 0.9 | 0.9 |  | - Additional Tamper to be procured for the TSR removal. This will result in £0.900k worth of planned predict and prevent works that will not be carried out | - Wider discussion with COO to understand long term strategy for tamper and funding for remaining predict and prevent works of which £500k of the £900k has already been priced
| 6 | Delay Per Incident (DPI) We are investing an additional £2.0m to expand our response, rectification and service recovery capability to improve response and fix times. | 2 | 2 | 2 | 0.118 | ü | Project Management | 2016-11-14 | 2017-03-31 |  | 0.076 |  | - General project management costs for the delivery team
[7 empty] | ü | Additional S&T Response teams | 2016-11-14 | 2017-03-31 | 0.274 | 0.474 | 0.118 | - 2 No. 3man(Grade 4,3 and 2) S&T trail response teams have been allocated to Windmill Bridge Junction and Balcombe Tunnel Junction | Discussion with Orpington and London DU's to confirm their requirements for S&T resources. Wider conversation with COO is needed to confirm if 24/7 faulting response teams are required in all locations.
[7 empty] | ü | Hot Spot Storage Facilities | 2016-12-05 | 2017-03-03 | 0.5 | 0.5 |  | - Investment authority granted for Capex work. Contractor Engaged. Site surveys arranged to confirm scope, procure and install containers.
[7 empty] | ü | Additional Strategic Spares | 2016-11-14 | 2017-03-31 |  | 0.35 |  | - All Sussex spares requirements have been obtained and understood. Commence procurement.P1 | Further discussions with Kent DU's to confirm spares and budget. Confirm procurement strategy to take into account any long lead spares that require procurement in advance.
[7 empty] | ü | Trespass & Fatality Prevention | 2016-11-21 | 2017-03-31 |  | 0.5 |  | - Sponsor Remit has been confirmed. Site surveys arranged for finalising scope | Obtain investment authority and engage contracts.
[7 empty] | ü | EIU & BTP Officer | 2016-11-30 | 2017-03-31 |  | 0.05 |  | - Initial conversations with the DU's. Current estimate assumes set up costs only for EIU | Operational costs for EIU to be considered and included within the DU's forecasts as required.
[7 empty] | ü | TOC Contingency Plans | 2016-11-30 | 2017-03-31 |  | 0.05 |  | - Initial conversations with DU's and TOC | Further discussions with Area Directors and TOC to understand strategy computing gaps and implementing improvements.
| 7 | Train Service Network Flow We are investing in additional Train Signal Routing Controllers at Three Bridges to improve train service network flow. | 0.8 |  | 0.15 |  |  | Three Bridges Desk Reconfiguration | 2016-08-26 | 2017-03-31 |  |  |  | - Have enhanced the Three Bridges control area to allow for integrated team (additional desks, hot desks, meeting rooms)
[7 empty] | ü | Additional Signalling Controllers at Three Bridges | 2016-08-26 | 2017-03-31 |  | 0.15 |  | - 3 full time additional signalling positions are now in place (£50k per role) - Reporting mechanisms and measures have been developed to understand the overall effect of signaller decision making | - Continued measurement of train service co-ordination KPIs and benefits of the additional roles - Post benefit review for 'go/no go' decision on increasing the number of additional signallers
| 8 | Customer experience Improved passenger experience through better passenger service, connected information and improved safety. | 2 |  | 1.825 |  |  | Victoria Station Wi-Fi | 2016-10-04 | 2017-03-20 |  | 0.35 |  | Initial survey completed and design received. Currently in stage two 'invasive survey'. Final design will then follow for review and authorisation.
[8 empty] | Customer Information Pods | 2016-10-22 | 2017-02-27 |  | 0.2 |  | Survey completed. Concept design and quote received. Awaiting final design and costs by 09/12 before authorisation.
[8 empty] | Refurbish Ticket office & reception | 2016-11-22 | 2017-03-31 |  | 0.25 |  | Survey completed. Awaiting final design and costs by 09/12 before authorisation.
[8 empty] | Mobility, Way finding & Poster Boards | 2016-10-22 | 2017-03-31 |  | 0.45 |  | Survey completed. Concept design and quote received. Awaiting final design and costs by 09/12 before authorisation.
[8 empty] | CCF Installation | 2016-10-22 | 2017-03-31 |  | 0.22 |  | Approximate quote given by suppliers. Station survey completed 30/11. Station survey to be completed by 16/11.
[8 empty] | Other schemes | 2016-10-22 | 2017-03-20 |  | 0.355 |  | Quotes received for Roving Mics, Seating, TVMs, Joint Uniform, Seating and Customer Service Training. Roving Mic trial 02/12.
|  | TOTAL | 20 | 11.547 | 13.174 | 3.707