## Contents
Key
KPI | Key Performance Indicator
PI | Performance Indicator
Req | Requirements that will help to develop future strategy or performance
DPI | Additional performance indicators specified by the Highways Monitor
Version control
V1.0 | Highways England annual return published July 2018

## PS1 - Making the Network safer
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS1: Making the network safer |  |  | For a definition of the metric and parameters for measuring and monitoring safety performance see Highways England’s Operational Metrics Manual
Performance specification
| Source of baseline | Actual | Annual Baseline | KPI/PI/ Req | Difference | [6 empty] | Notes
KPI
KSI
On-going reduction in Network KSIs to support a decrease of at least 40% by 31 December 2020 against the 2005-9 average baseline | [5 empty] | Validated data for 2017 is not available at year end. Please see Annual Report for more information. Personal injury collision and casualty data for Great Britain’s roads during 2016 was published on 28th September 2017 by the Department for Transport. Headline figures for the Strategic Road Network for the same period showed an overall decrease in the number of reported collisions and casualties. However KSI casualties increased by 12.39% per cent to 2,005 from 1,784 during 2015.
2005-09 | OMM p16 | 2321
2015 | Corporate management information | 1784 | 1750 | KPI | 34 | [6 empty] | [1]
2016 | Corporate management information | 2005 | 1678 | KPI | 327 | [6 empty] | [1]
2017 | DP p30, OMM p16 | X | 1607 | KPI | X | [6 empty] | [1]
2018 | DP p30, OMM p16 | X | 1536 | KPI | X | [6 empty] | [1]
2019 | PS p15,DP p30, OMM p16 | X | 1464 | KPI | X | [6 empty] | [1]
2020 | PS p15,DP p30, OMM p17 | X | 1393 | KPI | X | [6 empty] | [1]
PIs
Incident numbers for motorways
Illustrate the impact of activities undertaken by the Company, and the influence of external factors with regards to making the Network safer. | [5 empty] | There was a total of 56,136 lane impact incidents (on all days, between 6:00 am and 10:00 pm) recorded on the motorway network during 2017-18, this is a 14.26% increase on the 2016-17 total of 49,130.
2014-15 | OMM p25 | 44915
2015-16 | Corporate management information | 46558 |  | PI | [7 empty] | [2]
2016-17 | Corporate management information | 49130 |  | PI | [7 empty] | [2]
2017-18 | Corporate management information | 56136 |  | PI | [7 empty] | [2]
2018-19 | Delivery plan | X |  | PI | [7 empty] | [2]
2019-20 | Delivery plan | X |  | PI | [7 empty] | [2]
Casualty numbers for Motorways
Illustrate the impact of activities undertaken by the Company, and the influence of external factors with regards to making the Network safer. | [5 empty] | Validated data for 2017 is not available at year end. Please see Annual Report for more information. Total casualties on the motorway network decreased by 2.45% from 7,988 in 2015 to 7,792 in 2016. In terms of severity the number of KSI's has increased by 10.56% from 729 in 2015 to 806 in 2016.
2005 | Historic Data | 11200
2006 | Historic Data | X
2007 | Historic Data | X
2008 | Historic Data | X
2009 | Historic Data | X
2010 | Historic Data | 9378
2011 | Historic Data | 8752
2012 | Historic Data | 8211
2013 | Historic Data | 7837
2014 | OMM p25 | 8191
2015 | Corporate management information | 7988 |  | PI | [7 empty] | [3]
2016 | Corporate management information | 7792 |  | PI | [7 empty] | [3]
2017 | Delivery plan | X |  | PI | [7 empty] | [3]
2018 | Delivery plan | X |  | PI | [7 empty] | [3]
2019 | Delivery plan | X |  | PI | [7 empty] | [3]
2020 | Delivery plan | X |  | PI
Casualty numbers for APTR
Illustrate the impact of activities undertaken by the Company, and the influence of external factors with regards to making the Network safer. | [5 empty] | Validated data for 2017 is not available at year end. Please see Annual Report for more information. Total casualties on the APTR increased in 2016 to 8,441 from 8,387 in 2015 (0.64% increase); broken down by APTR category, dual carriageway casualties increased to 6,216 (1.82% more than 2015) and single carriageways decreased to 2,225 (2.63% less than 2015); in terms of severity, the number of KSIs had increased by 13.65% from 1,055 in 2015 to 1,199 in 2016.
2005 | Historic Data | 10503
2006 | Historic Data | X
2007 | Historic Data | X
2008 | Historic Data | X
2009 | Historic Data | X
2010 | Historic Data | 8644
2011 | Historic Data | 8968
2012 | Historic Data | 8462
2013 | Historic Data | 8251
2014 | OMM p33 | 8623
2015 | Corporate management information | 8387 |  | PI | [7 empty] | [3]
2016 | Corporate management information | 8441 |  | PI | [7 empty] | [3]
2017 | Delivery plan | X |  | PI | [7 empty] | [3]
2018 | Delivery plan | X |  | PI | [7 empty] | [3]
2019 | Delivery plan | X |  | PI | [7 empty] | [3]
2020 | Delivery plan | X |  | PI | [7 empty] | [3]
IRAP: International Road Assessment Programme
IRAP based road safety investigations, developed in conjunction with the Department, to feed into subsequent Route Strategies. Illustrate the impact of activities undertaken by the Company, and the influence of external factors with regards to making the Network safer. % of Network that has achieved Eurorap 3*, with 90% of travel on the SRN on roads with a safety rating of EuroRAP 3* (or equivalent) by end of 2020. | [5 empty] | Highways England has commenced development work with the Road Safety Foundation using the IRAP Safety Rating Model (International Roads Assessment Programme). This model is based on available asset information to code the network and determine a baseline safety star rating; it determines the impact of planned investments over the road period on this star rating. Based on the model used in 2010 (v1.0), on which the target was established, we have undertaken an assessment of the network which indicates that we will achieve the 90% target of travel on 3 star roads, this assessment includes a review of our 2020 and 2025 networks and reflects our planned major infrastructure investment programmes. We are currently reviewing the impact of latest iRAP model and have identified a range of areas where the model can be further developed and improved.
2015-16 | Corporate management information | N/A | N/A | PI | N/A | [6 empty] | [4]
2016-17 | Delivery plan - baseline score | X | [X] | PI | X | [6 empty] | [4]
2017-18 |  | X | [X] | PI | X | [6 empty] | [4]
2018-19 |  | X | [X] | PI | X | [6 empty] | [4]
2019-20 | DP p31, OMM P36 | X | 90% | PI | X | [6 empty] | [4]
AFR (Accident Frequency Rate) of construction and maintenance workers
This is the ratio of the number of Reporting of Injuries, Diseases & Dangerous Occurrences Regulation 2013 (RIDDOR) reportable personal injury accidents and fatalities in a population, to the hours worked by that population, and expressed per 100,000 hours | [5 empty] | The combined AFR for suppliers undertaking maintenance works and for suppliers undertaking Major Projects works was 0.12 during 2017-18. The AFR fell from the start of the year to a low of 0.07 in July, however since that period it has risen to 0.12. Example contributory factors include: • An increase of incidents involving slips and trips, manual handling and falls from vehicles within the maintenance community. • Third party (road) users involved in vehicle collisions with our suppliers. The supply chain workforce is a core part of our safety vision and value statements in our Health and Safety five year plan, visibly demonstrating our commitment to further improvements in this area. Notable examples include: • Developing and implementing a Supply Chain Safety Maturity Matrix, to be completed at various stages in the Supply Chain Lifecycle, which was developed with input from the supply chain to reflect best practice in the industry, and provided guidance on how to fully utilise it. • Hosting Health and Safety Awards and Forums regularly over the financial year, to allow for sharing recognition of the best health and safety practice in the supply chain, and to be able to discuss constructive improvements where possible.
2009-10 | Historic Data | 0.24
2010-11 | Historic Data | 0.17
2011-12 | Historic Data | 0.18
2012-13 | Historic Data | 0.12
2013-14 | Historic Data | 0.14
2014-15 | OMM p45 | 0.14
2015-16 | Corporate management information | 0.15 |  | PI | 0.15
2016-17 | Corporate management information | 0.11 |  | PI | 0.11
2017-18 | Corporate management information | 0.12 |  | PI | 0.12
2018-19 |  | X |  | PI | X
2019-20 |  | X |  | PI | X
AFR (Accident Frequency Rate) of Customer Operations Directorate: Is the ratio of the number of Reporting of Injuries, Diseases & Dangerous Occurrences Regulation 2013 (RIDDOR) reportable personal injury accidents and fatalities in a population, to the hours worked by that population, and expressed per 100,000 hours | [5 empty] | Highways England has seen an encouraging steady decrease in recent months in the AFR for our Customer Operations team from a high of 0.62 in June 2017 with a year-end value of 0.43. The majority of the incidents have been as a consequence of slips and trips, when attending road accidents and incidents on the network, generally in a mixture of demanding physical and environmental conditions. Workforce safety is at the core of our vision and values, and Health and Safety remains a required component of role profiles and employee objectives.
2011-12 | Historic Data | 0.43
2012-13 | Historic Data | 0.63
2013-14 | Historic Data | 0.34
2014-15 | OMM p44 | 0.36 |  | PI
2015-16 | Corporate management information | 0.77 |  | PI | 0.77
2016-17 | Corporate management information | 0.51 |  | PI | 0.51
2017-18 | Corporate management information | 0.43 |  | PI | 0.43
2018-19 |  | X |  | PI | X
2019-20 |  | X |  | PI | X
|  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Cumulative |  | Number of incidents resulting in KSI annual | Number of incidents resulting in KSI cumulative
Casualties numbers and contributory* factors for motorway (OMM p21)
Illustrate the impact of activities undertaken by the Company, and the influence of external factors with regards to making the Network safer. |  | The contributory factor data follows on from the performance indicators of casualties on the motorways and all-purpose trunk road network. We will analyse the validated 2017 personal injury collision and casualty data once available later in 2018; including contributory factors, this will inform our Reported Road Casualties on the SRN Report.
Factor (Reported Road Casualties on the SRN 2013) | Number
Failed to look properly | 1 | 182 | 215 | X | X | X | X | 397 | PI | X | X | [5]
Loss of control | 2 | 155 | 167 | X | X | X | X | 322 | PI | X | X | [5]
Failed to judge other person's path or speed | 3 | 142 | 160 | X | X | X | X | 302 | PI | X | X | [5]
Poor turn or manoeuvre | 4 | 53 | 67 | X | X | X | X | 120 | PI | X | X | [5]
Careless, reckless or in a hurry | 5 | 66 | 61 | X | X | X | X | 127 | PI | X | X | [5]
Swerved | 6 | 54 | 59 | X | X | X | X | 113 | PI | X | X | [5]
Fatigue | 7 | 72 | 73 | X | X | X | X | 145 | PI | X | X | [5]
Following too close | 8 | 64 | 52 | X | X | X | X | 116 | PI | X | X | [5]
Sudden braking | 9 | 64 | 61 | X | X | X | X | 125 | PI | X | X | [5]
Slippery road (due to weather) | 10 | 48 | 66 | X | X | X | X | 114 | PI | X | X | [5]
Travelling too fast for conditions | 11 | 50 | 50 | X | X | X | X | 100 | PI | X | X | [5]
Impaired by alcohol (driver or rider) | 12 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Illness or disability, mental or physical | 13 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Distraction in vehicle | 14 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Other - Please specify below | 15 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Exceeding speed limit | 16 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Aggressive driving | 17 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Learner or inexperienced driver/rider | 18 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Rain, sleet, snow or fog | 19 | X | X | X | X | X | X | 0 | PI | X | X | [5]
Distraction outside vehicle | 20 | X | X | X | X | X | X | 0 | PI | X | X | [5]
|  | 950 | 1031 | 0 | 0 | 0 | 0 | 1981 | PI | 0 | 0 | [5]
Casualties numbers and contributory factors for APTR (OMM P31) (Note that the Performance Specification refers to "causation factors") |  | The contributory factor data follows on from the performance indicators of casualties on the motorways and all-purpose trunk road network. We will analyse the validated 2017 personal injury collision and casualty data once available later in 2018; including contributory factors, this will inform our Reported Road Casualties on the SRN Report.
Illustrate the impact of activities undertaken by the Company, and the influence of external factors with regards to making the Network safer.
Factor (Reported Road Casualties on the SRN 2013) | Number
Failed to look properly | 1 | 341 | 340 | X | X | X | X | 681 | PI | X | X | [6]
Loss of control | 2 | 198 | 201 | X | X | X | X | 399 | PI | X | X | [6]
Failed to judge other person's path or speed | 3 | 226 | 230 | X | X | X | X | 456 | PI | X | X | [6]
Poor turn or manoeuvre | 4 | 170 | 146 | X | X | X | X | 316 | PI | X | X | [6]
Careless, reckless or in a hurry | 5 | 156 | 165 | X | X | X | X | 321 | PI | X | X | [6]
Swerved | 6 | 64 | 71 | X | X | X | X | 135 | PI | X | X | [6]
Fatigue | 7 | 73 | 71 | X | X | X | X | 144 | PI | X | X | [6]
Following too close | 8 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Sudden braking | 9 | 63 | 58 | X | X | X | X | 121 | PI | X | X | [6]
Slippery road (due to weather) | 10 | 51 | 75 | X | X | X | X | 126 | PI | X | X | [6]
Travelling too fast for conditions | 11 | 86 | 85 | X | X | X | X | 171 | PI | X | X | [6]
Impaired by alcohol (driver or rider) | 12 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Illness or disability, mental or physical | 13 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Distraction in vehicle | 14 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Other - Please specify below | 15 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Exceeding speed limit | 16 | 67 | 74 | X | X | X | X | 141 | PI | X | X | [6]
Aggressive driving | 17 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Learner or inexperienced driver/rider | 18 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Rain, sleet, snow or fog | 19 | X | X | X | X | X | X | 0 | PI | X | X | [6]
Distraction outside vehicle | 20 | X | X | X | X | X | X | 0 | PI | X | X | [6]
|  | 1495 | 1516 | 0 | 0 | 0 | 0 | 3011 | PI | 0 | 0 | [6]
Other monitoring requirements |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
We will analyse the validated 2017 personal injury collision and casualty data, once available later in 2018; including location of KSIs, this will inform our Reported Road Casualties on the SRN Report.
Location of KSI
East |  | 288 | 314 | X | X | X | X |  | DPI |  |  | [7]
London and south east |  | 530 | 611 | X | X | X | X |  | DPI |  |  | [7]
South west |  | 202 | 225 | X | X | X | X |  | DPI |  |  | [7]
Midlands |  | 359 | 395 | X | X | X | X |  | DPI |  |  | [7]
North west |  | 191 | 201 | X | X | X | X |  | DPI |  |  | [7]
Yorkshire and northeast |  | 214 | 259 | X | X | X | X |  | DPI |  |  | [7]
|  | 1784 | 2005 | 0 | 0 | 0 | 0 |  | DPI |  |  | [7]
Notes and commentary
[1] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[2] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[3] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[4] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[5] Explain significant year on year variances.
[6] Explain significant year on year variances.
[7] Explain significant year on year variances. Where one or two areas of the SRN are driving down performance, explanation of the variance should be disaggregated and published.
[X] HE and ORR to consider reporting this data once appropriate strategies and/or reporting has been developed.

## PS2 - User satisfaction
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS2: Improving user satisfaction |  | For a definition of the metric and parameters for measuring and monitoring User satisfaction see Highways England’s Operational Metrics Manual
Performance specification
| Source of baseline | Actual | Annual baseline | KPI/PI/ Req | Difference |  |  |  | Notes
KPI
NRUSS score
Achieve a score of 90% by 31 March 2017 and then maintain or improve it | [5 empty] | The overall cumulative score for March 2018 is 88.73%, providing our final end of year satisfaction score. In comparison to March 2017 (89.11%) the overall score is 0.38% lower. From May 2017 onwards, the overall cumulative score has seen a variance of 0.77% between the highest score in June 2017 (89.38%) and the lowest in November 2017 (88.61%). The overall in-month score when compared to March 2017 (87.97%), is up by 0.76%. In order to improve the customer satisfaction Highways England has targeted specific areas. Highways England continue to make improvements to the Variable Message Signs, implemented changes to several diversion routes based on customer feedback, continued management of top 25 litter spots, roll out best practise guidelines to the supply chain for roadworks, undertaken feasibility study of running 55mph in narrow lanes, running customer forums for our largest road schemes. To further support and improve the road user satisfaction score, and our customers' overall experience, we are launching the overarching Customer Service Strategic Plan 2018 - 2023 and the internal Customer Service Delivery Plan 2018-19. Transport Focus piloted the NRUSS replacement, the Strategic Roads User Survey (SRUS), during 2017-18. The new survey started in April 2018, carrying out face-to-face interviews with around 8,000 drivers who will be asked to identify their last journey within the last four weeks on the Strategic Road Network.
2011-12 | Historic Data | 91.48%
2012-13 | OMM p51, Historic Data | 90.7%
2013-14 | OMM p51, Historic Data | 89.6%
2014-15 | OMM p51, Historic Data | 88.51%
2015-16 | Corporate management information | 89.32% | 90% | KPI | -0.68 |  |  |  | [1]
2016-17 | Corporate management information | 89.11% | 90% | KPI | -0.0089 |  |  |  | [1]
2017-18 | Corporate management information | 88.73% | 90% | KPI | -0.0127 |  |  |  | [1]
2018-19 | Performance specification | X | 90% | KPI | X |  |  |  | [1]
2019-20 | Performance specification | X | 90% | KPI | X |  |  |  | [1]
PIs
Performance of factors that influence user satisfaction
Journey time
2011-12 | Historic Data | 91% |  |  |  | Customer satisfaction with journey time has seen an improvement to 87.83% for 2017-18. Satisfaction around journey time, for both motorways and trunk roads, was mainly attributed to customers not encountering any delays. A high point of customer satisfaction with journey time was achieved in September 2017 reaching of 88.28% (cumulative). 2016-17, we trialled increasing speed limits through our roadworks to 55 or 60mph on several schemes, where it was safe to do so. 2017-18, we expanded our trials by using biometrics to further understand our customers’ experience. We provided 36 participants with dash cams and watches incorporating heart rate monitors and GPS trackers, to monitor their reaction to driving at 60mph (M5 junctions 4a to 6) and 55mph (M3 junctions 33 to 4a). Participants from both trials exhibited a decrease in the average heart rate - 60% in the 60mph trial zone and 56% in the 55mph trial zone.
2012-13 | Historic Data | 88.98%
2013-14 | Historic Data | 88.51%
2014-15 | Historic Data | 87%
2015-16 | Corporate management information | 87.92% | 90% | PI | -2.08%
2016-17 | Corporate management information | 87.25% | 90% | PI | -2.75%
2017-18 | Corporate management information | 87.83% | 90% | PI | -2.17%
2018-19 |  | X | [X] | PI | X
2019-20 |  | X | [X] | PI | X
Roadwork management
2011-12 | Historic Data | 69.44% |  |  |  | Satisfaction with Roadworks Management continues to remain low at 62.90%, but remains consistent with 2016-17. Overall the main causes of dissatisfaction for customers around roadworks, on both motorways and trunk roads, that there was a lack of information regarding the roadworks and a lack of visible work being undertaken. Highways England Launched the ‘Roadworks: a customer view’ guidance document, which sets out what customers want. The guide sets out 20 key principles that our project teams and supply chain will focus on and review annually to ensure that known customer pain points are considered when agreeing, implementing and managing traffic management plans.
2012-13 | Historic Data | 66.03%
2013-14 | Historic Data | 71.73%
2014-15 | Historic Data | 66.95%
2015-16 | Corporate management information | 65.09% | 90% | PI | -24.91%
2016-17 | Corporate management information | 62.88% | 90% | PI | -27.12%
2017-18 | Corporate management information | 62.9% | 90% | PI | -27.1%
2018-19 |  | X | [X] | PI | X
2019-20 |  | X | [X] | PI | X
General upkeep
2011-12 | Historic Data | 92.67% |  |  |  | Satisfaction with General Upkeep ends the year at 88.71%, when compared to March 2017 (89.79%), is 1.08% lower. The most common cause of dissatisfaction on the motorways: litter, potholes, debris on the verges - which was perceived as potentially distracting to drivers and bad road surfaces. Highways England continues to focus on clearing the top 25 litter hotspots across the network. We are also undertaking a trial of funnel bins at motorway service areas to make it easier for heavy goods vehicle drivers, in particular, to dispose of litter before they enter onto the network.
2012-13 | Historic Data | 90.97%
2013-14 | Historic Data | 89.76%
2014-15 | Historic Data | 90.38%
2015-16 | Corporate management information | 89.52% | 90% | PI | -0.48%
2016-17 | Corporate management information | 89.79% | 90% | PI | -0.21%
2017-18 | Corporate management information | 88.71% | 90% | PI | -1.29%
2018-19 |  | X | [X] | PI | X
2019-20 |  | X | [X] | PI | X
Signage
2011-12 | Historic Data | 91.83% |  |  |  | The information & signage cumulative score of 92.10%, when compared to March 2017 (92.63%), is 0.53% lower. All regions, except Yorkshire & North East (+0.60%), the Midlands (+0.47%) and the East (+1.45%) have seen a decrease in their information & signage cumulative scores, when compared to March 2017. Highways England continue to undertake work to improve legends based on customer feedback and training of Regional Control Centre operatives for setting signals. We continue to review Variable Signs and Signals policy to give greater visibility and clarity of key information, from a safety and customer perspective.
2012-13 | Historic Data | 91.76%
2013-14 | Historic Data | 90.5%
2014-15 | Historic Data | 89%
2015-16 | Corporate management information | 91.99% | 90% | PI | 1.99%
2016-17 | Corporate management information | 92.63% | 90% | PI | 2.63%
2017-18 | Corporate management information | 92.1% | 90% | PI | 2.1%
2018-19 |  | X | [X] | PI | X
2019-20 |  | X | [X] | PI | X
Safety
2011-12 | Historic Data | 92.24% |  |  |  | Cumulative score for safety is 90.49%, when compared to March 2017 (91.56%), is 1.07% lower. All regions, except Yorkshire & North East (+0.17%) and the Midlands (+1.27%) saw their cumulative scores for safety decrease, when compared to March 2017. The main causes of concern across the regions and SRN were other drivers' behaviour (more notably mobile phone usage) and adverse weather conditions. Since April 2015 Highways England have funded and coordinated the use of an unmarked HGV tractor unit that police forces use to patrol the strategic road network to capture distracted HGV drivers using mobile phones, laptops or reading/cooking whilst driving.
2012-13 | Historic Data | 94.39%
2013-14 | Historic Data | 92.5%
2014-15 | Historic Data | 91.81%
2015-16 | Corporate management information | 92.33% | 90% | PI | 2.33%
2016-17 | Corporate management information | 91.56% | 90% | PI | 1.56%
2017-18 | Corporate management information | 90.49% | 90% | PI | 0.49%
2018-19 |  | X | [X] | PI | X
2019-20 |  | X | [X] | PI | X
Requirements
Activities undertaken to maintain or improve user satisfaction.
Demonstrate what activities have been taken, and how effective they have been, to maintain and improve user satisfaction. | Corporate management information | For 2017-18, we developed and implemented a Customer Service Plan, which enabled us to focus our efforts with the intention to improve customer experience. Initiatives within the Customer Service Plan that were successfully completed: • Raise Supply Chain customer service understanding and capability. Develop and roll out a supplier engagement programme. • Roll out best practise guidelines to the supply chain for roadworks e.g. decluttering and mobile VMS. • Undertake feasibility of running 55mph in narrow lanes. • Carried out customer audits on several major schemes, assessed information provision, perception of the scheme and overall safety. • Review of Variable Signs and Signals policy from a safety and customer perspective. • Roll out enhanced APTR virtual patrolling by tying media reports into our traffic data to get a better picture of APTR real-time performance. • Run customer forums for our largest road schemes, to engage with customers who are affected by our works. • Launched the ‘Roadworks: a customer view’ guidance document, which sets out what customers want. The guide has been positively received by project teams and will be used to help improve customers’ experience of roadworks. • Following a successful trial, a number of window high funnel bins at Lymm truck stop in the North West have been installed. Funding to continue rollout of the funnel bins to other locations has been obtained. • Continued management of top 25 litter hotspots to improve the appearance of the network. We have a dedicated team who manage our day to day engagement with Transport Focus, including the investigations to value and prioritise work for customers. We also have a new structure in place internally which consists of four Customer Service Directors, who are part of the Executive Customer Service Group. This group owns the customer service plan and delivery schedule. To further support and improve the road user satisfaction score, and our customers' overall experience, we are launching the overarching Customer Service Strategic Plan 2018 - 2023 and the internal Customer Service Delivery Plan 2018-19.
Support Transport Focus as it develops replacements, by April 2016, for the NRUSS
Feedback from TF on engagement | Corporate management information | Transport Focus has been working with the Company to understand SRN users’ key priorities that influences customer satisfaction. Key areas of work are:- • Collaborative insight project with Transport Focus to better understand SRN users’ views on road surface quality. • Improving SRN user experience during significant delays incidents. • Getting the basics right (maintenance). • Improving journey information. • Better understanding and responding to the needs of the freight and logistics sector. • Better understanding and responding to the needs of non-motorised users. •Discussions continue on our response to the incidents and roadworks report and improving roadworks information. •We have worked with Transport Focus in development of Strategic Road User Survey (SRUS) for more acurate customer datisfaction measuing tool. • We have worked collaboratively with Transport Focus to shape and prioritise the 2018-19 customer service plan. We have attended: • The quarterly Transport Focus Road User Panel to report on the business and answer questions from major transport stakeholder groups. We have a team who work on a day to day basis to engage with Transport Focus and who support with this relationship.
Other monitoring requirements |  | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
NRUSS score for motorways and All Purpose Trunk Roads | [7 empty] | Performance has decreased between 2016-17 and 2017-18 for All Purpose Trunk Roads, with minor decrease of 0.17% to 90.10%. Motorways have fallen by 0.58% to a score of 87.51%.
Motorways |  | 88.27% | 89.14% | 88.09% | 87.51% | X | X |  | [2]
APTR |  | 88.81% | 89.53% | 90.27% | 90.1% | X | X |  | [2]
NRUSS score based on location
East | Corporate management information | 92.02% | 91.75% | 91.05% | 90.27% | X | X | The 2017-18 end of year scores the Midlands (+1.75%), the M25 (+0.59%) Yorkshire & North East (+0.32) and the South East (+2.35%) are the only regions to have increased their cumulative scores, when compared to March 2017. The South East and East are the only regions to remain above the 90% target. | [3]
South East | Corporate management information | 88.41% | 89.07% | 88.46% | 90.81% | X | X |  | [3]
M25 | Corporate management information | 88.83% | 89.52% | 89.32% | 89.91%
South west | Corporate management information | 86.16% | 91.1% | 90.83% | 88.84% | X | X |  | [3]
Midlands | Corporate management information | 87.21% | 89.05% | 86.84% | 88.59% | X | X |  | [3]
North west | Corporate management information | 83.09% | 83.54% | 82.99% | 77.85% | X | X |  | [3]
Yorkshire and northeast | Corporate management information | 88.99% | 86.09% | 87.99% | 88.31% | X | X |  | [3]
Notes and commentary
[1] Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[2] Explain significant year on year variances. Compare the scores on Motorways to APTR
[3] Explain significant year on year variances. Where one or two areas of the SRN are driving down performance, explanation of the variance should be disaggregated and published.
[X] HE and ORR to consider reporting this data once appropriate strategies and/or reporting has been developed.

## PS3 - Traffic Flow
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS3: Supporting the smooth flow of traffic |  | For a definition of the metric and parameters for measuring and monitoring the flow of traffic see Highways England’s Operational Metrics Manual
Performance specification
Annual
| Source of baseline | Actual | baseline | KPI/PI/ Req | Difference |  |  |  | Notes
KPIs
Network availability
Maximise lane availability so that it does not fall below 97% in any one rolling year | [5 empty] | During 2017-18, Highways England achieved a score 98.26% of the network available to road users, exceeding our target of 97%. Annual performance was slightly lower than 2016-17. Highways England has increased the volume and percentage of works undertaken at night when there are lower traffic volumes reduces our impact on road users. Highways England continue to minimise road closures to keeping our customers moving. To this end, we have increased the proportion of road works carried out at night time when there are lower traffic volumes. We have also implemented more efficient ways of working to make better use of lane closures, including using shorter lengths of road works. The roll out of our new roadworks mapping tool allows us to plan roadworks more effectively to reduce the impact on our customers. Similarly, we have continued our trial increasing speed limits through roadworks to improve journey times. have implemented more efficient ways of working to make better use of lane closures, including using shorter lengths of road works.
2014-15 | Historical Data | 98.46%
2015-16 | Corporate management information | 98.4% | 97% | KPI | 1.4% |  |  |  | [1]
2016-17 | Corporate management information | 98.41% | 97% | KPI | 1.41% |  |  |  | [1]
2017-18 | Corporate management information | 98.26% | 97% | KPI | 1.26% |  |  |  | [1]
2018-19 | Performance specification | X | 97% | KPI | X |  |  |  | [1]
2019-20 | Performance specification | X | 97% | KPI | X |  |  |  | [1]
Incident management
At least 85% of all motorway incidents should be cleared within one hour in any one rolling year | [5 empty] | During 2017-18 Highways England met the target of clearing at least 85% of incidents on the motorway within an hour, achieving 87.94% It is 1.97% higher than the previous year and reflects the work undertaken across the organisation and Operations in particular to improve performance for example through intelligence led targeting of resources. We have responded to over 56,136 incidents during the tvelve months of the current financial year, an increase of over 14% on the corresponding period of the previous financial year. Highways England Traffic Officer Service amends its patrol strategies based on the local data, ensuring that traffic officers can be more effectively deployed to clear incidents, particularly at key time periods. While these are positive results, we know that we need to keep doing more to minimise the impact on our customers’ journey times.
2011-12 | Historic Data | 86.9%
2012-13 | Historic Data | 84.8%
2013-14 | Historic Data | 85.7%
2014-15 | Historic Data | 86.2%
2015-16 | Corporate management information | 85.96% | 85% | KPI | 0.96%
2016-17 | Corporate management information | 85.93% | 85% | KPI | 0.93%
2017-18 | Corporate management information | 87.9% | 85% | KPI | 2.9%
2018-19 | Performance specification | X | 85% | KPI | X
2019-20 | Performance specification | X | 85% | KPI | X
PIs
Planning Time Index (PTI)
This measure is designed to indicate how much additional time road users need to allow to ensure they arrive on time. It highlights roads where very slow journeys are encountered. This measure is the ratio of the 95%ile journey time and the free-flow journey time. | [5 empty] | The national PTI for 2017-18 was 1.74, remains stable in comraison to 2016-2017. * Currently a temporary methodology is being used to calculate the measure that uses speed limit as a proxy for free-flow speed, so all historical figures here have been reprocessed using this methodology as last year.
2009-10 | Reprocessed historical data* | 1.5481
2010-11 | Reprocessed historical data* | 1.5391
2011-12 | Reprocessed historical data* | 1.5009
2012-13 | Reprocessed historical data* | 1.539 | .
2013-14 | Reprocessed historical data* | 1.5716
2014-15 | Reprocessed historical data* | 1.6398
2015-16 | Corporate management information | 1.6634 | 1.64 | PI | 0.2
2016-17 | Corporate management information | 1.68 | 1.64 | PI | 0.04
2017-18 | Corporate management information | 1.74 | 1.64 | PI | 0.1
2018-19 | Delivery plan | X | [X] | PI | X
2019-20 | Delivery plan | X | [X] | PI | X
Traffic on the SRN - Vehicle miles travelled
Suite of indicators to illustrate the impact on traffic flow, of the activities undertaken by the Company, and the influence of other external factors, including at a minimum, reliability of journey times | [5 empty] | Traffic (total vehicle miles) on the SRN is collected via automatic and manual counters. The amount of traffic on the SRN is reported retrospectively on an annual basis via the validated count data, which is released by the DfT. The annual report entitled ‘Road Traffic Estimates in Great Britain’ provides a breakdown of the data by motorway and APTR. In 2017 traffic on the SRN increased by 2.1%, to a total of 94.1 billion vehicle miles. Note: Between 1999 and 2012, the length of the SRN reduced by 12.6%.This was a result of the detrunking prgramme, where the management of parts of the SRN transferred from Highways England (then Highways Agency) to the relevant local authorities.
Amount of Traffic (total vehicle miles on the SRN - per billion vehicle miles)
2000 | Historical Data | 88.8
2001 | Historical Data | 87
2002 | Historical Data | 86.6
2003 | Historical Data | 84.1
2004 | Historical Data | 84.4
2005 | Historical Data | 83.3
2006 | Historical Data | 85
2007 | Historical Data | 85.2
2008 | Historical Data | 84.9
2009 | Historical Data | 84.3
2010 | Historical Data | 83.1
2011 | Historical Data | 84.5
2012 | Historical Data | 84.7
2013 | Historical Data | 85.5
2014 | https://www.gov.uk/government/statistical-data-sets/tra42-traffic-based-on-a-static-road-management-status | 87.3
2015 | https://www.gov.uk/government/statistical-data-sets/tra42-traffic-based-on-a-static-road-management-status | 89.7
2016 | https://www.gov.uk/government/statistical-data-sets/tra42-traffic-based-on-a-static-road-management-status#history | 91.9 |  | PI
2017 | https://www.gov.uk/government/statistics/road-traffic-estimates-in-great-britain-2017 | 94.1 |  | PI
2018 | Delivery plan | X |  | PI
2019 | Delivery plan | X |  | PI
2020 | Delivery plan | X |  | PI
Acceptable Journeys
A high proportion of journeys above the threshold journey time will reflect road performance that is largely unaffected by significant congestion or incident effects. Percentage of the journeys faster than 4/3 of the free flow. | [5 empty] | In 2017-18 82.45% of journeys were classified as acceptable, this is a 1.01% decrease on the 2016-2017 figure of 83.46%. Typically over the financial year, in month performance would be bester on a weekends due to lower traffic volumes, and the performance scoring days occured during school holidays or days with very poor weather. * Currently a temporary methodology is being used to calculate the measure that uses speed limit as a proxy for free-flow speed, so all historical figures here have been reprocessed using this methodology.
2009-10 | Reprocessed historical data* | 85.75%
2010-11 | Reprocessed historical data* | 86.65%
2011-12 | Reprocessed historical data* | 87.74%
2012-13 | Reprocessed historical data* | 87.08%
2013-14 | Reprocessed historical data* | 85.81%
2014-15 | Reprocessed historical data* | 83.44%
2015-16 | Corporate management information | 83.58% | 83.44% | PI | 0.1387%
2016-17 | Corporate management information | 83.46% | 83.44% | PI | 0.02%
2017-18 | Corporate management information | 82.45% | 83.44% | PI | -0.99%
2018-19 | Delivery plan | X | [X] | PI | X
2019-20 | Delivery plan | X | [X] | PI | X
Average Speed (Miles per Hour)
2009-10 | Reprocessed historical data* | 60.7759 |  |  |  | This metric is measured using individual car journeys across all times of day and night. The average speed across the SRN for 2017-18 was 58.36 mph. This is a small decrease after 2016-17 increase score. * Currently a temporary methodology is being used to calculate the measure that uses speed limit as a proxy for free-flow speed, so all historical figures here have been reprocessed using this methodology.
2010-11 | Reprocessed historical data* | 61.1884
2011-12 | Reprocessed historical data* | 61.879
2012-13 | Reprocessed historical data* | 61.3359
2013-14 | Reprocessed historical data* | 60.7148
2014-15 | Reprocessed historical data* | 59.4117
2015-16 | Corporate management information | 59.3279 | 59.41 | PI | -0.08209
2016-17 | Corporate management information | 59.45 | 59.41 | PI | 0.04
2017-18 | Corporate management information | 58.36 | 59.41 | PI | -1.05
2018-19 | Delivery plan | X | [X] | PI | X
2019-20 | Delivery plan | X | [X] | PI | X
Requirements
Impact of activities undertaken to minimise inconvenience to road users through road works
Demonstrate what activities have been taken, and how effective they have been, to maintain and improve user satisfaction. |  | Through different working practices and innovative techniques Highways England can minimise the impact of work on customers. Examples include: Engagement Forums - Customer Engagement Forums are now underway on five of our major schemes. We undertook engagement activities with our M1 J23a-25 forum to better understand customer experience of diversion routes. Roadworks: A customer view - We presented our ‘Roadworks: A customer view’ guidance to Transport for Greater Manchester and agreed to work with them to embed the customer principles into the planning, design and communication of all roadworks schemes in the Greater Manchester area, including smart motorway schemes and local authority works. The lessons learnt from this will be used to inform Roadworks: A customer view version 2. Incursions - We have completed our second virtual reality trial to test the effectiveness of incursion mitigation measures which yielded a number of qualitative observations. The observations are currently being analysed and we will publish a briefing note of the findings in March. In February we began the trial of the Intellicone incursion warning system on the A14 major scheme. The trial is expected to run until March 5 and data is currently being collected for analysis by end of March. We have agreed the deployment location of the Redflex camera system and have started to collect baseline data in advance of deployment in the first week of March. Dynamic Roadworks - We have an aspiration to enable a speed limit of 60mph when the workforce isn’t present (such as overnight / on Sundays). As part of this we will test 2 primary scenarios: one where traffic management is designed to 70mph standards, but is reduced to 50mph in the day for other safety reasons, such as works traffic merging. The second scenario is to develop a new standard for 60mph running in narrow lanes. As part of this, we have completed simulation trials for car and HGV drivers in narrow lanes at 60mph (and 55mph).
Working effectively with partners to improve incident response
Demonstrate that it is working effectively with its partners to improve incident response. |  | We adopt a continuous improvement approach to how we manage incidents. By constantly looking at ways we can improve our incident response and clearance times we allow quicker access to casualties and reduce the likelihood of secondary incidents occurring. Our current activities in this area are grouped into four main areas: We have increased our operational capability and flexibility through initiatives such as mandatory single crew training for all Traffic Officers to have the potential to provide better coverage for incident management on the network. Within region it is then decided how to best deploy resource to meet operational requirements. Whilst there are safety considerations to be made when deploying single crew Traffic Officers to different road environments and incident types, we review these on a regular basis to ensure they are appropriate e.g. we are currently reviewing the use of single crew Traffic Officers on ALR sections of motorway. Better collaboration - In each of the seven regions regular roads responder meetings are now held between Highways England and the emergency services in their areas to ensure more joined-up working tailored to each particular region. Better Planning and Knowledge Management - Regional rosters are now in place to allow team managers to utilise their local knowledge of the network to plan for peak periods. Detailed resource plans and programmes of activity have been produced to meet the increased pressure of All Lane Running Continue to support and work collaboratively with all emergency services including to identify where CLEAR is working effectively or not and to liaise with CLEAR leads on how to invigorate areas where further engagement is needed. This collaboration has supported our KPI on motorway incidents cleared, during 2017-18 Highways England remained above the 85% target and cleared 87.94% of motorway incidents within an hour.
Other monitoring requirements |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
No. impact incidents |  | 46561 | 49130 | 56136 | X | X | DPI | Note: hours of time lost in traffic for the year is currently not reported on. Future development under consideration. | [2]
Mean time to clear incidents |  | 0:41 | 0:36 | 0:33 | X | X | DPI |  | [2]
Median time to clear incidents |  | 0:23 | 0:23 | 0:22 | X | X | DPI |  | [2]
Hours of time lost in traffic for the year |  | n/a | n/a | X | X | X | DPI |  | [2]
Notes and commentary
[1] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[2] Explain external factors that have impacted the actuals and quantify that impact. Explain reason for the variance.
[X] HE and ORR to consider reporting this data once appropriate strategies and/or reporting has been developed.

## PS4 - Economic growth
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS4: Encouraging economic growth |  | For a definition of the metric and parameters for measuring and monitoring encouraging economic growth see Highways England’s Operational Metrics Manual
Performance specification
Annual
| Source of baseline | Actual | baseline | KPI/PI/ Req | Difference |  | Notes
KPI
Average delay (time lost, in seconds, per vehicle per mile)
The company should report annually on average delay | [5 empty] | In FY17/18, average delay was 9.19 seconds per vehicle per mile, 0.24 seconds greater than in FY16/17. This represents a 2.68% change from last year, indicating that average delay has increased slightly. This may relate to harsher weather conditions this year, which have had an impact on road user experience. Direct comparisons cannot be drawn between values up to and including 2014-15, and figures for 2015-16 onwards due to a transition to a different data source.
2009-10 | Reprocessed historical data | 7.7883
2010-11 | Reprocessed historical data | 7.4175
2011-12 | Reprocessed historical data | 6.7731
2012-13 | Reprocessed historical data | 7.2177
2013-14 | Reprocessed historical data | 7.7961
2014-15 | Reprocessed historical data | 8.9707
2015-16 | Historical data | 8.932 | 8.97 | KPI | -0.037958
2016-17 | Historical data | 8.95 | 8.93 | KPI | 0.02
2017-18 | Delivery Plan | 9.19 | 8.95 | KPI | 0.24
2018-19 |  | X | [X] | KPI | X
2019-20 |  | X | [X] | KPI | X
PIs
Being an active and responsive part of the planning system
99% percentage of formal Local Planning Authority issued planning application consultations should be responded to within 21 days of their receipt | [5 empty] | Continuing our trend of exceeding the target response rate, in 2017-18 we responded to 100% of planning applications within 21 days, a +1% difference relative to target and a 0.23% increase from 2016-17. This is in the context of a 0.73% rise in total planning applications received. *A previous rounding error has meant that we have revised the 2015-16 value to 99.85% from 99.80%.
2010-11 | Historical Data | 98.22%
2011-12 | Historical Data | 99.9%
2012-13 | Historical Data | 99.6%
2013-14 | Historical Data | 99.6%
2014-15 | Historical Data | 99.9%
2015-16 | Historical Data | *99.80% | 99% | PI | X
2016-17 | Historical Data | 99.77% | 99% | PI | 0.77
2017-18 | Delivery Plan | 100% | 99% | PI | 1
2018-19 | Delivery Plan | X | 99% | PI | X
2019-20 | Delivery Plan | X | 99% | PI | X
Average delay on Gateway Routes (Seconds per vehicle mile)
The company should report annually on average delay | [5 empty] | In 2017-18, average delay on Gateway routes was 8.70 seconds per vehicle per mile, 0.47 seconds greater than in 2016-17. This represents a 5.71% increase from the previous year, which may relate to harsher weather compared with the previous couple of years. Direct comparisons cannot be drawn between values up to and including 2014-15, and figures for 2015-16 onwards due to a transition to a different data source.
2009-10 | Reprocessed historical data | 7.5065
2010-11 | Reprocessed historical data | 6.9233
2011-12 | Reprocessed historical data | 6.1816
2012-13 | Reprocessed historical data | 6.5557
2013-14 | Reprocessed historical data | 7.2463
2014-15 | Reprocessed historical data | 8.6601
2015-16 | Historical data | 8.1108 | 8.66 | PI | -0.54921
2016-17 | Historical data | 8.23 | 8.11 | PI | 0.12
2017-18 | Delivery Plan | 8.7 | 8.23 | PI | 0.47
2018-19 |  | X | [X] | PI | X
2019-20 |  | X | [X] | PI | X
Helping the Government support small and medium sized enterprises
25% of direct and indirect spend to Small and Medium size Enterprises (SME) | [5 empty] | Highways England has achieved the required performance and met the 25% target with SME Spend as a proportion of total spend. *Due to agreed changes to the metric calculation methodology, the figures for previous years have been restated to become compliant with the Operational Metrics Manual methodology. This leads to reported figures for 2015-16 of 27.50%, and 2016-17 of 24.16%.
2013-14 | Historical Data | 30.7%
2014-15 | Historical Data | 26.9%
2015-16 | Historical Data | *26.88% | 25% | PI | X
2016-17 | Historical Data | *25.46% | 25% | PI | X
2017-18 | Delivery Plan | 25% | 25% | PI | 0
2018-19 | Delivery Plan | X | 25% | PI | X
2019-20 | Delivery Plan | X | 25% | PI | X
Requirements
Actively support the Construction 2025 goals
People – an industry that is known for its talented and diverse workforce |  |  |  | Req |  | • We launched Highways England Returners programme, a Major Projects programme aimed at career breakers of 2 years or more looking to come back into work. The initial group joined in September 2017 and was comprised of 14 members. The programme lasts for 6 months and upon completion we retained 13 members, making this retention of 93%. • As part of Highways England’s “grow our own” talent development programme, we have introduced structured Commercial and Quantity Surveyor career paths, including continued professional development (CPD) for commercial staff at all levels. This approach will support our increasing need for commercial capability and capacity throughout our business, the supply chain and industry wide as well.
Smart – an industry that is efficient and technologically advanced |  |  |  | Req |  | • We implemented the Asset Delivery programme, which helps to improve how we plan and programme major project schemes and undertake maintenance on the network. It was launched on 1st of July 2017 in the South West. Up to December 2017 over 30% of our network has been successfully awarded under the new Asset Delivery model and as a result, we now have 150 staff and 24 suppliers working under this programme. • We are implementing Contract Event Management and Reporting (CEMAR) which will enable us to manage our contracts in a more efficient and consistent way. CEMAR provides both employer and provider with a single version of the truth for all contract correspondence, thus reducing commercial risk. We have also issued customer specific performance measures to our supply chain to help us improve the service level that road users and communities receive.
Sustainable – an industry that leads the world in low-carbon and green construction exports |  |  |  | Req |  | • Air Quality Strategy has been published on 2nd of August 2017, showing our commitment of £100 million spend to improve air quality through to 2021. This strategy sets out our approach and activities which will enable us to achieve this goal as planned. • We developed a regional packaging strategy offering a number of work packages from contract award to create the right environment for our supply chain to grow and develop the skill base required to successfully deliver the RIS. We have also developed a number of programme level incentives designed to reduce overheads and transaction costs.
Growth – an industry that drives growth across the entire economy |  |  |  | Req |  | • M181 Lincolnshire Lakes project received £13.5 million from Growth & Housing fund to enable to proceed and allow more than 6,000 new homes to be built up and up to 4,000 jobs to be created by 2028 • Route to Market was launched and an event was held in July 2017 to share with the supply chain the intention to separate the procurement of the regional investment and smart motorways programme. We will be starting the process of procuring a number of regional investment program delivery partners by the end of the 2017-2018 financial year with the intention for a procurement solution to be in place by Spring 2018. The procurement process for the smart motorways programme will begin in the first quarter of 2018-2019 financial year and the anticipated conclusion will be by spring 2019. Sharing this with the market at such an early stage ensures that the suppliers are engaged with Highways England and can plan and invest effectively for the future. • After the launch of the C&P model we worked to develop a process map to describe how the model is deployed, thus we have created the contract lifecycle wheel. We also continue to increase our capacity and capability by recruiting to our workforce plan, which will enable us to deliver a range of new work areas and projects.
Leadership – an industry with clear leadership from a Construction Leadership Council |  |  |  | Req |  | • A group of HE staff recently graduated from the Roads Academy, a joint initiative within the roads industry. We also launched the Emerging Leaders programme in July 2017, a programme with a focus on operational leadership. We received 52 applications for this programme: 25 from Highways England and 27 from member organisations. 3 cohorts of the programme started in Oct 2017 and Nov 2017. • For senior leaders, cohort 9 is due to graduate in Jan 2018, while cohort 10 has successfully passed their first assignments and currently taking second module. • A new Level 5 apprenticeship “Step Up to Leadership” is being developed, creating a full leadership career pathway through Roads Academy, which has already produced 130 graduates by Oct 2017 • All leaders within Commercial and Procurement have either completed the Management Development programme or are set to complete the training. We have embedded this as a mandatory training requirement for new starters in leadership roles.
Roads academy programme
Deliver the Roads Academy programme across the industry |  |  |  | Req |  | On 14/02/18 the Roads Academy celebrated its ninth cohort graduation. The roads academy which is now in its eighth year provides a full leadership career pathway from Step Up to Leadership to an MA designed by experts from both industry and academic institutions. All graduates commented on the positive impact the programme had on their personal development helping them to become more resilient and reflective ideas. Through financial year 17/18 - 33 individuals have graduated from the Roads Academy, this was made up of 7 colleagues from Highways England and 26 from across our supply chain members. Overall we have had 123 people graduate from Roads Academy since it commenced in 2010 (including the 33).
Innovation strategy
Develop its Innovation, Technology, and Research Strategy and agree an implementation plan by March 2016 |  |  |  | Req |  | Plans for innovation portal remain on track, with the launch of 1st phase being planned at the end of April 2018 and the second phase later in 2018 - which will give it full functionality. Completed a strategic innovation road mapping project with Transport Systems Catapult which has identified a number of priority innovation focus areas and gaps where we need to focus more innovation effort. This is shared with stakeholders.
Identify constraints through route strategies
Through Route Strategies identify constraints to economic growth that the performance of the Network can help to alleviate and define future delivery and investment plans which address them. |  |  |  | Req |  | The 18 updated Route Strategies were successfully published in March 2017. The findings from these strategies are now feeding into the development of the next Road Investment Strategy. No updates for 2018, business continues as usual.
Notes and commentary
[1] Explain what actions and activities have been taken by management to achieve actual and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact.
[2] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[3] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[X] HE and ORR to consider reporting this data once appropriate strategies and/or reporting has been developed.

## PS5 - Environment
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS5: Delivering better environmental outcomes |  | For a definition of the metric and parameters for measuring and monitoring environmental performance see Highways England’s Operational Metrics Manual
Performance specification
|  |  | Annual |  |  | Cumulative
| Source of baseline | Actual | baseline | KPI/PI/ Req | Difference | Actual | baseline | KPI/PI/ Req | Difference | Notes
KPIs
Noise important areas
Mitigate at least 1,150 Noise Important Areas over RP1 |  | The total number of Noise Important Areas mitigated in 2017-18 is 448. This consists of 386 through noise insulation, 47 through resurfacing, 8 through major scheme bypasses, 2 through the provision of barriers and 5 with both noise insulation and resurfacing. The cumulative total for Roads Period 1 is 651 against the KPI target of 1150. This consists of 386 through noise insulation, 231 through resurfacing, 13 through major scheme bypasses, 5 through the provision of barriers and 16 with both noise insulation and resurfacing. The noise insulation project commenced in April 2017 from an initial pilot with the aims to: - improve the health and well-being of people living in properties adjacent to the road network - provide cost effective investment to properties worst affected by traffic noise, and the people who will have the greatest adverse health impacts The Noise Insulation Scheme will provide improved glazing to properties within Noise Important Areas where other mitigation measures are not practical. In 2017-18, 274 double glazing installations were completed, accounting for over 800 people benefting from reduced noise levels. The take up rate remains at or near to 40% and there is a steady number of people asking to be included in the scheme who had originally indicated they were not interested. As delivery moves in to the larger NIAs this is likely to increase as the work will be more visible. Due to agreed changes to metric calculation methodology the figures for previous years have been restated
2015-16 | Corporate management information | 62 | 0 | KPI | 62 | 62 | 0 | KPI | 62 | [1]
2016-17 | Corporate management information | 141 | 300 | KPI | -159 | 203 | 300 | KPI | -97 | [1]
2017-18 | Delivery plan | 448 | 300 | KPI | 148 | 651 | 600 | KPI | 51 | [1]
2018-19 | Delivery plan | X | 300 | KPI | X | X | 900 | KPI | X | [1]
2019-20 | Performance Specification | X | 250 | KPI | X | X | 1150 | KPI | X | [1]
Biodiversity plan
The Company should publish its Biodiversity Action Plan (BAP) by 30 June 2015 and report annually on how it has delivered against the Plan to reduce net biodiversity loss on an ongoing annual basis |  | Biodiversity Action Plan was delivered in the first year of RIS1. The 2015-16 annual report was summarised in the Delivery Plan Update 2016-17. The 2016-17 annual report will be externally published spring 2018. The 2017-18 annual report is currently in development for publication 2018-19. A new biodiversity metric is being developed using 2015 baseline data and will be trialled internally 2017-18. 15 SSSI management plans have been provided across directorates and validated following consultation with Natural England. The Chief Highways Engineer has approved the CHE memo launching the biodiversity metric.
Publish BAP by 30 June 2015 | Performance Specification | Biodiversity Action Plan published June 2015.
PIs
Develop an Air Quality Action Plan by March 2016
Number of Air Quality pilot studies started
2015-16 | Corporate management information | 6 | 6 | PI | 0 | By the end of March behavioural specialists submitted the final pilot study, concerning making better use of information to change customers' behaviours to improve air quality. 10 studies have been undertaken, nine of the studies have been finalised and specialists are working on responding to a technical clarification requirement on the remaining study to enable publication to share our learning. In addition, we are rapidly assembling a national programme of air quality barriers given emerging evidence that curved and overhanging barrier (as at Dordrecht, Netherlands) can improve air quality. Progress on all air quality activity continues to be reported to the Air Pollution Strategy Board. |  |  |  | [2]
2016-17 | DP p44, OMM p136, PS p24 | 4 | 6 | PI | -2 |  |  |  |  | [2]
2017-18 | Delivery plan | 0 | 0 | PI | 0 |  |  |  |  | [2]
2018-19 | Delivery plan | X | [X] | PI | X |  |  |  |  | [2]
2019-20 | Delivery plan | X | [X] | PI | X |  |  |  |  | [2]
Carbon and other greenhouse gas emissions (tonnes of CO2e):
Associated with Highways England's activities
2008-09 | Historical Data | X |  |  |  | The current Greening Government Commitment target is to reduce our carbon emissions by at least 32% by 2020 (cf 2009-10 baseline). Our 2017-18 actions contributed towards a 36% reduction against the 2009-10 baseline (final figures awaited) so we are continuing to make good progress toward the 2020 target. We have installed energy-saving LED bulbs in our street lights with a programme to replace more in 2018-19 and increase efficiency of Highways England Traffic Officers patrols by utilising cameras more to reduce emissions. Highways England has worked to reduce the carbon emissions associated with our business travel and commuting to help promote sustainable modes of travel including walking, cycling, public transport and car sharing.
2009-10 | Historical Data | 132500
2010-11 | Historical Data | 127310
2011-12 | Historical Data | 104043
2012-13 | Historical Data | 102862
2013-14 | Historical Data | 98496
2014-15 | Historical Data | 104978
2015-16 | Corporate management information | 95373 | 104978 | PI | -9605 |  |  |  |  | [3]
2016-17 | Corporate management information | 89591 | 95373 | PI | -5782 |  |  |  |  | [3]
2017-18 | Delivery plan | 83659 | 89591 | PI | -5932 |  |  |  |  | [3]
2018-19 | Delivery plan | X | [X] | PI | X |  |  |  |  | [3]
2019-20 | Delivery plan | X | [X] | PI | X |  |  |  |  | [3]
Associated with the Supply chain activities
2008-09 | Historical Data | X |  |  |  | The publication of the sustainable development strategy, with its carbon management priority, encourages the business to engage with the supply chain. The supply chain was also reminded of contractual requirements to use the carbon tool and submit returns in a timely manner. We have undertaken internal audits to focus areas for improvement and completed the following actions that aim to improve carbon reporting within our supply chain: • Instituted a consistent process for collating CO2 data in all Asset Delivery Areas • Process was put in place to remind directorates and suppliers on the correct procedures and deadlines to be followed • Instituted a process of nil returns with explanations for nil returns in all areas • Instituted a process for review (accuracy and completeness, analytical) of CO2 data across directorates. As part of the A160 upgrade scheme, early engagement across the supply chain ensured that innovations such as lower temperature asphalt were built into the road design, saving more than 200 tonnes of carbon dioxide equivalent.
2009-10 | Historical Data | 567500
2010-11 | Historical Data | 507000
2011-12 | Historical Data | 411124
2012-13 | Historical Data | 203648
2013-14 | OMM p153, Historical Data | 303620
2014-15 | Historical Data | 383487
2015-16 | Corporate management information | 406523 | 383487 | PI | 23036 |  |  |  |  | [3]
2016-17 | Corporate management information | 326535 | 406523 | PI | -79988 |  |  |  |  | [3]
2017-18 | Delivery plan | 255000 | 326535 | PI | -71535 |  |  |  |  | [3]
2018-19 | Delivery plan | X | [X] | PI | X |  |  |  |  | [3]
2019-20 | Delivery plan | X | [X] | PI | X |  |  |  |  | [3]
Total
2008-09 | Delivery plan | X
2009-10 | Delivery plan | 700000
2010-11 | Delivery plan | 634310
2011-12 | Delivery plan | 515167
2012-13 | Delivery plan | 306510
2013-14 | Delivery plan | 402116
2014-15 | Delivery plan | 488465
2015-16 | Delivery plan | 501896 | 488465 | PI | 13431 |  |  |  |  | [3]
2016-17 | Delivery plan | 416126 | 501896 | PI | -85770 |  |  |  |  | [3]
2017-18 | Delivery plan | 338659 | 416126 | PI | -77467 |  |  |  |  | [3]
2018-19 | Delivery plan | X | [X] | PI | X |  |  |  |  | [3]
2019-20 | Delivery plan | X | [X] | PI | X |  |  |  |  | [3]
Requirements |  |  | Annual
| Source of baseline | Actual | baseline | KPI/PI/ Req | Difference
Demonstrate what activities have been taken, and how effective they have been, to improve environmental outcomes. |  | Final drafts of both an Environment Action Plan and a Sustainable Development Action Plan are with the Chief Highways Engineer for approval. Communication materials have been prepared to support their introduction to the business. A first draft Environment and Wellbeing Strategy for Roads Period 2 has been prepared. Draft environmental metrics for consideration in RP2 are well advanced with a biodiversity metric ready for internal trial in 2018-19. Detailed discussions are underway with Government colleagues around their alignment with Gov policy and their practical applicability within the Highways England business to drive the right behaviours and outcomes. | [7 empty] | [4]
Develop metrics covering broader environmental performance; new or improved biodiversity metrics
2015-16 | Develop and monitor against programme | Yes | X | Req | X | The mechanism to report progress against the RIS 1 KPI requirement has been developed using 2015 baseline data and will be trialled internally. The Chief Highways Engineer has approved the CHE Memo with the intent to launch the biodiversity metric in spring 2018-19. |  |  |  | [5]
2016-17 | Develop and monitor against programme | Yes | X | Req | X |  |  |  |  | [5]
2017-18 | Metric established by December 2017 (BAP) | Yes | X | Req | X |  |  |  |  | [5]
2018-19 | Metric reported | X | X | Req | X |  |  |  |  | [5]
2019-20 | Metric reported | X | X | Req | X |  |  |  |  | [5]
Develop metrics covering broader environmental performance; Carbon and other greenhouse gas emissions arising from the use of the SRN
2015-16 | Develop and monitor against programme | Yes | X | Req | X | An estimated carbon emission for the SRN-user was produced for 2014 using the Highways England’s Network Performance Model (NPM) methodology and the Carbon Metric Lead requested additional baselining of 2016 and 2017. It has become apparent that the NPM methodology was not incorporated within the NPM as originally anticipated and this has meant that it has not been possible to collect the relevant baseline information. Specialist additional consultancy resource would now appear to be required to fully validate the model and incorporate the 2016 methodology into the NPM. |  |  |  | [6]
2016-17 | Develop and monitor against programme | Yes | X | Req | X |  |  |  |  | [6]
2017-18 | Develop and monitor against programme | Yes | X | Req | X |  |  |  |  | [6]
2018-19 | Develop and monitor against programme | Yes/No | X | Req | X |  |  |  |  | [6]
2019-20 | Metric established | Yes/No | X | Req | X |  |  |  |  | [6]
The number of validated flooding hotspots mitigated
2015-16 | Corporate management information | 72 | 69 | Req |  | In total for 2017-18 we have 40 flooding hotspots mitigated across directorates. Separately, a Technical Liaison Group with the Environment Agency has been set up, including a working brief on future plans for collaboration. 3 hotspots were rescinded from previous 2017-18 numbers reported due to the reoccurrence of flooding. These were the first hotspots rescinded and when it became apparent that these were no longer risk addressed, discussions with the Service Provider were undertaken to understand the reasons. The initial training session on the new process is being held May/June and there is a programme identified going forward to ensure all regions compliant. Across directorates new process maps and guidance are currently being agreed to facilitate identification of mitigated assets and improve reporting processes. A training programme has been developed to support and refresh directorate teams on their reporting requirements for 2018-19. |  |  |  | [6]
2016-17 | Corporate management information | 61 | 72 | Req | -8 |  |  |  |  | [6]
2017-18 | Milestones in Delivery plan | 40 | 61 | Req | -21 |  |  |  |  | [6]
2018-19 | Milestones in Delivery plan | X | [X] | Req | X |  |  |  |  | [6]
2019-20 | Milestones in Delivery plan | X | [X] | Req | X |  |  |  |  | [6]
The number of validated culverts mitigated
2015-16 | Corporate management information | 3 | 21 | Req |  | There is 1 culvert mitigated across directorates. Highways England will continue to work closely across directorates to ensure delivery of mitigated hotspots and culverts into 2018-19. In partnership with Major Projects, new process maps and guidance is currently being agreed to facilitate identification of mitigated assets and improve reporting processes. A training programme has been developed to support and refresh Operations Directorate teams on their reporting requirements for 2018-19. |  |  |  | [6]
2016-17 | Corporate management information | 5 | 3 | Req | 2 |  |  |  |  | [6]
2017-18 | Milestones in Delivery plan | 1 | 5 | Req | -4 |  |  |  |  | [6]
2018-19 | Milestones in Delivery plan | X | [X] | Req | X |  |  |  |  | [6]
2019-20 | Milestones in Delivery plan | X | 21 | Req | X |  |  |  |  | [6]
The number of validated outfalls mitigated
2015-16 | Corporate management information | 0 | [X] | Req |  | In total, for 2017-18, 5 outfalls have been confirmed as mitigated – 2 from Environmental Designated Fund (EDF) (1 outfall through at J8 M65 and 1 on the A30 Temple to Carblake scheme) and 3 from Major Projects. For the remainder of Roads Period 1, Safety, Engineering and Standards are working across directorates to confirm forward delivery programmes. |  |  |  | [6]
2016-17 | Corporate management information | 5 | 0 | Req | 5 |  |  |  |  | [6]
2017-18 | Milestones in Delivery plan | 5 | 5 | Req | 0 |  |  |  |  | [6]
2018-19 | Milestones in Delivery plan | X | [X] | Req | X |  |  |  |  | [6]
2019-20 | Milestones in Delivery plan | X | [X] | Req | X |  |  |  |  | [6]
The number of validated soakaways mitigated
2015-16 | Corporate management information | 0 | 0 | Req | 0 | No soakaways have been mitigated in the current year. For the remainder of Roads Period 1, Safety, Engineering and Standards are working across directorates to confirm forward delivery programmes. |  |  |  | [6]
2016-17 | Corporate management information | 0 | 0 | Req | 0 |  |  |  |  | [6]
2017-18 | Milestones in Delivery plan | 0 | 0 | Req | 0 |  |  |  |  | [6]
2018-19 | Milestones in Delivery plan | X | [X] | Req | X |  |  |  |  | [6]
2019-20 | Milestones in Delivery plan | X | [X] | Req | X |  |  |  |  | [6]
Other monitoring requirements
None
Notes and commentary
[1] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[2] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[3] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[4] Where an activity has been rated very effective, explain the reason why. Where an activity has been rated as very ineffective - explain the reason why.
[5] Explain reasons for the variance.
[6] Explain reasons for the variance.
[X] HE and ORR to consider reporting this data once appropriate strategies and/or reporting has been developed.

## PS6 - Vulnerable Users
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS6: Helping cyclists, walkers, and other vulnerable users of the Network |  |  |  | For a definition of the metric and parameters for measuring and monitoring performance regarding vulnerable users see Highways England’s Operational Metrics Manual
Performance specification
|  |  | Annual |  |  | Cumulative
| Source of baseline | Actual | baseline | KPI/PI/ Req | Difference | Actual | Baseline | KPI/PI/ Req | Difference | Notes
KPIs
The number of (completed) new and upgraded crossings |  |  | In 2017-18 Highways England delivered 28 new crossings and 72 upgraded crossings across the strategic road network, a total of 100 crossings. This takes our cumulative total to 331 schemes delivered so far in the current Road Period. The A160/ A180 Port of Immingham Improvement Scheme, delivered in spring 2017. The objectives of this scheme were to improve safety, reduce congestion and improve journey time reliability and meet the demands for predicted future growth for this important route into the Port. This has been achieved by upgrading existing single carriageway sections of the port’s main access road to dual carriageway as well as several junction improvements. As well as the integration benefits delivered by this scheme, we have also provided accessibility improvements. We have delivered a new bridge providing access for cyclists, pedestrians and equestrians over the dual carriageway, addressing a severance issue. We have also delivered 1300m new cycleway, to provide a safe and direct route for cyclists, removing conflict with high speed dual carriageway traffic. Additional schemes delivered are subject to further validation throughout the year and may be included in our future validated figures. *Due to methodology changes for validation of Vulnerable Users the breakdown of equestrian, pedestrian and cycle crossings for the period 2015-16 is under review, and will be stated in next year’s report
2015-16 | Corporate management information | *204 | X | KPI | X | 204 | X | KPI | X | [1]
2016-17 | Corporate management information | 27 | X | KPI | X | 231 | X | KPI | X | [1]
2017-18 | Delivery Plan | 100 | [X] | KPI | X | 331 | [X] | KPI | X | [1]
2018-19 | Delivery Plan | X | [X] | KPI | X | X | [X] | KPI | X | [1]
2019-20 | Delivery Plan | X | [X] | KPI | X | X | [X] | KPI | X | [1]
The number of (completed) new crossings
2015-16 | Corporate management information | 39 | X | KPI | X | 39 | X | KPI | X | [1]
2016-17 | Corporate management information | 20 | X | KPI | X | 59 | X | KPI | X | [1]
2017-18 | Delivery Plan | 28 | [X] | KPI | X | 87 | [X] | KPI | X | [1]
2018-19 | Delivery Plan | X | [X] | KPI | X | X | [X] | KPI | X | [1]
2019-20 | Delivery Plan | X | [X] | KPI | X | X | [X] | KPI | X | [1]
The number of (completed) upgraded crossings
2015-16 | Corporate management information | 165 | X | KPI | X | 165 | X | KPI | X | [1]
2016-17 | Corporate management information | 7 | X | KPI | X | 172 | X | KPI | X | [1]
2017-18 | Delivery Plan | 72 | [X] | KPI | X | 244 | [X] | KPI | X | [1]
2018-19 | Delivery Plan | X | [X] | KPI | X | X | [X] | KPI | X | [1]
2019-20 | Delivery Plan | X | [X] | KPI | X | X | [X] | KPI | X | [1]
PIs
The number of vulnerable users casualties on the SRN
Cyclists
2010 | Historical Data | 148 |  |  | Validated data for 2017 is not available at year end. Please see Annual Report for more information. Validated cyclist casualties for 2016 were recorded at 148 (Fatalities - 3; Serious - 41; and Slight - 104); this is slightly lower than the 2015 results of 153 casualties.
2011 | Historical Data | 173
2012 | Historical Data | 170
2013 | Historical Data | 149
2014 | Historical Data | 179
2015 | Corporate management information | 153 |  | PI | [5 empty] | [1]
2016 | Corporate management information | 152 |  | PI | [5 empty] | [1]
2017 | Delivery Plan | X |  | PI | [5 empty] | [1]
2018 | Delivery Plan | X |  | PI | [5 empty] | [1]
2019 | Delivery Plan | X |  | PI | [5 empty] | [1]
Pedestrians
2010 | Historical Data | 199 |  |  | Validated data for 2017 is not available at year end. Please see Annual Report for more information. Validated pedestrian casualties for 2016 were recorded at 154 (Fatalities - 40; Serious - 54; and Slight - 60); this is slightly lower than the 2015 results of 156 casualties.
2011 | Historical Data | 182
2012 | Historical Data | 148
2013 | Historical Data | 183
2014 | Historical Data | 182
2015 | Corporate management information | 158 |  | PI | [5 empty] | [1]
2016 | Corporate management information | 154 |  | PI | [5 empty] | [1]
2017 | Delivery Plan | X |  | PI | [5 empty] | [1]
2018 | Delivery Plan | X |  | PI | [5 empty] | [1]
2019 | Delivery Plan | X |  | PI | [5 empty] | [1]
Motorcyclists
2013 | Historical Data | 846 |  |  | Validated data for 2017 is not available at year end. Please see Annual Report for more information. Validated motorcyclist casualties for 2016 were recorded at 864 (Fatalities - 27; Serious - 345; and Slight - 492); this represents a slight increase from 2015 where 849 casualties were recorded.
2014 | Historical Data | 917
2015 | Corporate management information | 849 |  | PI | [5 empty] | [1]
2016 | Corporate management information | 864 |  | PI | [5 empty] | [1]
2017 | Delivery Plan | X |  | PI | [5 empty] | [1]
2018 | Delivery Plan | X |  | PI | [5 empty] | [1]
2019 | Delivery Plan | X |  | PI | [5 empty] | [1]
Equestrians
2013 | Historical Data | 0 |  |  | Validated data for 2017 is not available at year end. Please see Annual Report for more information. We have not had any deaths or serious injuries in this category since 2005.
2014 | Historical Data | 0
2015 | Corporate management information | 0 |  | PI | [5 empty] | [1]
2016 | Corporate management information | 0 |  | PI | [5 empty] | [1]
2017 | Delivery Plan | X |  | PI | [5 empty] | [1]
2018 | Delivery Plan | X |  | PI | [5 empty] | [1]
2019 | Delivery Plan | X |  | PI | [5 empty] | [1]
Total vulnerable users casualties
2013 | Historical Data | 1178 |  |  | Validated data for 2017 is not available at year end. Please see Annual Report for more information. Validated data for 2016 shows a slight increase in total vulnerable user casualties on 2015. This was caused by the increase in motorcyclist casualties.
2014 | Historical Data | 1278
2015 | Corporate management information | 1160 |  | PI | [5 empty] | [1]
2016 | Delivery Plan | 1170 |  | PI | [5 empty] | [1]
2017 | Delivery Plan | X |  | PI | [5 empty] | [1]
2018 | Delivery Plan | X |  | PI | [5 empty] | [1]
2019 | Delivery Plan | X |  | PI | [5 empty] | [1]
Identification and Delivery of the Annual Cycling Programme |  |  | In 2017-18, we delivered 22 cycling schemes, progressed 18 into construction, completed detailed design on 12 and brought 9 more potential schemes into the programme to begin design work. This means that, since the beginning of this Road Period, we have delivered 79 cycling schemes cumulatively, putting Highways England 52.66% of the way along to achieving its Delivery Plan 2015-20 commitment of delivering 150 cycling schemes by the end of RP1. A5 Cycling Corridor was a long standing ambition to extend existing cycling and walking facilities within the Churchbridge/Cannock area beyond the current town boundaries. Approximately 5KM has been provided/upgraded on the North side of the A5 between A452 roundabout and Churchbridge. This provides a direct link between a number of employment areas as well as connecting a number of population centres. Since February there has been a renewed emphsis on stricter evidence requirement and on the approval process for KPI6. This improvement in the Level 1 Assurance is a good indicator that the implementation of the process is gaining traction and that its embodiment in the delivery partners is becoming much stronger. There has lso been a more pro-active response from Major Project. Much work hs been done on improving the means of managing the process including "a what good looks like" activity as well as promoting the means of capturing evidence in a more accurate fashion and the development of a more robust esclation process. There has also been an improvement with regards the provision of evidence so that we are now in good position to provide adequate assurance as to the progress of a number of commitments relating to KPI6.
Number of cycling schemes begin design
2015-16 | Corporate management information | 80 | X | PI | X | 80 | X | PI | X | [1]
2016-17 | Corporate management information | 14 | X | PI | X | 94 | X | PI | X | [1]
2017-18 |  | 9 | [X] | PI | X | 103 | 0 | PI | 103 | [1]
2018-19 |  | x | [X] | PI | X | X | 0 | PI | X | [1]
2019-20 |  | X | [X] | PI | X | X | 0 | PI | X | [1]
Number of cycling schemes finish design
2015-16 | Corporate management information | 49 | X | PI | X | 49 | X | PI | X | [1]
2016-17 | Corporate management information | 17 | X | PI | X | 66 | X | PI | X | [1]
2017-18 |  | 12 | [X] | PI | X | 78 | 0 | PI | 78 | [1]
2018-19 |  | X | [X] | PI | X | X | 0 | PI | X | [1]
2019-20 |  | X | [X] | PI | X | X | 0 | PI | X | [1]
Number of cycling schemes start work
2015-16 | Corporate management information | 49 | X | PI | X | 49 | X | PI | X | [1]
2016-17 | Corporate management information | 14 | X | PI | X | 63 | X | PI | X | [1]
2017-18 |  | 18 | [X] | PI | X | 81 | 0 | PI | 81 | [1]
2018-19 |  | X | [X] | PI | X | X | 0 | PI | X | [1]
2019-20 |  | X | [X] | PI | X | X | 0 | PI | X | [1]
Number of cycling schemes completed | [9 empty] | [1]
2015-16 | Delivery Plan | 25 | 40 | PI | -15 | 25 | 40 | PI | -15
2016-17 | Corporate management information | 32 | X | PI | X | 57 | X | PI | X | [1]
2017-18 |  | 22 | [X] | PI | X | 79 | [X] | PI | X | [1]
2018-19 |  | X | [X] | PI | X | X | [X] | PI | X | [1]
2019-20 |  | X | [X] | PI | X | X | [X] | PI | X | [1]
Requirements
Report annually on how it is delivering against the Public Sector Equality Duty
Remove or minimise disadvantages suffered by persons who share a relevant protected characteristic that are connected to that characteristic. Protected characteristics age; disability; gender reassignment; pregnancy and maternity; race; religion or belief; sex; sexual orientation. |  | Customer and communities’ deliverables have included the completion of the disability awareness in construction pilot in Major Projects in the North. This has resulted in a toolbox of information to be imminently rolled to help project managers involved in delivering schemes across the strategic road network. Our supply chain partners who were part of the steering group have produced a specific advice booklet which, as well as being in the toolkit, will be publicised widely across the sector. Work with the Supplier Diversity Forum (SDF) has included; funding a research project examining attraction, recruitment and retention in the sector, improving the quality of collected workforce data, expanding SDF membership, work to create a threshold to support the business case for inclusion, and the ‘making a difference in leadership’ event involving 90 leaders from across our sector. The equality, diversity and inclusion performance of our supply chain has continued to be monitored through our Collaborative Performance Framework (CPF). Training sessions were delivered to assessors, and workshops provided to 14 eligible schemes, as well as biannual supplier sessions to share good practice. Whilst our strategic alignment review tool assessments (StART) revealed that from those who participated previously, over 50% has improved their performance. Cross objective activity has included the launch of revised Equality Impact Assessment (EqIA) guidance. Work is currently commencing on the development of associated training material including a tailored e-learning product. We are also involved in outreach work as part of the ‘2018 Year of the Engineer’ to attract diverse talent into the sector. | [5 empty] | Req |  | [2]
Take steps to meet the needs of persons who share a relevant protected characteristic that are different from the needs of persons who do not share it; . | [7 empty] | Req |  | [2]
Encourage persons who share a relevant protected characteristic to participate in public life or in any other activity in which participation by such persons is disproportionately low. . | [7 empty] | Req |  | [2]
Other monitoring requirements |  | 2015 | 2016 | 2017 | 2018 | 2019 | Cumulative
Validated data for 2017 is not available at year end. Please see Annual Report for more information.
Location of vulnerable user KSI
East |  | 57 | 80 | X | X | X | 137 | DPI |  | [3]
South east |  | 166 | 168 | X | X | X | 334 | DPI |  | [3]
South west |  | 40 | 54 | X | X | X | 94 | DPI |  | [3]
Midlands |  | 87 | 104 | X | X | X | 191 | DPI |  | [3]
North west |  | 38 | 48 | X | X | X | 86 | DPI |  | [3]
Yorkshire and northeast |  | 42 | 56 | X | X | X | 98 | DPI |  | [3]
|  | 430 | 510 | 0 | 0 | 0 | 940
|  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Cumulative
Location new or upgraded crossings
East |  | X | 14 | 2 | X | X | 16 | DPI | Additional schemes delivered are subject to further validation throughout the year and may be included in our future validated figures | [4]
South east |  | X | 0 | 3 | X | X | 3 | DPI |  | [4]
South west |  | X | 0 | 2 | X | X | 2 | DPI |  | [4]
Midlands |  | X | 3 | 30 | X | X | 33 | DPI |  | [4]
North west |  | X | 9 | 46 | X | X | 55 | DPI |  | [4]
Yorkshire and northeast |  | X | 1 | 17 | X | X | 18 | DPI |  | [4]
|  | [X] | 27 | 100 |  | 0 | 127 |  |  | [4]
Notes and commentary
[1] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[2] Explain significant year on year variances.
[3] Explain reasons for the variances.
[4] Explain correlation with new and upgraded crossings by location with KSI by location.
[X] HE and ORR to consider reporting this data once appropriate strategies and/or reporting has been developed.

## PS7 - Achieving real efficiency
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS7: Achieving real efficiency
Performance specification
|  |  | Annual |  |  | Cumulative | Cumulative
| Source of baseline | Actual | baseline | KPI/PI/ Req | Difference | Actual | baseline | KPI/PI/ Req | Difference | Notes
Cost savings
KPI: Total savings of £1.212 billion over RP1 on capital expenditure |  |  |  |  | Efficiency savings of £556m were identified in 2017-18 against the cumulative KPI target of £377m. The Internal Audit team have validated £485.6m of this figure, with ongoing review of the remainder. Given the pipeline of efficiencies, these figures will be updated over the next 2 years, and will remain under review. We continued to develop and increase the maturity of efficiency delivery and reporting during 2017-18, with robust assurance and an internal training programme to clarify roles and responsibilities. This progress is reflected by an increase to 87.3% (from 66.8% last year) in the total reported value that has been assured by the IA team. The Efficiency Working Group continues to share best practice, with cross-Directorate representatives meeting regularly to share efficiency initiatives and apply repeatable efficiency processes.
2015-16 | Corporate management information | 33.6 | 32.9 | PI | 0.7 | 33.6 | 32.9 | PI | 0.7 | [1]
2016-17 | Efficiency baseline, DP p54 | 135.4 | 106.4 | PI | 29 | 169 | 139.3 | PI | 29.7 | [1]
2017-18 | Efficiency baseline, DP p54 | 316.6 | 238.1 | PI | 78.5 | 485.6 | 377.4 | PI | 108.2 | [1]
2018-19 | Efficiency baseline, DP p54 | X | 345.1 | PI | X | X | 722.5 | PI | X | [1]
2019-20 | Performance Specification | X | 489.5 | PI | X | X | 1212 | KPI | X | [1]
Delivery plan progress
KPI: Progress of work, relative to forecasts set out in the Delivery Plan, and annual updates to that Plan, and expectations at the start of RP1 |  |  |  |  | See Investment Plan tables IP1 to IP5
CPI and SPI at PCF 5 and beyond
Suite of performance indicators to demonstrate that the portfolio is being developed and the investment plan is delivered in a timely and efficient manner. These should include CPI and SPI for schemes at Project Control Framework Stage 5 and beyond |  |  |  |  | This efficiency performance indicator covers the overall major improvement programme in construction( including SR10 schemes) after Project Control Framework (PCF) stage 5.The earned value scope covers programme costs, excluding programme risk, lands and salaries. The cumulative programme position at 31st March 2018 was as follows: • CPI 0.96 indicating that the overall programme to date was 126m over budget. • SPI 1.01 indicating that the overall programme to date was £26m ahead of schedule Pre 2015, Highways Agency used a different methodology.
PCF 5
CPI - major projects | Corporate management information | 0.96 | 1 | PI | -0.04 |  |  |  |  | [2]
SPI - major projects | Corporate management information | 1.01 | 1 | PI | 0.01 |  |  |  |  | [2]
Demonstrating efficiencies
Demonstrate on an annual basis how efficiency savings have been achieved |  |  |  |  | Efficiencies are demonstrated annually through the Efficiency report, which is shared with ORR. The report demonstrates how efficiencies have been achieved against the principles in the Efficiency and Inflation Monitoring manual, i.e. the three elements of efficiency reporting: performance against RIS, register build up and movement of unit costs.
Notes and commentary
[1] Explain how efficiencies have been achieved
[2] Explain drivers of reported CPI and SPI at PCF 5

## PS7x (alternative format) (hidden)
Statement PS7: Achieving real efficiency
Performance specification
|  |  | 2015-16 |  |  | 2016-17 |  |  | 2017-18 |  |  | 2018-19 |  |  | 2019-20 |  |  |  | Cumulative
| Source of baseline | KPI, PI or Req | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Notes
Cost savings
Total savings of £1.212 billion over RP1 on capital expenditure | Efficiency baseline, DP p54 | PI | X | 30 | No actuals | X | 110 | No actuals | X | 245 | No actuals | X | 357 | No actuals | X | 470 | No actuals | X | 1212 | No actuals
[1]
Delivery plan progress
Progress of work, relative to forecasts set out in the Delivery Plan, and annual updates to that Plan, and expectations at the start of RP1 |  |  | No of projects |  |  | No of projects |  |  | No of projects |  |  | No of projects |  |  | No of projects |  |  | No of projects
PCF 0 | Delivery plan update | KPI | X | 0 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 1 | Delivery plan update | KPI | X | 62 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 2 | Delivery plan update | KPI | X | 15 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 3 | Delivery plan update | KPI | X | 6 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 4 | Delivery plan update | KPI | X | 0 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 5 | Delivery plan update | KPI | X | 0 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 6 | Delivery plan update | KPI | X | 20 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 7 | Delivery plan update | KPI | X | 6 | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 8 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
|  |  | £m |  |  | £m |  |  | £m |  |  | £m |  |  | £m |  |  | £m
PCF 0 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 1 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 2 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 3 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 4 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 5 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 6 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 7 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
PCF 8 | Delivery plan update | KPI | X | X | No actuals |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | X | X | X | [2]
CPI and SPI at PCF 5 and beyond
Suite of performance indicators to demonstrate that the portfolio is being developed and the investment plan is delivered in a timely and efficient manner. These should include CPI and SPI for schemes at Project Control Framework Stage 5 and beyond
PCF 5
CPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
CPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
PCF 6
CPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
CPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
PCF 7
CPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
CPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
PCF 8
CPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
CPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
Total PCF 5-8
CPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - major projects | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
CPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
SPI - programmes | Delivery plan | PI | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [3]
|  |  | 2015-16 |  |  | 2016-17 |  |  | 2017-18 |  |  | 2018-19 |  |  | 2019-20 |  |  | Cumulative
Demonstrating efficiencies
Demonstrate on an annual basis how efficiency savings have been achieved |  |  | £m |  |  | £m |  |  | £m |  |  | £m |  |  | £m |  |  | £m
List efficiencies | [20 empty] | [4]
SR13 and prior schemes | [20 empty] | [4]
List activities |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  | [4]
RIS 1 schemes | [20 empty] | [4]
List activities |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  | [4]
RIS 2 development | [20 empty] | [4]
List activities |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  | [4]
Feasibility studies | [20 empty] | [4]
List activities |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  | [4]
Resurfacing | [20 empty] | [4]
List activities |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  | [4]
Other renewals | [20 empty] | [4]
List activities |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  | [4]
|  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X
Other monitoring requirements
|  |  | 2015-16 |  |  | 2016-17 |  |  | 2017-18 |  |  | 2018-19 |  |  | 2019-20 |  |  | Cumulative
| Source of baseline |  | Actual | baseline | Difference | Actual | baseline | Difference | Actual | baseline | Difference | Actual | baseline | Difference | Actual | baseline | Difference | Actual | baseline | Difference | Notes
Cost savings
Total savings of £1.212 billion over RP1 on capital expenditure
SR13 and prior schemes | Efficiency baseline | DPI | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals
RIS 1 schemes | Efficiency baseline | DPI | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals
RIS 2 development | Efficiency baseline | DPI | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals
Feasibility studies | Efficiency baseline | DPI | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals
Resurfacing | Efficiency baseline | DPI | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals
Other renewals | Efficiency baseline | DPI | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals
|  |  | 2015-16 |  |  | 2016-17 |  |  | 2017-18 |  |  | 2018-19 |  |  | 2019-20 |  |  | Cumulative
| Source of baseline |  | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Actual | Baseline | Difference | Notes
Actual efficiency
As actual efficiency eventuates each year – a re-forecast of the remaining efficiency to be achieved for each year in RP1. If the gap shortfall is widening include what actions are being taken to overcome it and their expected impact. | Efficiency baseline | DPI | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | X | X | No actuals | [6]
Notes and commentary
For each table above - Highways England is to provide to us its view of the data quality [possibly in an alpha numeric value].
The commentaries should also include how the company is managing the risks identified for the delivery of the outputs. This is both in terms of operational risks and risks associated with the data collation for the output or milestone.
[1] Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[2] Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[3] Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[4] Explain significant year on year variances.
[5] Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[6] Explain significant variances.

## PS8 - Network in good condition
Highways England Performance Monitoring Statements Year end 2017-18
Statement PS8: Keeping the Network in good condition |  | For a definition of the metric and parameters for measuring and monitoring performance regarding network condition see Highways England’s Operational Metrics Manual
Performance specification
|  |  | Annual |  |  | Cumulative | Cumulative |  | Cumulative
| Source of baseline | Actual | baseline | KPI/PI/ Req | Difference | Actual | baseline | KPI/PI/ Req | Difference | Notes
KPI
Pavement
The percentage of pavement asset that is in a condition that does not require further investigation for possible maintenance to be maintained at 95% or above | [5 empty] | In 2017-18, Highways England achieved a year-end actual of 95.2%, 0.2pp above target, performance has continued to improve since the low point of 2015-16, rising by 2.9pp from the re-baselined figure of 92.3%. This signifies the positive impact of our ongoing recovery and performance improvement work. Over the last two years Highways England has delivered additional renewals to ensure alignment between our renewals programme and KPI target. Highways England delivered 15 lane km as part of a recovery plan in 2016-17 and subsequently completed another 15 km of resurfacing in addition to the planned renewals programme in 2017-18. *Additional data was received in May 2016 and subsequently validated in June 2016. resulting in a reduction in the published year-end performance figure (of 95.4%) to 92.3%. For consistency with the 2016-17 Annual Report & Accounts, the original validated figure has been shown with a statement acknowledging the re-baselined figure of 92.3%.
2011-12 | Historic Data | 95.6%
2012-13 | Historic Data | 96.4%
2013-14 | Historic Data | 95.2%
2014-15 | Historic Data | 94.9%
2015-16 | Corporate management information | *95.40% | 95% | KPI | 0.4% |  |  |  |  | [1]
2016-17 | Corporate management information | 94.3% | 95% | KPI | -0.7% |  |  |  |  | [1]
2017-18 | Performance specification | 95.2% | 95% | KPI | 0.2% |  |  |  |  | [1]
2018-19 | Performance specification | X | 95% | KPI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | 95% | KPI | X |  |  |  |  | [1]
PIs
Asset measures have remained stable since 2016-17. All Geotechnical inspections have been carried out as planned in year. The performance over the baseline period of 2010-15 is largely stable, with the increase in survey length and length of network keeping pace.
Geotechnical asset inventory & geotechnical asset risk level (condition)
Length of the network for which a geotechnical inventory survey has been completed (km)
2010-11 | Historic Data | 12835
2011-12 | Historic Data | 12816
2012-13 | Historic Data | 12787
2013-14 | Historic Data | 12860
2014-15 | Historic Data, OMM | 12984
2015-16 | Corporate management information | 12978 | 12984 | PI | [5 empty] | [1]
2016-17 | Corporate management information | 12987 | 12978 | PI | 9 |  |  |  |  | [1]
2017-18 | Performance specification | 12994 | 12987 | PI | 7 |  |  |  |  | [1]
2018-19 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
Length (and percentage) of geotechnical assets with low risk or below
2010-11 | Historic Data | 91%
2011-12 | Historic Data | 91%
2012-13 | Historic Data | 92%
2013-14 | Historic Data | 93%
2014-15 | Historic Data, OMM | 96.4%
2015-16 | Corporate management information | 96.6% | 96.4% | PI | 0.2% |  |  |  |  | [1]
2016-17 | Corporate management information | 96.8% | 96.6% | PI | 0.2% |  |  |  |  | [1]
2017-18 | Performance specification | 97.2% | 96.8% | PI | 0.4% |  |  |  |  | [1]
2018-19 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
Drainage Asset - inventory and condition data coverage
The percentage of the network with drainage inventory data recorded on HADDMS
2010-11 | Historic Data | 69% |  |  |  | Drainage measures incorporate all of the SRN, including DBFO routes. The inventory data has remained stable at 88% in March 2018. DBFO routes were first included in the figures for May 2015, when the score was 84%. Although this indicator is below the 2014-15 90% baseline, the data now includes more of the SRN. Coverage excluding DBFOs for March 2017 is 95.6%. This is the number that can be directly compared with the 90% baseline figure. A number of data sets are used to identify locations on the network with a risk of flooding including routine inspections, the drainage inventory and condition database and records of flooding incidents. The absence of drainage inventory and condition data does not prevent the identification of ‘flooding hotspots’ that are then risk rated and prioritised for potential signing and/or alleviation schemes.
2011-12 | Historic Data | 77%
2012-13 | Historic Data | 84%
2013-14 | Historic Data | 87%
2014-15 | Historic Data, OMM | 90%
2015-16 | Corporate management information | 87% | 90% | PI | -3% |  |  |  |  | [1]
2016-17 | Corporate management information | 88% | 87% | PI | 1% |  |  |  |  | [1]
2017-18 | Performance specification | 88% | 88% | PI | 0% |  |  |  |  | [1]
2018-19 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
Percentage of the network with drainage condition data
2010-11 | Historic Data | 4%
2011-12 | Historic Data | 10%
2012-13 | Historic Data | 15%
2013-14 | Historic Data | 19%
2014-15 | Historic Data, OMM | 23%
2015-16 | Corporate management information | 27.1% | 23% | PI | 4.1% |  |  |  |  | [1]
2016-17 | Corporate management information | 31% | 27.1% | PI | 3.9% |  |  |  |  | [1]
2017-18 | Performance specification | 34% | 31% | PI | 3% |  |  |  |  | [1]
2018-19 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
Technology Asset Availability
The availability and performance of each technology asset type
RCC technology
2013-13 | Historic Data, | 99.93%
2012-14 | Historic Data, | 99.95%
2014-15 | Historic Data, OMM | 99.94% | 99.95%
2015-16 | Corporate management information | 99.92% | 99.94% | PI | -0.02% |  |  |  |  | [1]
2016-17 | Corporate management information | 99.97% | 99.92% | PI | 0.05% |  |  |  |  | [1]
2017-18 | Performance specification | 99.97% | 99.97% | PI | 0% |  |  |  |  | [1]
2018-19 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
Roadside technology
2012-13 |  | 98.13%
2013-14 | Historic Data | 98.23%
2014-15 | Historic Data, OMM | 99.98% | 98.23%
2015-16 | Corporate management information | 98.67% | 99.98% | PI | -1.31% |  |  |  |  | [1]
2016-17 | Corporate management information | 98.79% | 98.67% | PI | 0.12% |  |  |  |  | [1]
2017-18 | Performance specification | 98.4% | 98.79% | PI | -0.39% |  |  |  |  | [1]
2018-19 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
NRTS
2012-13 | Historic Data | 99.96%
2013-14 | Historic Data | 99.98%
2014-15 | OMM | 98.2% | 99.98%
2015-16 | Corporate management information | 99.99% | 98.2% | PI | 1.79% |  |  |  |  | [1]
2016-17 | Corporate management information | 99.99% | 99.99% | PI | 0% |  |  |  |  | [1]
2017-18 | Performance specification | 99.99% | 99.99% | PI | 0% |  |  |  |  | [1]
2018-19 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Performance specification | X | [X] | PI | X |  |  |  |  | [1]
Structure Asset - inventory and condition
Percentage of structures that have basic inventory information
2014-15 | OMM | X
2015-16 | Corporate management information | 97.8% | 97.8% | PI | 0% |  |  |  |  | [1]
2016-17 | Corporate management information | 98.1% | 97.8% | PI | 0.3% |  |  |  |  | [1]
2017-18 | Delivery Plan | 98.2% | 97.8% | PI | 0.4% |  |  |  |  | [1]
2018-19 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
Condition indicator - Average Structural Condition (Scav)
2014-15 | OMM | X
2015-16 | Corporate management information | 84.32% | 84.3% | PI | 0.1% |  |  |  |  | [1]
2016-17 | Corporate management information | 84.79% | 84.3% | PI | 0.49% |  |  |  |  | [1]
2017-18 | Delivery Plan | 84.56% | 84.3% | PI | 0.26% |  |  |  |  | [1]
2018-19 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
Condition indicator - Critical Element Condition (SCcrit)
2014-15 | OMM | X
2015-16 | Corporate management information | 61.01% | 61% | PI | 0.1% |  |  |  |  | [1]
2016-17 | Corporate management information | 63.28% | 61% | PI | 2.28% |  |  |  |  | [1]
2017-18 | Delivery Plan | 62.76% | 61% | PI | 1.76% |  |  |  |  | [1]
2018-19 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
Condition indicator - Structural Condition Index (SCI)
2014-15 | OMM | X
2015-16 | Corporate management information | 79.1% | 78.2% | PI | 0.9% |  |  |  |  | [1]
2016-17 | Corporate management information | 79.2% | 78.2% | PI | 1% |  |  |  |  | [1]
2017-18 | Delivery Plan | 79.8% | 78.2% | PI | 1.6% |  |  |  |  | [1]
2018-19 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
2019-20 | Delivery Plan | X | [X] | PI | X |  |  |  |  | [1]
Requirements
Asset information quality plan
Produce an implementation plan, by 31 March 2016, to show how the Company will improve asset information quality over RP1 | Highways England has produced The Asset Information Improvement Plan (AIIP). The AIIP has now been taken under the governance of the Information Leadership Group (ILG) and presented to them. Key achievements in 2017/18 include: • Asset Data Management Manual (ADMM) v7 was published in March 2018 and now includes inventory requirements for all the four main asset types: Pavements, Structures, Drainage and Geotechnical. • The Asset Information Quality (AIQ) Toolkit has now been developed. A trial commences May 2018 with Areas 7 and 13, to finalise the toolkit and its use, prior to wider roll-out and embedment across the company. • A tool to assist the business to check compliance of data with the Asset Data Management Manual (ADMM) has been developed in conjunction with the Toolkit. The ADMM Compliance Checker enables logic checks of our data, helping to avoid erroneous data entries. • IAN128/15/B (Highways England Supply Chain Health and Safety Reporting) has been produced and is being published in April 2018. The amendments to IAN128/15 strengthen the procedure when reporting Failures of Infrastructure Assets (FOIA), ensuring that effective reporting is in place to ensure that the national impact of localised FOIAs is consistently assessed and appropriate actions are implemented to both mitigate associated incidents and prevent future occurrence. • In order to improve the clarity and consistency of Highways England’s asset information, high level Asset Data Transfer Process Maps have been developed. These aim to clarify and simplify the process by which asset data is transferred between and within HE directorates, indicating who is to do what, and by signposting to relevant supporting processes, guidance and tools.
Annual
| Source of baseline | Milestone achieved Y/N | Actual | baseline | KPI/PI/ Req | Difference
New condition measures indicator
Pavements (DP p35)
Milestones
2015-16 | N/A
2016-17 | Agreement by 31 March 17 | N | X | X | Req | X |  | Proposed indicator is undergoing calibration and validation. Evidence from the validation exercise is now being gathered to provide a final assessment in time for the March 2019 deadline. |  | [2]
2017-18 | Delivery plan update |  | X | X | Req | X |  |  |  | [2]
2018-19 | Delivery plan update / Complete validation | X | X | X | Req | X |  |  |  | [2]
2019-20 | Delivery plan update | X | X | X | Req | X |  |  |  | [2]
Structures (DP p35)
Milestones
2015-16 | N/A | N/A
2016-17 | Agreement by 31 March 17 | N | X | X | Req | X |  | Proposed indicator is undergoing calibration and validation. Shadow testing alongside the current metric to commence in 2018 |  | [2]
2017-18 | Delivery plan update |  | X | X | Req | X |  |  |  | [2]
2018-19 | Delivery plan update / Complete validation | X | X | X | Req | X |  |  |  | [2]
2019-20 | Delivery plan update | X | X | X | Req | X |  |  |  | [2]
Drainage (DP p350
Milestones
2015-16 | N/A | N/A | [5 empty] | A proposed indicator has been developed and agreed internally in line with the March 2018 deadline.
2016-17 | N/A | N/A
2017-18 | Agreement by 31 March 18 | Y | X | X | Req | X |  |  |  | [2]
2018-19 | Delivery plan update | X | X | X | Req | X |  |  |  | [2]
2019-20 | Delivery plan update / Complete validation | X | X | X | Req | X |  |  |  | [2]
Technology (DP p35)
Milestones
2015-16 | N/A | N/A | [5 empty] | Various options are being considered to assess whether there is a need for a technology indicator that differs from the metric currently in use.
2016-17 | N/A | N/A
2017-18 | Agreement by 31 March 18 | N | X | X | Req | X |  |  |  | [2]
2018-19 | Delivery plan update | X | X | X | Req | X |  |  |  | [2]
2019-20 | Delivery plan update / Complete validation | X | X | X | Req | X |  |  |  | [2]
Geotechnical works (DP p35)
Milestones
2015-16 | N/A | N/A | [5 empty] | A proposed indicator has been developed and agreed internally in line with the March 2018 deadline.
2016-17 | N/A | N/A
2017-18 | Agreement by 31 March 18 | Y | X | X | Req | X |  |  |  | [2]
2018-19 | Delivery plan update | X | X | X | Req | X |  |  |  | [2]
2019-20 | Delivery plan update / Complete validation | X | X | X | Req | X |  |  |  | [2]
Other monitoring requirements
|  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
Asset pavement condition measure for motorways and APTR
Motorways | Corporate management information | 98.3 | 98 | 97.9 | X | X | DPI |  |  | [3]
APTR | Corporate management information | 93.5 | 91.7 | 93.3 | X | X | DPI |  |  | [3]
For the entire network, provide proportion of pavement for which condition data is collected in each year
Physical km monitored | Corporate management information | 11694 | 11688 | 11658 | X | X | DPI |  |  | [4]
Notes and commentary
[1] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[2] Explain what actions and activities have been taken by management to achieve trajectory and explain whether they were successful. Explain external factors that have impacted the actuals and quantify that impact. Explain reasons for the variance.
[3] Explain reasons for movements year on year and reasons for variance in APTR and Motorway.
[4] Explain reasons for movements year on year.
[X] HE and ORR to consider reporting this data once appropriate strategies and/or reporting has been developed.

## IP1
Statement IP1: Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
Highways England Delivery Plan - Major Improvements
Milestone Definitions:
PRE OPTIONS PHASE - Projects in the early stages of the lifecycle and for major schemes will often involve working up a range of options, however for more simple solutions or small scale enhancements this will typically be about development of a single solution to address the transport problem
OPTIONS PHASE - Typically only applicable to major schemes where multiple options will be developed and appraised, a number of these options may be presented to the public as part of formal consultation, at the end of this process a preferred route will normally be identified to be further developed. For smaller scale schemes or schemes where there is only one option this stage will involve further development and appraisal of the identified solution up to outline business case.
DEVELOPMENT PHASE - Preliminary design is undertaken during this phase for all projects. In addition for Major schemes where there are significant environmental impacts or where the land take is over a specified number of hectares, a submission to the Planning Inspectorate (PIN's) will be required. Later in phase all projects will complete detailed design’s in preparation for awarding contracts and for Major schemes this will often also involve exhibitions to inform the public of the final plans together with details of the construction schedule and any potential issues.
CONSTRUCTION PHASE - START OF WORKS - the date when the start of works is declared which typically will be when the construction budget has been agreed, a contract has been established, notice to proceed issued and physical works will start on site.
CONSTRUCTION PHASE - OPEN FOR TRAFFIC - the date when the public will benefit from the improvements, in some instances residual works on the verges and off site will continue including some potential over night closures to finalise certain elements.
2015-20 DELIVERY PLAN COMMITMENT - the date committed to in Highways England's 2015-20 Delivery Plan.
2017-18 DELIVERY PLAN COMMITMENT - the date committed to in Highways Englands delivery Plan update for the reported financial year.
CURRENT FORECAST POSITION / ACTUAL ACHIEVED - the latest Highways England forecast position where committed dates have not been achieved / the actual date that has been achieved.
|  | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works |  |  | Open for Traffic
|  |  |  | 2015-20 Delivery Plan Commitment | 2017-18 Delivery Plan Commitment | Current Forecast Position / Actual Achieved | 2015-20 Delivery Plan Commitment | 2017-18 Delivery Plan Commitment | Current Forecast Position / Actual Achieved | Lane miles delivered (actual)
Schemes Already in Construction (SR10) |  | 1 | A556 Knutsford to Bowden | N/A | N/A | 2014-11-10 | 2017-03-31 | 2017-03-01 | 2017-03-06 | 0
|  | 2 | A1 Coal House to Metro Centre | N/A | N/A | 2014-08-26 | 2016-06-30 | 2016-06-01 | 2016-07-04 | 8.7
|  | 3 | A1 Leeming to Barton | N/A | N/A | 2014-03-03 | 2017-06-30 | 2017-06-01 | 2018-03-28 | 23.6121
|  | 4 | M1 J28-J31 | N/A | N/A | 2014-08-01 | 2016-03-31 | 2016-03-01 | 2016-03-01 | 38.5
|  | 5 | A453 Widening | N/A | N/A | 2013-01-01 | 2015-09-30 | 2015-09-01 | 2015-07-01 | 14.3
|  | 6 | A14 Kettering bypass widening | N/A | N/A | 2013-11-01 | 2015-06-30 | 2015-06-01 | 2015-04-01 | 5.7
|  | 7 | M1 Junction 19/M6 | N/A | N/A | 2014-01-01 | 2016-12-31 | 2016-12-01 | 2016-12-01 | 0
|  | 8 | A45/A46 Tollbar End | N/A | N/A | 2014-01-31 | 2016-12-31 | 2016-12-01 | 2016-12-15 | 3.7
|  | 9 | A5/M1 J11a Link | N/A | N/A | 2015-02-27 | 2017-06-30 | 2017-06-01 | 2017-05-11 | 11.1847
|  | 10 | M25 J30 | N/A | N/A | 2015-02-01 | 2017-06-30 | 2017-06-01 | 2016-12-01 | 0
|  | 11 | M6 J10A-J13 | N/A | N/A | 2013-09-01 | 2015-12-31 | 2015-12-01 | 2016-02-01 | 19
|  | 12 | A30 Temple to Carblake | N/A | N/A | 2015-03-01 | 2016-12-31 | 2016-12-01 | 2017-07-01 | 7.8293
|  | 13 | M1 J32-J35A | N/A | N/A | 2014-03-01 | 2017-03-31 | 2017-03-01 | 2017-03-01 | 17.9
|  | 14 | M1 J39-J42 | N/A | N/A | 2013-11-25 | 2015-12-31 | 2015-12-01 | 2015-12-14 | 13
|  | 15 | M60 J8 to M62 J20 (Manchester Smart Motorway) | N/A | N/A | 2014-07-01 | 2017-09-30 | 2017-09-30 | Q2 2018
|  | 16 | M3 J2-J4A | N/A | N/A | 2014-11-03 | 2017-06-30 | 2017-06-01 | 2017-06-30 | 26.8432
Schemes Announced in June 2013 and due to start construction by end 2019/20 (SR13) |  | 17 | A160/A180 Immingham | 2015-06-30 | 2015-06-01 | 2015-03-27 | 2017-03-31 | 2017-03-01 | 2017-03-27 | 2.5
|  | 18 | A21 Tonbridge to Pembury | 2015-06-30 | 2015-06-01 | 2015-04-01 | 2017-03-31 | 2017-03-31 | 2017-09-21 | 5.0952
|  | 19 | M1 J13 - J19 Smart Motorway | 2015-12-31 | 2015-12-01 | 2015-11-01 | 2022-03-31 | 2022-03-01
|  | 20 | M5 J4a - J6 Smart Motorway | 2015-12-31 | 2015-12-01 | 2015-11-30 | 2018-03-31 | 2017-09-01 | 2017-05-25 | 17.6469
|  | 21 | M6 J16 - J19 Smart Motorway | 2015-12-31 | 2015-12-01 | 2015-11-30 | 2019-03-31 | 2019-03-01
|  | 22 | A14 Cambridge to Huntingdon | 2017-03-31 | 2016-12-01 | 2016-10-14 | 2021-03-31 | 2021-03-01
|  | 23 | M20 Junction 10a | 2018-03-31 | 2018-03-01 | 2018-03-01 | 2019-03-31 | 2019-03-01
|  | 24 | A19 / A1058 Coast Road | 2017-03-31 | 2016-09-01 | 2016-06-27 | 2019-03-31 | 2019-03-01
|  | 25 | M4 J3 - J12 Smart Motorway | 2017-03-31 | 2017-03-01 | 2017-03-27 | 2022-03-31 | 2022-03-01
|  | 26 | A63 Castle Street | 2017-03-31 | 2019-03-01 |  | 2021-03-31 | 2022-03-01
|  | 27 | M1 J24 - J25 Smart Motorway | 2017-03-31 | 2017-03-01 | 2017-03-30 | 2018-03-31 | 2019-03-01
|  | 28 | M6 J2 - J4 Smart Motorway | 2018-03-31 | 2018-03-01 | 2018-03-01 | 2020-03-31 | 2020-03-01
|  | 29 | M6 J13 - J15 Smart Motorway | 2018-03-31 | 2018-03-01 | 2018-03-20 | 2022-03-31 | 2022-03-01
|  | 30 | M20 J3 - J5 Smart Motorway | 2018-03-31 | 2018-03-01 | 2018-03-29 | 2020-03-31 | 2020-03-01
|  | 31 | M23 J8 - J10 Smart Motorway | 2018-03-31 | 2018-03-01 | 2018-03-29 | 2020-03-31 | 2020-03-01
|  | 32 | M27 J4 - J11 Smart Motorway | 2018-03-31 | 2019-03-01 |  | 2021-03-31 | 2021-03-01
|  | 33 | M6 J21a - J26 Smart Motorway | 2019-03-31 | 2019-03-01 |  | 2020-03-31 | 2022-03-01
|  | 34 | M60 J24 - J27 Smart Motorway | 2019-03-31 | 2021-03-01 |  | 2020-03-31 | 2023-03-01
|  | 35 | A19 Testos | 2019-03-31 | 2019-03-01 |  | 2021-03-31 | 2021-03-01
|  | 36 | M54 to M6 / M6 toll (Option D5) | 2019-03-31 | 2019-03-01 |  | 2022-03-31 | 2022-03-01
|  | 37 | A27 Chichester Bypass | 2019-03-31 | cancelled | cancelled | 2021-03-31 | cancelled | cancelled
|  | 38 | A38 Derby Junctions | 2020-03-31 | 2020-03-01 |  | 2023-03-31 | 2023-03-01
|  | 39 | A2 Bean & Ebbsfleet | 2020-03-31 | 2020-03-01 |  | 2023-03-31 | 2023-03-01
|  | 40 | M62 J10 - J12 Smart Motorway | 2020-03-31 | 2018-03-01 | 2018-03-29 | 2023-03-31 | 2020-03-01
|  | 41 | M56 J6 - J8 Smart Motorway | 2020-03-31 | 2019-03-01 |  | 2022-03-31 | 2021-03-01
|  | 42 | M3 J9 - J14 Smart Motorway | 2020-03-31 | 2020-03-01 |  | 2022-03-31 | 2022-03-01
Schemes announced in December 14 and due to start construction by end 2019/20 (AS14) |  | 43 | A19 Down Hill Lane junction improvement | 2020-03-31 | 2020-03-01 |  | N/A | 2021-03-01
|  | 44 | A19 Norton to Wynyard | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 45 | A1 & A19 Technology enhancements | 2020-03-31 | VfM N/A | N/A | N/A | VfM N/A | N/A
|  | 46 | M1 Junction 45 Improvement | 2020-03-31 | 2020-03-01 | 2017-01-01 | N/A | 2018-03-01 | 2018-03-01 | 0
|  | 47 | M621 Junctions 1-7 improvements | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 48 | M62/M606 Chain Bar | 2020-03-31 | VfM N/A | N/A | N/A | VfM N/A | N/A
|  | 49 | M62 Junctions 20-25 | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 50 | A585 Windy Harbour - Skippool | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 51 | A5036 Princess Way - Access to Port of Liverpool | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 52 | M6 Junction 22 upgrade | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 53 | M53 Junctions 5-11 | 2020-03-31 | VfM N/A | N/A | N/A | VfM N/A | N/A
|  | 54 | M56 new Junction 11A | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 55 | M6 Junction 19 Improvements | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 56 | A500 Etruria widening | 2020-03-31 | 2019-03-01 |  | N/A | N/A
|  | 57 | M1 Junctions 23A-24 | 2020-03-31 | 2020-03-01 | 2017-03-30 | N/A | 2019-03-01
|  | 58 | M6 Junction 10 improvement | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 59 | A5 Dodwells to Longshoot Widening | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 60 | M42 Junction 6 | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 61 | A46 Coventry junction upgrades | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 62 | M40/M42 interchange Smart Motorways | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 63 | A45/A6 Chowns Mill junction improvement | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 64 | M5 Junctions 5, 6 & 7 junction upgrades | 2020-03-31 | 2020-03-01 | 2015-07-01 | N/A | 2019-03-01
|  | 65 | A43 Abthorpe Junction | 2020-03-31 | 2020-03-01 | 2015-06-01 | N/A | 2017-06-01 | 2017-04-01 | 0
|  | 66 | A428 Black Cat to Caxton Gibbet | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 67 | M11 Junctions 8 to 14 - technology upgrade | 2020-03-31 | VfM N/A | N/A | N/A | VfM N/A | N/A
|  | 68 | A12 Chelmsford to A120 widening | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 69 | A12 whole-route technology upgrade | 2020-03-31 | VfM N/A | N/A | N/A | VfM N/A | N/A
|  | 70 | A1(M) Junctions 6-8 Smart Motorway | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 71 | M11 Junction 7 junction upgrade | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 72 | A34 Oxford Junctions | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 73 | A34 Technology enhancements | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 74 | M25 Junction 25 improvement | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 75 | M25 Junction 28 improvement | 2020-03-31 | 2022-03-01 |  | N/A | N/A
|  | 76 | M4 Heathrow Slip Road | 2020-03-31 | 2018-09-01 | 2017-09-01 | N/A | 2018-03-01 | 2018-03-01 | 0
|  | 77 | M2 Junction 5 improvements | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 78 | M25 Junctions 10-16 | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 79 | M25 Junction 10/A3 Wisley interchange | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 80 | M3 Junction 9 improvement | 2020-03-31 | 2022-03-01 |  | N/A | N/A
|  | 81 | M3 Junction 10-11 improved slip roads | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 82 | M3 Junctions 12-14 improved slip roads | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 83 | M27 Southampton Junctions | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 84 | M271 / A35 Redbridge Roundabout Upgrade | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 85 | A31 Ringwood | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 86 | M49 Avonmouth Junction | 2020-03-31 | 2020-03-01 | 2017-12-11 | N/A | N/A
|  | 87 | M5 Bridgwater Junctions | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 88 | A52 Nottingham Junctions | 2020-03-31 | 2020-03-01 | 2017-01-16 | N/A | N/A
|  | 89 | A14 Junction 10a | 2020-03-31 | VfM N/A | N/A | N/A | VfM N/A | N/A
|  | 90 | A5 Towcester Relief Road | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 91 | A30 Chiverton to Carland Cross | 2020-03-31 | 2020-03-01 |  | N/A | N/A
Schemes identified following the outcomes of six feasibility studies | A1 North of Newcastle | 92 | A1 Morpeth to Ellingham dualling | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 93 | A1 North of Ellingham | 2020-03-31 | 2020-03-01 |  | N/A | N/A
| A1 NGWB | 94 | A1 Scotswood to North Brunton | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 95 | A1 Birtley to Coal House widening | 2020-03-31 | 2021-03-01 |  | N/A | N/A
| Trans-Pennine Routes | 96 | A628 Climbing Lanes | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 97 | A61 Dualling | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 98 | Mottram Moor link road | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 99 | A57(T) to A57 Link Road | 2020-03-31 | 2020-03-01 |  | N/A | N/A
| The A47/A12 Corridor | 100 | A47 North Tuddenham to Easton | 2020-03-31 | 2022-03-01 |  | N/A | N/A
|  | 101 | A47 Blofield to North Burlingham dualling | 2020-03-31 | 2022-03-01 |  | N/A | N/A
|  | 102 | A47 Acle Straight | 2020-03-31 | 2020-03-01 | 2017-02-01 | N/A | 2018-03-01 | 2018-03-01 | 0
|  | 103 | A47 & A12 junction enhancements | 2020-03-31 | 2019-03-01 |  | N/A | N/A
|  | 104 | A47/A11 Thickthorn Junction | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 105 | A47 Guyhirn Junction | 2020-03-31 | 2021-03-01 |  | N/A | N/A
|  | 106 | A47 Wansford to Sutton | 2020-03-31 | 2021-03-01 |  | N/A | N/A
| The A27 Corridor | 107 | A27 Arundel Bypass | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 108 | A27 Worthing and Lancing improvements | 2020-03-31 | 2020-03-01 |  | N/A | N/A
| The A303/A30/A358 Corridor | 109 | A303 Amesbury to Berwick Down | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 110 | A303 Sparkford - Ilchester dualling | 2020-03-31 | 2020-03-01 |  | N/A | N/A
|  | 111 | A358 Taunton to Southfields | 2020-03-31 | 2020-03-01 |  | N/A | N/A
Schemes contributing to investment with local authorities |  | 112 | A50 Uttoxeter | 2015-12-31 | 2015-12-01 | 2015-12-01 | N/A | 2019-03-01

## IP2
Highways England Performance Monitoring Statements Year end 2017-18
Statement IP2: Strategic studies deliverables
Date for completion of study
Strategic studies (IP page 49) | Source of baseline date | Baseline date | Latest forecast date | Actual date | Notes
#REF!
Northern Trans-Pennine | Corporate management information | 2016-10-31 | 2016-10-31 | 2016-10-31 | This study has completed and published on 28th November 2016. https://www.gov.uk/government/publications/northern-trans-pennine-strategic-study-stage-3-report Highways England has continued development work for consideration in future RIS periods.
Trans-Pennine Tunnel | Corporate management information | 2016-10-31 | 2016-10-31 | 2016-10-31 | This study has completed and published on 28th November 2016. https://www.gov.uk/government/publications/trans-pennine-tunnel-strategic-study-stage-3-report Highways England has continued development work for consideration in future RIS periods.
Manchester Northwest Quadrant | Corporate management information | 2016-10-31 | 2016-10-31 | 2016-10-31 | This study has completed and published on 28th November 2016. https://www.gov.uk/government/publications/manchester-north-west-quadrant-strategic-study-stage-3-report Highways England has continued development work for consideration in future RIS periods.
A1 East of England | Corporate management information | 2016-10-31 | 2016-10-31 | 2016-10-31 | This study has completed and published on 28th November 2016. https://www.gov.uk/government/publications/a1-east-of-england-strategic-study-stage-3-report Highways England has continued development work for consideration in future RIS periods.
Oxford to Cambridge Expressway | Corporate management information | 2016-11-30 | 2016-11-30 | 2016-11-30 | Study completed, stage 3 report published 28th November 2016. https://www.gov.uk/government/publications/oxford-to-cambridge-expressway-strategic-study-stage-3-report Highways England has continued development work for consideration in future RIS periods.
M25 South-west Quadrant | Corporate management information | n/a | 2017-02-28 | 2017-03-06 | Highways England were commissioned by DfT to procure and project manage this study. The study has completed and published 16th March 2017. https://www.gov.uk/government/publications/m25-south-west-quadrant-strategic-study-stage-3-report Highways England has continued development work for consideration in future RIS periods.
Other studies
Severn Crossing | n/a | This study is being led by DfT with input and support from Highways England. | n/a | n/a | n/a

## IP3
Highways England Performance Monitoring Statements Year end 2017-18
Statement IP3: Ring-fenced investment funds
Element | Deliverable |  | Comments
2017-18
| Developed | Delivered
Environment
Water | 10 | 13 | The feasibility work we've done in 2017-18 and previous years has led to 16 flooding and 15 water quality projects which will be delivered in 2018-19. Through the Environment Fund, we have mitigated 1 flooding hotspot, improving the safety of the network and making it more resilient – as well as removing flood risk to the adjacent community. We have improved water quality at 2 outfall locations to reduce the level of pollution to within acceptable thresholds. There are specific performance indicators within Highways England’s Delivery Plan for both these initiatives. A further 13 schemes have completed detailed design in preparation for delivery in future years.
Noise | 5 | 2 | The total number of Noise Important Areas mitigated in 2017-18 is 448. This consists of 386 through noise insulation, 47 through resurfacing, 8 through major scheme bypasses, 2 through the provision of barriers and 5 with both noise insulation and resurfacing. The cumulative total for Roads Period 1 is 651 against the KPI target of 1150. This consists of 386 through noise insulation, 231 through resurfacing, 13 through major scheme bypasses, 5 through the provision of barriers and 16 with both noise insulation and resurfacing.
Carbon | 18 | 16 | 16 projects have led to over 2000 lighting units and 100 traffic signals being converted to LED which will reduce our carbon footprint and improve the environmental performance of the SRN. 18 further projects have completed detailed design and will be delivered in 2018-19, further improving our environmental performance
Landscape | 48 | 25 | 25 landscape improvements included work to enhance the quality of the landscape on the SRN at 25 locations and to improve visual screening at 5 locations which will reduce visual intrusion to adjacent residents and communities. A further 48 locations have now completed detailed design. 66 landscape projects will be delivered in 2018-19 as a result of the detailed designs and feasibility carried out in previous years
Biodiversity | 20 | 13 | 13 biodiversity projects have created additional species rich grassland and improved connectivity for species across the landscape. 15 SSSI management plans were written, in conjunction with Natural England. When the work within the plans is carried out, we expect the condition of the SSSI units within our ownership to improve. 20 further biodiversity projects have completed their detailed design phase. 61 projects have been identified for construction in the 2018-19 programme as a result of the detailed designs and feasibility work done in previous years
Cultural Heritage | 11 | 4 | As a result of the feasibility work done in 2017-18 and in previous years, 20 projects have been identified for delivery in 2018-19 Cultural heritage enhancements were made at 4 sites to improve the area and encourage visitors. 11 further projects have completed their detailed design.
Legacy | 0 | 1 | £1.5m was awarded to the A5/M1 Link project to make improvements to Dunstable High Street. This is to improve the inter-connectedness of the area, give priority to pedestrians and cyclists and improve the aesthetics of the High Street, making it a better place for people to spend their time
Total | 112 | 74 | Environment outputs are assured by the EDF Programme Manager. All mitigated outfalls and flooding hotspots are subject to independent validation through the SES Environment Group. Noise resurfacing outputs are validated through the Highways England Pavement Management System (HAPMS).
Cycling, Safety & Integration
Cycling | 19 | 22 | Cycling - detailed design complete on 19 and construction completed on 22 cycling schemes, providing an additional 15 kilometres of new cycleway. The 22 schemes delivered are from across sub-funds; 15 cycling schemes, 5 Integration schemes, 1 Growth & Housing 1 scheme and 2 from Major Projects. Work to introduce new cycle paths and toucan crossings at the Two Mills Junction (A540/A550), in Cheshire, has been completed. The cycling programme has been developed for 2018-19 taking forward a further 44 designs and 25 construction schemes.
Safety | 61 | 45 | Safety - detailed design complete on 61 schemes and construction completed on 45 schemes at in-year. We are have started work on a scheme to improve safety on the A120 junctions at Harwich Road, Park Road and Pellens Corner, near Colchester. Work has also been completed at A5 Gledrid Roundabout in Shropshire. The safety programme has been developed for 2018-19 with a further 86 designs being taken forward and 51 construction schemes.
Integration | 34 | 17 | Integration - detailed design complete on 34 schemes and construction completed on 17 schemes at in-year. Work has been completed on the A40 by Wilton roundabout in Ross-on-Wye, with the installation of controlled crossing for vulnerable users and a new shared use footway. The integration programme has been developed for 2018-19 with a further 41 designs and 40 construction schemes.
Total | 114 | 84 | CSI outputs are assured by SES. The final figures relating to cycling schemes and new and upgraded crossings are subject to final Level 1 assurance. Photographs and completion certificates are submitted as evidence.
Innovation |  |  | The Innovation Programme has increased from 15 to 93 projects since April, which represents a rise of 84% through proactive engagement with Highways England delivery partners and the wider supply chain. The 78 projects added to the programme reflect the progress that has been made across Innovation this year and we have cause for optimism as we enter 2018-19. We continue to see around 10-15 new ideas submitted each month from across the company and supply chain which are then filtered in accordance with our innovation strategy.
Safety | 6 | 1 | 16 projects have been identified across safety with 13 of these having been introduced this financial year. Projects of note include the Southwick Tunnel Incident Detection, SVD on M25 and Safety Cams. The Fit2Go project in particular has proven successful in a number of trials to date. This involves the use of a tyre pressure sensor to ensure all tyres are legal before the vehicle can be used. Existing warning signals will only be displayed when the tyre is already under the legal limit to help safeguard against any tyre pressure related incidents. 4 of the 6 develop schemes relate to Smart Motorways' projects and these include SMP Red X, Orange Emergency Refuge Areas, 55/60 mph and rapid engineering modelling.
Improving Infrastructure | 0 | 0 | We currently have 24 projects in feasibility under the Improving Infrastructure theme and 22 of these were identified this year. This further outlines the progress that has been made under this theme, with only the asphalt rejuvenation and Sewerbatt acoustic drainage projects in the programme prior to this year. These projects are currently in their early stages with a number awaiting IDC approval.
Data & Information | 0 | 0 | 14 new projects were introduced under the data and information theme to supplement the 3 that had already been identified. The new schemes are still in feasibility with steady progress made against the existing fuel price signs, ONVIF CCTV and Dartford Check and Allow Tool projects.
New Technologies | 0 | 3 | Of the 21 projects under the new and emerging technologies theme, 19 of these were introduced this financial year. 3 schemes are still pending IDC approval with the remaining projects having started feasibility. Projects of note include the UK CITE, A2M2 and Freight Platooning schemes which are currently contributing to this theme.
Support to Sustainable Operation | 0 | 1 | 17 projects have been identified across the support to sustainable operation theme with 14 of these having been introduced this financial year. This includes the M6 M62 croft interchange and its evaluation piece which has now been completed along with our work on PV barriers. The other projects remain in feasibility with 4 of the 17 still pending IDC approval.
Total | 6 | 5 | The Innovation outputs have been assured by the Innovation Programme Manager. SMP have assured the 4 safety schemes relating to Smart Motorways' projects.
Air Quality | 0 | 0 | We completed work for the remaining air quality pilot studies during the year: - geographic pilot studies for M1 Sheffield, A38 Derby, M60 north-west quadrant Manchester and M6 West Midlands - Paraffinic fuel - Electric van demonstrator - Better use of information to influence customers' behaviours to improve air quality. - Mineral polymer barrier - awaiting technical clarification requirement We will incorporate any viable solutions identified into our forward programme. Six projects having potential to be successful received investment decision and feasibility studies are in progress. All projects will be progressed to detailed design if these studies confirm they are viable. There is sufficient evidence from our air quality monitoring around a tall, over-hanging sound barrier in the Netherlands for us to conclude that this form of barrier can help disperse and dilute pollution to improve the quality of air for our neighbours. A pilot is being quickly progressed for a location in South Yorkshire, to determine whether it is feasible to implement a barrier of this form. In parallel, we have started assembling a national programme for the design and construction of such barriers. Data from our National Air Quality Monitoring Network (NAQMN) is helping us identify the locations that will benefit the most.. We continue to progress the roll-out of the network of air quality monitoring stations. Some stations have now been operating for over a year and are providing valuable real-time data about the quality of air on our Network , which is informing (amongst other things) the priorities for our national barrier programme.
Total | 0 | 0
Growth & Development | 3 | 2 | 24 GHF schemes have completed appraisal and been approved. 20 of these have been announced, with 4 pending announcement following the end of Purdah period in May 2018. £83M of the £100m GHF allocation has now been committed, with a potential total pipeline value of approximately £135m. 3 GHF schemes completed detailed design and are either on site or in procurement pending award of construction contracts. 2 GHF projects completed construction and opened to traffic (M5 J29/A30 Tithebarn link road, A1 Darlington) with the A30 Turks Head already complete. A further 4 GHF schemes that completed detailed design in previous years remain in mobilisation or construction.
Total | 3 | 2 | GHF outputs have been assured by the GHF Programme Office.

## F2b (hidden)
Statement F2b: Summary analysis of operations general headcount (FTE)
| 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
Activity breakdown | X | X | X | X | X
| X | X | X | X | X
| X | X | X | X | X
Total operations general headcount | X | X | X | X | X
Baseline assumed | X | X | X | X | X
Variance | X | X | X | X | X
Commentary:Explanation of changes in NDD staff numbers during the year and the impact this had on operations-general costs.
Note:

## IP4
Highways England Performance Monitoring Statements Year end 2017-18
Statement IP4: Renewal volume reporting
Renewals Type | Asset Type | unit
Full year actual
|  |  | Total | Baseline | Variance | Reasons for variance from baseline (e.g Revised asset policy or information, Change in usage, Delivery of efficiency or inefficiency, re-programming, Slippage , etc)
RoR Pavement | Pavement | lane miles | 1563 | 994 | 569 | Delivered more lane miles than targeted to help improve KPI8 performance.
Renewal of Roads (RoR) Others | Road Marking | linear metre | 4289008.6691 | 2965500 | 1323508.6691 | Delivered above target due to additional resurfacing to improve KPI8 performance. In addition there were still some residual issues associated with target setting where the target did not take into account resurfacing although this has improved from the prior year.
| Kerbs | linear metre | 21151.64 | 1300 | 19851.64 | Delivered above target due to additional kerbs being associated with resurfacing schemes on all purpose trunk roads, as an efficient way of renewing assets as part of improving the performance of KPI8.
| Vehicle Restraint System (VRS) - Concrete | linear miles* | 86 | 57 | 29 | Concrete and Non Concrete VRS are now captured as one output. Delivered above target. The regions planned a prioritised programme based on assumptions of delivery according to agreed standards and value for money considerations. The actual programme delivered was based on the agreement of changed standards which resulted in significant additional delivery, particularly in the NW region.
| Vehicle Restraint System (VRS) - Non-Concrete | linear miles*
| Drainage | linear miles* | 199 | 87 | 112 | Delivered above target due to additional drainage being associated with resurfacing schemes on all purpose trunk roads, as an efficient way of renewing assets as part of the recovery of KPI8.
| Drainage - other | number | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
| Geotech | linear metre | 20301.39 | 5700 | 14601.39 | Delivered above target due to additional geotech being associated with resurfacing schemes on all purpose trunk roads, as an efficient way of renewing assets as part of the recovery of KPI8.
| Traffic Sign (non-electric) | number | 1700 | 2000 | -300 | Underdelivered as one region had set its target incorrectly. This was set on the basis of multiple sign heads instead of one insulation. Following a contract change, a number of traffic sign schemes were reassessed. The original target set was a total of traffic signs (non-elec) in various locations and did not reflect the work required. These schemes have now been reviewed and will be prioritised for future year programmes accordingly.
| Guardrail | linear metre | 1306 | 800 | 506 | Delivered above target partly due to the completion of improvement schemes and delivery of additional works as part of an efficient way of renewing the asset.
| Boundary Fencing | linear metre | 77140.56 | 33900 | 43240.56 | Delivered above target due to some residual issues associated with target setting where the target did not take into account secondary outputs as part of efficient scheme delivery.
| Footway | linear metre | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
| Lighting | number | 1327 | 1500 | -173 | Target not achivieved due to safety issues with Philips Luminaires as per Lighting CHE memo 418/18-420/18. (There were also errors in claiming outputs which were corrected in Q4. One of the reasons our lighting delivery was lower than the target was due to safety issues identified with Phillips Luminaires (as per CHE 418/18 – 421/18). As examples, one scheme was delayed due to having to return to the design stage to identify an alternative lantern appropriate for the columns used. Another was delayed whilst the safeguarding fix was identified, however temporary lighting remained in place.
| Roads - Other | number | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
| Soft Estate | number | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
Renewal of Structures (RoS) | Bridge Joint | number | 498.5 | 153 | 345.5 | Delivered above target partly due to the completion of improvement schemes and delivery of additional works as part of an efficient way of renewing the asset.
| Bridge Bearing | number | 186 | 110 | 76 | There are only a small number of schemes in this target which was exceeded due to additonal bearing refurbishments works in the East.
| Parapet | linear metre | 2913 | 1900 | 1013 | Delivered above target mainly due to additional schemes delivered on the M6 and M1 in the the Midlands.
| Waterproofing | square meters | 38396.92 | 29400 | 8996.92 | Delivered above target mainly due to significant additional waterproofing outputs on one key Midlands structure M5 Oldbury which takes the majority of traffic around the Birmingham Box.
| Vehicle Restraint System - Non Concrete | linear metre | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
| Drainage | linear metre | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
| Structures - Edge protection | number | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
| Structures - Other | number | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
Renewal of Technology (RoT) | Motorway coms equipment | number | 717 | 190 | 527 | Motorways comms equipment include treatment of individual control equipment and as such are subject to potential large variation in delivery.
| Technology renewals & improvements | number | 370 | 160 | 210 | Technology renewals and improvements include treatment of individual control equipment and as such are subject to potential large variation in delivery.
| Technology Projects - Economy | number | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
| Technology Projects -Safety | number | Not in Delivery Plan | Not in Delivery Plan | Not in Delivery Plan | No Delivery Plan target
* Converted to linear miles ton align with Annual Report

## F1
Highways England Performance Monitoring Statements Year end 2017-18
F1: Total income and expenditure
| 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total
| Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Resource expenditure
Maintenance (B3) | 266.1578 | 259.6289 | 259.0134 | 245.0837 | -13.9296 | 255.419 | 232.1658 | 233.9939 | 244.9624 | 242.2202 | 1208.7613
Renewals (B4) | 25.031 | 10.1304 | 10.7428 | 16.9041 | 6.1613 | 24.021 | 21.8342 | 22.0061 | 23.0376 | 22.7798 | 113.6787
General operations (B1) | 73.7802 | 67.7179 | 60.4725 | 60.5336 | 0.061151 | 73.8834 | 56.9457 | 51.1051 | 51.6892 | 52.5653 | 286.1888
Traffic management (B2) | 178.8663 | 108.7816 | 108.6686 | 110.3377 | 1.6691 | 179.1166 | 138.0543 | 123.8949 | 125.3108 | 127.4347 | 693.8112
Private Finance Initiative (PFI) payments (B5) | 393.5116 | 412.9115 | 421.4021 | 428.5014 | 7.0993 | 393.5116 | 416 | 429 | 408 | 413 | 2059.5116
Support costs (C1) | 131.6925 | 134.5726 | 163.3876 | 158.2194 | -5.1682 | 107 | 154 | 164 | 164 | 165 | 754
Other project activities (including Protocols) | 0.14847 | 48.7427 | 57.7965 | 41 | -16.7965 | 39 | 40 | 42 | 50 | 49 | 220
Total resource expenditure | 1069.1879 | 1042.4856 | 1081.4835 | 1060.58 | -20.9035 | 1071.9516 | 1059 | 1066 | 1067 | 1072 | 5335.9516
Capital expenditure
Renewals | 683.8382 | 626.153 | 776.0543 | 793.9793 | 17.925 | 708.8373 | 595.4398 | 787.8871 | 761.0924 | 804.7434 | 3658
Other Capital Expenditure | 267.6993 | 96.8551 | 125.7117 | 35.8619 | -89.8498 | 239.6431 | -114.5505 | 218.915 | 249.358 | 212.2054 | 805.5709
SR10 & SR13 Schemes | 926.0293 | 1141.1788 | 1076.0305 | 921.7341 | -154.2963 | 927.1888 | 1137.1223 | 1060.2368 | 1345.0105 | 1447.2505 | 5916.8088
RIS Schemes | 23.4664 | 79.1576 | 173.579 | 180.6815 | 7.1024 | 19.9533 | 72.8126 | 88.6484 | 143.2051 | 285.5645 | 610.1838
Feasibility Studies | 8.1167 | 28.4853 | 57.3419 | 60.5295 | 3.1877 | 4.6279 | 40.3702 | 44.9428 | 63.6384 | 107.2985 | 260.8777
Major Projects Pipeline Schemes | 0 | 10.989 | 4.3687 | 0 | -4.3687 | 3.6 | 230 | 0 | 0 | 0 | 233.6
Air quality | 0 | 1.9731 | 0.68944 | 0.1 | -0.58944 | 0 | 5.1056 | 18.1254 | 18.5552 | 33.2139 | 75
Cycling, Safety & Integration | 16.506 | 18.1351 | 28.8775 | 41.5684 | 12.6909 | 16.9596 | 16.3378 | 50.3265 | 31.5517 | 59.8245 | 175
Environment | 2.6067 | 13.6746 | 34.9884 | 40.1656 | 5.1772 | 6.389 | 11.7428 | 69.1296 | 42.1682 | 95.5703 | 225
Innovation Fund | 2.684 | 8.7688 | 26.8147 | 80.5926 | 53.7779 | 3.801 | 20.0139 | 28.348 | 25.2005 | 42.6367 | 120
Supporting Growth Schemes | 0.060486 | 5.2169 | 14.5347 | 23 | 8.4653 | 0 | 5.1056 | 22.6483 | 18.5552 | 33.6909 | 80
Total capital expenditure | 1931.0086 | 2030.5872 | 2318.9908 | 2178.2005 | -140.7903 | 1931 | 2019.5 | 2389.2078 | 2698.3351 | 3121.9985 | 12160.0413
Total expenditure | 3000.1965 | 3073.0728 | 3400.4743 | 3238.7805 | -161.6938 | 3002.9516 | 3078.5 | 3455.2078 | 3765.3351 | 4193.9985 | 17495.993
Resource Expenditure by Type
Income | -31.7987 | -27.9526 | -49.471 | -26.6154 | 22.8556 | -31.3771 | -29.8671 | -31.7039 | -31.7336 | -31.8823 | -156.5639
Pay | 112.8547 | 120.4575 | 130.2132 | 136.6876 | 6.4744 | 105.6834 | 102.5298 | 112.5183 | 112.6238 | 113.1516 | 546.5068
Non-Pay | 76.643 | 85.358 | -16.4867 | -15.0144 | 1.4723 | 65.8013 | 82.1984 | 76.4145 | 76.4861 | 76.8446 | 377.7449
Projects | 911.4888 | 864.6227 | 1017.231 | 965.5222 | -51.7089 | 931.8441 | 904.1389 | 908.7711 | 909.6237 | 913.8862 | 4568.2639
Total resource expenditure | 1069.1879 | 1042.4856 | 1081.4866 | 1060.58 | -20.9066 | 1071.9516 | 1059 | 1066 | 1067 | 1072 | 5335.9516
Note:
Baseline data is taken from Version 2
2015-16 figures restated to remove the impact of provisions creation and utilisation, this increases the renewals expenditure and reduces major projects spend
Expenditure type split of baseline for future years has been allocated using 2015-16 actuals
Summary:
The full year Resource outturn is £1,081.5m, a total of £20.9m (2%) above the budget of £1,060.6m.
In addition to the original opex budget of £1,061m DfT has provided £20m of funding at supplementary estimate for Dartford and Severn Protocols pressures. The unaudited outturn for the year is in line with the revised funding of £1,081m, with a small level of spend above budget of £0.9m.
The full year capital expenditure was £2,319m. This is £141m (6%) higher than the budget of £2,178m.
We started the year with net £207m over-programming baked into our budget with the expectation that much of this would be managed out of the programme or we would have the opportunity to flex funding if required.
The capital budget was set to align with the original Delivery Plan funding and assumed pay back of the M20 Lorry Park. The Highways England budget held by DfT did not assume payback in this financial year and as such we had the ability to utilise some of this funding. We confirmed at supplementary estimate plans to utilise £140m of the M20 Lorry Park funding not yet handed back to DfT. This brings forward funding from future years. We have outturned within £1m of this target.

## F2
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2: Resource income and expenditure
| 2014-15 | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
| Actual | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Maintenance (B3)
Income | -9.9861 | -11.3723 | -6.5378 | -10.221 | -10.5 | -0.27903 | -10.9135 | -9.9199 | -9.998 | -10.4667 | -10.3495 | -51.6476
Pay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Pay | -8.7811e-08 | -1e-07 | 0.41153 | 0.9312 | 0 | -0.9312 | -9.5965e-08 | -8.7229e-08 | -8.7915e-08 | -9.2037e-08 | -9.1006e-08 | -4.5415e-07
Projects | 243.7014 | 277.5301 | 265.7551 | 268.3031 | 255.5837 | -12.7194 | 266.3324 | 242.0857 | 243.9919 | 255.429 | 252.5698 | 1260.4089
Subtotal | 233.7153 | 266.1578 | 259.6289 | 259.0134 | 245.0837 | -13.9296 | 255.419 | 232.1658 | 233.9939 | 244.9624 | 242.2202 | 1208.7613
Renewals (B4)
Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Pay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects | 41.685 | 25.031 | 10.1304 | 10.7428 | 16.9041 | 6.1613 | 24.021 | 21.8342 | 22.0061 | 23.0376 | 22.7798 | 113.6787
Subtotal | 41.685 | 25.031 | 10.1304 | 10.7428 | 16.9041 | 6.1613 | 24.021 | 21.8342 | 22.0061 | 23.0376 | 22.7798 | 113.6787
General operations (B1)
Income | -7.3722 | -8.2785 | -11.679 | -26.2937 | -5 | 21.2937 | -8.29 | -6.3896 | -5.7342 | -5.7997 | -5.898 | -32.1116
Pay | 9.508 | 10.6768 | 15.0498 | 14.2299 | 13.7429 | -0.48701 | 10.6917 | 8.2407 | 7.3955 | 7.48 | 7.6068 | 41.4146
Non-Pay | 2.3013 | 2.5842 | 7.0887 | 6.7838 | 7.8056 | 1.0218 | 2.5878 | 1.9945 | 1.79 | 1.8104 | 1.8411 | 10.0238
Projects | 61.2663 | 68.7977 | 57.2583 | 65.7525 | 43.9852 | -21.7673 | 68.894 | 53.1001 | 47.6539 | 48.1985 | 49.0155 | 266.862
Subtotal | 65.7033 | 73.7802 | 67.7179 | 60.4725 | 60.5336 | 0.061151 | 73.8834 | 56.9457 | 51.1051 | 51.6892 | 52.5653 | 286.1888
Traffic management (B2)
Income | -4.531 | -5.0884 | -3.3628 | -5.0297 | -4.9639 | 0.065821 | -5.0956 | -3.9274 | -3.5246 | -3.5649 | -3.6253 | -19.7378
Pay | 56.4357 | 63.3784 | 60.9082 | 60.7257 | 61.9395 | 1.2138 | 63.4671 | 48.9173 | 43.9002 | 44.4019 | 45.1545 | 245.8409
Non-Pay | 14.3342 | 16.0976 | 12.5845 | 11.0305 | 8.576 | -2.4546 | 16.1202 | 12.4246 | 11.1503 | 11.2777 | 11.4689 | 62.4417
Projects | 93.0337 | 104.4787 | 38.6517 | 41.942 | 44.7861 | 2.8441 | 104.6249 | 80.6397 | 72.369 | 73.1961 | 74.4367 | 405.2663
Subtotal | 159.2727 | 178.8663 | 108.7816 | 108.6686 | 110.3377 | 1.6691 | 179.1166 | 138.0543 | 123.8949 | 125.3108 | 127.4347 | 693.8112
Private Finance Initiative (PFI) payments (B5)
Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Pay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects | 390.647 | 393.5116 | 412.9115 | 421.4021 | 428.5014 | 7.0993 | 393.5116 | 416 | 429 | 408 | 413 | 2059.5116
Subtotal | 390.647 | 393.5116 | 412.9115 | 421.4021 | 428.5014 | 7.0993 | 393.5116 | 416 | 429 | 408 | 413 | 2059.5116
Support costs (C1)
Income | -6.2807 | -7.0543 | -5.9348 | -7.1218 | -6.1515 | 0.9703 | -5.7316 | -8.2493 | -8.7849 | -8.7849 | -8.8385 | -40.3892
Pay | 34.5448 | 38.7995 | 39.6105 | 50.3899 | 55.9742 | 5.5843 | 31.5246 | 45.3718 | 48.3181 | 48.3181 | 48.6127 | 222.1452
Non-Pay | 51.6051 | 57.9612 | 65.0438 | 33.7967 | 37.2948 | 3.4981 | 47.0934 | 67.7793 | 72.1805 | 72.1805 | 72.6206 | 331.8543
Projects | 37.3819 | 41.9861 | 35.8532 | 86.3228 | 71.1019 | -15.2209 | 34.1137 | 49.0982 | 52.2864 | 52.2864 | 52.6052 | 240.3898
Subtotal | 117.251 | 131.6925 | 134.5726 | 163.3876 | 158.2194 | -5.1682 | 107 | 154 | 164 | 164 | 165 | 754
Other project activities (including Protocols)
Income | 0 | -0.0051256 | -0.43822 | -0.80486 | 0 | 0.80486 | -1.3464 | -1.3809 | -1.45 | -1.7262 | -1.6917 | -7.5952
Pay | 0 | 0 | 4.8891 | 4.8677 | 5.031 | 0.16324 | 0 | 0 | 0 | 0 | 0 | 0
Non-Pay | 0 | 0 | 0.22949 | 0.21683 | 0.5416 | 0.32477 | 0 | 0 | 0 | 0 | 0 | 0
Projects | 0 | 0.15359 | 44.0624 | 53.5168 | 35.4274 | -18.0894 | 40.3464 | 41.3809 | 43.45 | 51.7262 | 50.6917 | 227.5952
Subtotal | 0 | 0.14847 | 48.7427 | 57.7965 | 41 | -16.7965 | 39 | 40 | 42 | 50 | 49 | 220
Total | 1008.2743 | 1069.1879 | 1042.4856 | 1081.4835 | 1060.58 | -20.9035 | 1071.9516 | 1059 | 1066 | 1067 | 1072 | 5335.9516
Commentary:
2017-18 Baseline only held at summary level. Split for this purpose in line with prior year actuals (2015-16)

## F2.1
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.1: Regional resource income and expenditure
| 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
| Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Maintenance (B3)
Centrally managed | 44.225 | 43.2471 | 43.1253 | 43.4594 | 0.33417 | 42.4406 | 38.5768 | 38.8806 | 40.7031 | 40.2475 | 200.8487
East | 28.3433 | 31.5902 | 41.6305 | 28.2728 | -13.3577 | 27.1998 | 24.7235 | 24.9182 | 26.0862 | 25.7942 | 128.7219
Midlands | 62.9873 | 45.7622 | 54.6167 | 50.6199 | -3.9968 | 60.4459 | 54.943 | 55.3756 | 57.9713 | 57.3224 | 286.0582
North West | 29.9514 | 41.2615 | 40.9768 | 34.7814 | -6.1954 | 28.743 | 26.1262 | 26.3319 | 27.5662 | 27.2577 | 136.025
South East | 42.2512 | 35.7723 | 30.5096 | 33.4903 | 2.9807 | 40.5465 | 36.8551 | 37.1453 | 38.8865 | 38.4512 | 191.8847
South West | 28.385 | 33.6644 | 24.1824 | 25.2301 | 1.0477 | 27.2397 | 24.7599 | 24.9548 | 26.1246 | 25.8321 | 128.9111
Yorkshire & North East | 30.0145 | 28.3312 | 23.9721 | 29.2297 | 5.2576 | 28.8035 | 26.1813 | 26.3874 | 27.6243 | 27.3151 | 136.3117
Subtotal | 266.1578 | 259.6289 | 259.0134 | 245.0837 | -13.9296 | 255.419 | 232.1658 | 233.9939 | 244.9624 | 242.2202 | 1208.7613
Renewals (B4)
Centrally managed | 0.019612 | -1e-08 | 0 | 0 | 0 | 0.01882 | 0.017107 | 0.017242 | 0.01805 | 0.017848 | 0.089066
East | 2.5503 | 0.8711 | 0.28607 | 3.3 | 3.0139 | 2.4474 | 2.2246 | 2.2421 | 2.3472 | 2.3209 | 11.582
Midlands | 6.1198 | 0.78542 | 0.23814 | 0.35 | 0.11186 | 5.8729 | 5.3382 | 5.3803 | 5.6325 | 5.5694 | 27.7932
North West | 0.88526 | 0.58372 | 2.4292 | 2.5873 | 0.1581 | 0.84954 | 0.7722 | 0.77828 | 0.81476 | 0.80564 | 4.0204
South East | 1.1396 | 1.9655 | 1.7374 | 4.5999 | 2.8625 | 1.0936 | 0.99404 | 1.0019 | 1.0488 | 1.0371 | 5.1754
South West | 2.882 | 2.6741 | 0.73635 | 0.76694 | 0.030594 | 2.7657 | 2.5139 | 2.5337 | 2.6525 | 2.6228 | 13.0887
Yorkshire & North East | 11.4345 | 3.2505 | 5.3157 | 5.3 | -0.015654 | 10.9731 | 9.9741 | 10.0527 | 10.5239 | 10.4061 | 51.9298
Subtotal | 25.031 | 10.1304 | 10.7428 | 16.9041 | 6.1613 | 24.021 | 21.8342 | 22.0061 | 23.0376 | 22.7798 | 113.6787
General operations (B1)
Centrally managed | 16.6898 | 14.675 | -1.6578 | -5.2757 | -3.6179 | 16.7131 | 12.8817 | 11.5605 | 11.6926 | 11.8908 | 64.7386
East | 7.4117 | 7.041 | 6.874 | 6.2503 | -0.62367 | 7.4221 | 5.7206 | 5.1338 | 5.1925 | 5.2805 | 28.7495
Midlands | 14.6047 | 16.8129 | 15.953 | 16.0919 | 0.13883 | 14.6251 | 11.2723 | 10.1162 | 10.2318 | 10.4052 | 56.6506
North West | 7.6067 | 4.999 | 8.0135 | 8.7277 | 0.71416 | 7.6173 | 5.8711 | 5.2689 | 5.3291 | 5.4194 | 29.5058
South East | 11.8614 | 9.6464 | 9.6356 | 9.3842 | -0.25134 | 11.878 | 9.155 | 8.216 | 8.3099 | 8.4508 | 46.0097
South West | 4.4521 | 5.5508 | 11.0238 | 12.7786 | 1.7548 | 4.4583 | 3.4362 | 3.0838 | 3.119 | 3.1719 | 17.2692
Yorkshire & North East | 11.1539 | 8.9928 | 10.6304 | 12.5766 | 1.9462 | 11.1695 | 8.6089 | 7.7259 | 7.8142 | 7.9467 | 43.2653
Subtotal | 73.7802 | 67.7179 | 60.4725 | 60.5336 | 0.061151 | 73.8834 | 56.9457 | 51.1051 | 51.6892 | 52.5653 | 286.1888
Traffic management (B2)
Centrally managed | 178.8663 | 55.7888 | 53.1787 | 53.2607 | 0.082023 | 179.1166 | 138.0543 | 123.8949 | 125.3108 | 127.4347 | 693.8112
East | 0 | 10.0483 | 9.9484 | 10.4927 | 0.54422 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | 0 | 11.5199 | 12.9202 | 13.1905 | 0.27029 | 0 | 0 | 0 | 0 | 0 | 0
North West | 0 | 9.3555 | 9.7815 | 9.8454 | 0.063871 | 0 | 0 | 0 | 0 | 0 | 0
South East | 0 | 10.7545 | 11.046 | 10.9899 | -0.056083 | 0 | 0 | 0 | 0 | 0 | 0
South West | 0 | 5.2662 | 5.3024 | 5.538 | 0.23568 | 0 | 0 | 0 | 0 | 0 | 0
Yorkshire & North East | 0 | 6.0484 | 6.4914 | 7.0205 | 0.52911 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal | 178.8663 | 108.7816 | 108.6686 | 110.3377 | 1.6691 | 179.1166 | 138.0543 | 123.8949 | 125.3108 | 127.4347 | 693.8112
Private Finance Initiative (PFI) payments (B5)
Centrally managed | -60.5641 | -65.0302 | -69.2327 | -69.2324 | 0.00030589 | 202.7191 | -70.3793 | -72.5786 | -69.0258 | -69.8717 | -79.1363
East | 56.8045 | 58.0179 | 61.18 | 60.3079 | -0.87211 | 56.8045 | 66.0103 | 68.0731 | 64.7409 | 65.5343 | 321.1631
Midlands | 4.7206 | 9.2017 | 9.1175 | 9.2094 | 0.091909 | 9.1449 | 5.4856 | 5.657 | 5.3801 | 5.4461 | 31.1137
North West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
South East | 275.4432 | 282.0625 | 284.4068 | 286.8226 | 2.4158 | 12.16 | 320.082 | 330.0846 | 313.9266 | 317.7737 | 1294.0268
South West | 27.0823 | 24.9424 | 25.9879 | 25.5341 | -0.45372 | 27.0823 | 31.4713 | 32.4548 | 30.8661 | 31.2444 | 153.1189
Yorkshire & North East | 54.4979 | 103.7173 | 109.9427 | 115.8597 | 5.917 | 85.6009 | 63.33 | 65.309 | 62.1121 | 62.8733 | 339.2253
Subtotal | 357.9844 | 412.9115 | 421.4021 | 428.5014 | 7.0993 | 393.5116 | 416 | 429 | 408 | 413 | 2059.5116
Support costs (C1)
Centrally managed | 131.6925 | 134.7676 | 161.4001 | 158.2194 | -3.1807 | 107 | 154 | 164 | 164 | 165 | 754
East | 0 | -0.052948 | 0.0039629 | 0 | -0.0039629 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | 0 | 0.34447 | 1.7682 | 0 | -1.7682 | 0 | 0 | 0 | 0 | 0 | 0
North West | 0 | -0.47721 | 0.00188 | 0 | -0.00188 | 0 | 0 | 0 | 0 | 0 | 0
South East | 0 | -0.01399 | 0.055412 | 0 | -0.055412 | 0 | 0 | 0 | 0 | 0 | 0
South West | 0 | 0.0016345 | 0.1361 | 0 | -0.1361 | 0 | 0 | 0 | 0 | 0 | 0
Yorkshire & North East | 0 | 0.0030309 | 0.021951 | 0 | -0.021951 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal | 131.6925 | 134.5726 | 163.3876 | 158.2194 | -5.1682 | 107 | 154 | 164 | 164 | 165 | 754
Other project activities (including Protocols)
Centrally managed | 0.14847 | 34.2979 | 45.1433 | 29.2556 | -15.8877 | 39.0005 | 40.0005 | 42 | 50 | 49 | 220.0011
East | 3.6e-07 | 0 | 0 | 0 | 0 | 9.4566e-05 | 9.6991e-05 | 9.9416e-05 | 9.9416e-05 | 0.00010184 | 0.00049223
Midlands | -3.15e-06 | 0.049987 | 0.04998 | 0.04998 | 0 | -0.00082745 | -0.00084867 | -0.00086989 | -0.00086989 | -0.0008911 | -0.004307
North West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
South East | 7.5e-07 | 0.074494 | 0 | 0 | 0 | 0.00019701 | 0.00020206 | 0.00020712 | 0.00020712 | 0.00021217 | 0.0010255
South West | -2.2e-07 | 5.3747 | 3.0738 | 2.07 | -1.0038 | -5.779e-05 | -5.9272e-05 | -6.0754e-05 | -6.0754e-05 | -6.2236e-05 | -0.00030081
Yorkshire & North East | 2.3e-07 | 8.9457 | 9.5294 | 9.6245 | 0.095115 | 6.0417e-05 | 6.1966e-05 | 6.3516e-05 | 6.3516e-05 | 6.5065e-05 | 0.00031448
Subtotal | 0.14847 | 48.7427 | 57.7964 | 41 | -16.7964 | 39 | 40 | 41.9994 | 49.9994 | 48.9994 | 219.9983
Total | 1069.1879 | 1042.4856 | 1081.4834 | 1060.58 | -20.9034 | 1071.9516 | 1059 | 1065.9994 | 1066.9994 | 1071.9994 | 5336.05
Note:
Regional 2014-15 data splits are not available.
Baseline split based upon 2015-16 splits
2015-16 PFI split restated - M25 included previously in centrally managed - moved SE to be consistent year on year and to ensure consistency in CRA reporting

## F2.2
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.2: Maintenance resource income and expenditure
|  | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
|  | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Income
| Income | -11.3723 | -6.5378 | -10.221 | -10.5 | -0.27903 | -10.9135 | -9.9199 | -11.4541 | -11.6778 | -11.5694 | -55.5347
| Income Subtotal | -11.3723 | -6.5378 | -10.221 | -10.5 | -0.27903 | -10.9135 | -9.9199 | -11.4541 | -11.6778 | -11.5694 | -55.5347
Pay
| Permanent staff salaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| National Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pension contributions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Employment agency staff costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capitalised Pay Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pay Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non Pay
| Travel and Subsistence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Training and Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Non Pay Costs | 0 | 0.41153 | 0.9312 | 0 | -0.9312 | 0 | 0 | 0 | 0 | 0 | 0
| Non Pay Subtotal | 0 | 0.41153 | 0.9312 | 0 | -0.9312 | 0 | 0 | 0 | 0 | 0 | 0
Projects
| Routine Maintenance | 233.4489 | 227.449 | 230.0766 | 213.6408 | -16.4358 | 224.0298 | 203.6343 | 206.4625 | 215.877 | 213.4792 | 1063.4827
| Winter Maintenance | 2.3893 | 2.5208 | 2.1581 | 1.5662 | -0.59195 | 2.2929 | 2.0841 | 2.1131 | 2.2094 | 2.1849 | 10.8844
| Technology - Maintenance | 36.9467 | 31.9305 | 30.2895 | 36.394 | 6.1045 | 35.456 | 32.2281 | 32.6757 | 34.1657 | 33.7862 | 168.3116
| Other | 4.7453 | 3.8548 | 5.7789 | 3.9827 | -1.7961 | 4.5538 | 4.1393 | 4.1968 | 4.3881 | 4.3394 | 21.6174
| Projects Subtotal | 277.5301 | 265.7551 | 268.3031 | 255.5837 | -12.7194 | 266.3324 | 242.0857 | 245.448 | 256.6402 | 253.7897 | 1264.296
| Total | 266.1578 | 259.6289 | 259.0134 | 245.0837 | -13.9296 | 255.419 | 232.1658 | 233.9939 | 244.9624 | 242.2202 | 1208.7613
| FTEs | X | X | X | X | X | X | X | X | X | X | X
Note:

## F2.3
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.3: Renewals resource income and expenditure
|  | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
|  | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Income
| Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Income Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pay
| Permanent staff salaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| National Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pension contributions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Employment agency staff costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capitalised Pay Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pay Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non Pay
| Travel and Subsistence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Training and Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Non Pay Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non Pay Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects
| Renewal of Roads - Non TPI | 8.8625 | 6.5825 | 5.242 | 9.1476 | 3.9055 | 8.505 | 7.7307 | 7.7915 | 8.1568 | 8.0655 | 40.2494
| Renewal of Structures - Non TPI | 11.3691 | 3.5334 | 5.5008 | 7.7566 | 2.2558 | 10.9104 | 9.9172 | 9.9952 | 10.4638 | 10.3466 | 51.6332
| Renewal of Technology | 0.069641 | 0.014491 | 0 | 0 | 0 | 0.066831 | 0.060747 | 0.061225 | 0.064095 | 0.063378 | 0.31628
| Other | 4.7296 | 0 | 0 | 0 | 0 | 4.5388 | 4.1256 | 4.1581 | 4.353 | 4.3043 | 21.4798
| Projects Subtotal | 25.031 | 10.1304 | 10.7428 | 16.9041 | 6.1613 | 24.021 | 21.8342 | 22.0061 | 23.0376 | 22.7798 | 113.6787
| Total | 25.031 | 10.1304 | 10.7428 | 16.9041 | 6.1613 | 24.021 | 21.8342 | 22.0061 | 23.0376 | 22.7798 | 113.6787
| FTEs | X | X | X | X | X | X | X | X | X | X | X
Note:

## F2.4
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.4: Private Finance Initiative (PFI) income and expenditure
|  | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
|  | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Income
| Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Income Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pay
| Permanent staff salaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| National Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pension contributions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Employment agency staff costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capitalised Pay Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pay Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non Pay
| Travel and Subsistence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Training and Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Non Pay Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Non Pay Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects
| A1 (M) Alconbury to Peterborough | 22.707 | 28.5633 | 29.3142 | 29.7284 | 0.41418 | 22.707 | 24.0047 | 24.7548 | 23.543 | 23.8315 | 118.841
| A1(M) Darrington to Dishforth | 27.962 | 23.532 | 24.0806 | 23.9942 | -0.08638 | 27.962 | 29.56 | 30.4838 | 28.9915 | 29.3468 | 146.3442
| A19 Dishforth to Tyne Tunnel | 18.9766 | 36.1878 | 39.3949 | 43.8822 | 4.4873 | 18.9766 | 20.0611 | 20.688 | 19.6753 | 19.9164 | 99.3175
| A249 Iwade to Queenborough | 12.16 | 12.1106 | 12.2384 | 12.7951 | 0.55672 | 12.16 | 12.8549 | 13.2566 | 12.6077 | 12.7622 | 63.6413
| A30/A35 Exeter to Bere Regis | 7.789 | 7.8581 | 8.1193 | 8.0717 | -0.04763 | 7.789 | 8.2341 | 8.4914 | 8.0758 | 8.1747 | 40.7651
| A419/A417 Swindon to Gloucester | 19.1007 | 17.048 | 17.7288 | 17.3906 | -0.33824 | 19.1007 | 20.1922 | 20.8232 | 19.8039 | 20.0466 | 99.9666
| A50/A564 Stoke - Derby link | 9.0957 | 9.3792 | 9.0915 | 9.2094 | 0.11789 | 9.0957 | 9.6155 | 9.916 | 9.4306 | 9.5462 | 47.6039
| A69 Carlisle to Newcastle | 10.5119 | 10.4028 | 10.9292 | 11.9951 | 1.0659 | 10.5119 | 11.1126 | 11.4599 | 10.8989 | 11.0325 | 55.0159
| M1-A1 Yorkshire link | 28.1095 | 28.3362 | 29.8338 | 29.8296 | -0.0041747 | 28.1095 | 29.7159 | 30.6445 | 29.1444 | 29.5016 | 147.1159
| M25 London Orbital Motorway contract | 263.8239 | 268.0864 | 269.2478 | 270.9674 | 1.7196 | 263.8239 | 278.9008 | 287.6165 | 273.5374 | 276.8895 | 1380.7681
| M40 Junctions 1-15 | 33.8395 | 35.2976 | 36.2908 | 36.3136 | 0.022839 | 33.8395 | 35.7734 | 36.8913 | 35.0854 | 35.5154 | 177.105
| PFI loan repayment credits | -60.5641 | -65.0302 | -69.2324 | -69.2324 | 0 | -60.5641 | -64.0252 | -66.026 | -62.794 | -63.5635 | -316.9729
| Other Central Costs | 0 | 1.1398 | 4.3652 | -2.4308 | -6.796 | 0 | 0 | 0 | 0 | 0 | 0
| Projects Subtotal | 393.5116 | 412.9115 | 421.4021 | 422.5141 | 1.112 | 393.5116 | 416 | 429 | 408 | 413 | 2059.5116
| Total | 393.5116 | 412.9115 | 421.4021 | 422.5141 | 1.112 | 393.5116 | 416 | 429 | 408 | 413 | 2059.5116
| FTEs | X | X | X | X | X | X | X | X | X | X | X
Note:

## F2.5
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.5: General operations income and expenditure
|  | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
|  | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Income
| Income | -8.2785 | -11.679 | -26.2937 | -5 | 21.2937 | -8.29 | -6.3896 | -7.4123 | -7.202 | -7.4078 | -36.7018
| Income Subtotal | -8.2785 | -11.679 | -26.2937 | -5 | 21.2937 | -8.29 | -6.3896 | -7.4123 | -7.202 | -7.4078 | -36.7018
Pay
| Permanent staff salaries | 27.0969 | 29.8487 | 43.3792 | 48.3734 | 4.9942 | 27.1348 | 20.9142 | 19.3233 | 19.4467 | 19.8039 | 106.6228
| National Insurance | 2.3299 | 3.2456 | 4.6653 | 5.0227 | 0.3574 | 2.3331 | 1.7983 | 1.6615 | 1.6721 | 1.7028 | 9.1678
| Pension contributions | 5.4493 | 5.3747 | 6.2114 | 7.1859 | 0.97448 | 5.4569 | 4.2059 | 3.886 | 3.9108 | 3.9826 | 21.4422
| Employment agency staff costs | 1.4871 | 2.869 | 3.3229 | 1.0592 | -2.2637 | 1.4892 | 1.1478 | 1.0605 | 1.0673 | 1.0869 | 5.8517
| Capitalised Pay Costs | -25.6864 | -26.2882 | -43.349 | -47.8984 | -4.5494 | -25.7223 | -19.8255 | -18.3174 | -18.4344 | -18.773 | -101.0727
| Pay Subtotal | [ | 15.0498 | 14.2299 | 13.7429 | -0.48701 | 10.6917 | 8.2407 | 7.6138 | 7.6624 | 7.8032 | 42.0118
Non Pay
| Travel and Subsistence | 1.3727 | 1.5848 | 2.0251 | 2.9106 | 0.88547 | 1.3746 | 1.0595 | 0.97887 | 0.98513 | 1.0032 | 5.4013
| Training and Development | 0.10125 | 0.05067 | 0.024864 | 0.035062 | 0.010198 | 0.10139 | 0.078148 | 0.072204 | 0.072665 | 0.074 | 0.39841
| Other Non Pay Costs | 1.1103 | 5.4533 | 4.7835 | 4.93 | 0.14653 | 1.1118 | 0.85693 | 0.79174 | 0.7968 | 0.81144 | 4.3687
| Non Pay Subtotal | 2.5842 | 7.0887 | 6.7838 | 7.8056 | 1.0422 | 2.5878 | 1.9945 | 1.8428 | 1.8546 | 1.8887 | 10.1684
Projects
| Local Network Management Schemes | 8.7344 | 0.85867 | 0.63792 | 1.239 | 0.60108 | 8.7466 | 6.7415 | 6.2286 | 6.2684 | 6.3836 | 34.3687
| S274/S278 Works | 7.8834 | 9.9026 | 27.7935 | 5.0796 | -22.7138 | 7.8945 | 6.0847 | 5.6218 | 5.6577 | 5.7617 | 31.0204
| Technology | 6.5487 | 5.1234 | 5.1995 | 9.869 | 4.6695 | 6.5579 | 5.0545 | 4.67 | 4.6998 | 4.7862 | 25.7684
| Other | 45.6312 | 41.3737 | 32.1216 | 27.7975 | -4.3241 | 45.695 | 35.2195 | 32.5404 | 32.7482 | 33.3498 | 179.5529
| Projects Subtotal | 68.7977 | 57.2583 | 65.7525 | 43.9852 | -21.7673 | 68.894 | 53.1001 | 49.0609 | 49.3742 | 50.2812 | 270.7104
| Total | 73.7802 | 67.7179 | 60.4725 | 60.5336 | 0.081548 | 73.8834 | 56.9457 | 51.1051 | 51.6892 | 52.5653 | 286.1888
| FTEs | X | 898.587 | 1245.5171 | 1371.141 | 125.6239 | X | X | X | X | X | X
Note:

## F2.6
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.6: Traffic management resource income and expenditure
|  | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
|  | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Income
| National Vehicle Recovery income | -5.0884 | -3.3628 | -5.0297 | -4.9639 | 0.065821 | -5.0956 | -3.9274 | -4.5561 | -4.4268 | -4.5533 | -22.5592
| Income Subtotal | -5.0884 | -3.3628 | -5.0297 | -4.9639 | 0.065821 | -5.0956 | -3.9274 | -4.5561 | -4.4268 | -4.5533 | -22.5592
Pay
| Permanent staff salaries | 49.8659 | 47.078 | 48.2351 | 49.0042 | 0.76913 | 49.9357 | 38.488 | 34.8201 | 35.1689 | 35.7789 | 194.1917
| National Insurance | 3.8099 | 4.6846 | 4.8202 | 4.7294 | -0.090801 | 3.8152 | 2.9406 | 2.6604 | 2.687 | 2.7336 | 14.8369
| Pension contributions | 9.7481 | 8.9049 | 8.581 | 9.1422 | 0.56119 | 9.7618 | 7.5239 | 6.8069 | 6.8751 | 6.9943 | 37.9619
| Employment agency staff costs | 0.39216 | 0.24076 | 0.03177 | 0 | -0.03177 | 0.39271 | 0.30268 | 0.27384 | 0.27658 | 0.28138 | 1.5272
| Capitalised Pay Costs | -0.43773 | 0 | -0.94286 | -0.93634 | 0.006529 | -0.43834 | -0.33785 | -0.30565 | -0.30872 | -0.31407 | -1.7046
| Pay Subtotal | 63.3784 | 60.9082 | 60.7253 | 61.9395 | 1.2143 | 63.4671 | 48.9173 | 44.2555 | 44.6988 | 45.4742 | 246.813
Non Pay
| Travel and Subsistence | 1.5696 | 0.90583 | 0.98397 | 1.2595 | 0.27557 | 1.5718 | 1.2115 | 1.096 | 1.107 | 1.1262 | 6.1126
| Training and Development | 1.5869 | 0.91912 | 0.011202 | 0.0424 | 0.031198 | 1.5891 | 1.2248 | 1.1081 | 1.1192 | 1.1386 | 6.1797
| Uniforms, Health and Safety | 0.20302 | 0.026711 | 0.27405 | 0.9 | 0.62595 | 0.2033 | 0.1567 | 0.14176 | 0.14318 | 0.14567 | 0.79062
| Accommodation | 6.203 | 5.7159 | 5.5612 | 6.072 | 0.51077 | 6.2117 | 4.7877 | 4.3314 | 4.3748 | 4.4507 | 24.1564
| Traffic Manager Vehicle Costs | 6.0505 | 4.7009 | 7.7217 | 4.7169 | -3.0047 | 6.059 | 4.67 | 4.2249 | 4.2672 | 4.3412 | 23.5623
| Other Non Pay Costs | 0.48456 | 0.31598 | -3.5216 | -4.4149 | -0.89332 | 0.48524 | 0.374 | 0.33836 | 0.34175 | 0.34767 | 1.887
| Non Pay Subtotal | 16.0976 | 12.5845 | 11.0305 | 8.576 | -2.4546 | 16.1202 | 12.4246 | 11.2406 | 11.3532 | 11.5501 | 62.6886
Projects
| Technology PFI | 51.0441 | 19.0716 | 24.0522 | 22 | -2.0522 | 51.1156 | 39.3974 | 35.6428 | 35.9999 | 36.6243 | 198.78
| Traffic Manager Projects | 28.3199 | 18.7345 | 16.9424 | 21.4361 | 4.4937 | 28.3595 | 21.8581 | 19.775 | 19.9731 | 20.3196 | 110.2853
| Other | 25.1147 | 0.8456 | 0.94746 | 1.35 | 0.40254 | 25.1498 | 19.3843 | 17.5369 | 17.7126 | 18.0198 | 97.8035
| Projects Subtotal | 104.4787 | 38.6517 | 41.942 | 44.7861 | 2.8441 | 104.6249 | 80.6397 | 72.9548 | 73.6856 | 74.9637 | 406.8688
| Total | 178.8663 | 108.7816 | 108.6681 | 110.3377 | 1.6696 | 179.1166 | 138.0543 | 123.8949 | 125.3108 | 127.4347 | 693.8112
| FTEs | X | 1570.1532 | 1615.0056 | 1729.9985 | 114.9929 | X | X | X | X | X | X
Note:

## F2.7
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.7: Support costs
|  | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
|  | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Income
| Lands income | -4.2789 | -4.3266 | -3.2029 | -3.2018 | 0.0011071 | -3.4766 | -5.0037 | -5.0231 | -5.1114 | -5.0659 | -23.6807
| Other income | -2.7754 | -1.6082 | -3.9066 | -2.9497 | 0.95688 | -2.255 | -3.2456 | -3.2582 | -3.3155 | -3.2859 | -15.3602
| Income Subtotal | -7.0543 | -5.9348 | -7.1095 | -6.1515 | 0.95799 | -5.7316 | -8.2493 | -8.2813 | -8.4269 | -8.3518 | -39.0409
Pay
| Permanent staff salaries | 48.8021 | 60.7623 | 82.0366 | 85.8486 | 3.812 | 39.6516 | 57.0687 | 60.5973 | 60.6485 | 60.9738 | 278.94
| National Insurance | 4.6287 | 6.8473 | 9.6764 | 8.5646 | -1.1117 | 3.7608 | 5.4128 | 5.7475 | 5.7523 | 5.7832 | 26.4566
| Pension contributions | 9.4947 | 10.8659 | 12.8375 | 12.8738 | 0.036326 | 7.7144 | 11.103 | 11.7895 | 11.7994 | 11.8627 | 54.2689
| Employment agency staff costs | 10.2642 | 23.2137 | 12.2228 | 3.4979 | -8.7249 | 8.3396 | 12.0028 | 12.745 | 12.7557 | 12.8241 | 58.6673
| Capitalised Pay Costs | -34.3901 | -62.0788 | -66.3834 | -54.8107 | 11.5727 | -27.9419 | -40.2154 | -42.702 | -42.7381 | -42.9673 | -196.5647
| Pay Subtotal | 38.7995 | 39.6105 | 50.3899 | 55.9742 | 5.5843 | 31.5246 | 45.3718 | 48.1772 | 48.2179 | 48.4766 | 221.7681
Non Pay
| Travel and Subsistence | 3.2842 | 4.0911 | 5.9496 | 6.8869 | 0.93731 | 2.6684 | 3.8405 | 4.0779 | 4.0814 | 4.1033 | 18.7715
| Training and Development | 1.803 | 3.6654 | 5.5878 | 4.6402 | -0.94753 | 1.465 | 2.1085 | 2.2388 | 2.2407 | 2.2527 | 10.3057
| Staff Welfare, Health and Safety | 0.34594 | 0.47023 | 0.58858 | 0.71348 | 0.1249 | 0.28107 | 0.40454 | 0.42955 | 0.42991 | 0.43222 | 1.9773
| Accommodation | 12.3815 | 12.4434 | 14.4743 | 14.3544 | -0.11995 | 10.0599 | 14.4788 | 15.374 | 15.387 | 15.4696 | 70.7693
| Recruitment | 0.84929 | 0.94307 | 1.1217 | 1.252 | 0.13029 | 0.69005 | 0.99315 | 1.0546 | 1.0554 | 1.0611 | 4.8543
| Restructuring and Staff transfers | 1.2131 | 0.23436 | 1.2158 | 0.57954 | -0.63625 | 0.98563 | 1.4186 | 1.5063 | 1.5075 | 1.5156 | 6.9336
| Office Equipment, Services and Consumables | 0.81446 | 0.58329 | 0.76199 | 0.67007 | -0.091918 | 0.66175 | 0.95242 | 1.0113 | 1.0122 | 1.0176 | 4.6553
| ICT and Consumables | 29.7022 | 32.7407 | 0.10482 | 0.165 | 0.060178 | 24.133 | 34.7335 | 36.8811 | 36.9123 | 37.1103 | 169.7702
| Admin Telecoms | 1.3205 | 1.3262 | 2.8099 | 0.0021 | -2.8078 | 1.0729 | 1.5442 | 1.6397 | 1.6411 | 1.6499 | 7.5478
| Communications and Hospitality | 0.86325 | 1.6418 | 1.3556 | 1.0898 | -0.26579 | 0.70139 | 1.0095 | 1.0719 | 1.0728 | 1.0786 | 4.9341
| Audit Fees | 0.289 | 0.401 | 0.453 | 0.257 | -0.196 | 0.23481 | 0.33795 | 0.35885 | 0.35915 | 0.36108 | 1.6518
| Other Costs | 5.0947 | 6.5034 | -0.63565 | 6.6843 | 7.32 | 4.1394 | 5.9577 | 6.3261 | 6.3314 | 6.3654 | 29.12
| Non Pay Subtotal | 57.9612 | 65.0438 | 33.7874 | 37.2948 | 3.5074 | 47.0934 | 67.7793 | 71.9701 | 72.0309 | 72.4173 | 331.291
Projects
| Research & Development | 8.606 | 0 | 9.1006 | -0.545 | -9.6456 | 6.9924 | 10.0638 | 10.6861 | 10.6951 | 10.7524 | 49.1898
| Lands - Expenditure | 3.9981 | 3.4304 | 3.8932 | 3.4458 | -0.44744 | 3.2484 | 4.6753 | 4.9644 | 4.9686 | 4.9952 | 22.852
| Other | 29.382 | 32.4227 | 73.3289 | 68.2011 | -5.1278 | 23.8729 | 34.3591 | 36.4835 | 36.5143 | 36.7102 | 167.94
| Projects Subtotal | 41.9861 | 35.8531 | 86.3228 | 71.1019 | -15.2209 | 34.1137 | 49.0982 | 52.134 | 52.178 | 52.4579 | 239.9818
| Total | 131.6925 | 134.5725 | 163.3905 | 158.2194 | -5.1711 | 107 | 154 | 164 | 164 | 165 | 754
| FTEs | 1368.94 | 1824.9378 | 2206.9793 | 2281.5125 | X | X | X | X | X | X | X
Segmental Analysis
Income
| Centrally Managed | -0.73217 | -0.66576 | 0 | 0 | 0 | -0.59489 | -0.85619 | -0.85952 | -0.87463 | -0.86683 | -4.0521
| Commercial and Procurement | -1.5e-05 | -1.4e-05 | -2e-06 | 0 | 2e-06 | -1.2187e-05 | -1.7541e-05 | -1.7609e-05 | -1.7919e-05 | -1.7759e-05 | -8.3015e-05
| Communications Directorate | 0 | -3e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Finance and Business Services | -1.7727 | -1.0988 | -5.0071 | -4.2755 | 0.7316 | -1.4403 | -2.0729 | -2.081 | -2.1176 | -2.0987 | -9.8105
| Human Resources | -0.2162 | -0.1372 | -0.20629 | -0.16 | 0.046294 | -0.17566 | -0.25282 | -0.25381 | -0.25827 | -0.25596 | -1.1965
| Major Projects | -4.3333 | -4.2093 | 0.018711 | 0 | -0.018711 | -3.5208 | -5.0673 | -5.087 | -5.1764 | -5.1303 | -23.9818
| Operations | 0 | -0.0046858 | 0.0046858 | 0 | -0.0046858 | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology Directorate | 0 | 0.31145 | 0.39384 | -1.716 | -2.1098 | 0 | 0 | 0 | 0 | 0 | 0
| Professional and Technical Services | 0 | -0.11892 | -1.3446 | 0 | 1.3446 | 0 | 0 | 0 | 0 | 0 | 0
| Strategy and Planning | 0 | 0 | -0.98107 | 0 | 0.98107 | 0 | 0 | 0 | 0 | 0 | 0
| General Counsel | 0 | -0.010922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Income Subtotal | -7.0543 | -5.9342 | -7.1218 | -6.1515 | 0.9703 | -5.7316 | -8.2493 | -8.2813 | -8.4269 | -8.3518 | -39.0409
Pay
| Centrally Managed | 6.6141 | 0.39795 | 1.4105 | 5.4085 | 3.998 | 5.3739 | 7.7344 | 8.2126 | 8.2196 | 8.2637 | 37.8042
| Commercial and Procurement | 3.4797 | 5.3356 | 6.1694 | 6.7489 | 0.57942 | 2.8273 | 4.0691 | 4.3207 | 4.3244 | 4.3476 | 19.8891
| Communications Directorate | 2.5773 | 2.1002 | 2.902 | 2.7951 | -0.10692 | 2.094 | 3.0138 | 3.2002 | 3.2029 | 3.2201 | 14.7309
| Finance and Business Services | 8.8445 | 8.2545 | 10.9099 | 10.5473 | -0.3626 | 7.1862 | 10.3427 | 10.9822 | 10.9915 | 11.0504 | 50.553
| Human Resources | 6.8703 | 5.3239 | 5.2133 | 5.0172 | -0.19615 | 5.5821 | 8.034 | 8.5308 | 8.538 | 8.5838 | 39.2687
| Major Projects | -0.5564 | 0.18119 | 4.9e-07 | 1.3712 | 1.3712 | -0.45208 | -0.65065 | -0.69088 | -0.69147 | -0.69518 | -3.1803
| Operations | 0 | 0.015483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology Directorate | 0 | 4.2867 | 5.2808 | 7.1828 | 1.902 | 0 | 0 | 0 | 0 | 0 | 0
| Professional and Technical Services | 7.3569 | 5.9291 | 9.6131 | 7.9409 | -1.6722 | 5.9775 | 8.6031 | 9.135 | 9.1428 | 9.1918 | 42.0502
| Strategy and Planning | 3.6132 | 5.4803 | 7.1181 | 7.4424 | 0.32422 | 2.9357 | 4.2253 | 4.4865 | 4.4903 | 4.5144 | 20.6522
| General Counsel | 0 | 2.3056 | 1.7726 | 1.52 | -0.25267 | 0 | 0 | 0 | 0 | 0 | 0
| Pay Subtotal | 38.7995 | 39.6105 | 50.3899 | 55.9742 | 5.5843 | 31.5246 | 45.3718 | 48.1772 | 48.2179 | 48.4766 | 221.7681
Non Pay
| Centrally Managed | 31.6463 | 0.42666 | 1.4369 | 0.57 | -0.86692 | 25.7126 | 37.0069 | 39.2951 | 39.3283 | 39.5392 | 180.882
| Commercial and Procurement | 0.49338 | 0.64793 | 0.39261 | 0.33321 | -0.059394 | 0.40087 | 0.57696 | 0.61263 | 0.61315 | 0.61644 | 2.8201
| Communications Directorate | 0.73935 | 1.2725 | 0.77494 | 0.7606 | -0.014338 | 0.60072 | 0.86459 | 0.91805 | 0.91882 | 0.92375 | 4.2259
| Finance and Business Services | 16.6707 | 16.0982 | 20.61 | 21.7949 | 1.1849 | 13.545 | 19.4946 | 20.7 | 20.7175 | 20.8286 | 95.2856
| Human Resources | 6.0335 | 8.0418 | 10.338 | 10.6428 | 0.30481 | 4.9022 | 7.0556 | 7.4918 | 7.4982 | 7.5384 | 34.4862
| Major Projects | 0.86915 | 1.3527 | 0.41614 | 0.15983 | -0.25632 | 0.70619 | 1.0164 | 1.0792 | 1.0801 | 1.0859 | 4.9679
| Operations | 0 | 0.48902 | 0.2127 | 0 | -0.2127 | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology Directorate | 0 | 34.6301 | 3.5499 | 1.0215 | -2.5284 | 0 | 0 | 0 | 0 | 0 | 0
| Professional and Technical Services | 1.0033 | 1.1304 | -4.9457 | 0.83662 | 5.7824 | 0.81522 | 1.1733 | 1.2459 | 1.2469 | 1.2536 | 5.7349
| Strategy and Planning | 0.50536 | 0.42263 | 0.6511 | 0.46898 | -0.18212 | 0.41061 | 0.59097 | 0.62751 | 0.62804 | 0.63141 | 2.8885
| General Counsel | 0 | 0.53187 | 0.36015 | 0.70631 | 0.34616 | 0 | 0 | 0 | 0 | 0 | 0
| Non Pay Subtotal | 57.9612 | 65.0438 | 33.7967 | 37.2948 | 3.4981 | 47.0934 | 67.7793 | 71.9701 | 72.0309 | 72.4173 | 331.291
Projects
| Centrally Managed | 4.3088 | 0.1525 | -0.20627 | -9.4281 | -9.2219 | 3.5009 | 5.0386 | 5.3502 | 5.3547 | 5.3834 | 24.6278
| Commercial and Procurement | 2.2686 | 2.6825 | 2.8425 | 5.2913 | 2.4487 | 1.8433 | 2.6529 | 2.8169 | 2.8193 | 2.8344 | 12.9669
| Communications Directorate | 0.041624 | 3.2549 | 5.3059 | 6.6022 | 1.2963 | 0.033819 | 0.048675 | 0.051684 | 0.051728 | 0.052005 | 0.23791
| Finance and Business Services | 0.15101 | 0 | 3.8728 | 3.3438 | -0.529 | 0.12269 | 0.17658 | 0.1875 | 0.18766 | 0.18867 | 0.86311
| Human Resources | -0.030764 | 0 | 0 | 0 | 0 | -0.024996 | -0.035975 | -0.038199 | -0.038232 | -0.038437 | -0.17584
| Major Projects | 4.9856 | 4.9309 | 2.7384 | 2.5086 | -0.22988 | 4.0508 | 5.8301 | 6.1906 | 6.1959 | 6.2291 | 28.4965
| Operations | 0.32945 | -0.55625 | 2.1219 | 0 | -2.1219 | 0.26767 | 0.38525 | 0.40907 | 0.40942 | 0.41161 | 1.883
| Information Technology Directorate | 0 | 0 | 37.1325 | 33.8293 | -3.3032 | 0 | 0 | 0 | 0 | 0 | 0
| Professional and Technical Services | 26.2304 | 12.9497 | 20.7258 | 17.4495 | -3.2763 | 21.3121 | 30.6735 | 32.5701 | 32.5976 | 32.7725 | 149.9259
| Strategy and Planning | 3.7014 | 10.3542 | 11.6854 | 11.8887 | 0.20323 | 3.0074 | 4.3284 | 4.5961 | 4.5999 | 4.6246 | 21.1565
| General Counsel | 0 | 2.0847 | 0.10383 | -0.38327 | -0.4871 | 0 | 0 | 0 | 0 | 0 | 0
| Projects Subtotal | 41.9861 | 35.8531 | 86.3228 | 71.1019 | -15.2209 | 34.1137 | 49.0982 | 52.134 | 52.178 | 52.4579 | 239.9818
Totals
| Centrally Managed | 41.837 | 0.31135 | 2.6411 | -3.4497 | -6.0908 | 33.9925 | 48.9237 | 51.9984 | 52.0279 | 52.3195 | 239.262
| Commercial and Procurement | 6.2417 | 8.666 | 9.4046 | 12.3733 | 2.9688 | 5.0714 | 7.299 | 7.7503 | 7.7568 | 7.7984 | 35.6759
| Communications Directorate | 3.3582 | 6.6275 | 8.9828 | 10.1579 | 1.1751 | 2.7286 | 3.9271 | 4.1699 | 4.1734 | 4.1958 | 19.1948
| Finance and Business Services | 23.8936 | 23.2539 | 30.3856 | 31.4105 | 1.0249 | 19.4135 | 27.941 | 29.7887 | 29.779 | 29.969 | 136.8912
| Human Resources | 12.6569 | 13.2285 | 15.345 | 15.5 | 0.15496 | 10.2837 | 14.8008 | 15.7306 | 15.7397 | 15.8278 | 72.3826
| Major Projects | 0.96508 | 2.2555 | 3.1733 | 4.0396 | 0.86633 | 0.78413 | 1.1286 | 1.492 | 1.4081 | 1.4896 | 6.3023
| Operations | 0.32945 | -0.056429 | 2.3393 | 0 | -2.3393 | 0.26767 | 0.38525 | 0.40907 | 0.40942 | 0.41161 | 1.883
| Information Technology Directorate | 0 | 39.2283 | 46.3571 | 40.3176 | -6.0395 | 0 | 0 | 0 | 0 | 0 | 0
| Professional and Technical Services | 34.5906 | 19.8903 | 24.0486 | 26.227 | 2.1785 | 28.1048 | 40.4499 | 42.951 | 42.9873 | 43.2179 | 197.711
| Strategy and Planning | 7.82 | 16.2571 | 18.4736 | 19.8 | 1.3264 | 6.3538 | 9.1447 | 9.7101 | 9.7183 | 9.7704 | 44.6972
| General Counsel | 0 | 4.9112 | 2.2366 | 1.843 | -0.39361 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 131.6925 | 134.5732 | 163.3876 | 158.2194 | -5.1682 | 107 | 154 | 164 | 164 | 165 | 754
FTEs | Centrally Managed | 0 | 44.6378 | 0 | 0 | 0 | X | X | X | X | X | X
| Commercial and Procurement | 190.31 | 279.4473 | 341.227 | 345.716 | 4.489 | X | X | X | X | X | X
| Communications Directorate | 87.51 | 107.2946 | 128.7649 | 122.01 | -6.7549 | X | X | X | X | X | X
| Finance and Business Services | 196.99 | 175.5608 | 250.7374 | 259.41 | 8.6726 | X | X | X | X | X | X
| Human Resources | 104.03 | 103.1892 | 108.9269 | 100.46 | -8.4669 | X | X | X | X | X | X
| Major Projects | 435.56 | 577.0054 | 707.1992 | 718.8105 | 11.6113 | X | X | X | X | X | X
| Operations | 0 | 0 | 0 | 0 | 0 | X | X | X | X | X | X
| Information Technology Directorate | 79.05 | 143.3568 | 144.4946 | 212.191 | 67.6964 | X | X | X | X | X | X
| Safety, Engineering and Standards | 221.15 | 305.6581 | 377.7712 | 363.893 | -13.8782 | X | X | X | X | X | X
| Strategy and Planning | 54.34 | 88.7878 | 123.5068 | 133.742 | 10.2352 | X | X | X | X | X | X
| General Counsel | 0 | 0 | 24.3513 | 25.28 | 0.9287 | X | X | X | X | X | X
| FTE Total | 1368.94 | 1824.9378 | 2206.9793 | 2281.5125 | 74.5332 | X | X | X | X | X | X
Note:

## F2.8
Highways England Performance Monitoring Statements Year end 2017-18
Statement F2.8: Other project activities income and expenditure
|  | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | RIS 1 Total
|  | Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Income
| Income | -0.0051256 | -0.43822 | -0.80486 | 0 | 0.80486 | 0 | 0 | 0 | 0 | 0 | 0
| Income Subtotal | -0.0051256 | -0.43822 | -0.80486 | 0 | 0.80486 | 0 | 0 | 0 | 0 | 0 | 0
Pay
| Permanent staff salaries | 0 | 4.2126 | 4.9703 | 4.5274 | -0.44296 | 0 | 0 | 0 | 0 | 0 | 0
| National Insurance | 0 | 0.22146 | 0.30428 | 0.1855 | -0.11878 | 0 | 0 | 0 | 0 | 0 | 0
| Pension contributions | 0 | 0.30956 | 0.39542 | 0.33832 | -0.057101 | 0 | 0 | 0 | 0 | 0 | 0
| Employment agency staff costs | 0 | 0.14546 | 0.012035 | 0.035392 | 0.023357 | 0 | 0 | 0 | 0 | 0 | 0
| Capitalised Pay Costs | 0 | 0 | -0.81434 | -0.05562 | 0.75872 | 0 | 0 | 0 | 0 | 0 | 0
| Pay Subtotal | 0 | 4.8891 | 4.8677 | 5.031 | 0.16324 | 0 | 0 | 0 | 0 | 0 | 0
Non Pay
| Travel and Subsistence | 0 | 0.12225 | 0.063613 | 0.0575 | -0.0061131 | 0 | 0 | 0 | 0 | 0 | 0
| Training and Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Non Pay Costs | 0 | 0.10723 | 0.15322 | 0.4841 | 0.33089 | 0 | 0 | 0 | 0 | 0 | 0
| Non Pay Subtotal | 0 | 0.22949 | 0.21683 | 0.5416 | 0.32477 | 0 | 0 | 0 | 0 | 0 | 0
Projects
| Other | 0.14847 | 44.0624 | 53.5168 | 35.4274 | -18.0894 | 39 | 40 | 42 | 50 | 49 | 220
| Projects Subtotal | 0.14847 | 44.0624 | 53.5168 | 35.4274 | -18.0894 | 39 | 40 | 42 | 50 | 49 | 220
| Total | 0.14847 | 48.7427 | 57.7965 | 41 | -16.7965 | 39 | 40 | 42 | 50 | 49 | 220
| FTEs | X | 53.9797 | 214.4744 | 53.862 | -160.6124 | X | X | X | X | X | X
Note:

## F3
Highways England Performance Monitoring Statements Year end 2017-18
Statement F3: Capital expenditure
|  | 2015-16 | 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
|  | Actual | Actual - Restated | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Renewals
| Renewal of Roads | 663.3152 | 683.8382 | 441.6847 | 541.7007 | 520.2746 | -21.4261 | 708.8373 | 595.4398 | 787.8871 | 761.0924 | 804.7434 | 3658
| Renewal of Structures | 0 | 0 | 142.8923 | 202.8379 | 233.2372 | 30.3993 | 0 | 0 | 0 | 0 | 0 | 0
| Renewal of Technology | 0 | 0 | 30.5468 | 22.0811 | 34.9682 | 12.8871 | 0 | 0 | 0 | 0 | 0 | 0
| Winter Maintenance - Assets | 0 | 0 | 11.0291 | 9.4321 | 5.4993 | -3.9328 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Maintain/Renew | 663.3152 | 683.8382 | 626.153 | 776.0518 | 793.9793 | 17.9275 | 708.8373 | 595.4398 | 787.8871 | 761.0924 | 804.7434 | 3658
Feasibility Schemes
| A1 in Northumberland (A1 North of Ellingham & A1 Morpeth to Ellingham Dualling) | 0.84 | 0.84 | 1.9997 | 4.7646 | 5.5508 | 0.78616 | 0 | 0 | 0 | 0 | 0 | 0
| A1 Morpeth to Ellingham Dualling | 0 | 0 | 0 | 0 | 0 | 0 | 0.44991 | 2.526 | 7.4827 | 15.6289 | 23.9242 | 50.0117
| A1 Scotswood to North Brunton | 0.35601 | 0.35601 | 0.7207 | 2.7444 | 2.3482 | -0.39616 | 0.16276 | 1.1082 | 1.9 | 2.6 | 8.6 | 14.3709
| A1 Birtley to Coal House widening | 0.81647 | 0.81647 | 1.1459 | 3.3967 | 1.6714 | -1.7253 | 0.44706 | 1.6622 | 2.9473 | 2.9473 | 4.0009 | 12.0048
| A628 Climbing Lanes | 0.78071 | 0.78071 | 2.3186 | 3.7394 | 5.4436 | 1.7042 | 0 | 0 | 0 | 0 | 0 | 0
| A61 Dualling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Montrrom Moore Link Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Trans-Pennine Routes (A57 (T) to A57 Link Road, Montrrom Moore Link Road, A61 Dualling & A628 Clyman Lanes) | 0 | 0 | 0 | 0 | 0 | 0 | 0.45478 | 1.9891 | 1.687 | 1.663 | 7.564 | 13.3579
| A47 North Tuddenham to Easton | 1.3331 | 1.3331 | 0.91031 | 1.9121 | 2.9751 | 1.0631 | 0.28322 | 4.3113 | 2.3002 | 2.3002 | 2.3002 | 11.4952
| A47 Blofield to North Burlingham dualling | 0.039783 | 0.039783 | 0.78658 | 1.6766 | 3.1804 | 1.5038 | 0.15368 | 2.1801 | 2.2571 | 2.2571 | 2.2571 | 9.1051
| A47 Acle Straight | 0.37796 | 0.37796 | 0 | 0 | 0 | 0 | 0.12511 | 0 | 0 | 0 | 0 | 0.12511
| A47 & A12 junction enhancements | 0.053371 | 0.053371 | 1.2534 | 1.7965 | 2.2719 | 0.47547 | 0.15368 | 0.55408 | 0.48528 | 2.6699 | 1.8733 | 5.7363
| A47/A11 Thickthorn Junction | 0.062077 | 0.062077 | 1.3296 | 2.056 | 2.5729 | 0.51696 | 0.15368 | 2.3102 | 1.086 | 1.086 | 1.086 | 5.722
| A47 Guyhirn Junction | 0.044936 | 0.044936 | 0.8719 | 1.3822 | 1.8079 | 0.42573 | 0.15368 | 0.44991 | 0.50985 | 0.64661 | 1.3872 | 3.1472
| A47 Wansford to Sutton | 0.040071 | 0.040071 | 0.7185 | 1.867 | 2.5858 | 0.7188 | 0.15368 | 2.6031 | 2.0857 | 2.2566 | 6.4387 | 13.5378
| A27 Arundel Bypass | 0.31566 | 0.31566 | 0.58711 | 2.8608 | 1.998 | -0.86283 | 0.15368 | 3.8184 | 4.5394 | 5.5642 | 8.5998 | 22.6755
| A27 Worthing and Lancing improvements | 0.37231 | 0.37231 | 0.54599 | 1.7342 | 1.7572 | 0.023063 | 0.15368 | 1.3749 | 1.6344 | 2.0034 | 6.0924 | 11.2588
| A27 East of Lewes | 0 | 0 | 0.94491 | 1.0652 | 1.317 | 0.25181 | 0.15368 | 3.8741 | 2.9739 | 2.9739 | 4.8015 | 14.7771
| A303 Amesbury to Berwick Down | 1.3634 | 1.3584 | 11.104 | 16.4809 | 14.5085 | -1.9723 | 0.5794 | 8.6356 | 8.1037 | 9.9629 | 12.2998 | 39.5814
| A303 Sparkford - Ilchester dualling | 0.62204 | 0.62204 | 1.3095 | 3.388 | 3.6106 | 0.22266 | 0.43264 | 1.176 | 3.3171 | 4.491 | 8.4511 | 17.8678
| A358 Taunton to Southfields | 0.7089 | 0.7039 | 1.9386 | 3.8754 | 4.25 | 0.37461 | 0.46358 | 1.7969 | 1.633 | 4.5871 | 7.6224 | 16.1031
| A34 SB Car Wash EW13780 E/Rep | 0 | 0 | 0 | 0.054335 | 0 | -0.054335 | 0 | 0 | 0 | 0 | 0 | 0
| A27 Broadmarsh Revetments DS |  |  |  | 0.01116 | 0 | -0.01116
| A19 Moor Farm |  |  |  | 0.0076495 | 0 | -0.0076495
| M20 J7 Kent |  |  |  | 0.0073867 | 0 | -0.0073867
| Staff Capitalisation | 0 | 0 | 0 | 2.4001 | 0 | -2.4001 | 0 | 0 | 0 | 0 | 0 | 0
| Categorisation error? | 0 | 0 | 0 | 0.12076 | 2.68 | 2.5592 | 0 | 0 | 0 | 0 | 0 | 0
| Total Feasibility Schemes | 8.1267 | 8.1167 | 28.4853 | 57.3412 | 60.5295 | 3.1883 | 4.6279 | 40.3702 | 44.9428 | 63.6384 | 107.2985 | 260.8777
Major Projects Pipeline Schemes
| M20 Lorry Park | 0 | 0 | 10.989 | 4.3687 | 0 | -4.3687 | 3.6 | 230 | 0 | 0 | 0 | 233.6
| Total Major Projects Pipeline Schemes | 0 | 0 | 10.989 | 4.3687 | 0 | -4.3687 | 3.6 | 230 | 0 | 0 | 0 | 233.6
Air Quality
| Scheme details - available | 0 | 0 | 1.9731 | 0.68944 | 0.1 | -0.58944 | 0 | 5.1056 | 18.1254 | 18.5552 | 33.2139 | 75
| Total Air Quality | 0 | 0 | 1.9731 | 0.68944 | 0.1 | -0.58944 | 0 | 5.1056 | 18.1254 | 18.5552 | 33.2139 | 75
Cycling, Safety & Integration
| Scheme details - available | 16.6134 | 16.506 | 18.1351 | 28.8775 | 41.5684 | 12.6909 | 16.9596 | 16.3378 | 50.3265 | 31.5517 | 59.8245 | 175
| Total Cycling, Safety & Integration | 16.6134 | 16.506 | 18.1351 | 28.8775 | 41.5684 | 12.6909 | 16.9596 | 16.3378 | 50.3265 | 31.5517 | 59.8245 | 175
Environment
| Scheme details - available | 2.6067 | 2.6052 | 13.6746 | 34.9884 | 40.1656 | 5.1772 | 6.389 | 11.7428 | 69.1296 | 42.1682 | 95.5703 | 225
| Total Environment | 2.6067 | 2.6067 | 13.6746 | 34.9884 | 40.1656 | 5.1772 | 6.389 | 11.7428 | 69.1296 | 42.1682 | 95.5703 | 225
Innovation
| Scheme details - available | 2.684 | 2.684 | 8.7688 | 26.8147 | 80.5926 | 53.7779 | 3.801 | 20.0139 | 28.348 | 25.2005 | 42.6367 | 120
| Total Innovation | 2.684 | 2.684 | 8.7688 | 26.8147 | 80.5926 | 53.7779 | 3.801 | 20.0139 | 28.348 | 25.2005 | 42.6367 | 120
Supporting Growth
| Scheme details - available | 0.060486 | 0.060486 | 5.2169 | 14.5347 | 23 | 8.4653 | 0 | 5.1056 | 22.6483 | 18.5552 | 33.6909 | 80
| Total Supporting Growth | 0.060486 | 0.060486 | 5.2169 | 14.5347 | 23 | 8.4653 | 0 | 5.1056 | 22.6483 | 18.5552 | 33.6909 | 80
Other Capital
| Pinch Point Programme | 71.2591 | 71.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Core LNMS/ Congestion Relief | 55.2206 | 55.2206 | 17.5468 | 37.3334 | 100.5356 | 63.2021 | 0 | 0 | 95 | 66 | 45 | 206
| Strategic Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.8 | 30.5 | 0 | 46.3
| Operations Technology | 41.7044 | 41.7044 | 9.678 | 4.3981 | 15.8668 | 11.4686 | 0 | 0 | 0 | 0 | 0 | 0
| Legacy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Corporate Capital | 61.3619 | 61.3619 | 41.2304 | 66.4345 | -106.9526 | -173.3871 | 249.7787 | 99.9105 | 73.2565 | 72.4873 | 57.2537 | 552.6867
| Operations Staff Capitalisation | 25.6864 | 25.6864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| R&D Transfer | 0 | 0 | 9.8573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Capital | 14.5769 | 12.4669 | 18.5616 | 17.5404 | 26.4121 | 8.8717 | -10.1356 | -214.4611 | 34.8585 | 80.3707 | 109.9516 | 0.58422
| Total Other Capital | 269.8093 | 267.6993 | 96.8741 | 125.7065 | 35.8619 | -89.8446 | 239.6431 | -114.5505 | 218.915 | 249.358 | 212.2054 | 805.5709
SR10/13 Schemes
| A1 Coal House to Metro Centre | 28.9041 | 28.2215 | 16.2334 | 0.106 | 0.28443 | 0.17843 | 23.5992 | 17.9985 | 0 | 0 | 0 | 41.5977
| A1 Leeming to Barton | 115.091 | 114.9001 | 90.249 | 43.6739 | 31.6082 | -12.0657 | 110.8083 | 78.205 | 29.3954 | 0.27708 | 0.23926 | 218.925
| M1 Junctions 39-42 | 38.717 | 38.6613 | 3.6779 | 3.002 | 3.6524 | 0.65039 | 41.2865 | 0.90206 | 0 | 0 | 0 | 42.1886
| M1 Junctions 32-35A | 35.6389 | 35.5778 | 40.7939 | 4.1177 | 10.2048 | 6.0871 | 45.0724 | 32.6137 | 0.24314 | 0 | 0 | 77.9292
| M60 Junction 8 to M62 Junction 20 | 58.0996 | 58.0015 | 75.4517 | 90.0789 | 60.7958 | -29.2832 | 63.9192 | 69.3494 | 14.3565 | 0 | 0 | 147.625
| A556 Knutsford to Bowdon | 52.3334 | 53.3996 | 69.4063 | 12.1864 | 14.1028 | 1.9164 | 49.524 | 64.7962 | 17.036 | 0 | 0 | 131.3561
| M1 Junctions 28-31 | 58.4661 | 61.4428 | 10.4868 | 4.7581 | 7.9113 | 3.1532 | 53.7769 | 4.6332 | 0 | 0 | 0 | 58.4101
| A453 Widening | 3.983 | 4.8819 | 1.967 | -0.23846 | 0.68089 | 0.91934 | 5.1742 | 0.45532 | 0.04 | 0 | 0 | 5.6695
| M6 Junctions 10a-13 | 17.3105 | 17.3017 | 0.26075 | 0.12731 | 1.8408 | 1.7135 | 14.1498 | 0 | 0 | 0 | 0 | 14.1498
| A14 Kettering bypass widening | -2.401 | -2.4058 | 2.2705 | 0.81973 | 0.18734 | -0.63239 | -2.357 | 0.14191 | 0.094119 | 0 | 0 | -2.121
| M1 Junction 19 improvement | 50.9383 | 51.8557 | 33.7146 | 4.4471 | 2.403 | -2.0441 | 56.6139 | 36.1752 | 0 | 0 | 0 | 92.7891
| A45-A46 Tollbar End | 24.1005 | 24.4651 | 7.752 | -3.9439 | 0.82593 | 4.7699 | 21.5151 | 10.276 | 0 | 0 | 0 | 31.7911
| M3 Junctions 2-4A | 49.1428 | 49.1428 | 68.5501 | 18.5629 | 10.4735 | -8.0894 | 57.2305 | 59.488 | 3.6695 | 0 | 0 | 120.388
| M25 Junction 30 | 35.7468 | 35.6183 | 37.832 | 2.3688 | 0.88844 | -1.4804 | 39.0531 | 25.0865 | 0 | 0 | 0 | 64.1396
| A5/M1 J11a Link | 60.0448 | 61.0537 | 50.5962 | 0.88642 | 1.6121 | 0.72571 | 62.429 | 51.311 | 5.7093 | 0 | 0 | 119.4493
| A30 Temple to Carblake | 19.0363 | 19.0363 | 27.9104 | 0 | 0 | 0 | 33.6662 | 13.5142 | 0 | 0 | 0 | 47.1804
| RIP Commercial | 0 | 0 | 0 | 1.0598 | 1.62 | 0.56018 | 0 | 0 | 0 | 0 | 0 | 0
| Other legacy Schemes | 0.55215 | -2.9376 | 20.9175 | 7.9269 | 19.4792 | 11.5523 | 0 | 0 | 0 | 0 | 0 | 0
| SR10 Schemes SubTotal | 666.1722 | 648.2166 | 558.0701 | 189.9396 | 168.5709 | -21.3687 | 675.4612 | 464.9461 | 70.544 | 0.27708 | 0.23926 | 1211.4677
| A14 Cambridge to Huntingdon | 36.1921 | 36.1921 | 142.0804 | 380.3458 | 340 | -40.3458 | 27.9202 | 106.2557 | 411.5 | 403.171 | 323 | 1271.8469
| Lower Thames Crossing | 16.5351 | 16.5435 | 0 | 0 | 0 | 0 | 16.4693 | 35.6 | 45 | 45 | 45 | 187.0693
| SR13 Complex Infrastructure SubTotal | 52.7271 | 52.7356 | 142.0804 | 380.3458 | 340 | -40.3458 | 44.3895 | 141.8557 | 456.5 | 448.171 | 368 | 1458.9162
| M3 Junctions 9-14 | 0 | 0 | 0.11481 | 2.7793 | 4.3555 | 1.5762 | 0.49832 | 1.869 | 1.8249 | 6.3637 | 3.8222 | 14.3782
| M27 Junctions 4-11 | 0 | 0 | 0.50708 | 4.2196 | 11.8538 | 7.6341 | 0.69801 | 11.6196 | 15.5746 | 33.5408 | 128.5997 | 190.0327
| M20 Junctions 3-5 | 0.070401 | 0.070401 | 4.722 | 10.9782 | 6.5988 | -4.3794 | 0.36324 | 7.5741 | 4.7545 | 77.6445 | 1.8344 | 92.1709
| M23 Junctions 8-10 | 0.087238 | 0.087238 | 5.3837 | 13.5361 | 8.8138 | -4.7224 | 0.44577 | 9.6021 | 6.0514 | 96.2784 | 46.0119 | 158.3895
| M4 Junctions 3-12 | 10.0368 | 10.0379 | 29.5501 | 39.6912 | 41.6908 | 1.9996 | 8.8621 | 30.729 | 123.2614 | 127.3643 | 121.838 | 412.0547
| M6 Junctions 13-15 | 3.9561 | 3.9561 | 9.7572 | 15.3872 | 10.7259 | -4.6613 | 0.71049 | 10.8763 | 7.5318 | 95.182 | 92.7826 | 207.0832
| M6 Junctions 2-4 | 3.0325 | 3.0325 | 13.1254 | 19.5187 | 8.2676 | -11.251 | 0.57845 | 9.4457 | 5.289 | 100.5925 | 56.4814 | 172.3871
| M5 Junctions 4A-6 | 23.2048 | 23.001 | 73.602 | 9.771 | 10.3818 | 0.61084 | 14.3221 | 50.6897 | 0 | 0 | 0 | 65.0118
| M1 Junctions 24-25 | 2.8103 | 2.8103 | 6.5723 | 58.1341 | 58.111 | -0.023095 | 0.77267 | 9.8245 | 107.7178 | 0 | 0 | 118.315
| M1 Junctions 13-19 | 32.9536 | 32.9536 | 75.1727 | 70.533 | 54.2014 | -16.3316 | 25.6805 | 92.6628 | 7.4442 | 93.3417 | 110.1 | 329.2292
| M6 Junctions 21A-26 | 0 | 0 | 0.36726 | 2.2181 | 4.4235 | 2.2054 | 0.54106 | 5.0072 | 9.4671 | 18.7512 | 74.2145 | 107.9811
| M62 Junctions 10-12 | 0 | 0 | 0.3226 | 5.0748 | 6.0437 | 0.96897 | 0.45451 | 2.8364 | 1.8178 | 70.9636 | 68.0418 | 144.1142
| M60 Junctions 24-27 & J1-4 | 0 | 0 | 0.70639 | 2.4405 | 5.8274 | 3.3869 | 0.46508 | 3.8174 | 7.0812 | 3.7442 | 3.7442 | 18.852
| M56 Junctions 6-8 | 0 | 0 | 0.18923 | 1.8895 | 3.4299 | 1.5405 | 0.37054 | 2.4153 | 4.6738 | 7.2917 | 56.5288 | 71.2802
| M6 Junctions 16-19 | 12.054 | 11.992 | 64.5261 | 81.7641 | 76.329 | -5.4351 | 10.3248 | 95.4403 | 70.205 | 0 | 0 | 175.9701
| MP SMP Data collection | 0 | 9.7486 | 4.1736 | -0.19764 | 0 | 0.19764 | 0 | 0 | 0 | 0 | 0 | 0
| SR13 SMP Other | 0 | 3.2546 | 0.75706 | 0.12421 | 0 | -0.12421 | 0 | 0 | 0 | 0 | 0 | 0
| SR13 Smart Motorway Programme SubTotal | 88.2056 | 100.9441 | 289.5495 | 337.862 | 311.054 | -26.808 | 65.0875 | 344.4095 | 372.6945 | 731.0586 | 763.9995 | 2277.2498
| A19 Coast Road | 4.7844 | 4.7794 | 25.8831 | 32.3218 | 35.6632 | 3.3414 | 4.397 | 53.7906 | 36.952 | 1.3875 | 0 | 96.527
| A19 Testos | 1.7521 | 1.7511 | 2.1981 | 10.8421 | 10.8265 | -0.015559 | 1.5542 | 2.2748 | 9.8859 | 8.5539 | 43.9087 | 66.1776
| A63 Castle Street | 6.3747 | 6.3747 | 5.1153 | 2.4271 | 6.5 | 4.0729 | 5.6979 | 18.1765 | 4.154 | 8.8385 | 29.7027 | 66.5696
| A160/A180 Immingham | 39.2885 | 38.8576 | 34.8455 | 3.2516 | 1.53 | -1.7216 | 42.1562 | 25.2423 | 0 | 0 | 0 | 67.3985
| A38 Derby Junctions | 1.599 | 1.599 | 2.1942 | 1.5841 | 3.0299 | 1.4458 | 1.7315 | 3.6376 | 5.5083 | 5.6854 | 46.1764 | 62.7392
| A21 Tonbridge to Pembury | 25.806 | 26.6485 | 48.3819 | 24.8179 | 25.1772 | 0.35932 | 29.3946 | 12.4353 | 0.4634 | 0 | 0 | 42.2933
| A27 Chichester Bypass | 1.2926 | 1.2926 | 0.76128 | 0.0023785 | 0.0075 | 0.0051215 | 1.2541 | 3.5771 | 3.9372 | 36.5153 | 80.3894 | 125.6731
| M54 to M6 / M6 toll | 0.14068 | 0.15379 | 0.59276 | 1.1871 | 2.3299 | 1.1428 | 0.51341 | 4.9293 | 7.6344 | 3.3558 | 66.6275 | 83.0604
| A2 Bean & Ebbsfleet | 1.3049 | 1.3049 | 1.4277 | 2.7186 | 3.3029 | 0.58433 | 1.131 | 2.2794 | 2.168 | 3.5586 | 5.0474 | 14.1844
| M20 Junction 10a | 1.8247 | 1.8245 | 2.276 | 15.8244 | 14.1147 | -1.7097 | 1.2258 | 1.5567 | 37.2312 | 30.5362 | 0 | 70.5498
| SR13 JWB Other | 0 | 0 | 0.27437 | -0.69026 | 0.38528 | 1.0755 | 0 | 0 | 0 | 0 | 0 | 0
| SR13 Junctions, Widening & Bypasses SubTotal | 84.1678 | 84.5862 | 123.9501 | 94.2867 | 102.8671 | 8.5804 | 89.0557 | 127.8995 | 107.9345 | 98.4311 | 271.8521 | 695.173
| MP Staff Capitalisation | 19.4046 | 19.4046 | 35.6776 | 30.0168 | 33.1403 | 3.1235 | 37.0307 | 40.0927 | 41.1445 | 42.1727 | 43.1595 | 203.6002
| Operations Staff Capitalisation | 0.43773 | 0.43773 | 0 | 0.45479 | 0 | -0.45479 | 0 | 0 | 0 | 0 | 0 | 0
| SES Staff Capitalisation | 5.5845 | 5.5845 | 7.5725 | 10.1771 | 9.4819 | -0.69523 | 0 | 0 | 0 | 0 | 0 | 0
| FBS Staff Capitalisation | 1.3659 | 1.3659 | 0.42065 | 1.2729 | 1.5294 | 0.25646 | 0 | 0 | 0 | 0 | 0 | 0
| CPD Staff Capitalisation | 5.6079 | 5.6079 | 10.245 | 14.041 | 12.577 | -1.464 | 0 | 0 | 0 | 0 | 0 | 0
| CAC Staff Capitalisation | 2.4285 | 2.4285 | 3.1018 | 3.8643 | 3.416 | -0.44831 | 0 | 0 | 0 | 0 | 0 | 0
| IT Staff Capitalisation | 0 | 0 | 2.4135 | 3.5053 | 2.4656 | -1.0397 | 0 | 0 | 0 | 0 | 0 | 0
| GC Staff Capitalisation | 0 | 0 | 0 | 0.056806 | 0 | -0.056806 | 0 | 0 | 0 | 0 | 0 | 0
| Adj | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other none funded Capex | 13.0032 | 0 | 2.6478 | 1.788 | -80.3804 | -82.1685 | 0 | 0 | 0 | 0 | 0 | 0
| Other Capital SubTotal | 47.8324 | 34.8291 | 62.0788 | 65.1771 | -17.7703 | -82.9473 | 37.0307 | 40.0927 | 41.1445 | 42.1727 | 43.1595 | 203.6002
| A50 Growth Corridor | 4.7176 | 4.7176 | 11.5186 | 8.4276 | 17 | 8.5724 | 14.8641 | 17.4187 | 10.9192 | 0 | 0 | 43.202
| M62 J19 Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 1.3
| M55 J2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 24.9 | 0 | 25.9
| Contributions to local Authority schemes budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Funding contributions received | 0 | 0 | -46.0687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HE Contributions to Local Authority Schemes | 4.7176 | 4.7176 | -34.5501 | 8.4276 | 17 | 8.5724 | 16.1641 | 17.9187 | 11.4192 | 24.9 | 0 | 70.402
| TOTAL SR10 & SR13 Schemes | 943.8228 | 926.0293 | 1141.1788 | 1076.0387 | 921.7217 | -154.317 | 927.1888 | 1137.1223 | 1060.2368 | 1345.0105 | 1447.2505 | 5916.8088
RIS Schemes
| A19 Down Hill Lane junction improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| A19 Norton to Wynyard | 0.47112 | 0.47112 | 0.40518 | 2.6134 | 1.5956 | -1.0178 | 0.19164 | 0.47568 | 5.4089 | 3.0575 | 14.6971 | 23.8309
| A1 & A19 Technology enhancements | 1.8159 | 1.8159 | 0.2775 | 0 | 0 | 0 | 0.19164 | 8.2055 | 0 | 0 | 0 | 8.3972
| M1 Junction 45 Improvement | 0.33172 | 0.33172 | 1.2239 | 8.9231 | 6.6597 | -2.2634 | 0.40351 | 1.1 | 9.9 | 0 | 0 | 11.4035
| M621 Junctions 1-7 improvements | 0.10502 | 0.10502 | 0.69596 | 1.1122 | 0.9139 | -0.19833 | 0.19164 | 0.32703 | 0.825 | 1.1 | 3.1625 | 5.6062
| M62/M606 Chain Bar | 0.80903 | 0.80903 | 0.77153 | 0 | 0 | 0 | 0.39942 | 1.7436 | 0 | 0 | 0 | 2.1431
| M62 Junctions 20-25 | 0 | 0 | 0.22173 | 2.3064 | 2.7471 | 0.4407 | 0.40351 | 0.7925 | 2.3775 | 3.17 | 41.1137 | 47.8573
| A585 Windy Harbour - Skippool | 1.0126 | 1.0126 | 1.3475 | 3.472 | 3.7661 | 0.29402 | 0.4513 | 1.3081 | 1.1 | 2.1 | 4.2 | 9.1594
| A5036 Princess Way - Access to Port of Liverpool | 1.2057 | 1.2057 | 1.1357 | 2.0595 | 2.8335 | 0.77402 | 0.4014 | 3.5676 | 4.2 | 5 | 7 | 20.169
| M6 Junction 22 upgrade | 0 | 0 | 0 | 0 | 2.4733 | 2.4733 | 0.40351 | 0.31 | 1.5696 | 4.1739 | 24.7915 | 31.2485
| M53 Junctions 5-11 | 0 | 0 | 0.22173 | 0.021327 | 0 | -0.021327 | 0.40351 | 0.5 | 0 | 0 | 0 | 0.90351
| M56 new Junction 11A | 0.65451 | 0.65451 | 1.2084 | 1.4629 | 3.0455 | 1.5827 | 0.19164 | 0.11892 | 0.2 | 0.2 | 4.6 | 5.3106
| M6 Junction 19 Improvements | 0.5354 | 0.5354 | 0.96061 | 0.95118 | 1.1458 | 0.19457 | 0.38471 | 1.2067 | 2.1868 | 1.947 | 12.5696 | 18.2948
| A500 Etruria widening | 0.49121 | 0.49121 | 0.82251 | 1.8263 | 1.555 | -0.27132 | 0.19164 | 0.23784 | 1.3246 | 1.3246 | 10.9005 | 13.9791
| M1 Junctions 23A-24 | 0.80355 | 0.80355 | 2.6616 | 13.3176 | 22.714 | 9.3964 | 0.40351 | 0.7 | 0 | 0 | 0 | 1.1035
| M6 Junction 10 improvement | 0.47095 | 0.47095 | 1.5403 | 2.5978 | 2.2908 | -0.30704 | 1.0286 | 1.2629 | 0.76838 | 2.1688 | 17.4927 | 22.7214
| A5 Dodwells to Longshoot widening | 0.1086 | 0.10565 | 0.087332 | 0.28 | 0.4475 | 0.1675 | 0.20295 | 0.1 | 0.1938 | 0.1938 | 0.1938 | 0.88434
| M42 Junction 6 | 0.95262 | 0.95262 | 2.1777 | 3.9864 | 3.7946 | -0.19181 | 0.19164 | 0.83839 | 1.41 | 4.23 | 9.321 | 15.991
| A46 Coventry junction upgrades | 0.71848 | 0.71848 | 1.1402 | 2.1364 | 2.12 | -0.016369 | 0.19164 | 0.31217 | 0.7875 | 1.05 | 10.0188 | 12.3601
| M40/M42 interchange Smart Motorways | 0 | 0 | 0.19851 | 0.78824 | 1.4793 | 0.6911 | 0.40351 | 0.2 | 0.6 | 0.8 | 3.3 | 5.3035
| A45/A6 Chowns Mill junction improvement | 0.63077 | 0.63077 | 0.3607 | 0.14223 | 0.23967 | 0.097441 | 0.33 | 0.2 | 0.6 | 0.8 | 8.3 | 10.23
| M5 Junctions 5, 6 & 7 junction upgrades | 2.3716 | 2.3716 | 0.22694 | 0.76167 | 3.1722 | 2.4105 | 0.51675 | 11.6423 | 0 | 0 | 0 | 12.1591
| A43 Abthorpe Junction | 1.4651 | 0.98476 | 7.3866 | 0.60465 | 0.64051 | 0.035858 | 2.2007 | 4.456 | 1.13 | 0 | 0 | 7.7867
| A428 Black Cat to Caxton Gibbet | 0.19192 | 0.19192 | 2.6254 | 4.7888 | 5.4245 | 0.63572 | 0.19164 | 0.83245 | 1.4 | 4.2 | 5.6 | 12.2241
| M11 Junctions 8 to 14 - technology upgrade | 0.18936 | 0.18936 | 0.034816 | 0 | 0 | 0 | 0.19164 | 0.23784 | 0 | 0 | 0 | 0.42949
| A12 Chelmsford to A120 widening | 0.19099 | 0.19099 | 2.5702 | 6.8552 | 5.3578 | -1.4974 | 0.19164 | 1.0406 | 3.6723 | 3.0768 | 3.176 | 11.1572
| A12 whole-route technology upgrade | 0.18936 | 0.18936 | 0.63082 | 0 | 0 | 0 | 0.19164 | 0.17838 | 0 | 0 | 0 | 0.37003
| A1(M) Junctions 6-8 Smart Motorway | 0 | 0 | 0.19851 | 0.90984 | 1.519 | 0.60912 | 0.40351 | 0.5 | 0.865 | 1.73 | 5.6225 | 9.121
| M11 Junction 7 junction upgrade | 0.18936 | 0.18936 | 0.85976 | 0 | 1e-06 | 1e-06 | 0.19164 | 0.11892 | 0.25 | 14.5 | 3.75 | 18.8106
| A34 Oxford Junctions | 0.169 | 0.169 | 0.43804 | 0.24664 | 3.5 | 3.2534 | 0.40351 | 0.45 | 3.5 | 0 | 0 | 4.3535
| A34 Technology enhancements | 0.1888 | 0.1888 | 0.15144 | 0 | 0.66993 | 0.66993 | 0.047495 | 0.11892 | 0.1 | 0.1 | 1.5 | 1.8664
| M25 Junction 25 improvement | 0.31311 | 0.31111 | 0.821 | 1.2116 | 0.99173 | -0.21987 | 0.19164 | 0.17838 | 1.1661 | 0.64851 | 1.0626 | 3.2473
| M25 Junction 28 improvement | 0.36049 | 0.35749 | 1.0666 | 2.0418 | 1.3378 | -0.70393 | 0.19164 | 0.47568 | 2.2161 | 1.4967 | 1.4967 | 5.8769
| M4 Heathrow slip road | 0.12992 | 0.12992 | 0.2647 | 1.5855 | 2.5 | 0.91455 | 0.40351 | 0.35 | 2.5 | 0 | 0 | 3.2535
| M2 Junction 5 improvements | 0.2633 | 0.2633 | 0.64383 | 1.6251 | 1.6978 | 0.072734 | 0.19164 | 0.23784 | 0.2 | 0.6 | 4.2 | 5.4295
| M25 Junctions 10-16 | 0.14434 | 0.14434 | 0.35914 | 0.27054 | 1.345 | 1.0745 | 0.40351 | 1 | 0.75542 | 6.1455 | 5.3997 | 13.7041
| M25 Junction 10/A3 Wisley interchange | 0.42969 | 0.42969 | 1.159 | 4.562 | 1.5115 | -3.0505 | 0.19164 | 1.0406 | 1.7979 | 4.3724 | 4.3724 | 11.7749
| M3 Junction 9 improvement | 0.65653 | 0.65353 | 1.3063 | 1.5866 | 2.1114 | 0.52483 | 0.19164 | 0.9038 | 1.962 | 1.962 | 2.3654 | 7.3848
| M3 Junction 10-11 improved sliproads | 0.1136 | 0.1136 | 0 | 0 | 0.716 | 0.716 | 0.19164 | 0.18195 | 0.70077 | 0.8926 | 3.2641 | 5.231
| M3 Junctions 12-14 improved sliproads | 0 | 0 | 0 | 0 | 0.764 | 0.764 | 0.19164 | 0.3853 | 0.73689 | 0.91437 | 3.8967 | 6.1249
| M27 Southampton Junctions | 0.3559 | 0.3559 | 1.3399 | 1.3763 | 1.9429 | 0.56659 | 0.19164 | 0.77061 | 1.944 | 2.592 | 7.452 | 12.9503
| M271 / A35 Redbridge roundabout upgrade | 0.32999 | 0.32999 | 0.51615 | 1.7899 | 1.078 | -0.71189 | 0.19164 | 0.11892 | 0.775 | 2.79 | 4.185 | 8.0606
| A31 Ringwood | 0.22699 | 0.22499 | 0.49571 | 1.0893 | 1.0572 | -0.032087 | 0.19164 | 0.14865 | 0.95067 | 0.42785 | 0.42785 | 2.1467
| M49 Avonmouth Junction | 0.41725 | 0.41225 | 1.4074 | 3.8972 | 7.6906 | 3.7935 | 0.26407 | 2.1319 | 10.3645 | 34.0365 | 0 | 46.797
| M5 Bridgwater Junctions | 0.27878 | 0.27878 | 0.36142 | 0.016813 | 0 | -0.016813 | 0.11717 | 16.5895 | 0 | 0 | 0 | 16.7066
| A52 Nottingham junctions | 0.42022 | 0.42022 | 2.8373 | 5.6688 | 3.467 | -2.2018 | 0.19164 | 0.28244 | 2.5304 | 4.5499 | 7.4494 | 15.0037
| A14 Junction 10a | 0.51072 | 0.51072 | 0.3227 | 0 | 0 | 0 | 0.19164 | 0.11892 | 0 | 0 | 0 | 0.31057
| A5 Towcester Relief Road | 0.046372 | 0.046372 | 0 | 0 | 0 | 0 | 0.40351 | 0.05 | 0.15 | 0.2 | 0.575 | 1.3785
| A30 Chiverton to Carland Cross | 0.75484 | 0.75484 | 2.3957 | 2.2933 | 3.8958 | 1.6025 | 0.19164 | 1.0406 | 2.625 | 3.5 | 5.0625 | 12.4197
| A47 AcleStrt PadysLoke SgnMrkg | 0 | 0 | 0 | 0.019439 | 0 | -0.019439 | 0 | 0 | 0 | 0 | 0 | 0
| A47 Halvergate | 0 | 0 | 0 | 0.041267 | 0.071 | 0.029733 | 0 | 0 | 0 | 0 | 0 | 0
| A12N GtYarm-Lowes Renumber A47 | 0 | 0 | 0 | 0.19977 | 0.19977 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| A50 Uttoxeter Project B | 0 | 0 | 0 | 1.3976 | 0 | -1.3976 | 0 | 0 | 0 | 0 | 0 | 0
| A63 Princes Quay Bridge | 0 | 0 | 0 | 0.25906 | 0 | -0.25906 | 0 | 0 | 0 | 0 | 0 | 0
| Staff Capitalisation | 0 | 0 | 0 | 6.819 | 0 | -6.819 | 0 | 0 | 0 | 0 | 0 | 0
| RIS 1 Baseline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RP1 Starts (49) Subtotal | 22.0147 | 21.5164 | 47.9007 | 99.9145 | 112.483 | 12.5685 | 15.5743 | 69.0876 | 75.744 | 120.0507 | 242.5189 | 522.9754
| A64 Hopgrove Junction | 0.023753 | 0.023753 | 0.21581 | 0.68454 | 0.6974 | 0.012857 | 0.62676 | 0.6 | 1.4014 | 3.0142 | 5.0236 | 10.6659
| M1/M62 Lofthouse Interchange | 0.24404 | 0.24404 | 1.178 | 0.99527 | 0.90424 | -0.091028 | 1.5249 | 1.5 | 1.8892 | 4.8053 | 9.1928 | 18.9122
| A1 Redhouse to Darrington | 0.3582 | 0.3582 | 0.10509 | 0.27588 | 0.017326 | -0.25855 | 0.31653 | 0 | 0.0092619 | 0.04631 | 0.23155 | 0.60365
| M1 Junctions 35A-39 | 0 | 0 | 0 | 0.41549 | 1.5463 | 1.1308 | 0 | 0 | 1.6499 | 2.578 | 3.0286 | 7.2566
| A1(M) Doncaster Bypass | 0 | 0 | 0 | 0 | 0 | 0 | 0.175 | 0 | 0.0051206 | 0.025603 | 0.12801 | 0.33374
| M60 Simister Island Interchange | 0.13587 | 0.13587 | 0.008576 | 0.66185 | 1.4485 | 0.78668 | 0.20733 | 0 | 1.6655 | 2.0883 | 2.7838 | 6.7449
| A46 Newark Northern Bypass | 0.187 | 0.187 | 0.0073144 | 0.38522 | 1 | 0.61478 | 0.175 | 0 | 0.541 | 1.082 | 2.164 | 3.962
| M1 Junctions 19-23A | 0 | 0 | 0 | 0.35965 | 1.5463 | 1.1866 | 0 | 0 | 0.97069 | 1.9414 | 3.4737 | 6.3858
| M5/M42 Birmingham Box Phase 4 | 0 | 0 | 0 | 0.21603 | 1.5463 | 1.3303 | 0 | 0 | 1.3996 | 1.6386 | 3.0845 | 6.1227
| A45 Stanwick to Thrapston | 0.19476 | 0.19476 | 0 | 0.28068 | 0.5 | 0.21932 | 0.175 | 0 | 0.7685 | 2.3055 | 3.5998 | 6.8488
| A12 Colchester Bypass widening | 0.18936 | 0.18936 | 0.28191 | 0.78556 | 0.753 | -0.03256 | 0.1218 | 0.175 | 0.22767 | 0.30235 | 0.45352 | 1.2803
| A12 M25 to Chelmsford | 0.19067 | 0.19067 | 0.34209 | 1.0545 | 0.6 | -0.45451 | 0.1218 | 0.175 | 0.39193 | 0.39193 | 0.65322 | 1.7339
| A3 Guildford | 0.26216 | 0.26216 | 0.13079 | 0 | 0.175 | 0.175 | 0.175 | 0 | 0.17308 | 0.58104 | 1.1621 | 2.0912
| A417 'Missing link' at Air Balloon | 0.13947 | 0.13947 | 0.788 | 0.61969 | 1.6919 | 1.0722 | 0.75991 | 1.275 | 1.8115 | 2.3538 | 8.0665 | 14.2667
| A5/A49 Dobbies Jcn Imp | 0.015107 | 0.015107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| M6 J15 Imp | 0.0096155 | 0.0096155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lower Thames Crossing | 0 | 0 | 28.2403 | 55.3898 | 47.0422 | -8.3476 | 0 | 0 | 0 | 0 | 0 | 0
| RIS2 Manchester NW Quad | 0 | 0 | 0 | 0.4438 | 1.4 | 0.9562 | 0 | 0 | 0 | 0 | 0 | 0
| RIS2 North Trans-Pennine | 0 | 0 | 0 | 1.2241 | 1.95 | 0.72588 | 0 | 0 | 0 | 0 | 0 | 0
| RIS2 Projects Oxford to Cambs | 0 | 0 | 0 | 6.5424 | 1.975 | -4.5674 | 0 | 0 | 0 | 0 | 0 | 0
| A120 BraintreeMarksTeyECC RIS2 | 0 | 0 | 0 | 3.3257 | 3.405 | 0.079266 | 0 | 0 | 0 | 0 | 0 | 0
| RIS 2 Baseline | 0 | 0 | -0.04208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RP2 Schemes (16) Subtotal | 1.95 | 1.95 | 31.2558 | 73.6603 | 68.1985 | -5.4618 | 4.379 | 3.725 | 12.9044 | 23.1543 | 43.0457 | 87.2084
| TOTAL RIS Schemes | 23.9647 | 23.4664 | 79.1565 | 173.5748 | 180.6815 | 7.1067 | 19.9533 | 72.8126 | 88.6484 | 143.2051 | 285.5645 | 610.1838
| Excluding Stack Funding | 1931.0033 | 1931.0071 | 2030.6051 | 2318.9864 | 2178.2005 | -140.7859 | 1931 | 2019.5 | 2389.2078 | 2698.3351 | 3121.9985 | 12160.0413
Note:
2015-16 figures have been restated to remove the impact changes to lands treatment

## F3.1
Highways England Performance Monitoring Statements Year end 2017-18
Statement F3.1: Regional capital income and expenditure
| 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20
| Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2
Maintenance & Renewals
Centrally managed | 8.9536 | 32.0622 | 66.2649 | 56.6359 | -9.629 | 9.5681 | 8.0375 | 10.6352 | 10.2735 | 10.8627 | 49.377
East | 37.3488 | 44.4878 | 81.8691 | 56.3181 | -25.551 | 39.9124 | 33.5273 | 44.3634 | 42.8547 | 45.3126 | 205.9705
Midlands | 171.5737 | 168.877 | 219.2439 | 231.1146 | 11.8707 | 183.3505 | 154.0186 | 203.7978 | 196.867 | 208.1579 | 946.1917
North West | 86.3988 | 86.2439 | 76.75 | 75.0556 | -1.6943 | 92.3292 | 77.5586 | 102.6257 | 99.1356 | 104.8213 | 476.4705
South East | 184.445 | 151.9815 | 181.2981 | 188.4714 | 7.1733 | 197.1053 | 165.573 | 219.0865 | 211.6358 | 223.7738 | 1017.1744
South West | 69.8133 | 71.2717 | 56.6443 | 73.5562 | 16.9119 | 74.6053 | 62.6702 | 82.9253 | 80.1051 | 84.6994 | 385.0052
Yorkshire & North East | 104.7749 | 71.2365 | 93.9839 | 112.8275 | 18.8435 | 111.9666 | 94.0545 | 124.4531 | 120.2207 | 127.1157 | 577.8107
Subtotal | 663.308 | 626.1606 | 776.0543 | 793.9793 | 17.925 | 708.8373 | 595.4398 | 787.8871 | 761.0924 | 804.7434 | 3658
Major Schemes
Centrally managed | 48.3845 | 42.1132 | 84.4012 | 9.0392 | -75.362 | 47.5314 | 71.9881 | 57.4374 | 74.4019 | 86.6304 | 337.9892
East | 107.852 | 200.3509 | 399.2524 | 359.1172 | -40.1352 | 105.9504 | 160.4658 | 128.0314 | 165.8462 | 193.1043 | 753.3981
Midlands | 237.2037 | 247.2977 | 225.2619 | 224.4101 | -0.85172 | 233.0213 | 352.9196 | 281.585 | 364.7529 | 424.7028 | 1656.9817
North West | 126.031 | 268.7565 | 204.2811 | 185.6649 | -18.6162 | 123.8089 | 187.5132 | 149.6117 | 193.8005 | 225.6531 | 880.3874
South East | 151.3935 | 215.8522 | 212.643 | 195.5424 | -17.1006 | 148.7241 | 225.2483 | 179.7196 | 232.8009 | 271.0634 | 1057.5564
South West | 20.6466 | 32.863 | 10.8964 | 13.2783 | 2.3819 | 20.2826 | 30.7187 | 24.5097 | 31.7487 | 36.9669 | 144.2266
Yorkshire & North East | 276.295 | 224.0909 | 117.2274 | 115.3511 | -1.8764 | 271.4234 | 411.081 | 327.9904 | 424.8644 | 494.6941 | 1930.0533
Subtotal | 967.8064 | 1231.3243 | 1253.9633 | 1102.4032 | -151.5602 | 950.7421 | 1439.9348 | 1148.8852 | 1488.2156 | 1732.815 | 6760.5927
Designated Schemes
Centrally managed | 0.23961 | 12.3254 | 31.1971 | 90.9936 | 59.7965 | 0.29618 | 0.63606 | 2.0572 | 1.484 | 2.8902 | 7.3636
East | 3.1511 | 4.0335 | 15.3598 | 22.0704 | 6.7106 | 3.895 | 8.3647 | 27.054 | 19.5154 | 38.0086 | 96.8377
Midlands | 5.5718 | 5.4868 | 21.1752 | 23.3991 | 2.224 | 6.887 | 14.7904 | 47.8365 | 34.5069 | 67.2063 | 171.2271
North West | 4.8812 | 14.9494 | 21.3041 | 16.3723 | -4.9318 | 6.0335 | 12.9573 | 41.9076 | 30.2301 | 58.8768 | 150.0052
South East | 6.5845 | 2.6327 | 8.0026 | 14.5816 | 6.579 | 8.1389 | 17.4788 | 56.5317 | 40.7792 | 79.4224 | 202.3511
South West | 0.5504 | 3.3691 | 3.8494 | 9.9901 | 6.1406 | 0.68032 | 1.461 | 4.7254 | 3.4087 | 6.6388 | 16.9143
Yorkshire & North East | 0.986 | 4.9716 | 5.0165 | 8.0196 | 3.0031 | 1.2188 | 2.6174 | 8.4653 | 6.1065 | 11.8931 | 30.301
Subtotal | 21.9646 | 47.7685 | 105.9048 | 185.4266 | 79.5219 | 27.1496 | 58.3057 | 188.5778 | 136.0307 | 264.9362 | 675
Feasibility Studies
Centrally managed | 0 | 0 | 19.0168 | 17.1885 | -1.8282 | 0 | 0 | 0 | 0 | 0 | 0
East | 1.5733 | 5.8704 | 10.6903 | 15.3941 | 4.7038 | 0.89594 | 7.8155 | 8.7008 | 12.3202 | 20.7726 | 50.505
Midlands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North West | 0 | 2.3389 | 3.7394 | 5.4436 | 1.7042 | 0 | 0 | 0 | 0 | 0 | 0
South East | 1.0659 | 13.1847 | 5.7257 | 5.0722 | -0.65345 | 0.607 | 5.2951 | 5.8948 | 8.347 | 14.0736 | 34.2175
South West | 2.6943 | 3.2481 | 7.2634 | 7.8606 | 0.59727 | 1.5343 | 13.3842 | 14.9001 | 21.0984 | 35.5733 | 86.4902
Yorkshire & North East | 2.7932 | 3.8433 | 10.9057 | 9.5704 | -1.3353 | 1.5906 | 13.8755 | 15.4471 | 21.8728 | 36.8791 | 89.665
Subtotal | 8.1267 | 28.4853 | 57.3412 | 60.5295 | 3.1883 | 4.6279 | 40.3702 | 44.9428 | 63.6384 | 107.2985 | 260.8777
Other Capital Expenditure
Centrally managed | 106.2382 | 62.2917 | 80.6713 | -22.2356 | -102.9069 | 94.3602 | -45.1046 | 86.1985 | 98.1854 | 83.5565 | 317.196
East | 15.9834 | 4.1722 | 0.73556 | 2.6232 | 1.8877 | 14.1963 | -6.7859 | 12.9684 | 14.7719 | 12.5709 | 47.7217
Midlands | 27.7903 | 4.9772 | 8.6382 | 7.4621 | -1.176 | 24.6832 | -11.7987 | 22.5482 | 25.6838 | 21.8571 | 82.9737
North West | 13.0664 | 10.1515 | 7.0326 | 5.6645 | -1.3681 | 11.6055 | -5.5475 | 10.6017 | 12.076 | 10.2767 | 39.0123
South East | 55.9343 | 1.9217 | 14.0615 | 14.4013 | 0.33977 | 49.6806 | -23.7475 | 45.3834 | 51.6946 | 43.9924 | 167.0034
South West | 22.1572 | 4.871 | 5.2708 | 8.4384 | 3.1675 | 19.6799 | -9.4071 | 17.9777 | 20.4777 | 17.4266 | 66.1548
Yorkshire & North East | 28.6395 | 8.4887 | 9.3017 | 19.5079 | 10.2062 | 25.4374 | -12.1592 | 23.2372 | 26.4686 | 22.525 | 85.5091
Subtotal | 269.8093 | 96.8741 | 125.7117 | 35.8619 | -89.8498 | 239.6431 | -114.5505 | 218.915 | 249.358 | 212.2054 | 805.5709
Total | 1931.015 | 2030.6127 | 2318.9754 | 2178.2005 | -140.7748 | 1931 | 2019.5 | 2389.2078 | 2698.3351 | 3121.9985 | 12160.0413
Note:
Baseline figures split based upon 2015-16 Actuals - excluding Major projects and feasibility which are split on a project by project basis
All capitalised salaries have been treated as centrally managed costs.

## F4
Highways England Performance Monitoring Statements Year end 2017-18
Statement F4: Analysis of protocols expenditure
| 2015-16 | 2016-17 | 2017-18 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 |  | 2015-16 | 2016/17 | 2017-18 | 2018-19 | 2019-20 | RIS 1 Total
| Actual | Actual | Actual | Budget | Budget Difference | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v2 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1
Abnormal Loads | 1.3075 | 1.5155 | 1.6863 | 1.9483 | 0.26191 | 1.1281 | 1.157 | 1.2148 | 1.4462 | 1.4173 | 6.3634 | 1.1281 | 1.157 | 1.1859 | 1.1859 | 1.2148 | 5.8717
Dart Charge | 30.3627 | 30.7038 | 32.4488 | 22 | -10.4488 | 26.1965 | 26.8682 | 28.2116 | 33.5852 | 32.9135 | 147.775 | 26.1965 | 26.8682 | 27.5399 | 27.5399 | 28.2116 | 136.356
M6 Toll | 0.048156 | 0.049938 | 0.04998 | 0.04998 | 0 | 0.041548 | 0.042614 | 0.044744 | 0.053267 | 0.052202 | 0.23438 | 0.041548 | 0.042614 | 0.043679 | 0.043679 | 0.044744 | 0.21626
Historical Railways Estate | 8.3121 | 9.0521 | 9.6678 | 9.93 | 0.26222 | 7.1715 | 7.3554 | 7.7232 | 9.1943 | 9.0104 | 40.4548 | 7.1715 | 7.3554 | 7.5393 | 7.5393 | 7.7232 | 37.3287
National Salt Reserve | 1.0471 | 0.24553 | 1.8731 | 1.2511 | -0.62201 | 0.90342 | 0.92659 | 0.97292 | 1.1582 | 1.1351 | 5.0962 | 0.90342 | 0.92659 | 0.94975 | 0.94975 | 0.97292 | 4.7024
Severn Crossings | 2.2348 | 5.381 | 11.0751 | 3.8207 | -7.2544 | 1.9281 | 1.9776 | 2.0764 | 2.472 | 2.4225 | 10.8766 | 1.9281 | 1.9776 | 2.027 | 2.027 | 2.0764 | 10.0362
Technical Regulations | 1.8902 | 1.7948 | 0.99534 | 2 | 1.0047 | 1.6308 | 1.6726 | 1.7563 | 2.0908 | 2.049 | 9.1995 | 1.6308 | 1.6726 | 1.7145 | 1.7145 | 1.7563 | 8.4887
Total Protocols Expenditure | 45.2024 | 48.7427 | 57.7965 | 41 | -16.7965 | 39 | 40 | 42 | 50 | 49 | 220 | 39 | 40 | 41 | 41 | 42 | 203
Note:
Protocols baseline phased in line with 2015-16 Actuals