The Government of the United Kingdom of Great Britain and Northern Ireland (the Government) represented by the Foreign and Commonwealth Office (FCO) / and / Corporación Andina de Fomento (“CAF”)
TECHNICAL ASSISTANCE AND COLLABORATION AGREEMENT

THIS TECHNICAL ASSISTANCE AND COLLABORATION AGREEMENT IS ENTERED INTO AS OF NOVEMBER 23, 2017
The Government of the United Kingdom of Great Britain and Northern Ireland (the Government) represented by the Foreign and Commonwealth Office (FCO)
and
 “Corporación Andina de Fomento (“CAF”)

THIS AGREEMENT IS DATED NOVEMBER 23, 2017
Between
The Government of the United Kingdom of Great Britain and Northern Ireland (the Government) represented by the Foreign and Commonwealth Office (FCO) of King Charles Street SW1A 2AH (the “FCO” or “The Funder”); and
Corporación Andina de Fomento, a legal entity created under public international law pursuant to its Constitutive Agreement approved in Bogota, Republic of Colombia on February 7, 1968, with offices at Carrera 9 No. 76-49, piso 7, Bogotá, Colombia (“CAF”).
Each referred to as “Party” and collectively as “the Parties”.
# DEFINITIONS
  1. In this Agreement the following terms shall have the following meanings:
Beneficiary	an organisation in receipt of Grant Funding as a consequence of its involvement in a Project approved by The Funder for such funding, as listed at Annex 1.
Business Day	any weekday other than a bank or public holiday in England and Wales, Venezuela, Perú, United States and Colombia.
Confidential Information	information, including any information or analysis derived therefrom, relating to, without limitation, the business, products, affairs, strategy and finances of the relevant Party for the time being confidential to the relevant Party and trade secrets including, without limitation, technical data and know-how, relating to the business of the relevant Party or any of its staff, management, clients, customers, visitors, partners, suppliers, agents, or distributors. / This information does not however include any information which is already in, or comes into, the public domain otherwise than through a breach of this Agreement, was available to the Party prior to its commencement, or which the Parties agree in writing is not confidential or may be disclosed.
Contribution	the sum, to be paid by the Funder to CAF in accordance with the terms of this Agreement.
Data Protection Legislation	means all laws and regulations relating to processing of personal data and privacy, to the extent applicable to CAF.
Effective Date	November 23, 2017
Expiry Date	March 31, 2022.
Fund	means the Fund established and administered by CAF specifically for the purposes of receiving, holding and administering funds transferred to it by the FCO.
Grant Funding	the proportion of the Contribution reserved for onward disbursement by CAF to the Beneficiaries that are mentioned at Annex 1 which have been approved by The Funder for such funding.
Non-Grant Contribution	the remainder of the Contribution, not assigned as Grant Funding, which is reserved for non-grant costs (as stated at Annex 2) to be incurred by CAF in delivering the Programme on behalf of the Funder. Such non-grant costs include (without limitation) costs associated with promotional, management, assessment and monitoring activities.
Primary Contact	the person(s) nominated by each Party who shall have primary responsibility for overseeing delivery of the Programme on behalf of that Party, and being the primary point of contact in all matters concerning the operation of the Agreement.
Programme	those Projects or other activities approved for Grant Funding, as detailed at Annex 1.
Prohibited Act(s)	means CAF committing any offence: / under applicable legislation creating offences concerning fraudulent acts, or / defrauding, attempting to defraud or conspiring to defraud the Funder.
Project	shall mean approved Programme projects by The Funder, being undertaken by Beneficiaries of Grant Funding, as listed at Annex 1.
Prosperity Fund	means the £1.3bn fund created by the UK Government to promote the economic reform and development needed for growth in partner countries.
Representative	a Party’s employees, officers, advisors and agents.
All references made in the Annexes to “shall”, “Administration Agreement” and “Parties” will have the same meaning as the term “will”, “Administration Arrangement” and “Participants” herein. In addition, references in the Annexes to “agreements” or to tenses of the verb “to agree” will be deemed to constitute references to “decisions” or to tenses of the verb “to decide”, and references to “comply”, “non-compliance” and “obligations” will deemed to constitute references to “adhere”, “non-adherence” and “terms”.

# PURPOSE, KEY OBJECTIVES AND USE OF THE FUNDS
  1. The Funder makes available to CAF a sum not exceeding £ 7.180.000 (“the Contribution”) to support the execution of the projects set out at Clause 2 of this Technical Assistance and Collaboration Agreement (“the Programme”).
  2. Of the Contribution, a total of up to £ 718.000 (“the Non-Grant Contribution”) is reserved for costs CAF reasonably expects to incur in supporting Programme delivery, as detailed in Annex 2.
  3. This Technical Assistance and Collaboration Agreement (the “Agreement”) sets out the terms and conditions on which the Parties will collaborate with each other in delivering the Programme, in particular:
    1. the key objectives of the Programme;
    2. the principles of collaboration; and
    3. the respective roles and responsibilities the Parties will have during the Term of the Programme.
  4. The parties agree to work collaboratively to achieve the following objectives:
    1. poverty reduction and gender equality through inclusive economic development in Colombia;
    2. the creation of commercial opportunities including for UK companies;
    3. In Colombia the focus for the Prosperity Fund is on post conflict areas where inclusive economic growth is most needed.
  5. The Funder agrees to grant to CAF the administration of the resources allocated to the Fund and CAF agrees to accept and administer the resources of the Fund in accordance with the terms and conditions set forth in the Agreement.
  6. The Parties agree that the funds resources will be used in the following projects, that were approved by The Funder:
• Project 1: Support capacity building in regional government for better planning, prioritization and implementation of programs and projects that promote regional inclusive economic development, poverty reduction and gender equality (Presidency of the Republic through the High Presidential Counselling for the Private Sector and Competitiveness).
• Project 2: Support capacity building in the development of Public Private Partnerships (PPPs), improving national and local administrative standards and processes (National Agency of Infrastructure - ANI) to support inclusive growth, poverty reduction and gender sensitive infrastructure services.
• Project 3: Technical assistance and capacity building to develop the agricultural insurance sector which is inclusive and benefits women and men farmers, large and MSMEs, including the improvement of information systems, risk management, education and technology to support the acceptance of insurance and pilot programs (Ministry of Agriculture and Rural Development - MADR and Fund for the Financing of the Agricultural Sector - FINAGRO).
2.7	In achieving the objectives described above, CAF will assume the following roles and responsibilities:
- Design and structure the three (3) projects identified in Section 2.6. above ensuring they support inclusive growth, poverty reduction and gender equality.
- Establish the process that allows to follow up execution and control of the projects, as well as procedures for making changes to project documentation or agreements.
- Follow CAF's internal policies in connection with procurement process related to the projects, in each case and under to compliance regulations.
- Enter in to all necessary agreements with the executors, and/or contractors carrying out the projects or part of the selected projects.
- CAF will carry out the activities related to this Agreement, complying with principles of equality, generally accepted, and will establish measures for its employees, agents, suppliers to comply with generally accepted principles of equality.
- Carry out an annual external audit on the Programme management and financial statements.	Make the disbursements of the resources according to the internal policies of CAF for the execution of the approved projects.
- Present quarterly and annual technical and financial progress reports to the British Embassy in Colombia.
- Establish the financial mechanism for advances of resources and the account in which the Funder must deposit them.
- Carry out the activities agreed upon in the program and the expected results.
- Meet with stakeholders and local experts to deliver the program effectively. This includes the Prosperity Fund monitor, reporting, evaluating and learning MREL partners and those implementing the PF Global programme in Colombia.
- Communicate with external stakeholders to promote activities with stakeholders.
- Attend an annual review of the program to be conducted by the Embassy.
- Attend the monthly project management meeting to review the program progress
- Submit the reports established in the Agreement.
- Support the impact or results assessment of each of the projects in accordance with this Agreement.

2.8 The Funder will assume the following responsibilities:
- Review quality assured and evaluate the activity and financial report that CAF submits.
- Approve the accountability of expenses and income, the destination and the achievement of the objectives and goals achieved.
- Approve the advances and refunds requested by CAF, according to the Agreement.
- Designate the Project Manager.
- Indicate the procedure for the dissolution and liquidation of the project.
- Indicate the methodology of impact evaluation or project results.
- Comply with the requirements specified in the Agreement.
# PRINCIPLES OF COLLABORATION
  1. The Parties agree to work together in accordance with the principles set out in this Clause 3. The Parties will:
    1. work together, and abide by the terms and conditions of this Agreement to ensure that the Programme is delivered in a timely and cost efficient way;
    2. take on, manage and account to each other for performance of their respective roles and responsibilities set out in this Agreement;
    3. communicate openly about major concerns, issues or opportunities relating to, or arising from, the Programme;
    4. work collaboratively to identify solutions, eliminate duplication of effort, mitigate risk and reduce cost;
    5. adhere to statutory requirements and best practice, by complying with applicable laws and standards; act in a timely manner and respond accordingly to requests for support; and
    6. act in good faith to support achievement of the key objectives and compliance with these principles.
# TERM
  1. This Agreement shall come into force on the Effective Date.
  2. This Agreement shall continue in force for five (5) years from the Effective Day, subject to any provisions for earlier termination outlined in this Agreement.
# PRIMARY CONTACTS
  1. The Funder’s Primary Contact is:
# Attention: Programme Manager - Colombia Prosperity Fund
# Address/Contact Details: British Embassy Colombia, Prosperity Fund
  1. CAF’s Primary Contact is: Corina Arroyo, Director, Development Cooperation Trust Funds
# Address/Contact Details: CAF Colombia
# (FINANCIAL) CONTRIBUTION
  1. The Contribution will be administered by CAF on behalf of the Funder in accordance with its standard policies, procedures and practices.
  2. CAF shall establish and maintain a Fund, to receive, hold, administer and implement Prosperity Fund resources transferred by the Funder.
  3. Grant Funding shall be used exclusively for those Programme activities detailed in Annex 1, while the Non-Grant Contribution shall be used to cover those non-grant costs expressly included at Annex 2. CAF shall not use the Contribution for any other purpose, unless otherwise agreed to in writing by the Funder.
  4. Payment of the Contribution by the Funder to CAF is expected to be made in accordance with the following indicative spend profile, which shall be paid in its equivalent in US Dollars at the Representative Market Exchange Rate on the date of the respective payment:
	Grant Funding	Non-Grant Contribution
FY {2018-19}	£ 2.538.564	£ 253.856
FY {2019-20}	£ 2.469.504	£ 246.950
FY {2020-21}	£ 969.976	£ 96.998
FY {2021-22}	£ 509.669	£ 50.967
TOTAL	£ 6.487.714	£ 648.771

  1. CAF shall use its reasonable endeavours to ensure that no part of the Contribution is used in a way that infringes, or could reasonably be expected to infringe any laws and/or regulations applicable to CAF and in force at the time.
  2. CAF guarantees that the Grant Funding will not be delivered to any State Entity.
  3. Any additional expense derived from exchange rate differential will be assumed by The Funder.
  4. The Funder will pay to CAF a Non-Grant Contribution which is reserved for non-grant costs (as stated at Annex 2) to be incurred by CAF in delivering the Programme on behalf of the Funder of the equivalent Grant Funding amount of 10%, which will be deposit in the account indicated by CAF. The Non-Grant Contribution will be paid a quarter in advance in equal instalments.
# ODA
  1. CAF acknowledges that it is the FCO’s intention that all monies paid to CAF under this agreement will be properly categorised as ODA by the OECD.
  2. CAF will undertake reasonable endeavours to provide the necessary information to FCO in order to meet the requirements for categorizing the Fund´s resources as ODA, in accordance with the CAF roles and responsibilities set out in Clause 2.7 of the Agreement.
# PAYMENT OF CONTRIBUTION
  1. If CAF is a new supplier or partner, it agrees to register with the Funder, according to instructions provided by the Funder.
  2. If CAF is an existing supplier or partner, payments will be made into the CAF bank account held on file by the Funder (please ensure your details are up to date). If the payment is to go to a different account from the one already registered, CAF shall notify the Funder accordingly. If CAF has more than one account registered with the Funder, it agrees to confirm the account entry to be used.
  3. In accordance with Clause 6.4, the Funder agrees to transfer the Contribution to CAF in a quarterly in advance instalments, upon receipt of a request for payment from CAF accompanied by a signed statement that:
          1. specifies actual expenditure committed and spent (incurred and defrayed) in the relevant quarter; and
          2. confirms that such expenditure has been used towards agreed Programme activities only (including the Non-Grant Contribution, whose use shall be supported by appropriate records).
  4. The Funder agrees to settle an amount submitted in accordance with Clause 8.2 within 10 Business Days of receiving that requirement.
  5. Where actual expenditure in a given financial year deviates from the Agreement allocated by the Funder for that financial year in the payment profile at Clause 6.4 the payment profile will be amended with the Funder’s approval. The Funder will, in any event, ensure that CAF is reimbursed for any authorised payments actually made by CAF in delivering the Programme.
  6. The Funder agrees to meet any costs CAF incurs in funding projects whose end dates slip beyond the financial year they were due to complete – including those projects whose end dates slip beyond the Expiry Date – unless the Parties mutually agree that this course of action cannot be justified on financial and/or technological grounds. The Funder will, in any event, reimburse CAF for any payments actually made by CAF in delivering the Programme.
  7. In order to accommodate variations to timescales for completing specific Competition activities, monies assigned by the Funder to Non-Grant costs in a given financial year that remain unspent at the end of that financial year may be rolled forward to future years – including any time after the Expiry Date – unless the Parties mutually agree that this course of action cannot be justified on financial grounds, or that doing so would not support the effective delivery of the Programme.
  8. In the event that either Party terminates this Agreement in accordance with Clause 18 and as a result the Funder withdraws any part of the Contribution which has not (or will not have) been committed, at the date upon which termination takes effect, to eligible costs incurred by (a) Beneficiary(ies), CAF may, in its sole and absolute discretion, discontinue future grant payments, or substantively vary the terms of its grant offers, to (a) Beneficiary(ies), in accordance with the notice provisions contained within its Grant Offer Letters. In any event, the Funder will use all reasonable endeavours to meet all costs that have been incurred by a Beneficiary (-ies) as of the date of termination.
  9. Should any part of the Contribution remain unspent by the Expiry Date, or upon termination of this Agreement, whichever occurs sooner, CAF shall ensure that such unspent funds are either returned to the Funder within 30 Business Days of that date, or, subject to the written agreement of the Funder, are otherwise re-allocated to related, but separate, funding programmes or activities.
  10. In the event that a cost overrun occurs in delivering the Programme that result in the total Contribution being exceeded, the Parties agree to use reasonable endeavours to find a mutually acceptable course of action to address this.
  11. CAF shall promptly repay the Funder any money incorrectly paid to it in error, including such instances where part of the Contribution is paid by the Funder before CAF has complied fully with all conditions attaching to payment that part of the Contribution.
# ACCOUNTING AND REPORTING
  1. CAF shall keep accurate and up-to-date accounts and records relating to the Contribution, separate from those it keeps for the rest of its business, therefore, the Contribution not will be commingled with money from another business. This records will be kept in US Dollar.
  2. Grant Funding and Non-Grant contribution contracts made by CAF with Beneficiaries in accordance with this Agreement will be made in US Dollars. .
  3. All reporting made by CAF to the Funder will be made in Pound Sterling and will be calculated in accordance with the exchange rate between US Dollar and Pound Sterling provided by the US bank at the date on which it received the instalments.
  4. In the event that the Funder pays CAF a part of the Contribution prior to disbursement, CAF agrees to hold that part of the Contribution in an account where those funds may be accounted for separately.
  5. Upon the reasonable request of the Funder, CAF will provide the Funder with a copy of annual accounts relating to the Contribution within 2 months of the end of each financial year during the Term of this Agreement, or such other period as the Parties may mutually agree in writing.
  6. CAF shall keep all invoices, receipts, and accounts and any other relevant documents relating to the expenditure of the Contribution for a period of at least 5 years following receipt of any Contribution monies to which they relate. The Funder shall have the right to review, at its reasonable request, CAF's accounts and records that relate to the expenditure of the Contribution and shall have the right to take copies of such accounts and records.
  7. Upon its reasonable request, CAF shall provide the Funder with a financial report detailing all claims for Grant Funding received from Beneficiaries.
  8. Where CAF has obtained funding from a third party to delivery any part of the Programme, CAF shall include the Agreement of such funding in its financial reports together with details of what that funding has been used for.
  9. Upon its reasonable request, CAF shall provide the Funder with such further information, explanations and documents as the Funder may reasonably require in order for it to establish that the Contribution has been used for the proper purpose outlined at Annex 1.
  10. CAF shall permit any person authorised by the Funder such access, as the Parties agree to in writing, to its employees, agents, premises, facilities and records, for the purpose of discussing, monitoring and evaluating CAF's fulfilment of the conditions of this Agreement and shall, if so required, provide appropriate oral or written explanations from them.
  11. As part of the regular reporting requirements outlined above, CAF will provide a proportionate and meaningful assessment of how the project is contributing to reducing gender inequality including a specific assessment on progress against any gender related commitments made as part of this Arrangement, that is supportive of the SDGs and international commitments to address gender equality
# PROGRAMME MANAGEMENT
  1. Except as otherwise agreed by both Parties in writing, and incorporated as a special condition of this Agreement by application of Clause 22, the Programme is expected to be managed in accordance with CAF’s standard operational procedures, and as may be amended, updated or modified from time to time.
# MONITORING
  1. CAF shall monitor the Programme in accordance with its monitoring policies, as may be amended from time to time, to ensure that the aims and objectives of the Programme are being met.
  2. Any consequent additional costs incurred by CAF will be recoverable by CAF from the Funder.
  3. CAF may invite a Representative of the Funder to attend and observe quarterly Project review meetings with Beneficiaries.
  4. Monitoring should include qualitative and quantitative approaches with sex disaggregated data where appropriate with KPIs which among other things, are able to capture the differentiated impact on women and men.
# NO DISCRIMINATION POLICY
  1. The Recipient shall not unlawfully discriminate either directly or indirectly against protected characteristics such as race, colour, ethnic or national origin, disability, sex or sexual orientation, religion or belief, or age.
# COMMUNICATIONS, ACKNOWLEDGEMENT AND PUBLICITY
  1. CAF shall acknowledge the Contribution in its annual report and accounts, including an acknowledgement of the Funder as the source of the Contribution.
  2. The Parties have agreed to collaborate to build support for, and raise awareness of, the UK government's funding for development of regional government capabilities, corporate governance reform of Colombia’s National Infrastructure Agency (ANI), Agri-Insurance. Both Parties shall proactively consider ways to raise awareness of UK government funding through dissemination activities and publications. CAF shall explicitly acknowledge the Funder’s support through use of its logo in all communications with the public or third parties about the Programme, unless otherwise agreed in writing by the Parties.
  3. The Parties shall consider and explore other awareness raising activities, where feasible and appropriate, in the UK and overseas, to publicise the Programme and its outputs.
  4. If either Party wishes to communicate publicly about the Programme, beyond the terms and conditions of this Agreement, a collaborative communication agreement should be entered into which would stipulate permissions, guidelines and co-ordination processes for such communication.
# SYNERGY WITH OTHER COLLABORATIONS
  1. CAF will endeavour to find synergies and work with Her Majesty’s Government and UK-funded programs such as the thematic Prosperity Fund programs.
# CONFIDENTIALITY AND DATA SHARING
  1. Except for this Agreement, neither the Funder nor CAF shall disclose to a third party the content or details of negotiations entered into in scoping and developing the Programme, unless the Parties agree in writing to make public the content and details of such negotiations.
  2. Each Party undertakes that it shall not at any time disclose to any person any Confidential Information in any form (including in written, oral, visual or electronic form or on any magnetic or optical disk or memory or wherever located) concerning the business, Know-How, affairs, customers, clients or suppliers of the other Party, or of any of the other Party’s contractors, customers, agents, distributors, shareholders, managers or business contacts, except as permitted by Clause 15.3.
  3. Each Party may disclose the other Party's Confidential Information:
    1. to its Representatives who need to know such information for the purposes of exercising the Party's rights or carrying out its obligations under or in connection with this Agreement. Each Party shall ensure that its Representatives, to whom it discloses the other Party's Confidential Information, comply with this Clause 15; or
    2. as may be required by law, a court of competent jurisdiction or any governmental or regulatory authority.
  4. No Party shall use the other Party's Confidential Information for any purpose other than to exercise its rights and perform its obligations under or in connection with this Agreement.
# INTELLECTUAL PROPERTY
  1. The Parties intend that any intellectual property rights created in the course of collaborative working on the Programme shall vest in the Party whose employee created them or in the case of any intellectual property rights created by employees of both Parties the intellectual property rights shall vest jointly in both Parties.
  2. Where any intellectual property right vests in either Party in accordance with the intention set out in Clause 16.1, that Party shall grant an irrevocable, royalty-free non-exclusive licence to the other Party to use that intellectual property for any purpose relating to this Agreement.
  3. The Parties agrees to share all rights which arise from inventions, intellectual creations, research, studies, industrial privileges and/or professional services created and performed in relation to this Agreement, including, but not limited to, all inventions developed in the framework of the implementation of this Agreement. The rights to any intangible creation, including anything specifically classified as confidential information, which is susceptible to protection as intellectual property shall be owned jointly by the Parties.
# STATUTORY OBLIGATIONS
  1. The Funder hereby agrees that it shall provide all necessary assistance and cooperation as reasonably requested by CAF to enable its compliance with its obligations arising from this Agreement, its respective internal policies and any applicable regulations.
# TERMINATION
  1. Except as expressly provided for otherwise in Clause 19, either Party may terminate this Agreement for any reason on giving the other Party 90 Business Days’ notice in writing, in the manner prescribed at Clause 26.
  2. Notwithstanding any exceptional provisions for immediate termination outlined in Clause 19, the Funder may terminate this Agreement with immediate effect in the event of one of the following occurring:
    1. CAF ceases to operate for any reason, or it passes a resolution (or any court of competent jurisdiction makes an order) that it be wound up or dissolved (other than for the purpose of a bona fide and solvent reconstruction or amalgamation); or
    2. CAF becomes insolvent, or is declared bankrupt, or is placed into receivership, administration or liquidation, or a petition has been presented for its winding up, or it enters into any arrangement or composition for the benefit of its creditors, or it is unable to pay its debts as they fall due.
  3. Upon termination of the Agreement, any part of the Contribution which has been paid to CAF but which has not been allocated to eligible costs incurred by (a) Beneficiary(ies) as of that date shall be repaid to the Funder within 30 Business Days of termination occurring (unless the Funder instructs CAF otherwise in writing).
  4. No such termination shall affect contractual obligations of any Party.
# SUSPENSION (FOLLOWED BY TERMINATION) AND REPAYMENT OF CONTRIBUTION
  1. The Parties may suspend the implementation of the Agreement in case of non-compliance attributable to the occurrence of a force majeure event (the "Event") which is ongoing for a continuous calendar period equal to or greater than eight (8) days. Force majeure shall mean those events whose effects cannot be resisted or that are not possible to avoid or anticipate, such as acts of God, war, revolution, strike, fire, governmental actions or any other unforeseen cause which is beyond the control of the Parties and which is impossible to resist by the non-complying Party. In this sense, within eight (8) calendar days after the occurrence of an Event, the Party which alleges the case of force majeure shall submit a notice in writing to the other Party which shall include: (i) detailed proof of the existence of such Event; and (ii) detailed information on the causes and the measures taken. Within fifteen (15) calendar days after receipt of the notice and for a period not to exceed thirty (30) calendar days, the Parties shall enter into negotiations to determine the impact of the Event on the Project´s Execution, and if necessary, to reach a common agreement on the extension of the term of this Agreement, the suspension of this Agreement, or, if necessary, termination of the Project and this Agreement along with the resolution of any resulting financial affairs. If the Parties fail to come to an agreement during the thirty (30) day period, either Party may terminate this Agreement unilaterally and permanently
    1. CAF is found to have misused the Contribution, or to have used it for purposes other than Programme activities;
    2. Programme activities have not started within {number} months of the Effective Date, and CAF has failed to provide the Funder with a reasonable explanation for the delay;
    3. CAF has not made satisfactory progress in delivering the Programme;
    4. CAF is, delivering the Programme in a negligent manner;
    5. CAF is found to have obtained duplicate funding from an international assistance agency, different to the Funder, for the Programme. This Clause does not restrict CAF to obtain the co-funding that is mentioned at Annex 1.
    6. CAF is found to have obtained funding from a third Party which, in the reasonable opinion of the Funder, undertakes activities that are likely to bring the reputation of the Funder into disrepute;
    7. CAF has provided the Funder with any materially misleading or inaccurate information;
    8. CAF is having committed a Prohibited Act;
  2. If CAF fails to make sufficient progress in rectifying, investigating or disproving the actual, as defined in Clauses 19.1.1 to 19.1.87, within {number} Business Days of notice being served on it by the Funder, and such progress is reasonable to expect in the circumstances, then the Funder may terminate this Agreement with immediate effect.
    1. The Funder may request repayment of any part of the Contribution in the event of any of the following:
    2. it is found that CAF, knowingly or unknowingly, has provided false information associated with, or in support of, an invoice for payment of the Contribution;
    3. the Contribution has been paid against expenditure incurred and defrayed for activities unrelated to the Programme; or
    4. the Contribution being clawed back is subject to a proven Prohibited Act having been committed by CAF.
  3. Should CAF be subject to financial or other difficulties which are capable of having a material impact on its effective delivery of the Project or compliance with this Agreement it will notify the Funder as soon as possible so that, if possible, and without creating any legal obligation, the Funder will have an opportunity to provide assistance in resolving the problem or to take action to protect the Funder and the Contribution monies.
# FRAUD AND CORRUPTION
  1. The Funder and CAF both have a zero tolerance approach towards any fraud and fraudulent behaviour that may result in the misuse of the Contribution, and agree in principle to use their reasonable endeavours to ensure adequate anti-fraud policies and controls are in place to prevent and/or detect fraud, including money laundering, involving any part of the Contribution.
  2. In the event of any credible indications being received that the Contribution (or any proportion thereof) may have been used for fraudulent purposes, the Funder may, at any time during the Term of this Agreement and up to 2 of years after its Expiry Date or date of termination, arrange for additional fraud investigations, on-the spot checks and/or inspections to be carried out, such investigations, checks and/or inspections being carried out by the Funder at its own cost.
# LIABILITIES
  1. Except as otherwise provided for in this Agreement, the Parties shall each bear their own costs and expenses incurred in complying with their obligations hereunder.
  2. Each Party shall remain liable for any losses or liabilities incurred due to their own or their employee's actions and neither Party intends that the other Party shall be liable for any loss it suffers as a result of this Agreement.
  3. Any tax, fee, levy or financial commission caused in relation with this Agreement shall be assumed by the Funder.
# SPECIAL CONDITIONS
  1. Any special conditions at Annex 3 are incorporated as terms of this Agreement.
  2. In the event of a conflict between a special condition and any other term of this Agreement, subject to any overriding duty and/or obligation imposed on either of the Parties by law, the Special Condition shall prevail.
# VARIATION
  1. No variation of this Agreement shall be effective unless it is in writing and agreed by both Parties.
# DISPUTE RESOLUTION
  1. In the event that any claim or dispute arises out of or in connection with this Agreement, the affected Party shall serve written notice on the other Party, and attempt to resolve by way of good faith negotiations and discussions any such dispute or claim as soon as reasonably practicable (and in any event within 30 Business Days after such notice or by such later date as the Parties may otherwise agree in writing).
  2. If the Parties are unable to resolve the dispute or claim within the time frame specified in clause 24.1, the matter shall be escalated to the Executive Management Teams of both Parties, who shall jointly decide on an appropriate way of resolving the dispute, with an instruction to attempt to resolve the dispute by agreement within 30 Business Days, or such other period as may be mutually agreed by both Parties.
  3. In the absence of agreement under clause 24.2, the Parties may either:
    1. terminate the Agreement in accordance with clause 18; or
    2. seek to resolve the matter through mediation, or such other appropriate dispute resolution model as is agreed by both Parties. Unless otherwise agreed, the Parties shall bear the costs and expenses of the mediation equally.
# STATUS
  1. This Agreement is not intended to be legally binding. The Parties enter into the Agreement intending to honour all their obligations. The rights and obligations set forth in this Agreement are valid and enforceable, in accordance with their terms and conditions, without relation to the applicable law of a specific country.
  2. Nothing in this Agreement is intended to, or shall be deemed to, establish any partnership or joint venture between the Parties, constitute either Party as the agent of the other, nor authorise either Party to make or enter into any commitments for or on behalf of the other Party.
  3. Nothing in this document may or shall be interpreted as a waiver of the privileges, exemptions and immunities granted to CAF, its directors, representatives, agents, employees and/ or officers by its Constitutive , or by the agreements or treaties entered into among CAF and its member countries or granted by the laws of each of such country.
## This Agreement does not imply any financial commitment, fiducially duty or obligation of any of the Parties to provide any additional finance services, nor does it represent any commitment with regard to funding, hiring, secondment, or any other activities on the part of the Parties. Any other such commitment shall be reflected in separate agreements that may be entered into by the Parties in due course. Furthermore, this Agreement shall not represent any commitment on the part of any Party to give preferred treatment to the other Party in any matter contemplated herein or otherwise. This Agreement is not exclusive; therefore, each Party may freely contract with any other person, firm or entity concerning the subject matter hereof.
# NOTICES
  1. All notices to be given hereunder shall be in writing and may be served:
    1. in person;
    2. by pre-paid first-class post or other next day delivery service; or
    3. by email, provided always that a hard copy of the notice is also served,
### to the relevant Party’s registered address (or as it may from time-to-time be notified in writing to the other Party) or to such email address as shall be notified in writing to the other Party (as appropriate).
  1. Any notice shall be deemed to have been received:
    1. if delivered by hand, on signature of a delivery receipt;
    2. if sent by pre-paid first-class post or other next working day delivery service, at 9.00 am on the second Business Day after posting; or
    3. if sent by email, at 9.00 am on the next Business Day after sending.
  2. This Clause does not apply to the service of any proceedings or other documents in any legal action or, where applicable, any arbitration or other method of dispute resolution.
# ENTIRE AGREEMENT
  1. This Agreement(including the Schedules and Annexes to it, or otherwise referred to in it) constitutes the entire agreement between the Parties exclusively in delivering the Programme, and supersedes all previous agreements, promises, assurances, warranties, representations and understandings between them, whether written or oral.
# GOVERNING LAW AND JURISDICTION
  1. This Agreement shall be governed by and construed in accordance with Colombian law.

This Agreement has been entered into as a deed on the date stated at the beginning of it.
Authorised signatory on behalf of CAF	Authorised signatory on behalf of the Funder
Signed on behalf of CAF	Signed on behalf of the UK Government
Position in Organisation	Position in Organisation
Address	Address
Date:	Date:

# ANNEX 1
PROGRAMME OVERVIEW
# Project 1: Development of local government capabilities
## Objective
Strength regional economic development competitiveness in Colombia by supporting the creation of the regional government’s ability to do better planning, prioritization, and implementation of programs and projects that prioritize economic development.
## Understanding the program and the context
CAF is supporting the High Presidential Council for the Private Sector and Competitiveness with the first phase of the capability development program headed by the National System for Competitiveness, Science, Technology and Innovation and implemented by Confecamaras Confederation of Chambers of Commerce) for a total amount of USD 192,000, of which CAF is contributing USD 91,000.
This project, which will end in December 2017, seeks to implement a strategy for strengthening the Regional Competitiveness Commissions (CRC in Spanish) in 11 of Colombia’s departments: Norte de Santander, Magdalena, Arauca, Risaralda, Cauca, Meta, Cesar, Sucre, Atlantic, Cundinamarca (including Bogota) and Valle del Cauca; support for the National System of Competitiveness, Science, Technology and Innovation (SNCCTI in Spanish) in the construction of the Integrated Agenda of Competitiveness, Science, Technology and Innovation in those territories in conjunction with the country's competitiveness agenda, in line with the CONPES Productive Development Document (approved in the second half of 2016) and of Science, Technology and Innovation in the process of analysis and review by the National Government. Likewise, the project seeks to reinforce the SNCCTI at the regional level both that of the CRCs internally and of their relationship with the stakeholders and SNCCTI resources in the departments. This will be done through a diagnosis of the existing capabilities of the CRCs in order to foster proper coordination between the national and territorial levels in the public sector as well as with the private sector at the departmental level.
In accordance with the Outlook 2032, Colombia should be the third most competitive economy in Latin America through exports of goods and services with a high added value and innovation. Nevertheless, the country has not shown significant progress in achieving that vision on the international indicators. In the regional context, the policies are not always in line with the shared vision with regard to Competitiveness, Science, Technology and Innovation (CCTI in Spanish) and the royalty funds for science, technology and innovation (CTI in Spanish), etc. are not having an impact on the productive sectors that the departments should be managing. The CRC's are called to be the entities for dialog, coordination and cooperation on CCTI issues and will take responsibility for supporting the implementation and follow-up of the actions that have regional scope. Considering the diversity of agencies and agendas, it is necessary for the CRCs to combine the agendas of the different departmental stakeholders into a prioritization instrument that concentrates on a solution to market failures and allows better Nation-Region coordination processes. Confecamaras actively participates in the Committee for Regionalization of the CCTI System It is a permanent member of the Executive Committee and is the co-coordinator of the CRCs through its link with the Chambers of Commerce since it is the entity that brings together all of the Chambers of Commerce throughout the country and these are the ones who exercise the role of coordinators and technical secretariat for the CRCs. Confecamaras is also capable of managing the monetary contributions of the Chambers of Commerce Network that serve as the co-financing contribution for the first and second phase of this project. Because of the above, Confecamaras has the competence to continue with the implementation of the second phase of this project which is why selecting another entity is not considered appropriate since this would be to the detriment of the project's implementation.
In the second phase of the project, support for the reinforcement of the CRCs in 8 departments will be sought as well as the construction of the Integrated Agenda for Competitiveness, Science, Technology, and Innovation of said territories in coordination with the country’s competitiveness agenda and the institutional supply of the national government agencies. The departments to be included in this phase will be selected on the basis of the study that the British Embassy in Bogota is currently commissioning. So far the departments that have shown interest in joining the project are: Santander, Caldas, Bolivar, Nariño, Quindío, Guainia, Huila, Choco, Tolima, Boyaca, Casanare, and Putumayo which may coincide with those that are derived from the above mentioned study of region and department prioritization.
In this regard, there will be two options:
1. Of the 8 selected departments in the study commissioned by the British Embassy in Bogota, those departments that participated in the first phase and that already have defined integrated agendas will start directly with the activities related to the structuring and implementation of up to 4 prioritized projects per department . These projects will be prioritized based on the alignment with the economic development and competitiveness priorities of national and local governments as defined in their overall agendas, the impact they will have in the Department and their feasibility. Factors related to the deadline for achieving results, the co-finance potential (especially those which already have resources form the Department or from a third party) and the budget are also taken into account.
2. Of the 8 selected departments in the study commissioned by the British Embassy in Bogota, those departments that do not have defined integrated agendas will have to start with all the project activities that are detailed below.
## Outline of the management approach, implementation of the program and activities
Within the framework of the British fund’s objectives and considering the steps to follow in order to build an integrated CCTI agenda, the project will have the following specific objectives:
Reduction of poverty and the fostering of gender equity through economic development.
Creation of commercial opportunities for British companies will be able to apply.
Strengthen the CRCs as a strategic scenario for the integration of territorial entities with the National System of Competitiveness, Science, Technology, and Innovation and coordination with the National Government as well as impress the importance of coordinated institutions on the local stakeholders through the CRCs.
Reinforce the capabilities of the local institutions to identify, structure, and implement the projects as well as evaluate the opportunities for internal and external financing (public and private).
Identify and prioritize projects based on the Integrated Agendas, their feasibility and impact on the department in order to be co-financed, that have the potential to be structured and implemented in up to 8 departments with support from foreign investment including possible productive chains.
Provide technical training and support to implement and monitor the structuring and implementation of projects.

This project, in turn, will include the following components and activities:
COMPONENT 1: Prepare a diagnosis on the state of the department in areas of Competitiveness, Science, Technology, and Innovation (CCTI), in other words, of the CUE, CODECTI, Regional Entrepreneurship Networks, Regional MSMEs Councils, and of the CRCs, etc. which include a description of the existing bodies in the department that work on issues related to CCTI in different sectors.

COMPONENT 2: Support the Presidential Council for the Competitiveness and Innovation System by giving technical advice on the design and doing follow-up on the construction and implementation of the integrated agenda in 8 departments (planning and coordination).

COMPONENT 3: Prepare a final matrix of the Integrated CCTI Agenda approved by the Department

COMPONENT 4: Concerted proposal for monitoring CCTI indicators.

COMPONENT 5: Design a strategy for aligning and using the national institutional supply vis-à-vis the Integrated Agenda of the Department.

COMPONENT 6: Propose an optimal governance plan for the department based on its state of economic and social development with regard to CCTI through a workshop that results in a model for governance.

COMPONENT 7: Give at least 8 workshops, one per department, to transfer knowledge on structuring, identifying, and implementing projects including the evaluation of financing options.

COMPONENT 8: Carry out at least 8 workshops, one per department, to provide technical training and support for developing, monitoring and evaluation strategies for implementing the projects.

COMPONENT 9: Structuring of up to 32 prioritized projects, approximately 4 projects per department. This component will have in turn 3 activities:
Activity 1: Prioritization of up to 4 projects per department that will be in line with the development and competitiveness priorities of national and local governments as defined in their overall agendas, and that will have feasibility and impact on the department development in order to be co-financed.
Activity 2: Development of structuring models for up to 32 projects that will have implementation potential in order to be co-financed by internal and external financial sources (public and private). Projects with co-finance potential or that already have resources from the Department or from a third party will be highlighted.
Activity 3: Development of monitoring and evaluation models for up to 32 projects in order to leave them ready for implementation.
## Expected Results
Results Component 1: Prepare a diagnosis on the state of the department in areas of Competitiveness, Science, Technology, and Innovation (CCTI), in other words, of the CUE, CODECTI, Regional Entrepreneurship Networks, Regional MSMEs Councils, and of the CRCs, etc. which include a description of the existing bodies in the department that work on issues related to CCTI in different sectors.
Eight diagnostic reports on the state of departmental bodies in the area of competitiveness, science, technology and innovation such as the CUE, CODECTI, CONSEA, Regional Entrepreneurship Networks, Regional MSME Councils, etc. that includes the description of existing bodies in the department.
Eight review reports on the priority planning territorial documents (PDD, PAED, Regional Competitiveness Plan, etc.) These reports must also contain the pre-identification agreed upon with the Commission's projects or initiatives manager. These are projects or initiatives that are in line with the competitive vision of the territory and their objectives and products satisfy the requirements of competitiveness, science, technology, and innovation (CCTI) determined to be of interest for the Commission's work.
Eight reports on the support needs of the CRCs by the national government and the entities that it is made up of.
Presentation of the final reports at the Regionalization Committee and the Productive Development Policy Committee of the National Competitiveness System
Results Component 2: Support the Presidential Council for the Competitiveness and Innovation System by giving technical advice on the design and doing follow-up on the construction and implementation of the integrated agenda in 8 departments (planning and coordination).
Eight diagnostic reports of the Regional Competitiveness Commissions (CRC) on Commission's management capability; ability to coordinate institutions, dialog and consult with the territorial authorities: and identification of the estimated size of the agenda (number of projects or initiatives) that each one of the CRCs are able to manage.
Presentation of progress of the CRC's final diagnostic reports at the Regionalization Committee and the Productive Development Policy Committee of the National Competitiveness System.
Eight reports (one per Regional Competitiveness Commission) on the identification and selection of programs, projects and initiatives that the CRC will prioritize that benefit more than one economic sector.
Eight analysis and prioritization reports on the projects, programs, and initiatives based on the impact they will have on the territory’s competitive conditions and the period in which they will be able to obtain results.
Presentation of progress and final reports on the identification, selection, analysis, and prioritization of projects in the Regionalization Committee and in the Productive Development Policy Committee of the National Competitiveness System.
Presentation of progress and final reports on the integrated agendas and the control panels at the Regionalization Committee and the Productive Development Policy Committee of the National Competitiveness System.
Presentation of the optimal governing structure in the committees of the National Competitiveness System.
Presentation of the strategy for aligning and using the institutional supply vis-à-vis in the integrated agendas in the committees of the National Competitiveness System.
Presentation of the CRC’s 32 structured projects with a monitoring, evaluation and funding strategy (4 projects per department).
Presentation of the progress in structuring the terms of reference, selection and evaluation of projects to be co-financed, supervision and technical assistance, and monitoring and follow-up on the projects to be co-financed at the committees of the National Competitiveness System

Results Component 3: Prepare a final matrix of the Integrated CCTI Agenda approved by the Department.
Eight integrated agendas approved by the department within the framework of the Assembly of the Regional Competitiveness Commission, in which priority is made evident as a function of the impact that their results will have on economic development and prosperity in the Department. This rating should be given within the Commission (Executive Committee and technical committees) based on the support that the members estimate that the results of the projects and initiatives will have on the achievement of the competitive vision of the Department.
Eight reports on workshops, one per department, in which public and private stakeholders contribute to the positioning and consolidation of the integrated agenda of competitiveness, science, technology, and innovation.
Results Component 4: Concerted proposal for monitoring CCTI indicators.
Eight monitoring mechanisms for doing follow up on the management of the Agenda. This mechanism will be built with the active participation of those who are responsible for each project or initiative (which should be formulated as a project) and they must commit themselves to the management of the funds in the hands of the Commission.
Results Component 5: Design a strategy for aligning and using the national institutional supply vis-à-vis the Integrated Agenda of the Department.
Eight reports on the strategy for aligning and using the institutional supply vis-à-vis the Integrated Agenda of the Department.
Results Component 6: Propose an optimal governance plan for the department based on its state of economic and social development with regard to CCTI through a workshop that results in a model for governance.
Eight optimum governance plans, one for each department, that considers the current state of governance and the description of institutions with regards to competitiveness, science, technology, and innovation as well as the state of economic and social development in each department.
Results Component 7:	Give at least 8 workshops, one per department, to transfer knowledge on structuring, identifying, and implementing projects including the evaluation of financing options.
Standardized Methodology of the workshops and practical guidelines on the design and structuring of projects.
Twenty-four projects (three per CRC) structured and with financing options identified.
Results Component 8: Carry out at least 8 workshops, one per department, to provide technical training and support for developing, monitoring and evaluation strategies for implementing the projects
Standardized Methodology of the workshops and practical guidelines on monitoring and follow-up on projects
Results Component 9: Structuring of up to 32 prioritized projects, approximately 4 projects per department.
Terms of reference prepared for co-financing projects that are part of the integrated agendas.
Report with analysis, recommendations, and selection of the projects for co-financing that will be carried out in two phases: a) Phase 1: Expression of Interest: corresponds to the submission, assessment and prioritization of the expressions of interest, on the basis of which a short list shall be drawn up; and b) Phase 2: Feasibility Assessment: Presentation of projects to the Committee for consideration (as defined in the framework of the program) for final approval.
Selection, approval, and allocation of funds to projects
Reports on supervision and technical assistance in the development or implementation of the projects.
Report on monitoring, follow-up and control of implementation of the selected projects.
Taking these expected results into account, CAF plans to sign a Technical Cooperation Agreement with Confecamaras in order to be able to manage the co-funding resources from the Chambers of Commerce. Confecamaras will be responsible for components 1 to 8. Lastly, for component 9 and its activities, CAF will sign a total of up to eight (8) contracts with a national or international experts depending on the nature of the projects to be structured. These experts will have expertise in development of structuring, monitoring and evaluation models for project implementation.

## Activity Schedule (Gantt Chart)
COMPONENTS AND ACTIVITIES		2018					2019					2020					2021
		1Q			2Q			3Q			4Q			5Q			6Q			7Q			8Q			9Q			10Q			11Q			12Q			13Q			14Q			15Q			16Q
Component 1: Prepare a diagnosis on the state of the department in areas of Competitiveness, Science, Technology, and Innovation (CCTI), in other words, of the CUE, CODECTI, Regional Entrepreneurship Networks, Regional MSMEs Councils, and of the CRCs, etc. which include a description of the existing bodies in the department that work on issues related to CCTI in different sectors
Component 2: Support the Presidential Council for the Competitiveness and Innovation System by giving technical advice on the design and doing follow-up on the construction and implementation of the integrated agenda in 8 departments (planning and coordination)
Component 3: Prepare a final matrix of the Integrated CCTI Agenda approved by the Department
Component 4: Concerted control panel proposal for monitoring CCTI indicators
Component 5: Design a strategy for aligning and using the national institutional supply vis-à-vis the Integrated Agenda of the Department
Component 6: Propose an optimal governing plan for the department based on its state of economic and social development with regard to CCTI through a workshop that results in a model for governing
Component 7: Give at least 8 workshops, one per department, to transfer knowledge on structuring, identifying, and implementing projects including the evaluation of financing options.
Component 8: Carry out at least 8 workshops, one per department, to provide technical training and support for developing monitoring and evaluation strategies for implementing the projects
Component 9: Implementation of 32 integrated agenda projects, approximately 4 projects per department.
	Prioritization of up to 4 projects per department that will be in line with the development and competitiveness priorities of national and local governments as defined in their overall agendas and will have feasibility and impact on the department in order to be co-financed.
	Development of structuring models for up to 32 projects that will have implementation potential in order to be co-financed by internal and external financial sources (public and private). Projects with co-finance potential or that already have resources from the Department or from a third party will be highlighted
	Development of monitoring and evaluation models for up to 32 projects in order to leave them ready for implementation

## Project Risk Matrix
Risk	IMPACT Low/Medium/High	PROBABILITY Low/Medium/High	MITIGATION	DATE
Lack of support from the departmental governments	Low	Low	The governments of the departments that will be part of the project are defined on the basis of the interest shown by those regions. If any Department loses interest, another department which is interested can be identified.	At the beginning of the project during the identification stage of the departments that could be part of the project.
Selected experts lack of capability	Medium	Low	Application of default clauses to the experts and selection and hiring of a new one	Over the course of the project
Lack of support and interest on the part of the national government and the Productive Development Policy Committee of the National Competitiveness System	High	Low	The Productive Development Policy of the National Competitiveness System is given in the CONPES documents and presidential decrees that give priority to this issue.	At the beginning of the project when a start-up meeting is held with the departments and representatives of the national government (High Presidential Council for the Private Sector and Competitiveness) in 2017.
Lack of support from the CRC	Medium	Low	The Productive Development Policy of the National Competitiveness System is given in the CONPES documents and presidential decrees that give priority to this issue. The experts can have an impact on the degree of involvement of the CRCs.	2018
Lack of a clear definition of the projects and limited possibilities for co-financing to implement them.	High	Low	The projects will prioritized as they go through several filters within the CRCs The national government, CAF, and the British Embassy can participate in the search for co-financing options.	2018
Lack of projects that attract funding	High	Low	Of the 11 departments with integrated and agendas and of the eight that will be selected, there is the potential for projects that could attract funding. The national government, CAF, and the British Embassy can participate in the search for co-financing options.	2019-2020

# Project 2: Support the agencies and the creation of standards and capacity of Public Private Partnerships (PPP)
## Objective
Support the creation of capabilities in the development of PPPs, improving standards, and administrative processes at the national and local levels (National Infrastructure Agency - ANI).
## Understanding the program and the context
The current government started a process that took the policy of private participation for the development of the country’s infrastructure deeper. In the transportation sector, this process led to the restructuring of the National Institute for Concessions (INCO in Spanish) and its conversion into the National Infrastructure Agency (ANI in Spanish) as an agency that specialized in developing projects as a Public Private Partnerships (PPP). CAF participated in this process with technical cooperation that made it possible to have specialized support for the design of the new entity.
This institutional restructuring was accompanied by legal and regulatory changes to encourage private participation in the projects and overcome bottlenecks that have historically turned up during the implementation of the projects. That is how Act 1508/2012 was adopted to regulate private participation and Acts 1682/2013 and 1742/2014 were adopted to manage sites, networks, mining titles and environmental licensing.
Parallel to these institutional changes, the government organized an ambitious program of road concessions called Program 4G thus alluding to the fourth generation of road concessions in the country. This program involves investments of nearly 32 trillion pesos and is currently underway with more than 18 projects under contract.
As a result of this process, the new entity has succeeded in: (i) establishing a multidisciplinary work team; (ii) incorporating transparency practices in their bidding processes; (iii) designing follow-up and monitoring systems and; (iv) incorporating anti-corruption practices.
In spite of the achievements to date, it is necessary to continue the process of institutional strengthening to ensure its consolidation. This is particularly true with regard to the competencies of the management team that is responsible for decision-making with respect to structuring new projects, negotiation of contracts and contractual management of renegotiations, settlements and / or claims against the State, in such a way that the actions that emerge from their obligations satisfy technical autonomy.
Under this scenario, the opportunity has been identified to continue supporting ANI in the consolidation of its institutional process through the formulation of a Corporate Governance Program by which to identify, design and implement the necessary actions. Special attention will be accorded the dissemination of the advantages and benefits of the initiative to different public sector agents.
In addition, CAF’s Corporate Governance Program contributes to responsible competitiveness on the part of public and private companies in the region as well as to the strengthening of regulatory and supervisory systems in the banking, insurance, pension, and stock market sectors.
Through continuous work in this field since 2003 which was done in partnership with various governmental institutions, business associations and other specialized organizations from the region and at the global level, CAF has succeeded in accumulating significant experience and knowledge and become the expert on corporate governance in Latin America.
CAF encourages the adoption of good corporate governance practices throughout the region by means of the generation of knowledge, guidelines, and practical tools as well as providing technical assistance products with reimbursable and non-reimbursable funds in the following areas:
  1. Improvement of corporate governance in medium-sized and family-owned businesses with the potential for access to the capital market.
  1. Promotion and dissemination of good practices of corporate governance.
  1. Reinforcement of the corporate governance of microfinance institutions.
  1. Improvement of corporate governance and management in State-owned Companies (SOCs).
A methodology has also been developed be means of which the state of corporate governance of companies can be evaluated in 5 specific areas:
Rights and treatment of shareholders.
General meeting of shareholders.
Directory (policies and practices).
Transparency of information and accountability mechanisms.
Control environment (identification and management of risks).
For each area, specific standards are established that, depending on the degree to which the principles of corporate governance are implemented, will determine the level of overall governance risk at which the company and each one of the above mentioned areas under assessment may be found.
CAF has published papers on guidelines for corporate governance in Latin America that today serve as a benchmark in the region:
  1. "Guidelines for a Latin American Code of Corporate Governance".
  1. "Guidelines for a Corporate Governance Code for SMES and Family Businesses".
  1. "Guidelines for Good Corporate Governance of State-owned Companies".
  1. "Corporate Governance: What every business owner should know".
  1. "The importance of Corporate Governance in State-owned Companies".
  1. "Corporate Governance and Development of Capital Markets in Latin America".
  1. "Corporate Governance and Determination of Risks in Debt Instruments".
  1. "Manual of Corporate Governance for Privately Held Businesses".
  1. These publications can be consulted at http://scioteca.caf.com.
## Outline of the management approach, implementation of the program and activities
Within the framework of the British fund’s objectives and considering the reasons set out above, the project for the agencies and the creation of standards and PPP have the following specific objectives:

Reduction of poverty and fostering of gender equity through economic development
Creation of commercial opportunities that British companies will be able to apply for.
Development of a Corporate Governance program for the ANI.
Identification of a certification methodology for entities implementing PPP to be adopted by the National Department of Planning (DNP in Spanish).
Construction of a plan for citizen oversight of the implementation of the measures.
Evaluation of the results of the implementation of the Corporate Governance Program for ANI as of the first and third year.
This project, in turn, will include the following components and activities:
COMPONENT 1: Benchmarking recommendations.
Activity 1: Experiences with the presence of independent members on Boards of Directors of Executive Agencies.
Activity 2: Diagnosis of the current situation of ANI’s corporate governance and recommendations.
Activity 3: Initial workshop on disseminating the program, which will take into account the study on best practices from Executive Agencies in the United Kingdom and in other developed Commonwealth markets that the Prosperity Fund in Colombia is currently commissioning.
COMPONENT 2: Identification and management of relevant stakeholders.
Activity 1: Hold two workshops with relevant stakeholders in view of the modification of the corporate governance of executive agencies.
COMPONENT 3: Advice on the adoption of measures.
Activity 1: Advice on the construction of the necessary regulations (Rules of Procedure of the Board of Directors and Committees, procedure for selecting the members and Chairman of the ANI).
Activity 2: Preparation of a draft bill with its explanatory statements (ANI reforms and parameters for territorial entities).
Activity 3: Development of a document on the methodology for certifying entities that are implementing PPP which the DNP should adopt.
COMPONENT 4: Oversight and training in the implementation of the measures.
Activity 1: Building a plan for citizen oversight of the implementation of the measures.
Activity 2: Training for independent members and of the staff of the Ministries involved in the Board of Directors.
Activity 3: Establishment of hiring baselines for the evaluations of the first and third year.
COMPONENT 5: Evaluation first year after implementation.
COMPONENT 6: Evaluation third year after implementation.
COMPONENT 7: Implementation of the recommendations arising from the evaluations.
## Expected Results
Results Component 1: Benchmarking recommendations.
Document of experiences with the presence of independent members on Boards of Directors of Executive Agencies.
Document on the diagnosis of the current situation for ANI’s corporate governance and recommendations.
Holding an initial workshop to disseminate the program
Results Component 2: Identification and management of relevant stakeholders.
Hold two workshops with relevant stakeholders in view of the modification of the corporate governance of executive agencies
Results Component 3: Advice on the adoption of measures.
Document with the Rules of Procedure of the Board of Directors and Committees, procedure for selecting the members and Chairman of the ANI.
The draft of a bill with its explanatory statements (ANI reforms and parameters for territorial entities).
Document on the methodology for certifying entities that are implementing PPP which the DNP should adopt.
Results Component 4: Oversight and training in the implementation of the measures.
Document with the definition of a plan for citizen oversight of the implementation of the measures.
Holding training workshops for independent members and the staff of the Ministries involved in the Board of Directors.
Document with the results of the baselines for the evaluations of the first and third year.
Results Component 5: Evaluation first year after implementation.
Document with the results of the evaluation of the first year after implementation.
Results Component 6: Evaluation third year after implementation.
Document with the results of the evaluation of the third year after implementation.
Results Component 7: Implementation of the recommendations arising from the evaluation.
Taking into account the expected results, CAF will sign one contract with a national or international experts with expertise in the design, implementation and evaluation of corporate governance for Executive Agencies.

## Activity Schedule (Gantt Chart)
COMPONENTS AND ACTIVITIES	2018					2019					2020					2021
	1Q			2Q			3Q			4Q			5Q			6Q			8Q			9Q			10Q			11Q			12Q			13Q			14Q			15Q			16Q			17Q
COMPONENT 1: Benchmarking recommendations.
Activity 1: Experiences with the presence of independent members on Boards of Directors of Executive Agencies.
Activity 2: Diagnosis of the current situation of ANI’s corporate governance and recommendations.
Activity 3: Initial workshop on disseminating the program.
COMPONENT 2: Identification and management of relevant stakeholders
Activity 1: Hold two workshops with relevant stakeholders in view of the modification of the corporate governance of executive agencies.
COMPONENT 3: Advice on the adoption of measures
Activity 1: Advice on the construction of the necessary regulations (Rules of Procedure of the Board of Directors and Committees, procedure for selecting the members and Chairman of the ANI).
Activity 2: Preparation of a draft bill with its explanatory statements (ANI reforms and parameters for territorial entities).
Activity 3: Development of a document on the methodology for certifying entities that are implementing PPP which the DNP should adopt.
COMPONENT 4: Oversight and training in the implementation of the measures.
Activity 1: Building a plan for citizen oversight of the implementation of the measures.
Activity 2: Training for independent members and of the staff of the Ministries involved in the Board of Directors.
Activity 3: Establishment of hiring baselines for the evaluations of the first and third year.
COMPONENT 5: Evaluation first year after implementation.
COMPONENT 6: Evaluation third year after implementation.
COMPONENT 7: Implementation of the recommendations arising from the evaluations.

## Project Risk Matrix
Risk	IMPACT Low/Medium/High	PROBABILITY Low/Medium/High	MITIGATION	DATE
Selected experts lack of capability	Medium	Low	Application of default clauses to the experts and selection and hiring of a new one	During the implementation of the project
Lack of support from the national government with respect to ANI’s need for a code of corporate governance.	High	Low	The current government is committed to the project. It is important to start the project before the change of government in August 2018 and get different stakeholders involved so that they understand and recognize relevance of the topic	Start of the project in 2017
Lack of commitment on the part of the independent members	Medium	Low	The selection of the independent members should be based on strict criteria of suitability. If those who were initially selected do not meet the criteria, there should be a new selection process	Start of the project in 2017
Incomplete or unclear terms of reference that could lead to a poorly specified baseline.	Medium	Low	The ANI, the DNP, CAF and the British Embassy will work on a clear definition of terms of reference that should mitigate this risk	During the implementation of the project
Lack of support from the national government for implementing the recommendations.	High	Medium	Importance of getting different stakeholders from technical entities involved so that they understand and recognize the relevance of the subject and show international evidence	2021
That the change of government next year will affect the project.	High	Low	It is important to start the project before the change of government in August 2018 and get different stakeholders involved so that they understand and recognize relevance of the topic.	2018

# Project 3: Insurance for the agricultural sector
## Objective
Increase the penetration of agricultural insurance in Colombia and expand the market to open up opportunities for national and international insurance providers, including companies from the United Kingdom. This will be done through building capabilities, improved training in agricultural insurance, the creation and implementation of an information system, educating in risk management and in technologies and the implementation of agricultural insurance pilots.
## Understanding the program and the context[1]
[1] This section is taken from the document that FINAGRO and CAF have worked on to design the Information System for Risk Management in the Agricultural Sector, entitled "Proposal for technical cooperation for the design of an information system for risk management in the agricultural sector.” October 2016
Agricultural activity is considered one of the most risky compared to other economic activities due to the constant exposure to various types of risks, whether natural (geological, climatic), health (pests and diseases) or market (fluctuations of prices for products and supplies, exchange rate), etc. This type of risk can affect productivity, yields and profitability, and producers’ income. They may be affected by a high level of indebtedness and a decrease in their financial ability to meet their obligations, make new investments, implement innovations and development, as well as the impact on the marketing of products, and the effect on food security in their territories.
In recent years, the national agricultural policy has been to implement strategies and mechanisms that make it possible to foster agricultural risk management in Colombia’s rural sector by means of various instruments. Furthermore, technological research and development has been implemented to strengthen capabilities to adapt to and mitigate variability and climate change in public and private institutions in the agricultural sector.
In this respect, the 2015-2018 agricultural policy, framed in the National Development Plan, is intended among other things to implement mechanisms that make agricultural risk management possible. This is the reason the national government has prepared a number of instruments that seek to address this situation through the Ministry of Agriculture and Rural Development of Colombia (MADR in Spanish) and that make it possible to attract and maintain private investment as well as generate the institutional, financial and legal security conditions that allow the various strategies, programs, plans and mechanisms to be developed. In developing it, the government established the "Adaptation Strategy for the Agricultural Sector to Climate Phenomena" and the "National Policy for Disaster Risk Management (Act 1523/2012)", appropriating and incorporating risk management through the three processes included in the standard: (i) knowledge of risk, (ii) risk reduction, and (iii) disaster management, demonstrating that this initiative is aligned with the priorities and supported by the national government.
Considering the above, it is necessary to work on several aspects of the public policy for developing insurance, encouraging the generation, dissemination and added value of the information about the sector; the building of capacity in the insurance sector; educating and training to demand agricultural insurance and catastrophic insurance for the sector; technological development in the sector and applied to public goods that support risk management; training and development of appropriate skills in the insurance sector to offer relevant products to different classes of individual, group or area producers in different regions around the country and for different kinds of crops.
In addition, it is necessary to work with the participation of the public and private sectors, such as the Ministry of Agriculture and Rural Development of Colombia (MADR in Spanish), FINAGRO, the Rural and Agricultural Planning Unit (UPRA in Spanish), the Ministry of the Treasury and Public Credit (MHCP in Spanish), the Financial Superintendency of Colombia (SFC in Spanish), the insurance sector and with FASECOLDA as an association for the insurance sector in Colombia. On this last point it is very important to encourage and ensure that national and international insurance companies, including companies in the United Kingdom, offer Colombia agricultural insurance and reinsurance effectively and sustainably, in order to have a significant number of hectares insured in the country.
However, there are obstacles to success in a program to boost agricultural insurance in Colombia, which seeks to stabilize the income of producers and this has to do with a lack of an insurance mindset and limited supply. The population in general, and particularly the agricultural producers do not have an insurance mindset and thus this situation must be resolved by more education and training on the benefits of insurance for the agricultural sector in particular.[2] Likewise, the supply of agricultural insurance in Colombia is limited and there are few companies that provide this service;[3] this problem is exacerbated by insufficient information and the specialized nature of the industry. This requires training and strengthening companies on these issues, through the establishment of a training program and medium-term implementation plan, including the reinforcement of existing capabilities in the companies, with a view to expanding the offer, considering new models such as parametric insurance, livestock, aquaculture, etc.
[2] "MISSION FOR THE TRANSFORMATION OF THE COUNTRYSIDE" (Rural Mission) which is on Page 199, Volume 3.
[3] As indicated in the study, "FINANCIAL ANALYSIS OF THE AGRICULTURAL INDUSTRY IN COLOMBIA" (FINAGRO-CAF. 2015).
The studies entitled "FINAGRO and SNCA" (MIDAS.2008)[4] and "PROPOSALS FOR REFORMING THE AGRICULTURAL FINANCING SYSTEM" (USAID, FINAGRO, and CAF. 2013) identified serious problems in the quality of information on the sector. This was corroborated and developed further in the study, "Development of Agricultural Insurance in Colombia" (FINAGRO, and CAF. 2015) This study pointed out that deficient information does not allow the insurance, credit, and capital market sector to properly manage the financial, productive, and climatic risks thus generating an inappropriate restriction on investments and perversely limiting the supply of products and financial services for the agricultural sector. Regarding this aspect, the Rural Mission in paragraph 5.3.3, Volume 3, recommends that "MADR should work toward the achievement, building and updating of climate information, costs and value of production per municipality or micro-region. This must be periodic, automated, available online and be public in nature." This important restriction is being tackled with the Technical Cooperation approved by CAF (09/2016) for FINAGRO, with the participation of MADR and UPRA, for the design of the Risk Information System in the Agricultural Sector, under the "Project Minutes of Incorporation" signed on 31/03/2016, by the MADR, the UPRA and FINAGRO.
[4] This work recommended several key points such as: i) Create the Risk Map of the Agricultural Sector; ii) Improve, facilitate and reduce the cost of access to support information such as meteorological, and improve the Network of registration stations since it is insufficient; iii) Increase and improve the training of certified inspectors / adjusters for the agricultural sector; iv) Transfer risks to specialized insurance and reinsurance sectors, at a reasonable cost, in order to optimize State resources dedicated to FAG or to provide aid for climate damages. "Finagro and SNCA". MIDAS. 2008.
In fact, since the country does not have a platform that is suitable, homogeneous, automated and easy to access and that meets or centralizes the use of the information required to carry out a comprehensive management of agricultural risks, it is necessary to implement a risk management information system[5] to collect and assemble the information and generate added value in relation to climate information, soil and its uses, pests and diseases, research and technology, infrastructure, in addition to sectoral statistics of the production process (production yields, costs, etc.), prices, credit, etc.
[5] In this respect, for a pertinent definition of the agricultural risk management approach, it is considered indispensable to be consistent with the "Strategy for Adaptation of the Agricultural Sector to Climate Phenomena" and the "National Policy for Disaster Risk Management (Act 1523/2012)", established by the government, appropriating and incorporating risk management through the three processes included in the standard: i) knowledge of risk, ii) risk reduction, and iii) disaster management.
The elimination of the obstacles initially identified expands the perimeter of the agricultural insurance market and opens the door for the entrance of new national and international players to increase the culture of insurance and the supply of agricultural insurance in its different versions and regions of the country. At the same time, the initiative to organize the business model for agricultural sector information generates opportunities for companies that offer technological solutions for the rural sector, national and international information networks, and in particular companies based on Agtech with the birth of more room for new companies or technology initiatives.
## Outline of the management approach, implementation of the program and activities
Within the framework of the British fund’s objectives and considering the obstacles previously identified, it is necessary to improve the competence of the people and businesses who demand agricultural insurance and reinforce the provision of agricultural insurance in Colombia.
This project will take into account recommendations, knowledge and evidence presented in the Political Economy Analysis (PEA) of Colombia’s Agriculture Sector, and will include the following components and activities.
COMPONENT 1: Data and Information.
Activity1: Development and implementation of Risk Information System for the Agricultural Sector (SIGRA in Spanish).
Considering that the country does not have a proper, homogeneous, automated and easily accessible platform that brings together and centralizes the use of the necessary information to carry out comprehensive management of agricultural risks, it is necessary to implement a risk management information system that collects and organizes the information and generates added value with the information that the entities in the sector have in relation to the climate, soil and its uses, pests and diseases, research and technology, infrastructure in addition to sectoral statistics on the production process (yields, production costs, etc.), prices, credit, etc.
The design of the system that is starting at present establishes different aspects to be treated as the most important agricultural risks, the information available and necessary in Colombia on the agricultural sector; the different existing sources of information, the services offered by the information system and the added value to be offered; the identification of users who would be interested; how the system and users would relate to each other and how the system would contact them; the channels that will be used to serve the users; the key resources needed to operate the system; and the financial structure of the system.
Development of an information system for agricultural risk management would go through several phases such as i) planning, ii) the architecture of the system, iii) engineering, iv) use and appropriation and v) pilot tests before expanding the system.
Activity 2: Development of a Geographic Information System for FINAGRO.
In the conceptualization of SIGRA, FINAGRO is the entity selected as the provider of the financial risk assessment of the Sector, given its knowledge and role as administrator of instruments for agricultural development and risk reduction, such as the Agricultural Guarantee Fund (FAG in Spanish) and the National Fund for Agricultural Risks (FNRA in Spanish), so it is essential to have a robust geo-referenced information system that guarantees an adequate supply of information.
The financial information that FINAGRO has shall be analyzed using a flexible system of management, with the ability to integrate a variety of sources and permanent update, to avoid duplication of records, becoming outdated, parallel efforts, dispersion of information, incompatibility of formats, inaccessibility of the data and wasted resources.
Geographic Information Systems (GIS), function as a database that manages information with an absolute position (coordinates), a relative position (topology) and attributes (alphanumeric data), designed to view, edit and analyze spatial information in order to help solve complete planning and management problems since they are productive and financial data from the agricultural sector. As a consequence, the implementation of a GIS is key to the development of FINAGRO’s objectives.
Activity 3: Risk Maps of the Agricultural Sector.
As discussed in note 4 of this document, one of the subjects that it has been recommended be developed is the construction of risk maps of the agricultural sector, which would also feed the information system. Considering the periodic changes in the environment and/or agronomic demand, and today, climate change, risk maps should be updated regularly which implies the need to create a methodology for producing risk maps on a regular basis.
Furthermore, based on this methodology, it is necessary to build risk map scenarios for the crops with greater quality insurance in this country, such as rice, bananas, corn, sugar cane, timber, etc., and those from areas of greater promotion and development for each crop in the country.
Activity 4: Support in the construction of production costs based on the methodology of economic reference and/or relatively homogeneous areas.
Under the Colombian Agricultural Financial System Support Project (PASAC in Spanish), an initiative developed by the governments of Canada and Colombia and operated by Développement International Desjardins (DID) and FINAGRO, actions are being carried out jointly to accelerate the development of the Colombian agricultural financial sector in order to contribute to the reduction of poverty, and improve agricultural productivity and the well-being of rural communities.
Through this cooperation, FINAGRO seeks a methodology for building frames of reference that will make it possible to give the different stakeholders in the National System of Agricultural Credit, valuable, consistent, periodic and technically validated information following the methodology of CORPOICA, DANE and UPRA, for some strategic crops prioritized by the entity.
This will improve access to credit and other financial instruments in the rural sector, providing information to intermediaries and insurance companies that do not yet have a significant share in the rural portfolio. FINAGRO seeks to capitalize on the methodology through UGRA, coordinating working tables between production associations, producer associations, MADR, government entities, academia, financial intermediaries and national and international experts.
This is strategic for FINAGRO, since it means handing over information that, at present, no entity provides to the rural sector and that is essential for fostering better management of the rural sector information. It is necessary to put pilot programs into effect in areas and with crops of interest by funding and insurance.
COMPONENT 2: Training and Education on Agricultural Insurance.
Activity 1: Train users in agricultural insurance.
This is directed towards disseminating information on agricultural insurance and to provide training at the regional level (public and private) for agricultural producers and their associations, and other related stakeholders, through the generation of information about the classes of existing agricultural insurance and its modalities. An education program on agricultural risk management should be organized jointly with the government and the insurance and reinsurance sector.
It will be necessary to establish the information, materials, and channels to be used to disseminate the contents that the producers, associations, and productive chains require about insurance in order to understand it and the ways and channels by which this knowledge will be transferred and indicating the benefits to be obtained. The partnerships that have to be made with the public and private sector to carry out this dissemination and training will be identified considering the insurance companies and producer associations at the national and regional level in order to circulate the information and training properly.
As MADR has made clear, to properly determine the contents of the training it is important to create regional agriculture-climate technical tables (MTA in Spanish) to take stock of the environmental supply by region. Furthermore, plans are already made to include training for the agricultural climatologists of the associations in order to incorporate risk management and the performance of prediction/prognosis in developing productive activity. Similarly, the channels for circulation and/or training such as the development of virtual modules, the provision of specific information through mobile media and Agtech or traditional means of communication. In order to ensure the sustainability of the training, support will be given to the creation of courses and majors on agricultural insurance with universities, aimed at both demand and insurance companies.
Activity 2: Training State entities.
As various studies have indicated, at the same time as training is done on the supply and the demand for insurance, it is essential to inform and train state officials who are connected with the regulation and supervision of agricultural insurance. Both the Ministry of the Treasury and Public Credit (MHCP in Spanish) and the Financial Superintendency of Colombia (SFC in Spanish) should be invited to the training that will be held in the sector; and specialized training for them on the regulation and supervision of the sector must be prepared. This could be done through exclusive courses and/or internships to learn about international experiences in both agricultural insurance and risk information systems.
Activity 3: Train the insurer. Companies and insurance brokers.
The training must be given to officials of the insurance companies, brokers and independent agents who sell insurance, and are the direct contact with agricultural producers. The training will be regional and guided initially by the location of the offices of the insurance companies. The training should focus on the legal information, the phonology of the crops, on how an adjustment is made and how a claim is settled.
This training will be special and focused on the adjusters and claims adjusters. The training will include the preparation of related professions, whether these are agronomists, biologists (aquaculture), veterinarians, animal husbandry, etc. based on the specific area; and the training of professionals who are also experts in a specific crop, or in livestock, aquaculture, or forestry and with experience in insurance adjustment. In this respect, training an association insurer will also be key (FASECOLDA).
The training will also consider the knowledge and evidence presented in the Political Economy Analysis (PEA) of Colombia’s Agriculture Sector and the following topics suggested by the MADR and Finagro:
Models of specific actuarial calculations for the agricultural industry.
Models of loss adjustment and appraisal on the field for agricultural insurance.[6]
[6] Currently, with the support of the Federation of Colombian insurers, FASECOLDA, the National Insurance Institute -INS and FINAGRO, work is underway on strengthening the technical capabilities of the agronomists, technicians/technologists in agronomy, adjusters and experts in inspection and adjustment of the crops that have agricultural insurance in the country.
Good practices in portfolio management for the agricultural industry.
Operation and limitations of index-based insurance.
Interpretation of satellite information, prospective risk models, and new variables for the estimate of losses.
Preparation of adjustment manuals for different crops and activities of the agricultural sector.
Innovation and development of insurance models (parametric and catastrophic).
Activity 4: Generation of Knowledge.
This starts with the generation of content, an initial diagnosis of the situation regarding the supply of agricultural insurance and the companies that offer insurance or want to offer it, in order to promote and identify allies to carry out training and implementation of agricultural insurance. Allies should be found among the reinsurance companies,[7]insurance companies and at the level of insurance intermediaries to whom it is important to explain the implications of providing agricultural insurance. In any case, the reinsurance companies are key allies in the operational and financial flow of insurance since they know the insurance products and take on a significant part of the risks; and accompany the public sector in the design and implementation of a stable and comprehensive policy on risk management, and in particular in the review of the participation of the Agricultural Guarantee Fund (FAG in Spanish) in the comprehensive policy on risk management in the sector.
[7] Agricultural Reinsurance Association (ALASA).
In addition, the agricultural insurance products will be designed, based on the kind of insurance, the cultivation area, etc. In these areas, the development of products by customer segments, high-tech or not, have to be included whether they are agricultural, livestock raising, aquacultural or forestry, and catastrophic thus continuing the work developed by WB and FINAGRO. In this matrix of insurance products whether or not the insurance is for production (income: price and/or quantity) or per plant has to be considered. In this case it is necessary to identify the techniques that must be learned for the design of products such as the models of actuarial calculations, adjustment models and pricing in the field, and insurance models for the livestock and aquaculture sectors. The companies, in turn, must determine the operating plan that will be used, whether by views or parametric.
COMPONENT 3:[8] Use of Technology for the Agricultural Sector
[8] MARD and FINAGRO.
Activity 1: Hydrometeorological Stations
For several years the inadequacy of the hydrometeorological stations that the country uses,[9] their poor quality, and low degree of interconnectivity has been pointed out. The network does not offer the minimum national or regional geographical coverage that is needed. The required number of stations do not exist, nor do they cover all the regions where there are crops, nor are all of them modern while few are on line, nor are they interconnected or measure all climatic phenomena that occurs.
[9] Agricultural insurance in Colombia. MIDAS. 2008
Thus it is necessary to do a diagnosis of the network of stations, both public and private, determine the existing problems, do a diagnosis of its current state, and make recommendations for its improvement. A strategy to update the existing ones and the placement of new ones needs to be constructed which will contribute to the building of insurance models.
Activity 2: Simulation tools and estimation of information
As a complement to the creation of the above mentioned information system, it is important to have information and simulation tools based on meteorological information and satellite images to record yields, planting and harvesting periods, as well as the climate impact assessments in crops. For this activity, the current situation of these technologies in the country will be studied, as well as the most applicable international experiences, and some recommendations for its implementation will be suggested in order to develop a work plan.
COMPONENT 4: Pilots for New Models of insurance
Considering the matrix of insurance products that establishes different types of interventions, the proposal to finance catastrophic insurance pilots is being made based on the work FINAGRO has done with the World Bank in recent years that make it possible to measure the validity and sustainability of new products. These pilots should promote and select between insurance companies.
In addition, banks, credit unions and microfinance institutions are very important placement channels in the agricultural sector, but do not have an innovative design that makes it possible to deliver agricultural insurance policies in bulk for producers who require that.
## Expected Results
Results Component 1: Data and Information
Activity 1: Development and implementation of Risk Information System for the Agricultural Sector (SIGRA in Spanish)
Conceptualization. FINAGRO-CAF Project.
Comparison of results of the diagnostic work and design of the information system which was done in the first phase of conceptualization with Open Data guidelines.
Planning:
  1. Definition of planning.
  1. General strategic plan and plan per entity.
  1. Prioritization.
  1. Presentation to MinTic for coordination and support.
  1. Interoperability agreements between entities and the state.
  1. Government agreement on data and institutions (at the central level, by entity and with MinTic).
Engineering (Architectural and Engineering):
By entity:
  1. Planning.
  1. Analysis and design.
  1. Quality of data.
  1. Agricultural and geographic node.
  1. Determination of threads of information per entity.
  1. Work on each thread of information of each selected entity (10).
  1. Tests per entity.
The coordination of the system:
  1. Determination and activation of the institution that coordinates and manages the system.
  1. Structuring of the display of the system.
  1. Deployment.
Use and Appropriation
  1. Communication Plan.
  1. Dissemination and Training
  1. Consolidation of coordination.
Put into Production by entity:
  1. Production Planning.
  1. Planning of training.
  1. Production environment by entity.
Activity 2: Development of a Geographic Information System (GIS) for FINAGRO.
Design of Terms of Reference for the geographic information system for FINAGRO.
Agreement in FINAGRO for hiring.
GIS hiring for FINAGRO.
GIS assembly in FINAGRO.
Activity 3: Risk Maps of the Agricultural Sector.
Risk mapping methodology built.
Risk maps made for the main insured products, such as rice, bananas, corn, forestry, sugar cane, potato, and of those areas with the greatest stimulus and development for each crop in the country.
Activity 4: Support in the construction of production costs based on the methodology of economic reference and/or relatively homogeneous areas.
Conceptualization of the methodology for building frames of reference for some of the prioritized strategic crops.
Establish the methodology through UGRA.
Coordinate working groups that include production associations, producer associations, MADR, government entities, academia, financial intermediaries and national experts.
Put pilot programs into effect in areas and with crops of interest for funding and insurance.

Results Component 2: Training and Education on Agricultural Insurance.
Activity 1: Train users in agricultural insurance.
Dissemination:
Dissemination Program on agricultural insurance designed for the existing classes of agricultural insurance and its modalities and includes commercial and catastrophic insurance; costs and parametric; products and regions, etc.
Identification of the producers to train by crop and by geographic area.
Identification of the information to disseminate.
Design of the material to disseminate.
Partnerships:
A partnership established with FASECOLDA.
A partnership established with ALASA.
Alliance with SENA for the competence-based design of the agricultural insurance program.
Alliance established with the country’s main trade associations in the agricultural sector (Fedapalma, Fedecafe, Fedecacao, Fedearroz, Fedecerales, Fedealgodon)
Training:
Training and material design.
Training agricultural producers in areas of the country (100 regions).
SILABUS design for a course offering a diploma on risks and agricultural insurance in coordination with several universities in Colombia (7 universities).
SILABUS design for a specialized course of study on risks and agricultural insurance in coordination with several universities in Colombia (7 universities). Three courses offering a diploma could be designed so that if all of them are completed they would be equal to a specialization.
Activity 2: Training State entities
Training and internships for policy makers to get international experience.
Workshops on agricultural insurance exclusively for the Ministry/SFC/MHCP.
Workshops on insurance for secretaries of agriculture of specific municipalities where insurance is being copied or where it is desirable to foster it.
Train regional secretaries of agriculture in the governorships (20) and secretaries of agriculture of certain municipalities (100) with the presence of clusters and / or productive chains.
Specialized internships to learn about agricultural insurance.
Activity 3: Training for Insurance Companies.
Hold workshops on agricultural insurance at the central level for insurance companies, brokers and independent agents who sell insurance.
Give regional workshops in specific municipalities where insurance is being copied or where you want to foster it. This training should focus on the legal information, the phenology of the crop, on how adjustments are made and how a claim is settled along with other topics.
Preparation of adjustment manuals for different crops and activities in the agricultural sector.
Special and focused training for the adjusters and claims adjusters. The training will include the preparation of related professions, whether these are agronomists, biologists (aquaculture), or veterinarians, etc. based on the specific area; and the training of professionals who are also experts in a specific crop, or in livestock, aquaculture, or forestry and with experience in insurance adjustment. In this respect, the involvement an association insurer will also be key (FASECOLDA).
Build the content of the training on:
  1. Models of specific actuarial calculations for the agricultural industry.
  1. Models of claims adjustment and appraisal on the field for agricultural insurance.
  1. Good practices in portfolio management for the agricultural industry.
  1. Innovation and development of insurance models.
Activity 4: Generation of Knowledge
An initial diagnosis of the situation regarding the supply of agricultural insurance and the companies that offer insurance products.
Based on the type of insurance, the agricultural insurance products will be designed after the work developed by the WB and FINAGRO. In this matrix of insurance products it will be considered both production insurance (income: price and/or quantity) and crop insurance.
Identify the techniques that will be learned for the design of products such as the models of actuarial calculations, adjustment models and pricing in the field, and insurance models for the livestock and aquaculture sectors.
Advise the public sector in the design and implementation of a stable and comprehensive policy on risk management and, specifically, in the review of the participation of the Agricultural Guarantee Fund (FAG in Spanish) in the comprehensive policy on risk management in the sector.

Results Component 3:[10] Use of Technology for the Agricultural Sector.
[10] MARD and FINAGRO.
Activity 1: Hydrometeorological Stations.
Do a diagnosis of the network of stations, and make recommendations for its improvement and staffing.
Support the updating, location and relocation of stations or radars in the network, in order to contribute to greater coverage of the country, and build a budget for updating the network of stations.
Design a tool/methodology to facilitate the use of the IDEAM geovisor.
Support the staffing and completion of missing information.
Activity 2: Simulation tools and estimation of information
Based on meteorological information and satellite images, generate information and simulation tools to record yields, planting and harvesting periods, as well as, the climate impact assessments in crops.
Studies of the most applicable international experiences.
Develop a work plan with recommendations for the implementation of the simulation tools and information estimation.

Results Component 4: Pilots for New Models of insurance.
Activity 1: Catastrophic insurance pilots.
A study that considers FINAGRO’s previous work that was done with the WB and chooses the pilots to run, mainly those of new models of catastrophic insurance.
Catastrophic insurance pilot for small-scale agriculture in Colombia, based the results from the first phases and the work to be done with some previously selected associations.
Activity 2: Commercial and Parametric insurance pilots
Study about parametric insurance pilots.
Commercial and Parametric insurance pilot for small-scale agriculture and by region, based on the results from the first phases and the work with some previously selected associations.
Taking these expected results into account, CAF plans to sign a variety of Technical Cooperation Agreements and contracts with a national or international firms for each component and its activities. For component 1, CAF will sign a total of up to six contracts with experts that will have experience in Risk Information Systems, Geographic Systems, agricultural risk maps and development of production costs in the agricultural sector.
For component 2, CAF will sign a Technical Cooperation Agreement with FASECOLDA to train users of agricultural insurance and sign five contracts with national or international firms. The experience of these experts will be in training State Entities, insurance companies and insurance brokers, as well as in commercial, catastrophic and parametric insurance. Likewise, it is expected to promote some alliances with SENA and universities (national or international) to strength the training of State Entities, insurance companies and insurance brokers.
For component 3, CAF will sign a Technical Cooperation Agreement with IDEAM and three contracts with national or international companies with expertise in hydrometeorology, satellite systems and designing geovisors. Lastly, for component 4, CAF will sign two contracts, in order to develop commercial, catastrophic and parametric insurance pilots for small-scale in agriculture in Colombia.
## Activity Schedule (Gantt Chart)
COMPONENTS AND ACTIVITIES	2018					2019					2020					2021
	1Q			2Q			3Q			4Q			5Q			6Q			8Q			9Q			10Q			11Q			12Q			13Q			14Q			15Q			16Q			17Q
COMPONENT 1: Data and Information
Activity 1: Development and implementation of Risk Information System for the Agricultural Sector (SIGRA in Spanish)
Activity 2: Development of a Geographic Information System for FINAGRO
Activity 3: Risk Maps of the Agricultural Sector
Activity 4: Support in the construction of production costs based on the methodology of economic reference and/or relatively homogeneous areas
COMPONENT 2: Training and Education on Agricultural Insurance
Activity 1: Train users in agricultural insurance
Activity 2: Training State entities
Activity 3: Train the insurer. Companies and insurance brokers
Activity 4: Generation of Knowledge
COMPONENT 3: Use of Technology for the Agricultural Sector
Activity 1: Hydrometeorological Stations
Activity 2: Simulation tools and estimation of information
COMPONENT 4: Pilots for New Models of insurance
Activity 1: Catastrophic insurance pilots.
Activity 2: Commercial and parametric insurance pilots.

## Project Risk Matrix
Risk	IMPACT Low/Medium/High	PROBABILITY Low/Medium/High	MITIGATION	DATE
Lack of support from the national and local government in the development of the project	Medium	Low	The project is in line with the 2015-2018 agricultural policy framed within the National Development Plan and accompanies all the Government efforts on agricultural risk management / Furthermore, a committee with the State shall be established to supervise the development of activities just as inter-institutional agreements will be formalized to ensure the fulfillment of the activities. / The MADR and FINAGRO are the owners of this risk.	2017-2021
Lack of interest on the part of State entities.	Medium	Low	Agreements between entities will be drawn up in order to ensure the continuity and implementation of the project. / Just as in component 4: Pilots for new insurance models have established tasks to measure this risk, which will materialize in the middle of the project, in order to identify sufficient monetary incentives to support the existence of catastrophic insurance.	2017-2019
Poor planning of technical aspects	High	Medium	The institutions involved in each of the activities through their experts are expected to clearly define all the technical aspects required to mitigate this risk. / Likewise, the development and expertise work will be monitored. / The institution in charge of the activity and company hired are the owners of the risk. / MADR, FINAGRO, and CAF are the owners of this risk	2018-2019
Lack of coordination among the entities that will work together for the development of activities	High	High	At the beginning of the activities, the participation of each of the entities involved and their willingness to work together with other institutions will be formally agreed upon. In the case of a non-confirmation, that one will be replaced by another. / Creation of a planning and entity participation strategy. / MADR and FINAGRO are the owners of this risk.	2017-2021
That the change of government next year will affect the project.	High	Low	This risk will be monitored together with FINGRO, MARD, and the Committee. / Agreements between the entities involved and with the FPS project will be formalized. / Furthermore, a rapid organization and initiation of activities before the change of government will be sought.	2018
That the development of the activities is not clearly established, considering all its characteristics	Low	Low	There is consensus in the public and private sectors on the need to move ahead on this project which ensures its implementation and continuity. / There are already express manifestations of MADR, FINAGRO, and UPRA’s participation. / There is also a manifestation of FASECOLDA.	2018
Lack of collaboration to train the demand for agricultural insurance	High	Low	The rapprochement with FASECOLDA has already begun and will be formalized with an agreement on its support for the project. / The participation of SENA in the project will be formalized. The owners of this risk are FINAGRO and FASECOLDA	2018
That the insurance sector may not be interested in agricultural insurance	Low	Medium	Monitoring will be done with FASECOLDA, who will be the institutional leaders in this training component. / FASECOLDA and FINAGRO are the owners of this risk.	2017-2018
There is no clarity about the focus of the research for some activities.	Low	Low	The committee, CAF and all the institutions involved will do a special follow-up on the activities that require an investigation to ensure their effectiveness in the project. CAF is planning on a diagnostic study of agricultural insurance in the Pacific Alliance that will shed light on the focus of this generation of knowledge. CAF and FINAGRO are the owners of this risk along with FASECOLDA.	2018
That the insurance model is not well structured	Low	Low	Task have been included so that technicians and FASECOLDA can validate the catastrophic insurance products. In addition the work that WB and FINAGRO have pushed ahead ensure a better perspective on the initiative due to the fact that it has already been worked on. / FINAGRO and CAF are the owners of this risk.	2019

# ANNEX 2
NON-GRANT PROGRAMME DELIVERY COSTS

	2018	2019	2020	2021	TOTAL
Project monitoring and preparing reports costs	182.777	177.804	69.838	36.696	467.115
CAF Assessments costs	71.080	69.146	27.159	14.271	181.656
TOTAL	253.856	246.950	96.998	50.967	648.771

### ANNEX 3
SPECIAL CONDITIONS

1.	EXCHANGE RATE

Grant Funding payments made by CAF to Beneficiaries in accordance with this Agreement will be made in US Dollar or other currencies. Where a Beneficiary incurs costs as part of an agreed programme of work in a currency other than US Dollar, the conversion rate of those costs into Pound Sterling will be calculated in accordance with the exchange rate between both currencies in force at the date on which the award is confirmed.