Annual Review - Summary Sheet

PROGRAMME TITLE: Algeria CSSF Country Programme
Country/Region:	Algeria, North Africa
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD), Home Office (HO), National Crime Agency (NCA)
Total Spend:	ODA: £4.94m (due to a financial uplift in year)			Non-ODA: £0
Start Date: April 2017		End Date: March 2018
Outputs					Score
Economic Reform: Economic reforms designed and disseminated to make the Algerian economy more sustainable (outcome impact weighting: 35%)					A
Employability: Training, education and development activities are tailored to increase employability of youth (outcome impact weighting: 30%)					A
Governance: Parliament staff have gained new skills and knowledge of systems and practices of legislative drafting, and a better understanding - and integration of gender equality issues into Parliament is promoted (outcome impact weighting: 25%)					A
Human Rights: The newly appointed Child Protection Commissioner is established and operational (outcome impact weighting: 10%)					B

Overall output score:					A
Outcome Assessment: Outcomes partially did not meet expectations.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	B	A	B
Risk Rating	N/A	Medium	Medium

*output/outcome scores

What support is the UK providing?

Last year, the £4.25m Algeria CSSF programme sought to support the Government of Algeria (GoA) and the Algerian people through ten projects focused on economic reform and youth access to employment; political participation and inclusivity; and good governance and human rights.

These projects were implemented by ten implementing partners and aimed to:
- improve education outcomes for Algerian students by supporting skills and labour market insertion of university graduates and improving their employability prospects;
- enhance innovation and entrepreneurship through increased opportunities for small and medium-sized enterprises to access technical support;
- assist the GoA as they design their long-term economic vision for Algeria;
- strengthen the Algerian parliament’s capacity to fulfil its oversight function;
- support Algeria’s political parties to participate effectively in electoral processes;
- enhance the participation of women in elected assemblies;
- better understand the drivers of gender-based violence in Algeria;
- develop a free and representative public service media in Algeria;
- foster compliance with international standards with respect to prison reform.

The programme supports President Bouteflika’s constitutional reforms and the GoA’s five-year Action Plan to implement the President’s 2014 rule of law, education, and economic programme. It complements other donors and institutions’ programming priorities which similarly major on employment and economic reform and strengthening democratic political institutions. The programme is purposely weighted towards economic transformation because this is a GoA priority, and because an improved economic outlook in Algeria underpins Algeria’s security and sustainable mutual prosperity.

Summary of progress and lessons learnt/actions taken since last review

Progress

The Algeria NAGGF/CSSF programme made good progress last year in what was its first full year of implementation. The CSSF programme team based in the British Embassy in Algiers has built on lessons learnt from initial investments and underpinned by in-depth analysis, to develop a coherent portfolio of projects.

At the start of 2017/18, the pace of implementation and spend was slower. Only two implementing partners out of ten were able to carry out any of their project activities in quarters one and two. The programme was backloaded as a result, with the majority of activities taking place in quarters three and four. Most of those interviewed attribute this to capacity and capability gaps in the programme team, protracted contract negotiations, legislative elections in Algeria in 2017, and seasonal delays (notably breaks over Ramadan, Eid and the summer holidays).

By contrast, quarters three and four witnessed considerable headway made on implementation, with a new, more experienced programme team in place. Interviewees commented favourably on improved financial management processes and embassy engagement and responsiveness in support of a “programme that had come such a long way in such a short time”. Both the Ambassador and Deputy Head of Mission were commended by interviewees for their enthusiastic engagement with the programme, and the political impetus their involvement generated for individual projects. These factors enabled the delivery of the majority of outputs as the output A rating against attests.

What the indicators in the results framework do not capture is the programme’s contribution to progress made on strengthening the bilateral relationship, unprecedented access to Algeria’s decision-makers, and potential entry points to other economic reform priorities that could benefit from UK-provided technical support. The programme has enabled the development of relationships with the Ministries of National Education, Interior and Finance, as well as the National Council for Human Rights and the Prison Directorate.

Lessons learned

Relationships determine progress. The projects that delivered most of their outputs by the end of the programme cycle were those where implementing partners enjoyed a positive and productive relationship with partner Ministries and these strong relationships facilitated access to a broader range of Algerian decision-makers. Penal Reform International, for instance, was able to use their networks with the Algerian authorities to reach out to Algerian parliamentarians to advocate on human rights issues.

Monitoring is key to cost efficient programming. The programme team has applied rigour in monitoring activities for cancellations, challenging project delivery plans, scrutinising budgets and quarterly reports, and returning unspent funding to the centre.

Creative approaches can generate much needed momentum. In seeking to address blockages to Westminster Foundation for Democracy’s (WFD) efforts to forge a relationship with Parliament, a critical prerequisite for the project’s success, the programme team changed tack, and both the team and the implementing partner trialled a different approach. This new approach succeeded in giving WFD the opening that they needed, and the programme team has witnessed an encouraging acceleration of pace.

The importance of planning ahead. The programme team started working with implementing partners January 2018 to ensure contract extensions were in place to ensure a smooth transition into 2018/19, with spend taking place from the first quarter. Planning involved circulating guidance to partners on devising project-level results frameworks and completing activity-based budgets.

Summary of recommendations for the next year

Recommendations made in the body of this review cover conducting a strategic internal review of the programme’s relevance, impact and coherence, and strengthening conflict sensitivity, monitoring & evaluation activity and risk identification and mitigation. The programme team is aware that these areas require improvement. The head and deputy head of the team have already acted in response. They have commissioned a Joint Analysis of Conflict and Sensitivity, and through the new Monitoring, Evaluation and Learning contract, independent reviews of certain individual projects to assess their relevance.