Annual Review - Summary Sheet

PROGRAMME TITLE: Jordan Inclusive and Sustainable Economic Reform Programme
Country/Region:	Jordan (Middle East and North Africa-MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £1.65m[1]			Non-ODA: £0m
Start Date: April 2016[2]		End Date: March 2018
Outputs					Score
Improved capacity of the Jordanian Ministry of Labour (MoL) to anticipate, address and resolve labour disputes.					A
Greater understanding and awareness of key economic reform priorities among the Jordanian public.					A
Good communications strategy in use by Jordanian Ministries' spokespersons.					B
Overall output score					A
Outcome Assessment: / 1) Improved labour relations in Jordan – B (insufficient evidence to demonstrate likely contribution to outcome); / 2) A conducive environment exists for the implementation of key economic reforms in Jordan – B (insufficient evidence to demonstrate likely contribution to outcome); / 3) Economic reforms are more effectively implemented through building government technical capacity for communications – B (outcome partially did not meet expectation).
Outcome Score: B			Risk: Medium
[1] There is a difference between the final annual expenditure (£1.65m) and the amount indicated in the Programme Document (£5.15m) which refers to the total programme spend over three years ending in FY17/18.
[2] Although the Jordan Inclusive and Sustainable Economic Reform Programme in its current configuration began in 2016-17, previous configurations extend back to 2015-16, which explains the inclusion of previous Annual Review scores. In April 2018 this programme was renamed the Economic Sustainability Programme.

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	A	A	B
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

In 2017/18 the UK provided £1.65m across three projects: Labour Dispute Resolution (LDR - £0.75m), Economic Research, Analysis and Debate (EconRAD - £0.4m) and technical assistance on strategic communications to support economic reform (£0.5m). Together these projects comprised the Inclusive and Sustainable Economic Reform (ISER) programme which aimed to contribute to a more economically stable Jordan. The programme has now concluded, with the LDR and EconRAD projects finishing (having begun in 2015/16) and the strategic communications technical assistance transferring into Jordan’s CSSF Political Stability programme.

Summary of progress and lessons learnt/actions taken since last review

The LDR project completed the rollout of 26 trained mediators in regional offices across Jordan and developed a labour disputes database for MoL. The EconRAD project focussed solely on the Malna (meaning ‘our money’ in Arabic) platform to disseminate economic research, which continued to grow and achieve good levels of audience participation. After initial scoping, the strategic communications project began in September 2018. The project received significant engagement from the Jordanian Prime Ministry and other host government departments, particularly around the successful rollout of a cross-government media communications grid.

The programme results framework was refined and kept up to date, but the difficulties of designing appropriate indicators and milestones remained apparent, particularly in the absence of a well-developed programme level theory of change. Sustainability plans were produced for the LDR and EconRad projects, which highlighted the difficulty of achieving sustainability and the need to build this into projects early on. The difficulty of achieving gender outcomes in the Jordanian context was also highlighted. A stability focussed gender analysis and a conflict sensitivity strategy were produced helping to mainstream both of these in future CSSF programming. The importance of continually testing the added value of projects was highlighted by the EconRad project, which although successful in terms of tracked results, could have been structured to offer better value for money. Finally, good progress has continued in cross Whitehall working with the establishment of a cross Embassy working group for the UK-Jordan Partnership and good collaboration with DFID Jordan.

Summary of recommendations for the next year

Ensure that the new Economic Sustainability Programme results framework is periodically tested against a well-developed, up to date programme level theory of change so that the link between outputs and outcomes is clear and measurable. The development and review of the Theory of Change and Results Framework should ideally be carried out in collaboration with DFID Jordan.

The British Embassy Amman should make use of opportunities to follow up on subsequent progress with LDR project outputs and outcomes. This could be achieved through DFID’s forthcoming programming with the World Bank covering labour markets. Alternatively, UK engagement with a similar Danish project and the relationships established with the trade unions will provide another channel through which to achieve progress.

Develop Government Communication Service (GCS) project theory of change and streamline and refine the project results framework to better reflect the project, including one output indicator for each work stream.

Engage a local expert as part of the GCS project team, who can provide continuous presence on the ground, staff continuity and an understanding of the Jordanian context. This will help to mitigate the risk of stasis during weeks when the project team are based in London and to further integrate the project into Jordanian government architecture.

Formalise the GCS project political reporting lines and governance structure within the British Embassy Amman. This will be increasingly important as the project gets more directly involved in communications strategies and campaigns and the potential reputational risk to UK Government increases.

Mainstream conflict and gender sensitivity into GCS project activities, including scoring GCS as an implementer according to conflict sensitivity strategy methodology. The project should also proactively look for opportunities to mainstream gender into project activities.

Value for Money indicators should be developed for the GCS project going forward, in order to try and better assess efficiency and cost-effectiveness. Different indicators will be required for the different work streams, and some strands of work may not be quantifiable. Consideration should also be given to gender mainstreaming and disaggregation where possible in order to assess project equity, whilst acknowledging that this is unlikely to be straightforward.