Annual Review - Summary Sheet

PROGRAMME TITLE: Lebanon CSSF Security Programme
Country/Region:	Lebanon (Middle East and North Africa –MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD)
Total Spend:	ODA: £6.96m[1]			Non-ODA: £8.80m[2]
Start Date: April 2016		End Date: March 2019
Outputs					Score
Lebanese Armed Forces (eight outputs)					A
Internal Security Services (six outputs)					A
Preventing Violent Extremism (three outputs)					A
Overall output score: A
Outcome Assessment: B
Outcome Score: B			Risk: High
[1] The difference between the final annual ODA expenditure (£6.96m) and the amount indicated in the Programme Document (£5.0m) is accounted for by ‘in year’ reallocations and uplifts of funding to the ISF and the PVE projects.
[2] The difference between the final annual non-ODA expenditure (£8.8m) and the amount indicated in the Programme Document (£9.0m) is accounted for by ‘in year’ reallocations and uplifts of funding to the LAF project.

Summary of Programme Performance[3]
[3] Although the Lebanon CSSF Security Programme in its current configuration began in 2016-17, previous configurations extend back to 2015-16, which explains the inclusion of previous Annual Review scores.

Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A	B
Risk Rating	High	High	High

*output/outcome scores

What support is the UK providing?

The UK is providing a total of £45.82m from FY 15/16 to FY 19/20; £15.76 in FY 17/18 to build Lebanese capacity to tackle threats to Lebanon and mitigate spill-over from the conflict in Syria. This support is delivered in three complementary areas, firstly building the capacity of the Lebanese Armed Forces (LAF), with a focus on enabling improved border security. Secondly, building capacity of the Internal Security Forces (ISF) and LAF to successfully manage domestic security issues and build community cohesion. Thirdly, supporting locally-developed peacebuilding and reconciliation projects.

Summary of progress and lessons learnt/actions taken since last review:

This review assesses the progress of the programme between April 2017 and March 2018. Overall, the programme is performing well and has built upon successful initial delivery of activity in the first half of the Spending Review period to demonstrate continued impact in meeting UK strategic objectives in Lebanon. This is set against a back-drop of an increasingly challenging security context as a result of the volatile situation in Syria, in particular, in relation to Da’esh. This has significantly affected the LAF element of the programme, yet delivery of the programme’s objectives has retained focus and adapted with admirable success to the new operating environment.

As was noted in the last Annual Review, the LAF-related activity continues to deliver benefits to Lebanon and to the UK Government’s efforts in the country. Its excellent reputation was clearly demonstrated in discussion with Lebanese stakeholders and in anecdotal evidence gathered in regular reviews by the programme team. The strong institutional links it has developed have already demonstrated the ability to withstand changes in host partners at senior levels and urgent operational demands. Both these aspects also serve to allow the Embassy access and influence far beyond the remit of the programme.

The implementation of the ISF Strategic Plan, developed and fully supported at the most senior levels of the ISF marks a positive change in this programme in the last FY. It was launched at the Lebanon – Rome II conference in support of the Lebanese security forces in March 2018. Key international donors have recognised the plan as a framework for their own interactions with the ISF and it has proven invaluable in cementing the UK as a thematic leader on policing and driving forward change according to HMG strategic objectives. The role out of station refurbishments continues following the successful pilot at Ras Beirut, also expanding the model to US provision of assistance. The systemic changes now embedded in the operation of the new station is, in the opinion of its users, transformational for this district and something that can withstand changes in personnel. Public trust in the ISF has increased in the area. The focus on intelligence-led policing and introduction of measures that encourage greater interaction between the community and the ISF is an encouraging new trend. Examples include the mobile policing of the Corniche and adapted facilities for women, juveniles and for domestic violence complainants. Reform of the ISF approach to Human Rights, public order and police training also continues according to targets.

The peacebuilding and reconciliation projects delivered by implementing partners MARCH and Adyan, non-governmental organisations, have continued to deliver or exceed expectations against output-level targets. There is interest among the UK Government in MARCH’s work in Lebanon and the programme team are engaging with other stakeholders to share their experience and knowledge.

Summary of recommendations for the next year:

Results Framework: The Results Framework should be reviewed in its entirety. There are currently issues related to the selection of the most appropriate metrics/data to demonstrate delivery at both output and outcome levels; a lack of weightings according to value and contribution to delivery of objectives. Delivery of impact towards UK Government objectives should be included across all strands i.e. Preventing Violent Extremism (PVE) from ISF and LAF. It would also be useful to capture, more formally, the implications of programming on the UK Government’s access and influence. The ITAD (Monitoring and evaluation consultants) review of the Results Framework and Theory of Change will assist on this point and the team should use this review document to inform their work. The inclusion of clear gender targets and milestones for all strands would better demonstrate consideration of and achievements in this area.

Overseas Security Justice Assessments (OSJA): Given changes in context and activity OSJAs for each programme strand should be reviewed. If activity related to the security services around Preventing Violent Extremism work is pursued, the PVE strand will also need an OSJA.

Recommendations for Annual Review 18/19:

Following recommendations from the last Annual Review, the opportunity to visit the border posts was extremely useful. Meeting with all implementers and some of the beneficiaries of the programme activity also added considerable value. There are a few things that would be useful to consider for the next Annual Review:

- Larger review team – three people (including a Monitoring and Evaluation expert)
- Field visits to all programmes – ISF/LAF/PVE – Adyan and MARCH
- Use of information gathered in the course of the planned external evaluation to include views from beneficiaries of all programmes – Senior ISF staff, Religious Leader Network members, Community Representatives in Tripoli and relevant area of Beirut.
- Review of programme team’s response to recommendations of the LAF external evaluation and the ITAD-led review of the Results Framework/Theory of Change.
- Well-ordered transfer of documentation – clear version control and demonstration of iterative development of documents, as appropriate.