## Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Morocco Country Programme
Country/Region:	Morocco
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD), Home Office (HO), National Crime Agency (NCA)
Total Spend for FY 17/18 :	ODA: £3.19m			Non-ODA: £0
Start Date: April 2017		End Date: March 2018
Outputs					Score
Key Moroccan government political reform commitments in line with the 2011 constitution supported, and Moroccan media and civil society more able to hold the Moroccan government to account and shape the public policy debate					A
Livelihoods are improved through tackling the skills gap, creating jobs, and improving the regulatory environment for business.					A
The Moroccan justice system is better able to serve and protect the population.					A+
Overall output score: A					A
Outcome Assessment: UK supported aspects of Morocco's 2011 constitutional reform agenda on track, risks of radicalisation reduced, economic opportunities improved
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2016/17	2017/18*
Programme Score	B	A	B
Risk Rating	Medium	High

*output/outcome scores

What support is the UK providing?

The UK is providing £3.19m to support delivery of the political, economic and security pillars of the National Security Council (NSC) regional strategy to address both the supply and demand-side drivers of instability at the local and national level in Morocco. The programme delivers a combination of interventions, particularly in Northern Morocco, developing youth skills and jobs through social enterprise and education; community engagement to build resilience against violent extremism; capacity development of parliamentarians to set the law; capacity development of regional councils to support the regionalisation process and capacity development of civil society organisations to hold the government to account to deliver.

Summary of progress and lessons learnt/actions taken since last review

During the financial year 2017/18, the programme delivered eight projects, two of which were originally in the Global Britain Fund (GBF) but moved to the CSSF in November 2017. Overall, there has been a good effort to address the recommendations from the 2017/18 annual review and work to increase synergies between projects which are complementary continues to make progress. The contribution to the political pillar is good, although the programme contains high risk projects which require close management. A key lesson learnt through implementation in 2017/18 is that projects are having positive impacts on the UK’s bilateral relationship. Another key lesson is that to achieve sustainable reform a longer delivery time is sometimes needed. A good example is the social enterprise project which benefitted from additional time to influence legislation. One important action that was taken in 2017/18 was the development of the Finance Risk Mitigation Tool which contributed to overall strengthened financial management.

Key achievements

The programme has experienced some impressive achievements both qualitative and quantitative, inside and outside of the results framework. These achievements are summarised briefly below:

The Prison Reform International (PRI) project has redrafted Morocco’s prison law in accordance with the UN Standard Minimum Rules for the Treatment of Prisoners, known as the Mandela Rules. Changing or improving laws in Morocco is a difficult process, however now that the law has been approved by the Moroccan Ministry of Justice and other stakeholders it will be debated in parliament (and hopefully passed) in 2018/19.

The Favourable Opportunities to Reinforce Self-Advancement for Today’s Youth (FORSATY) project has created over 1600 jobs and internships for disadvantaged youth in the peri-urban communities of Northern Morocco. Additionally, the British Council project awarded nine grants and further support to student social enterprises. One of the students that received a grant was invited to the 2017 UN Climate Change Conference in Germany.

The Parliamentary Parity and Equity Working Group was established to promote and ensure the harmonisation of draft laws with the constitutional rights of gender equality. The working group has been successful at ensuring that gender issues are considered in legislation on domestic violence, legal aid of marriage and penalties for perpetrators of violence. The project has also established an ad hoc Public Policy Evaluation committee that is already reported by the media as holding the government to account (according to feedback received).

Summary of recommendations for the next year

Make use of the available evidence, or strengthen the evidence base where there are gaps, to ensure that all activities contribute coherently to UK priorities, this will strengthen the programme narrative which can then be clearly communicated to stakeholders.

Ensure the team has the capability and capacity to hold partners to account by continuing to develop the right set of project management skills and incentives. Work with central London teams to develop these skills

Continue to strengthen the value for money offer of the programme and ensure that conflict sensitivity and gender sensitivity are consistently reflected in all projects. This will help to ensure that projects consider the different needs of men and women in a way that delivers the most impact and does no harm.

Build on efforts to create synergies between projects which are complementary, or which work towards the same objective, between Embassy teams which could strengthen either the design or delivery of projects, and with other actors (such as donors) that could multiply the impact of our work.

Address gaps in the risk assessment to ensure that key risks are being identified and mitigated in a meaningful way.