Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria Cross Cutting
Country/Region: Syria/MENA	Syria (Middle East and North Africa –MENA)
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID) and Ministry of Defence (MOD)
Total Spend :	ODA: £6.73m		Non-ODA: 0
Start Date: April 2017	End Date: March 2018
Approved extensions: Yes[1]	Was the programme closed early? No
Outputs				Output Score
Moderate Syrian values are promoted and the effectiveness of the moderate opposition and moderate governance, security, justice and service structures communicated to target audiences in Syria				A
Violations of international law and human rights and other abuses (e.g. Sexual and Gender Based Violence / Violence Against Women and Girls) documented and effective victim support provided				A
Information and analysis inform UK Government programming and activities of other donors/actors				A
Overall output score:				A
Outcome: / a) Increased awareness, trust and engagement of Syrians in moderate values and moderate systems of governance, security, justice and service provision / b) Foundation for transitional justice and accountability / c) HMG Syria CSSF and external humanitarian and development actors operating in Syria deliver more effective programmes
FINAL Outcome Score: A		Risk: High
[1] A number of projects within this programme have been extended in the 18/19 Southern Syria Programme (no longer active) and the Whole Syria Programme.

Summary of Programme Performance[2]
[2] 2015/16 and 2016/17 scores refer to reviews of previous cross-cutting programmes in the Syria CSSF portfolio.
Year	2015/16	2016/17	2017/18*
Programme Score	B	A	A	A
Risk Rating	High	High	High

*output/outcome scores

What support did the UK provide?

The cross-cutting strand of the Syria CSSF Programme provided support in three distinct areas:
1. Strategic communications activities to promote and amplify moderate Syrian voices and to amplify content generated by other strands of the CSSF;
2. Documentation of human rights abuses, particularly sexual and gender-based violence, in preparation for any current or future transitional justice purposes;
3. Independent and credible third party monitoring of CSSF programming in Syria, through the collection of data and production of information products to support monitoring, evaluation and learning.

What results did the programme deliver? Will results be sustained?

The cross-cutting strand helped to make the Syrian conflict perhaps the well-documented war ever. Thanks to CSSF support, there is sufficient documentation, from credible sources and with a chain of custody, to enable credible criminal as well as civil actions against war crimes perpetrators. This is a permanent contribution to the historical record of the Syrian conflict. The programme has made a laid a strong foundation to advance accountability processes, in particular through working in partnership with the United Nations’ International, Impartial and Independent Mechanism (IIIM), the mechanism seeking to support accountability processes aimed at bringing about justice for the victims of serious international crimes committed in Syria since March 2011. The strand also ensured that moderate voices within Syria could be heard, and that human stories exposing the level of suffering under regime attacks could be told.

What lessons have been learned?

It is extremely difficult for organisations to operate in Syria. Most of the UK’s partners do so from headquarters in Turkey. This presents challenges to duty of care, risk management, and results verification, which partners have navigated well. Projects in this context have also had to be highly flexible and adaptive in response to the conflict itself and to changing UK funding priorities.