Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria Political
Country/Region:	Syria (Middle East and North Africa – MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £3.74m[1]			Non-ODA: 0
Start Date: April 2017		End Date: March 2018
Approved extensions: Yes[2]		Was the programme closed early? No (although one project under the programme was closed early)
Outputs					Score
Civil Society Organisations (CSOs) develop and sustain effective partnerships that improve collaboration, reduce duplication of efforts, and assist collective advocacy					A+
Networks and links built between local peacebuilders, civil society leaders, and higher level political dialogue and peace talks, including broad representation					A
Local peace building activities implemented					A+
Broad and representative range of Syrian actors discuss points of difference and commonality and wide audience of Syrians, international policymakers and other Track II implementers are informed of these					A
Effective mentoring of High Negotiations Committee (HNC) and key Syrian partners (including women, civil society and opposition) to help build their skills and confidence to present and respond to negotiation proposals that convey the interests of the Syrian people more broadly during negotiations					B
Materials delivered to HNC and key Syrian partners to support development of clear policy position					A
Overall output score: A
Outcome assessment: Taken at face value, this programme largely met its outcomes. However, it is difficult to assess the “real-world” meaning of many outcome indicators, as their definitions, measurement, and sources of verification generally lack clarification in the programme results frameworks. That said, interviews and reporting overall support the assessment for Track I and II activities. The Track III project was closed early and thus did not deliver at the outcome level.
FINAL Outcome Score: A			Risk: High
[1] The initial £5m budget was reduced to £3.87m within year, responding to the evolving political context within which the programme operated.
[2] A number of projects within this programme have been extended in the 18/19 Whole of Syria: Support to a Political Process programme. This includes continued support to community engagement and civil society.

Summary of Programme Performance[3]
[3] 2015/16 and 2016/17 scores refer to reviews of previous political programmes in the CSSF Syria portfolio.
Year	2015/16	2016/17	2017/18*
Programme Score	B	B	A	A
Risk Rating	Medium	High	High

*output/outcome scores

What support did the UK provide?

The CSSF Syria Political programme was designed to support the objective of achieving an inclusive political settlement leading to representative and competent Syrian local and national governments. The programme comprised three tracks:

Track I: Opposition is able to set out political vision and participate effectively in negotiations. Under this track, Independent Diplomat (ID) provided strategic and tactical advice to the HNC/Syrian National Council (SNC) and facilitated international and media engagement. Public International Law and Policy Group (PILPG) provided legal-technical assistance for negotiations. 2017-18 was a continuation of support provided through the two implementers since April 2015 and April 2016, respectively.

Track II: Informal high-level dialogues broaden the political process and improve inter- and intra- communal understanding. A continuation of UK support commenced in September 2015, The Shaikh Group (TSG) continued to facilitate consensus-building among a diversity of influential Syrians.

Track III: Community-level dialogue reduces communal and sectarian tensions, and lays the groundwork for a sustainable political settlement. As of 2017-18, civil society support was brought under the political strand of Syria CSSF programming. Previous support was phased out in the first quarter, when a new Syria Peacebuilding Programme (SPP) was tendered to sharpen the focus on inter- and intra-communal dialogue and peacebuilding and to facilitate links between Track III and Tracks I and II.

What results did the programme deliver? Will results be sustained?

A CSSF programme, alone or in conjunction with other UK efforts, cannot be expected to deliver an objective of “an inclusive political settlement” in the Syrian context, however successful it is in delivering its outputs and outcomes. That said, the programme did largely achieve its stated sub-objectives and supported UK political efforts. While it’s difficult to attribute progress directly to CSSF projects, Track I efforts overall responded well to opportunities and HNC/SNC needs as they arose, and positive feedback from reporting and interviews indicates that overall, the Syrian Opposition has significantly increased its capacity to articulate coherent positions on a range of topics, has increased its public profile, and has influenced the international community.

Likewise, Track II dialogue contributed to consensus-building among a diversity of elite representatives. The project fed into Opposition positions and Track 1 negotiations, TSG also achieved some initial momentum in a Joint Track with a range of Syrian voices issuing a paper with recommendations for a refreshed political process. However, by the end of the programme year, there had been no revival of Track I negotiations, raising questions about the relevance of the programme’s objectives. For reasons internal to the consortium as well as changes in the context and HMG policy and priorities regarding peacebuilding and activities in regime- and Kurdish-held areas, the civil society-focused Syria Peacebuilding Programme struggled to get off the ground and would have required significant reconceptualisation to deliver in year two. It was ultimately decided to close the SPP after eight months of implementation. There are some indications, however, that individual CSO partners may take forward elements of SPP activities with other donor support.

What lessons have been identified?

Monitoring and evaluation has been a recurring theme in previous annual reviews. This is the first year the programme is compliant with the basic CSSF requirement, i.e. to have a results framework in place. Although the results framework is not underpinned by an overall theory of change, it makes an effort to connect outcomes to outputs across projects. However, some are quite difficult to understand or simply repeat the same indicators for outputs and outcomes. Indicators and targets need to be reviewed according to a more rigorous and methodical approach, with an emphasis on SMART (Specific, Measurable, Achievable, Relevant, Time-bound) indicators and qualitative targets at outcome level. The team has utilised independent monitoring resources. Based on interviews, this is more informative as far as the overall utility of projects to direct and indirect beneficiaries – but doesn’t address outcomes as specified in results frameworks. Future programming should consider more systematically incorporating independent monitoring that also assesses results against specific objectives/outcome targets.

The short-lived SPP programme occasioned a number of lessons at programme and CSSF level. Among other issues, tender and start-up processes need to allow sufficient time for partners to work out basic expectations and working relationships, particularly where consortiums are expected to comprise quite diverse organisations, including possibly local CSOs whose primary experience is as grantees. Also, the latter could effectively be prohibited from joining consortiums led by commercial organisations, unless CSSF contracting/financial guidelines could be reviewed for options to allow prepayment to non-profit subcontractors. As a broader lesson, it may be worth considering whether one-year CSSF cycles provide a suitable framework for consortiums more generally, given the time it requires to establish such complex programme setups.

The effectiveness and credibility of Track I and Track II support depended critically on HNC/SNC and other Syrian counterparts trusting implementers to provide independent advice and dialogue facilitation, unbiased by any particular government’s view. Implementers were transparent about their funding, but also highly protective of their independence, to the point that some materials were never shared with the FCO. The issue of independence vs. risk management will be a challenge to any such programme. To manage the risk profile of the programme and to allow the UK Government to assess whether programming supports (or at least doesn’t contradict) UK objectives, future programming may consider requiring access to materials such as press briefings at least after the fact. The point would not be to interfere in the short term, but rather to be able to assess benefits against risks for forward programme planning.

Split project management and monitoring between Istanbul and Beirut was a challenge. Given the politically sensitive nature of the programme, it is understandable that many decisions were taken on a case-by-case basis, but more could have been done to provide clear steers for implementing partners and to ensure clarity of contact points and unified messaging across UK Government interlocutors. Similarly, from a programme management perspective, split offices make it even more important to ensure consistency in e.g. file management, to enable read-across and ease the challenges of staff turnover, absences, etc.