Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria CSSF Security Programme
Country/Region:	Syria (Middle East and North Africa –MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend:	ODA: £14.95m[1]			Non-ODA: 0
Start Date: April 2017		End Date: March 2018
Approved extensions: Yes		Was the programme closed early? Yes[2]
Outputs					Score
Basic community policing and justice services provided					A
Short-term support for stabilisation and to address priority community needs					A
Overall output score					A
Outcomes: / Security and justice actors respond effectively to community needs / Rapid, effective and coordinated support meets priority community needs and promotes stabilisation
FINAL Outcome Score: A			Risk: High
[1] The budgets for both projects within the Syria CSSF Security Programme were increased during the year.
[2] The security programme in its current form will not continue in 2018/19 as individual projects have been reorganised into geographical strands. As such a decision was made at this juncture to undertake a programme completion review as has been done with other programmes in the Syria CSSF portfolio.

Summary of Programme Performance [3]
[3] 2015/16 and 2016/17 scores refer to previous security programmes in the CSSF Syria portfolio.
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A	A
Risk Rating	High	High	High

*output/outcome scores

What support did the UK provide?

The UK has provided funding to projects which have aimed to support provision of effective and responsive security and justice services to local communities in Syria and deliver rapid, effective and coordinated stabilisation effect to communities in both Northern and Southern Syria. Projects in this programme:
- Access to Justice and Community Security (AJACS): community policing in Aleppo and Idlib provinces, as well as the South;
- Stabilisation Response Mechanism (SRM): stabilisation interventions to support community resilience and address where gaps arise in the rest of our programme.
What results did the programme deliver? Will results be sustained?

Despite a highly challenging context and the continued contraction of operating space, the security strand projects have made significant achievements. There is also some early evidence of their contribution to higher level Syria National Security Strategy objectives.

- AJACS is assessed to be delivering security and justice services to over one million Syrians through the Free Syrian Police (FSP). Community perceptions demonstrate that these services are highly valued. The project has also provided vital support to significant numbers of people to provide them with critical civil documentation, allowing them to register births, marriages and divorces, register children for school, pass checkpoints and receive humanitarian assistance.
- SRM has continued to provide stabilisation support in Northern and Southern Syria, successfully implementing 31 projects[4] between April 2017 - June 2018 ranging from support to local councils, education programmes, social cohesion and infrastructure. It also played a key coordinating role in the planning of stabilisation efforts in Idlib and the delivery of a peace dividend in support of the de-escalation area (DEA) in Southern Syria.
  [4] 20 projects were successfully implemented in the North; a further five were designed but not implemented in full due to changes in the conflict dynamic and increased risk. 11 projects were implemented in the South, a further two were designed but not implemented due to project closure.

Sustainability of these results is a key concern as the programme moves into its fourth year (albeit under a revised, geographical structure). Constriction in the operating space and the heightening of several key risks to the projects means that some will be drawing down in the coming months- future conflict dynamics are likely to be the overbearing factor on the sustainability of results.

In the South, the future of the programme and sustainability of results rests on the future of the DEA. However, whatever happens, there will be a lasting legacy to these projects - AJACS support to the FSP has created expectation among communities in Syria on how effective community policing can be delivered and this is unlikely to disappear if support to the programme ceases. Similarly SRM, has created an expectation amongst the local population that the Provincial and Local Council can provide and improve local services and support community resilience in the longer-term.

What lessons have been learned?

The fast changing context has necessitated learning and adaption throughout the life of the Strand’s projects and this was evident across the projects. One of the key lessons from the programme has been the importance of a strong research capability, providing regular contextual/situational analysis and results verification to inform programme decision making. However, this has not been enough to drive timely policy. The UK needs to learn from the challenges of working in a context where fast-changing events and territorial shifts quickly make policy decisions and direction obsolete.

The importance of cross-project coordination has also been demonstrated to be vital, particularly in the example of attempting to carry SRM quick impact projects into longer term programming. However, this needs to be clearly articulated at programme inception and parameters set to avoid overburdening partners.

Lesson learning by implementing partners has also drawn out key lessons of operating high risk projects in conflict and fragile states and has highlighted the need for; a thorough inception phase to fully understand conflict dynamics; better communication between donors and implementing partners on risk- including red lines and risk appetite; more regular programme oversight and review to better manage risks and ensure policy and programme decisions remain connected with the operational context.