Annual Review - Summary Sheet

PROGRAMME TITLE: Tunisia CSSF Economic and Governance Programme
Country/Region:	Tunisia
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office, Department for International Development, Ministry of Defence, National Crime Agency and Home Office
Total Spend:	ODA: £3.86m			Non-ODA: £0m
Start Date: April 2017		End Date: March 2018
Outputs					Score
Output 1 - Economic growth is more inclusive and generates jobs for marginalised groups (youth, women and underserved regions).					B
Output 2 - Organisation for Economic Co-operation and Development (OECD) project identifies main corruption risks to business and public service in three regions to allow targeting of interventions in financial years (FY) 18-20.					B
Output 3 - To develop government strategic communications plan delivering clear messages on economic reforms.					A
Overall output score					B
Outcome Assessment: / Outcome 1: Economic and employment growth driven by the private sector - likely met expectation (A) / Outcome 2: Improved finance and regulatory systems allows growth of private sector (including Micro Small Medium Enterprises and startups) - likely to be met (A) / Outcome 3: Government of Tunisia (GoT) has greater capability in delivering strategic communications campaigns improving confidence and awareness in private sector opportunities - likely to be met (A) / Outcome 4: A reformed education sector delivering high quality English language teaching and reducing school dropout rates - leading to meeting private sector needs for a skilled workforce - unlikely to be met (C)
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	B	A
Risk Rating	M	M	M

*output/outcome scores

What support is the UK providing?

The Tunisia Economic and Governance Programme aims to deliver results against the National Security Council NSC Strategy for the North Africa Region 2016-2020 by supporting small and medium enterprises (SMEs) to grow and create jobs. In 2017/18, the programme focused on reforming the financial sector to improve businesses’ access to finance; strengthening the GoT’s communications and anti-corruption capabilities; and helping decrease high school drop-out rates.

The programme was delivered through six projects, implemented by a diverse set of implementing partners, including a UK Government partner, multilateral institutions, and commercial suppliers.

Summary of progress and lessons learnt/actions taken since last review

The programme made important progress across all six projects over the last year. Some key achievements include:

- 129 SMEs successfully finalised business plans and many have submitted requests for funding to the African Development Bank’s (AfDB) project selection committee.
- The roll out of phase 2 of Innajim, a national female entrepreneurship communications campaign.
- The launch of Nheb Nkadem, a national communications campaign on economic reforms.
- The passing of the Electronic Exchanges and Electronic Commerce Law, developed with technical support from the World Bank.

Despite the progress made, the programme, overall, did not meet expectations as only one of the three projects captured in the programme results framework achieved its milestone targets for the period. However, it must be noted that this was not because projects were not achieving results, but because some of milestone targets in place in the programme’s results framework (RF) at the time of the review were unsuitable or unrealistic given contextual changes. This is partly due to limited resources within the CSSF programme team, which meant that the available capacity was mostly dedicated to ensuring delivery, rather than on strengthening monitoring and evaluation (M&E). The team have begun addressing this issue by engaging support from an M&E Adviser from the DFID/FCO North Africa Joint Unit (NAJU) and launching a process to contract a specialised M&E provider to support them to strengthen the programme’s M&E, including by refining its results framework.

Summary of recommendations for the next year

The NAJU should support the CSSF programme team to develop the theory of change (ToC) and results framework (RF) for 2018/19 through a ‘blank canvas’ approach, which is not constrained by the programme’s existing projects. To determine what economic and governance outcomes the UK wants to achieve and how, the CSSF programme team should develop its theory of change on the basis of the rich body of analysis it has undertaken to date. By ignoring the current portfolio of projects, the process will avoid path-dependency, ensuring future projects are based on an objective analysis of the problems and UK comparative advantage rather than what is already being done.

The CSSF programme team should review the education programming currently planned for 2018/19 to assess whether it is in line with the theory of change. Drawing on existing analysis by established institutions such as the World Bank, the AfDB, and the International Labour Organisation, the review should test whether the proposed project will effectively address the problems in education which are most directly constraining Tunisia’s economic growth and unemployment rate.

The Country Programme Board should consider using the programme, in line with the CSSF’s risk appetite, as a means to secure and facilitate catalytic investment in sectors where marginalised regions have growth potential through linkages to coast or external markets, including by using programme funds as guarantees or as seed funding for high-risk investments.

The CSSF programme team should secure the support of a DFID Conflict Adviser to conduct a conflict risk assessment of the programme in order to develop conflict sensitivity standards.