Annual Review - Summary Sheet

PROGRAMME TITLE: Yemen CSSF Country Programme
Country/Region:	Yemen (Middle East and North Africa – MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Spend:	ODA: £4.71m			Non-ODA: £0.16m
Start Date: December 2015		End Date: March 2018
Outputs					Score
UN Special Envoy access to expertise/communications					B
Increased diversity of Track II and Track III initiatives					A
Increased influence of UK on stabilisation and maritime security					B
Increased activity at local level contributing to peacebuilding and stabilisation					A
Overall output score: B
Outcome Assessment: Overall there is mixed evidence that the programme is achieving at impact level and therefore addressing National Security Council (NSC) objectives. At the outcome level, results in some areas have been less than expected. Nevertheless, there are clear mitigating factors for this, attributable largely to the ongoing civil war and overall lack of progress in the peace process by March 2018. The overall theory of change and approach of the programme remains correct, and the programme was correct to diversify projects.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	B/B
Risk Rating	High	High	High

*output/outcome scores

What support is the UK providing?

The 2017/18 Yemen CSSF programme aims to (1) support the UN in delivering the Track I peace process and prepare the ground for more inclusive political dialogue; (2) help stabilise parts of Yemen affected by the conflict; and (3) contribute to conflict prevention and mitigation in parts of Yemen where the social fabric is under strain. The programme includes stabilisation, conflict management and peacebuilding as well as its original focus supporting the political process. This diversification was considered necessary, both to prevent conflict from spreading and build confidence in areas of high fragility.

Summary of progress and lessons learnt/actions taken since last review

The programme represents the second full year of programming since the British Embassy’s evacuation from Sana’a in early 2015. Yemen remains a high risk and challenging operating environment, despite this several of the projects have made some progress over the review period.

- Support to the UN Special Envoy’s Office. The UK has helped in supporting the Special Envoy make progress should wider contextual conditions permit. This is especially important as the new Special Envoy sets out his vision for the peace process and way forward.
- Peacebuilding Pilots: This represented a strategic diversification of the programme and has performed well (according to third party monitoring) acting as a proof of concept and potentially creating space for DFID bilateral programming to take this on.
- Maritime Security Adviser: The importance of this role has increased during the reporting period, and this remains a strong example of CSSF adding value to the cross-government effort in a difficult humanitarian, conflict and policy environment. The advisor’s access and influence, as well as his ability to pivot towards DFID’s humanitarian objectives have been key.
- Demining Project: demining and Unexploded Ordinance (UXO) work has exceeded targets and will now be picked up by DFID funding.

The Annual Review found most of the recommendations from the 2016/17 Annual Review were addressed, with a number remaining relevant including:

- The need to commission a public opinion survey to deepen understanding of the diverse needs of Yemenis
- Production of an overall diagrammatic theory of change and results framework to articulate what the programme seeks to achieve from a strategic/impact level
- Continue to use evidence to drive programming
- Develop and apply a Value for Money (VfM) framework
- Share lessons from other teams working in similar circumstances (remote management in hot conflict settings)

Summary of recommendations for the next year

Overall: The decision to diversify the programme to both widen access to the peace process (Track II) and include peacebuilding and stabilisation interventions was the correct approach. The pilot approach to working in Yemen is still appropriate given the difficult context (remote management, active conflict, policy, limited potential partners). Progress against several of the projects has stalled for a variety of reasons but primarily the lack of progress in the peace process. The programme team should avoid running too many different projects as a means to respond quickly to contextual change to avoid these become legacy. The perceived risks of closing down under-performing programmes is often erroneously considered to be higher in the hope of maintaining flexibility.

Stabilisation: Agreeing a cross-government stabilisation strategy that sets direction and a level of realistic ambition remains a priority. Programming options should also be reconsidered in line with this strategy.

Monitoring and Evaluation: With the support of monitoring and evaluation advisors, prioritise the revision of the results framework, theory of change, and implementation of the new 2018/19 Monitoring, Evaluation and Learning Plan.

Implementer Coordination: There is a need for greater coordination amongst the UK funded Implementing Partners (IP) platform, as well as the need to widen out coordination to other donors/donors IPs based on geographic or thematic issues. The planned move of the programme team to Amman will make this easier.

CSSF-funded advisors: Such positions can be key, providing technical assistance and influence. The maritime position in particular has been an excellent value add for the UK Government. There should be strong consideration by MoD to transition this from a six month deployment to 12 months to build on access and influencing opportunities.

Building legitimacy through service delivery is a key area in a fragile context, but can be expensive to do this at scale. The underpinning programming approach needs to be clearer and linked to the new UK Government stabilisation strategy.

Donor Coordination: While the pilot approach to interventions has shown success in transitioning support to DFID bilateral fund, this programme was also acting as “proof of concept” to the UN and other donors. Although this may be too early for the Yemen programme to consider this, the team should be able to articulate a strong strategy of influencing other donors.

Countering Violent Extremism: To deliver against NSC objectives the team should explore drivers and programmatic links through research into the drivers of extremism in Yemen.