Annual Review - Summary Sheet

PROGRAMME TITLE: Tunisia CSSF Security Programme
Country/Region:	Tunisia
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office, Department for International Development, Ministry of Defence, National Crime Agency & Home Office
Total Spend:	ODA: £2.74m			Non-ODA: £0.6m This is higher than in the original 2017/18 programme budget. A project that was originally split between ODA/non-ODA became fully non-ODA in-year.
Start Date: April 2017		End Date: March 2018
Outputs					Score
Output 1 - Mentoring and coaching to Ministry of Interior (MoI) to establish strategies and/or national strategy actions plans on Counter Terrorism (CT), Counter Violent Extremism (CVE) and borders which follow the strategic planning methodology delivered by the UK Government in financial years (FY) 15-17 & reform the security sectors training system to incorporate this methodology.					A
Output 2 - UK expertise contributes to building an effective Tunisian counter-narrative platform.					C
Output 3 - Increased activities delivered to Tunisian border security forces to increase capability to operate resources in line with operational need.					A+
Output 4 - United Nations Development Programme (UNDP) activities to increase local capacity for tackling CT/CVE through improved police to citizen engagement on local security issues in two governorates.					C
Output 5: Training of Tunisian interior security forces and criminal justice practitioners to understand human trafficking and migrant smuggling, and how to apply the new anti-human trafficking law.					B
Overall output score					B
Outcome Assessment: / Outcome 1: Increased strategic planning by the security system affording to greater inter-governmental co-ordination and consensus – likely to be partially met (B) / Outcome 2: Increased capability of the Government of Tunisia (GoT) to counter extremist narrative and enable increased CT co-ordination – unlikely to be met (C) / Outcome 3: Increased effectiveness of GoT's border control in order to better manage threats to security, including terrorism and organised crime – likely to be partially met (B)
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	B	B
Risk Rating	M	M	M

*output/outcome scores

What support is the UK providing?

The Tunisia Security Programme aims to deliver results against the National Security Council (NSC) Strategy for the North Africa Region 2016-2020 by strengthening the Tunisian government’s capabilities to better manage threats to Tunisia’s security and effectively address issues which undermine public trust in the state’s security system. In 2017/18, the programme was comprised of the three strands:

- Integrated Strategic Planning (ISP) – Support the GoT security institutions to be more responsive to the public’s security and justice needs, more accountable and trusted by the Tunisian people, and more efficient and effective in combatting key security threats.
- Countering Violent Extremism (CVE) – Support the GoT to be more effective in contesting extremism, preventing radicalisation, and positively effecting attitudinal change.
- Borders – Support to the GoT to develop a more cohesive and integrated approach to border management; and improving GoT investigation and prosecution of human trafficking crimes.
The programme was delivered through six projects—one under ISP, two under CVE, and three under the Borders strand—implemented through cross-UK Government departments, multilateral institutions, commercial suppliers, and international non-governmental organisations.

The Security Programme complements other UK-funded security programming in Tunisia.

Summary of progress and lessons learnt/actions taken since last review

The programme made important progress across all three strands over the last year:

- Under ISP, the programme supported the development of a Borders strategy and of 18 ministerial action plans for implementation of the GoT’s 2016 Counterterrorism Strategy (CT Strategy).
- Under CVE, the programme supported the roll-out of a national communications campaign for youth (providing alternative, inspirational narratives to counter extremism) as well as the implementation of the GoT’s community policing strategy, including by refurbishing four new police/National Guard stations and setting up and training four new local security committees.
- Under Borders, the programme successfully trained 77 armed forces personnel in Intelligence, Surveillance, and Reconnaissance (ISR) and nearly 700 law enforcement and judicial officials in improved identification, investigation, and sentencing of human trafficking cases.

Despite the progress made, overall, the programme moderately did not meet expectation as three out of the five projects captured in the programme results framework did not achieve their milestone targets for the period. However, it must be noted that this was not because projects were not achieving results, but because some of the milestone targets set in the programme’s results framework (RF) were unrealistic given contextual changes. This is partly due to limited resources within the CSSF programme team, which meant that the available capacity was mostly dedicated to ensuring delivery, rather than on strengthening monitoring and evaluation (M&E). The team have begun addressing this issue by engaging support from an M&E Adviser from the DFID/FCO North Africa Joint Unit (NAJU) and launching a process to contract a specialised M&E provider to support them to strengthen the programme’s M&E, including by refining its results framework.

Summary of recommendations for the next year

The CSSF programme team, with support from NAJU, should develop a new theory of change for the security programme through a ‘blank canvas’ approach, which is not constrained by the programme’s existing projects. To determine what security outcomes the UK wants to achieve and how, the CSSF programme team should develop its theory of change on the basis of the rich body of analysis it has undertaken to date, ignoring the current portfolio of projects. By doing so, the process will avoid path-dependency, ensuring future projects are based on an objective analysis of the problems and UK comparative advantage rather than what is already being done.

Any future work on strategic planning should focus on longer-term reform, rather than building technical capacity. The CSSF programme should adopt a problem-driven iterative adaptation (PDIA) approach, an adaptive evidence-based process to identify the problems with local stakeholders and the possible entry points to solve them, in order to build coalitions for reform within the Government of Tunisia’s security services. With top-level buy-in, strategic planning support should focus fully on planning for reform priorities, with any future operational work with the Tunisian security services entirely linked to delivering against these.

The CSSF programme should continue to support the roll out of the community policing model across Tunisia, but by focusing on strengthening the GoT’s central capacity to plan and implement the roll out themselves. The programme should continue its planned shift from directly supporting infrastructure and training to providing technical support to strengthen the GoT’s planning, financial management, procurement, and human resource management capabilities. The programme should also include women’s desks into the Tunisian police station model to ensure dedicated services to women.

The CSSF programme team should engage with other donors supporting security sector reform and CVE programmes to ensure complementarity and to learn lessons. This will be essentially not only for the UK to better understand what other donors are doing (avoiding replication and clarifying the UK’s comparative advantage), but will help the CSSF to adapt its programming in line with other donors’ lessons.