Annual Review - Summary Sheet

PROGRAMME TITLE: Migration: Central Route
Country/Region:	Aegean & Mediterranean seas
HMG Partners / (LEAD in bold)	Home Office (Border Force), Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £5.03m			Non-ODA: £0.5m
Start Date: April 2017		End Date: March 2020
Outputs					Score
Deployment of BF cutter to Aegean Sea and Central Mediterranean to conduct search and rescue (SAR) operations in line with Frontex operational requirements.					A
Support Libya’s better management of borders (no output in Results Framework and therefore not formally reviewed in this review).					U
Overall output score: A
Outcome Assessment: A
Outcome Score: A			Risk: Medium/High

Summary of Programme Performance[1]
[1] The BF Cutters were funded through the ODA Crisis Reserve in FYs 15/16 and 16/17, in response to the Mediterranean migration crisis, and therefore not subject to CSSF review in the normal way.
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	N/A	A	A
Risk Rating	N/A	N/A	Medium/High

*output/outcome scores

What support is the UK providing?

The Central Route Migration programme aims to reduce loss of life in the Mediterranean and Aegean seas. CSSF funding supports Search and Rescue (SAR) activity through the deployment of two Border Force (BF) Cutters, as well as capacity building of the Libyan Coast Guard to enable better management of Libyan maritime borders.

The UK Government’s strategy for tackling illegal migration includes leaning into EU and international efforts to reduce the flows of illegal migration into the EU, and across the EU into the UK. On SAR, the UK support to operations in the Aegean and Mediterranean demonstrates commitment to resolving the humanitarian situation as part of the wider work to reduce flows into Europe.

The Central route is one of four programmes to support HMG’s strategy on illegal migration, working towards a stronger UK immigration system, a stable EU and a global approach to refugee and migration policy in order to protect UK security and economic interests and limit the risks to migrant.

BF vessels have supported humanitarian operations since May 2015, during which time they have rescued a total of 18,248 migrants. The UK’s contribution of resources has been well received by European partners who value the UK tactical response to a shared issue.

Summary of progress and lessons learnt/actions taken since last review

Last year’s recommendations highlighted in bold:

The primary output of SARs to save lives has been met. There have also been other secondary benefits such as the identification of facilitators, strong collaboration with EU partners and some evidence to suggest the contribution of political capital which demonstrate the value of continued deployment to conduct humanitarian SAR operations. Primary outputs and outcomes of SAR humanitarian operations continues to be met. Secondary benefits such as the identification of facilitators is enabling secondary benefits to UK law enforcement agencies, and collaboration with EU partners through mechanisms such as Frontex is positioning the UK as a niche player in EU efforts against irregular migration.

The Annual Review confirms that there is value in continuous engagement with European stakeholders to manage tasking and relative priorities for BF vessels (both in the Central Med and Aegean). Continuous engagement with European stakeholders is not providing effective intelligence led tasking of the two BF vessels to proactively support humanitarian efforts. Through this process, there is scope to influence the intelligence cycle and tasking process further.

There has been positive feedback from partners and anecdotal evidence to suggest increased political capital. Scoping work should be taken forward to measure whether EU influence can be recorded as an output and how to measure this effectively. There continues to be positive feedback from partners and anecdotal evidence to suggest increased political capital. However scoping monitoring and evaluation work to record political influence remains outstanding.

Summary of recommendations for the next year

Identify ways of influencing and improving FRONTEX intelligence reporting and assessment so that it can provide actionable start points for interdiction and migrant rescue operations. Interlocutors highlighted the extent to which FRONTEX products were currently geared towards capitals and generalist audiences, rather than towards enabling operational and tactical level activity.

Consider opportunities to conduct target development through existing (Organised Immigration Crime Task Force and National Crime Agency) support to the Hellenic Police, aimed at identifying maritime interdiction opportunities on the Aegean route. The review team accepts that the BF cutters do not currently have the mandate or force protection package required to act as an interdiction action and that such maritime disruptions would therefore need to be conducted by Hellenic Coast Guard (who have their own special forces) and FRONTEX assets.

Wider intelligence dividends, such as unusual sightings of maritime smuggling activity should be formally articulated as part of the BF Cutters’ mandate (noting possible ODA limitations) as well as captured within the programme documentation/results framework, in line with the logic of the UK’s new Fusion doctrine. The BF Cutter crew has, for example, already generated some useful insight into both state and non-state actor related smuggling activity.

Diplomatic dividends have clearly been generated through the deployment of the BF Cutters. These should be more clearly articulated within the Results Framework as a key project outcome, especially given the extent to which key stakeholders (including the Hellenic Coast Guard) highlighted the value of the UK’s contribution. This has also been reflected in Greece’s request for an additional BF Cutter in the Aegean.

Consideration should be given on how to improve or better generate, coordinate and share international actionable information/intelligence relating to the interdiction of migrant smugglers. FRONTEX and EUROPOL ought to operate more effectively as regional fusion centres capable of producing actionable products.

A Turkish liaison officer to FRONTEX would also likely improve intelligence sharing on smuggling activity and interdiction opportunities. The UK could play a pivotal role in influencing and brokering this placement through FRONTEX.

Opportunities to facilitate Turkish and Hellenic coast guard communication should also be considered, such as through bi-annual workshops or conferences (if appropriate). One avenue for lobbying Turkey on this approach might be through the already-established Bosporus Group discussions, which should also include a UK/Turkish dialogue on known embarkation points on the Turkish coast.

Consider conducting an organised immigration crime Serious and Organised Crime Joint Analysis (SOCJA) assessment focussed on the Aegean route focussing on understanding smuggling networks as well as the wider business model, vulnerabilities and entry points for further UK Government-supported interventions.

Generate a better understanding of some of the conflict sensitivity issues tied to Non-Governmental Organisation migrant-rescue and coalition migrant rescue operations in the Mediterranean and how this could impact the UKs reputation.

Generate much stronger reporting on the activities and impact of funds directed at helping the Libyan coast guard better manage its borders.