Annual Review - Summary Sheet

PROGRAMME TITLE: Migration – Eastern Route
Country/Region:	Turkey, Greece, Serbia
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO) / Home Office (HO)
Total Spend :	ODA: £ 4.34m			Non-ODA: £0
Start Date: April 2017		End Date: March 2019
Outputs					Score
Improving Migration Management in Turkey					A
Supporting Migrant Integration in Turkey					B
Strategic, policy and training support to Directorate General Migration Management					A
Expert staff to Greece under the EU-Turkey deal					C
Serbian Migration Systems					U
Overall output score: B
Outcome Assessment:
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	Amber/Red	B	B
Risk Rating	N/A	High	Medium

*output/outcome scores

What support is the UK providing?

The CSSF Eastern Route Programme delivers against the objectives in the UK Government’s Illegal Migration Strategy.
The programme includes projects designed to support and continue to build capacity in Turkey’s frontline migration institutions and develop Turkey’s migration policy framework, working with the Directorate General of Migration Management (DGMM), the Ministry of Interior, the Ministry of Labour and others.

In Greece, the programme supports the EU-Turkey deal by providing specialist deployments to the EU Commission in Athens and migrant camps on hotspot islands, and providing expert support to the European Asylum Support Office. UK staff work to support improved living and security conditions for migrants on the Greek island hotspots.

In Serbia, the programme contributes to capacity development of asylum and migration authorities’ adherence to international standards in the area of asylum and migration, including by using UK expertise.

Summary of progress and lessons learnt/actions taken since last review

This is the first year that the Eastern Route programme as a whole has been in existence and subject to an Annual Review. In 2016/17 the Turkey programme was examined as part of an overall Migration Returns Fund review. The Greece programme has not been reviewed since its inception.

There has been significant progress over the year in the management and delivery of projects in Turkey. A process of consolidation has led to fewer, more manageable projects some of which are beginning to deliver tangible results. Work with the relatively newly formed Directorate General of Migration Management stands out with interventions providing important support to the development of new policy and structural reform in key areas. The programme in Turkey has also continued to make progress in supporting Turkish institutions responsible for migrants and refugees to comply with international human rights standards.

The programme in Greece came about at the height of the migrant crisis and in support of the implementation of the EU-Turkey deal. The direct bilateral UK contribution to the running of two of the migrant camps on hotspot islands, involving the deployment of expert staff, has been well received. The context has shifted in the two years since the deployments, however, it was concluded that now was a good moment to conduct a more detailed strategic review of this intervention to ensure that it remains impactful and continues to represent value for money.

Key lessons centre on two areas. Firstly the importance of ensuring that interventions conceived initially in a crisis management/ humanitarian context are reviewed as the crisis abates to ensure that they remain relevant. Secondly that integrated working on migration issues are really important. In both Turkey and Greece the programmes are one element of a wider portfolio of the UK Government’s migration related work. Ensuring that governance mechanisms are in place to drive forward an overall strategy is important.

Summary of recommendations for the next year

Recommendations from this review focus broadly on the need to continue the process of strategic consolidation in Turkey, and initiating a more fundamental review of the approach in Greece given the changing context. In addition, both programme elements and the programme as a whole need a clearer, more achievable results framework and theory of change.