Annual Review - Summary Sheet

PROGRAMME TITLE: Countering Violent Extremism (CVE)
Country/Region:	East Africa (Uganda, Tanzania, Kenya)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend : £2.77m	ODA: £2.77m / (budget adjusted in-year)			Non-ODA:
Start Date: June 2015		End Date: September 2021
Output					Score
Regional Research Unit (RRU) products generate gender and conflict sensitive evidence on the drivers of Violent Extremism and best practice in addressing Violent Extremism Gender Equality Markers.					A
National strategies written and joint working across government on CVE which include gender and conflict sensitive approaches through national, sub-national and local levels					B
Strengthened delivery on CVE programming by government and civil society, including National Counter Terrorism Centre and prisons.					B
Overall output score B
Outcome Assessment: / FY17/18 has mostly focused on understanding CVE and building evidence-based approaches drawn from implementation lessons and research. Implementation has been largely in Kenya. This is in line with expected outcomes.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	B	B	A
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme delivers CVE projects (in Kenya only), research into CVE and dissemination of that research and support to Kenyan and Tanzanian governments’ national strategies for CVE. The programme also provides ad hoc technical support to partners.

Summary of progress and lessons learnt/actions taken since last review

Following a review in late 2016, the programme was substantially refreshed in May 2017 to re-align the approach with research evidence. This redefined the target audience, and provided a clearer method to reach this audience. Therefore, although FY17/18 was essentially an inception phase some substantive results have still been achieved.

The programme strategy refresh built on recommendations from 2016, including building the capacity of local implementers, delivering CVE projects, embedding research in the community, encouraging networks, and sharing knowledge and learning at the community level. In 2017/2018 the British High Commission (BHC) funded a total of 14 grants to local implementing organisations through the programme; 13 in Kenya and one in Tanzania. Research has been used to better understand CVE, and create network and learning platforms for stakeholders, particularly at the local level in Kenya. Grant recipients showed high levels of knowledge relating to gender and conflict sensitivity. Research findings will help establish next steps in both Uganda and Tanzania.

Summary of recommendations for the next year

A more strategic approach to research will help ensure focus on policy related questions and help ensure wider learning and practical application.

A decision is needed on whether the programme is, or aspires to be, a regional programme. If this is not possible, then the Theory of Change and Results Framework (RF) should be adjusted. The team also needs to decide whether the programme is best managed from one country or not.

There should be greater consultation across UK Government stakeholders to assess how CSSF activity can complement and coordinate with other departments’ work’ at the national and policy level, taking into account the United Nations Development Programme’s recent lead in Kenya on national CVE strategy development.

The RF and indicators should reflect more clearly that the majority of resource (time, money) continues to be in Kenya. The RF for each component should fit more explicitly with the overall programme RF.

The programme needs to develop a clear partnership strategy with the implementer to clarify expectations and ensure all stakeholders fully understand the deliverables.

The programme needs to identify the best way to capture and assess learning from grassroots implementation approaches and how best to share this across the region without disturbing the current community engagement process.