Annual Review - Summary Sheet

PROGRAMME TITLE: IMPROVING AFRICAN RESPONSES TO CRISES
Country/Region:	EASTERN AND SOUTHERN AFRICA
HMG Partners / (LEAD in bold)	Ministry of Defence (MoD), Foreign and Commonwealth Office (FCO)
Total Spend:	ODA:£1.31m			Non-ODA: £3.67m
Start Date: April 2016		End Date: March 2019
Outputs					Score
Clear strategic direction for British Peace Support Team (BPST) in place for multi-year programme					B
African military and policing capacity and capability developed					B

Overall output score: B
Outcome Assessment: The outcome for this programme has been achieved: the Local Strategy Board (LSB) signs off an Africa Peace and Security (APS) multi-year programme, with strong evidence base, sound theory of change and appropriate management structure.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	B	B/A
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme provides support for the development of African military and policing capacity in regional and country-level institutions, through two military/civilian teams – British Peace Support Teams (BPST) - based in Kenya and South Africa. During the course of this financial year, BPST South Africa closed and staff were merged into the Kenya-based BPST. The programme funds Real Life Support (RLS) costs for UK military personnel, all costs for civilian advisers, and the costs of the training activities provided.

Training includes Mission Specific Training (MST) and Pre-Deployment Training (PDT) for African Troop Contributing Countries (TCCs) contributing to African Union (AU) and United Nations (UN) peacekeeping missions; and advisory, training and capacity-building support to regional training centres (principally those in Rwanda, Ethiopia, and Kenya).

Summary of progress and lessons learnt/actions taken since last review

The Local Strategy Board (LSB) was revived to provide clearer strategic direction through a single, coherent UK Government governance structure. It met three times, bringing in representatives from the two other LSBs which funded BPST in FY 17/18. These meetings made progress on strategy, governance and staffing issues.

The approach to Monitoring & Evaluation (M&E) and building an evidence base for BPST’s activities has improved. This has been evident in: the commissioning of specific research pieces on the capacity of selected militaries; the work of the newly recruited data analyst and efforts by BSPT to monitor and gather evidence more systematically of progress against indicators.

The recruitment of a programme manager and other new staff will enhance programme management capacity. Co-locating the programme team with the policy team in Addis has also yielded benefits.

The team has improved Value for Money (VfM), including recruiting a civilian advisor locally and reducing reliance on consultants.

Summary of recommendations for the next year

The programme needs to provide clearer management and prioritisation of BPST activities, better applying strategic direction from the three LSBs that fund the programme. This requires an honest broker function to balance LSB and departmental interests in BSPT’s work. This needs to include the prioritisation of BPST’s activities at the tactical level.

A single governance structure is needed for all BPST activity: The decision taken in FY 17/18 to retain Counter–Improvised Explosive Devices (C-IED) work under a separate CSSF programme should be reconsidered. Including C-IED work within the APS programme would drive CSSF coherence.

A discussion should take place during FY18/19 as to the overall direction of travel of the BPST as part of the UK Government’s Africa peace and security objectives. This needs to cover the balance between civilian and military activity and alignment to the Protection of Civilians (PoC) approach. It should also agree whether BPST should be a genuinely cross-HMG platform; and agree future approaches to supporting Regional Training Centre (RTC)/ Regional Economic Community (REC)/ Africa Standby Force capacity-building.

Maintain a concerted focus on achieving Value for Money in the procurement process. Activities should be charged where they fall between the three UK Government strategies that the BSPT delivers against.

Fully implement and refine the M&E feedback loop and evidence-gathering, with the support of the M&E consultants, expertise within BPST, and the UK Government network. The UK Government network can play a crucial role in providing feedback on the performance of TCCs and advising on the state of the institutional absorptive capacity of military structures in TCCs, and therefore the sustainability of tactical training beyond immediate deployments. Beneficiary feedback continues to be vital, with beneficiaries conceived as direct trainees as well as their governing institutions in the TCC itself.

Agree a Results Framework early in the programme cycle: this is essential to underpin in-year M&E and to capture the substance of BPST’s work.