Annual Review - Summary Sheet

PROGRAMME TITLE: Nepal Peacebuilding Programme
Country/Region:	Nepal
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID) & Ministry of Defence (MoD)
Total Spend :	ODA: £0.59m			Non-ODA: N/A
Start Date: April 2017		End Date: March 2020
Outputs					Score
Communities supported to collectively identify areas of local tension and work to resolve them across ethnicity and regions.					B
Political party representatives increasingly reflect the interests of their constituents					B
Increased capacity of human rights and media organisations strengthens accountability of state institutions.					B
Local research capacity is developed to generate knowledge and data for use in policy formulation and programmes					C
Overall output score					B
Outcome Assessment: / The potential contribution of the programme to the 1HMG Strategy – as originally conceived – is strong and the programme provides a good opportunity to leverage a coherent cross-government approach on one of the most important issues affecting Nepal’s longer-term stability, as well as to inform that approach. There is however a misalignment between the programme as originally designed (i.e. as laid out in the CSSF programme document and approved by the CSSF regional board) and the approach that the programme partners have designed to deliver the outcome. In addition, there are some question marks over the targeting of activities. Significant work is required on re-evaluating the theory of change and assumptions in order to build confidence in the ability of the consortium-led programme to deliver.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2017/18
Programme Score	B	B
Risk Rating	High

*output/outcome scores

What support is the UK providing?

The Nepal CSSF Peacebuilding programme aims to support the achievement of Objective 2 of the UK’s National Security Council Strategy (sub-objectives 2.1 and 2.3) – to reduce the risk of sub-national conflict, strengthen democracy and trust in the political settlement and improve accountability of state institutions – by working directly with affected communities and those in power to address the trust deficit and support confidence-building measures between minority groups and the political establishment.

The programme is led by the Foreign and Commonwealth Office, and its management is supported by two programme-funded posts. The delivery of the programme’s outputs and outcome is currently sub-contracted to an International Alert-led consortium of Non-Governmental Organisations (international and national).

Summary of progress and lessons learnt

The programme has encountered a number of challenges in its first six months of operation, with the announcement of the introduction of federalism coming shortly before the CSSF programme sign-off, and resulting elections taking place during the consortium’s inception period. The consortium has missed an opportunity to analyse and understand the implications of these changes (recognising that dynamics are constantly shifting) and to integrate implications into their programme design and approach. The consortium has proceeded with a heavy focus on activities which have left the British Embassy, Kathmandu (BEK), CSSF team (and wider UK Government stakeholders) with a sense of misalignment with UK Government objectives. So, whilst the consortium has managed to deliver a significant number of outputs within the first 3 months of implementation, continuation will largely have to be put on hold whilst the UK Government and the consortium take stock of the programmatic approach.

Lessons learned: It is still very early in the programme and, as such, the explicit lessons learned are still limited:

  1. Strategic: A greater focus on assessing the impact of federalism and how that change related to the consortium’s intervention design and the original programme document, would likely have prevented the need to pause the programme after implementation had started, which has ramifications for a wider range of stakeholders. BEK and the consortium need to learn from this experience as the project continues, in relation to prioritising analysis and research that can help shape (or validate) the programme interventions and being wary of focussing too much on results and finances at the expense of learning and adaptation.

  1. Design to implementation: Peacebuilding programmes are notoriously difficult to articulate succinctly, but efforts must be made to ensure a consistency in language to avoid differing interpretations between stakeholders of what will be delivered.

  1. Delivery: Enabling coordination between consortium partners requires strong governance structures at varying levels to sufficiently build on the synergies envisaged.

Summary of recommendations for the next year

Consider building the additionality element of the programme into the results framework itself to ensure that this remains a focus for internal programme staff, as well as project implementation leads – i.e. outputs of cross-government work (strategic & programmatic) and political work/influencing.

Create a structured mechanism for cross-government engagement on the strategic direction of the policy areas covered by this programme.

Focus on fixing the misalignment between the original programme document and consortium approach as a matter of urgency – further actions below at bullet 35. Consider slowing or halting activities whilst this process is ongoing.

Consider whether there are gaps in the approach between the programme document and consortium and if a separate strand of activity within the wider CSSF programme is needed.

Boost the UK Government’s understanding and analysis around the Constitution and ensure it remains an area for monitoring through broader (and regular) political economy analyses.

The consortium International Non-Governmental Organisation (INGO) leads need to provide more strategic guidance to the programme, including in their use of analysis and evidence – to retain a strong focus on the wider context – and its partners.

The consortium to complete mapping exercise of other peacebuilding projects/activities identifying any areas of potential synergy and complementarity and acting on them.

The consortium needs to draft an exit strategy or sustainability plan for the project.

BEK to update the results framework – outputs, indicators, milestones and targets.