Annual Review - Summary Sheet

PROGRAMME TITLE: North East (NE) Nigeria Security and Conflict and Stabilisation Programme
Country/Region:	Nigeria
HMG Partners / (LEAD in bold)	Ministry of Defence (MoD) , Foreign and Commonwealth Office (FCO), Department for International Development (DFID), National Crime Agency (NCA)
Total Spend :	ODA: £1.05m / (budget adjusted in year)			Non-ODA: £7.57m
Start Date: April 2016		End Date: March 2019
Outputs					Score
Armed Forces of Nigeria (AFN) demonstrate improved ability at the tactical level to outmatch Boko Haram.					A
AFN Institutions develop capacity to sustain and maintain operational capability.					A
AFN and Multinational Joint Task Force (MNJTF) conduct comprehensive, intelligence led, IHL compliant, combined joint and multi-agency planning.					B
Violent extremist organisations’ capability and intent, access to resources, and ability to exploit conducive environments are reduced across the Lake Chad Basin.					B
Strengthened government and community cooperation to counter violent extremism, reduced youth participation in violence, and better preparedness for reintegration processes.					C
Conflict sensitive re-integration of conflict affected people in their communities of origin across Borno State supporting reconciliation and healing.					A
Relevant Nigerian Government agencies and community leaders’ ability to re-integrate former low-profile BH adherents is enhanced.					A
Overall output score					A
Outcome Assessment: Violent extremist organisations’ attacks reduce and AFN achieve successful outcomes in military engagements thus containing the threat. Improved cooperation between government, security forces and civilians reduce violent extremism and promote reintegration. Insufficient evidence to say outcome is on track.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	A	A	B
Risk Rating	N/A	High	High

*output/outcome scores

What support is the UK providing?

The programme provides military training and capacity building support to the AFN operating in NE Nigeria facilitated by a British Military Advisory and Training Team (BMATT). Training and advisory support is complemented by a modest programme of non-lethal equipment gifting. The training covers basic infantry training prior to operations: including basic medical training, International Humanitarian Law (IHL) and Human Rights (HR) compliance education and Counter-Improvised Explosive Device (C-IED) awareness. The programme also supports small teams of UK military personnel who liaise with the Nigerian forces in the NE, develop situational awareness and work with regional and international partners to liaise with the MNJTF. The programme also funds training activity in Cameroon to improve the effectiveness of local personnel dealing with cross-border issues from NE Nigeria.

The programme’s non-ODA work on conflict management and stabilisation seeks to strengthen government and civil society led efforts to counter violent extremism; strengthening government and community cooperation; preparing for the reintegration of displaced populations and working with the Nigerian Federal Government on civilian protection in operations against Boko Haram. It also supports civil society groups to call for better protection measures. This complements MoD’s work with the Nigerian military.

Summary of progress and lessons learnt/actions taken since last review

The programme has made progress in looking at the effectiveness of activity and in improving impact and Value for Money. The programme is increasingly integrated and more aware of partner contributions. This “bottom-up” analysis is complemented by an ongoing Joint Analysis of Conflict and Stability (JACS), and NE Nigeria strategy review. Evidence of this increased coherence and purpose was noted throughout the review, but there is still room for improvement at the programmatic level.

The BMATT and other military personnel generally made progress on delivering core objectives. There was some evidence of improved prioritisation and focus on training more directly geared to objectives in the NE. Access to key Nigerian and regional military stakeholders remained a challenge. Gender work has stalled since FY16/17 although this area was being re-energised at the time of the review. Limited to ODA activity has been International Alert projects and a short surge programme with the International Organisation for Migration.

The UK Government team has improved its internal cohesion. The DFID humanitarian lead for NE Nigeria is working with the BMATT Civilian Military Co-operation lead on the delivery of training. Externally, coherence with partners has also increased. A military P3+ forum (UK, US, France and others), has improved information-sharing and scope for complementarity.

Summary of recommendations for the next year

The programme team should agree with cross-government colleagues a more detailed risks tool, given the Human Rights context. This should include new and emerging risks. There should be clear thresholds for escalation to senior governance structures and mitigating action. Existing Overseas Security and Justice Assistance assessments need to be used more actively.

The programme team should manage the Results Framework more closely to help build the programme narrative and articulate success for a cross-government audience. The recruitment of a civilian programme officer would help achieve this. There should be further work to better capture political access and influence. The team should develop a broad transition plan, agreed with the Nigerian military, for those areas where we expect AFN to assume full ownership in future.

The UK Government team should consider setting up a strategy implementation group that looks at all UK Government programmes active in the NE. This should focus on where more can be done to support the aggregation of outputs to achieve outcomes, recommend prioritisation and report against the impact of cross-government resourcing accordingly. The current balance of military programming should be considered to ensure maximum coherence between ODA and non-ODA parts of the programme and to help increase civilian primacy in the NE.

Financial management has been sound but departmental systems should work better with CSSF processes. The review team hope that sustained effort at the centre can deliver this.