Annual Review - Summary Sheet

Programme Title: Strengthening Security and Resilience in Sierra Leone and Neighbouring Countries
Country/Region:	Sierra Leone with benefits for Liberia, Guinea and region
HMG Partners / (LEAD in bold)	Ministry of Defence (MoD); Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £1.7m	Non-ODA: £1.36m
Start Date: April 2015		End Date: March 2019
Outputs				Score
Improved security sector governance including through development of leadership, internal accountability, financial management and handover of the Horton Academy (HA).				B
More effective and efficient security sector, including through improved cross-sectoral coordination, strengthened institutions, police-led internal security framework and community policing initiatives.				A
Increased security sector operational capacity and capability, including through strengthened readiness and resilience.				A
Overall output score:				A
Outcome Assessment: “Sierra Leone security sector is more balanced, professional, resilient and accountable, and more capable of delivering core tasks”. Progress on track.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	A	A	A
Risk Rating	N/A	High	Medium

*output/outcome scores

What support is the UK providing?

The programme supports the International Security Advisory Team (ISAT) which promotes security sector reform, and improved capability within the Republic of Sierra Leone Armed Forces (RSLAF), while replicating reforms in other parts of the security sector, and building strengthened crisis response structures with stronger civilian oversight.

ISAT largely funds and oversees operation of the Horton Academy, which provides staff training to the RSLAF, the Sierra Leone Police, the Office of National Security (ONS), and West African regional participants, with the aim of consolidating the Academy’s reputation as a regional centre of excellence, and its sustainability.

ISAT also provides support to develop core professional and management skills in the ONS and robust and efficient resource management across the sector. The programme's six advisers and the Head of ISAT advise and mentor senior security sector partners, develop leadership and management skills and professionalism, and influence and coordinate among international partners and the Government of Sierra Leone. ISAT advisers draw in trainers from a range of sources to meet needs.

Summary of progress and lessons learnt/actions taken since last review

This is an internally well-integrated, strategically-aligned and high-impact programme which delivers impact in the interests of Sierra Leone and the UK Government, and which this year demonstrated its value by contributing greatly to an appropriate response by the Sierra Leone security sector in a tense elections period. Now, with a new administration in place, is a chance to review the strategic direction.

ISAT has continued delivery of mentoring, advising and training activities, delivered timely support to elections security planning, police primacy for election security, and training in public order policing. Elections were largely peaceful and saw an orderly transfer of power. ISAT assistance was instrumental in ensuring a positive outcome. Some new work was successfully rolled out including the Community Policing project; ISAT alumni are also taking forward a review of the Sierra Leone Government’s Defence White Paper. Horton Academy alumni give the programme cross security sector and regional reach and impact. Extra funds in year were used well to support Horton Academy expansion and sustainability. Evidence for sustainability is coming through, with trainers cascading learning and taking on their own training of recruits. Support to the up-country Brigade Battle Schools (BBSs) was stepped up.

Work on gender across the board has been self-generated, innovative and impressive, e.g. gender workshops, a competence-based recruitment push, and a gender assessment in the RSLAF. This excellent activity is not captured in the Results Framework (RF) and could be profitably meshed with what others, especially DFID, are doing.

The ISAT team is now fully staffed, including the new positions of ONS Advisor, and Resource Planning Advisor. The team responded thoroughly to the recommendations of last year's Annual Review (AR), with work on options for police accountability activities; commissioning of a Joint Analysis of Conflict and Stability (JACS) and a renewed theory of change etc; and gender and AR implementation trackers. Value for money is good; demonstrating consistent use of low-cost, high-impact options. The team have leveraged CSSF funds by attracting funding and human resources from other donors (US) and regional partners (Nigeria, Ghana and the Gambia).

Summary of recommendations for the next year

Use cross-government political messaging with the new Government of Sierra Leone, highlighting the importance of dedicating adequate resources to security, encouraging greater local financial and administrative ownership.

In light of the JACS and Country Strategy review and the new Africa Strategy, review the strategic direction of the programme and its delivery, including detail on exit strategies and realistic timelines to withdraw from some strands of work, and contingency planning for options if progress is stalled.

Take forward options for rebalancing work within the security sector towards policing while remaining mindful that RSLAF remains a vital security anchor.

Develop closer joint working with DFID on gender, justice and public financial management.

Refresh the RF and programme documentation to clarify outputs and capture more of the impact of ISAT’s political access and influence. Seek more opportunities to highlight impact to London, and give a clear sense of the continuing risks.

Develop clearer future planning on the Horton Academy, making the case for expansion, and continuing to encourage sustainability and a conditions-based transition to RSLAF ownership.