Annual Review - Summary Sheet

PROGRAMME TITLE: Maritime Governance and Environment (MGE) - integrating elements of the Sustainable Economic Development (SED) and Sovereignty, Defence and International Obligations (SDIO) Programmes
Country/Region:	Overseas Territories (OT’s)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office, FCO / Maritime Coastal Agency (MCA), Department for Transport, / UK Hydrographic Office (UKHO), Ministry Of Defence / Department Environment, Food and Rural Affairs (DEFRA);
Total Spend:	Total ODA: / SED - £3.22m / SDIO -£3.456m / (Of which £4.04m spent on outputs contributing to restructured MGE programme)			Total Non-ODA: / SED - £7.84m / SDIO - £9.83m / (Of which £4.29m spent on outputs contributing to restructured MGE programme)
Start Date: July 2016		End Date: May/June 2020
Outputs (carried over into Maritime Governance and Environment Programme)					Score
Maritime Obligations; / 1.1 Legislative enhancement tools developed to improve convention compliance and extend international protection. / Capacity building activities undertaken to ensure convention compliance.					A
Search And Rescue (SAR) Capability; / 4.1 Number of completed SAR reviews					A
Hydrography and seabed mapping; / 1.3 Seabed mapping surveys conducted / 1.4 Number of territories with staff at Phase 1 of the International Hydrographic Organisation's capacity development model					A
Blue Belt; / 2.1 Surveillance and enforcement tools developed and advocacy conducted to support the OT ‘Blue Belt’ / 2.2 Large-scale management tools for Marine Protected Areas developed to deliver the OT ‘Blue Belt					B
Natural Capital / 1.1 Training delivered to enable OT professionals to update economic valuations, value maps, monitoring programmes and vulnerability assessments. / 1.2 Natural capital management & evaluation tools developed for each participating OT / 1.3 Outreach activities undertaken through: Consultations with outreach partners; Project planning and initiation; Output dissemination.					A
Biosecurity and invasive species; / 3.4 Invasive species eradication, prevention and management tools developed					A
Overall output score					A
Outcome Assessment:
Outcome Score: A			Risk: Med

Summary of Programme Performance (*output/outcome scores)

Year	2015/16	2016/17	2017/18*
Programme Score	N/A	A	A	A
Risk Rating	N/A	Low-Med	Med

What support is the UK providing?

The UK Government allocated £4.3m in FY 16/17 and £11.8m in FY 17/18 to its Sustainable Economic Development project to undertake activities that promote prosperity, economic development and job creation across UK Overseas Territories (OTs), with the stated aims of progressing OTs towards financial independence. The programme documents set out activities under two broad umbrellas: economic development and infrastructure (in Ascension, Anguilla, South Georgia and South Sandwich Islands (SGSSI) and the Falkland Islands); and environmental protection and economic development (including activities in support of HMG’s ‘Blue Belt’ commitment and other activities in support of OT’s environmental resilience).

A further £2.50m in FY 16/17 and £10.85m in FY 17/18 was allocated to the Sovereignty, Defence and International Obligations (SDIO) project to undertake activities that promote sovereignty, defence and international obligations across UK Overseas Territories (OTs). The programme is split into two areas of focus; (i) International obligations: IMO Instruments Implementation (III) Code, international health conventions, (ii) Sovereignty and security focussed: BIOT, Security Needs Assessment, Montserrat Patrol Vessel, Search & Rescue which links into the III Code, seabed mapping.

Summary of progress and lessons learnt/actions taken since last review

As a result of recommendations from the 16/17 reviews to; ‘Improve communications of the three CSSF programmes (and non CSSF) at the OT level….’ and to “Further develop programme cohesion and cross-programme cohesion where suitable…..’ the programmes have been rationalised into two; the Maritime Governance and Environment Programme (MGE) and the Justice, Security and Governance Programme (JSG).

Whilst the programmes themselves have been able to continue their work, the reorganisation of the programmes has had some impact on project documentation. This work is still under way as results frameworks and other documentation are merged into the two new headings. Some of the aspects of the former SDIO project especially have been removed from the new MGE heading and whilst this does improve clarity within the programme going forward, it has presented challenges in separating out some of the activities from the 17/18 review, which still largely reflected the former project headings. Programme management ownership does seem to have been addressed in line with previous recommendations.

Summary of recommendations for the next year

- The various elements of the programme across a number of different specialist fields and territories makes understanding the scope and nature of the programme, as a whole, challenging. Continue to review and rationalise the programme documentation including Theories of Change, Results Framework and trackers and Risk Registers in line with the revised MGE programme, to ensure overarching documentation is clear and reflects language within the individual project documents in order that the strategic intentions are easy to map against activity and spend (action ongoing).
- Ensure strong communication exists across all stakeholders and that there is a clear and shared understanding of different programmatic elements and the areas in which they complement each other, to achieve as much interoperability across the programmes as possible.
- A greater focus on seeking buy in from OT Governments to ensure key components of the programme are interoperable, at a policy level and operationally.

Cross programme coordination is a key element of any programme, especially when some of the equipment needs to undertake more than one task (the Montserrat MPV).