## Annual Review - Summary Sheet

PROGRAMME TITLE: Consolidating Democracy Programme in Pakistan (CDIP)
Country/Region:	Pakistan/South Asia
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £ 6.7m (FY17-18)			Non-ODA: N/A
Start Date: July 2016		End Date: March 2019
Outputs					Score
Election management and election oversight processes are more credible, transparent and inclusive. (40% weight)					A
Parliamentary processes are more inclusive, and Parliamentarians are more effective in holding government to account. (20% weight)					B
Political parties across the mainstream political spectrum better represent, respond to and deliver for their constituents. (20% weight)					A
Expanded democratic space allows improved policy dialogue, political debate and public discourse. (20% weight)					B
Overall output score: A
Outcome Assessment: Since the outcome level milestones do not occur during the review period, it is not possible to score the programme’s outcome this year.
Outcome Score: n/a for this year			Risk: Medium

Summary of Programme Performance
Year	2016/17	2017/18
Programme Score (Output)	A	A
Programme Score (Outcome)		n/a
Risk Rating	Medium	Medium

What support is the UK providing?

The expected impact of the “Consolidating Democracy in Pakistan (CDIP)” Programme is to contribute to Objective 3 (sub-objectives 3.1, 3.4) of the British High Commission Pakistan’s Integrated Delivery Plan (IDP). These objectives aim to support Pakistan’s democracy to be more inclusive and effective by helping strengthen Parliament, improving electoral processes, and providing training for political parties. It exists within a broader framework of the UK’s cross-departmental programming, bilateral political engagement and interventions from other development partners and diplomatic missions. The CDIP is managed by the United Nations Development Programme (UNDP) and Development Alternatives International (DAI).

Summary of progress and lessons learnt/actions taken since last review

Elections
- Establishing the first donor-Election Commission of Pakistan (ECP) Steering Committee to enable efficient donor coordination on electoral support.
- Fostering strong partnerships and access with key government counterparts and institutions such as ECP, National Database and Regulatory Authority (NADRA), parliamentary bodies and the political parties.
- Developing a comprehensive training plan for elections polling staff, especially to ensure sustainability in the ECP elections academy and to integrate the implications of the new elections law. Supporting ECP in conducting by-elections and the senate elections.
- Implementing the first gender strategy at the ECP, to help address gender mainstreaming in the current elections and beyond.
- Meeting technical assistance demands of the ECP on areas such as monitoring capacity, Communication Strategy and other aspects of Elections Management.
- Engaging a wide constituency of political parties, parliamentarians, civil society and other arms of government on the issue of women’s participation and registration gaps. Facilitation of the first dialogue of political parties and the ECP on voter registration of women.

Parliament
- Developing a strong partnership with the Pakistan Institute of Parliamentary Studies (PIPS) to provide institutional support to Federal and Provincial parliaments, including training and capacity building for Parliamentary committees, with continued support to Khyber Pakhtunkhwa and Baluchistan Assemblies.
- Setting up the Parliamentary Support Group (PSG) as the first forum of its kind to coordinate parliamentary support across the sector.
- Holding the first inter-parliamentary dialogue on Sustainable Development Goal 16 (SDG16), which will be further leveraged through civil society grants under output 4.

Political parties
Providing information sessions to 13 political parties to boost their policy capacity enabling them to better understand and engage on key aspects of the 2017 Elections Act, UN Sustainable Development Goals, as well as on issues of women’s political participation.

Democratic space
- Reaching out to more than 16,000 citizens directly for civic education under the United Nations Volunteers (UNV) component.
- Setting up the Innovation and Research Fund (IRF) as a mechanism to mobilise small grants to civil society organisations and other citizen groups, focusing on the new SDG 16 as a coherent advocacy agenda.

Programme approaches
- Piloting live Political Economy Analysis as a case study of ‘thinking and working politically’ though adaptive programming.
- Developing an overarching narrative for SDG 16, to help the programme test and analyse how activities and data collected contribute to monitoring of SDG 16 – with Pakistan as a case study.

Summary of recommendations for the next year

Mainstream Political Economy Analysis (PEA): The programme has piloted an innovative approach to using robust PEA to adapt and flex programme interventions. The PEA needs to systemically identify incentives and interests across outputs.

Improve strategic focus: The programme needs a strategic forward look in three areas of assessment: a) readiness for the elections b) longer-term goals for a programme of this nature c) longer term goals beyond this programme and future work in support of the UK Government objectives of supporting democracy and stability in Pakistan.

Improve coherence across the outputs: Barring a couple of examples, the programme needs to demonstrate better coordination and integration across outputs. Both the leadership and output leads need to play a greater role to ensure read-across and cross-fertilisation. While the leadership and pace of delivery has improved in recent months, the programme also needs improved international technical expertise to quality assure strategic thinking and key deliverables.

Improve coordination between partners (UNDP and DAI): Although strategic level coordination is satisfactory for the elections strand (output 1), programme interventions need to demonstrate more coordination at an operational level, particularly across the parliament and democratic space strands.

Commission an impact evaluation: The programme has a good monitoring, evaluation and learning framework, to generate evidence but learning, application and dissemination need to be better addressed through an updated Monitoring, Evaluation and Learning (MEL) strategy and an Impact Evaluation. The evaluation will also be useful to monitor progress at outcome level.

Strengthen the overarching narrative: Based on the points above, and more generally, implementing partners need to pull together a clear overall narrative for the programme. As an integrated political governance programme, the programme has an opportunity to share lessons for the new SDG 16.