Annual Review - Summary Sheet

PROGRAMME TITLE: CARIBBEAN SERIOUS ORGANISED CRIME PROGRAMME
Country/Region:	Caribbean/Americas
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO);National Crime Agency (NCA), Crown Prosecutions Service (CPS); Immigration Enforcement International (IEI (HO)); Border Force; ACRO Criminal Records Office (HO); Department for International Development (DFID); Ministry of Defence (MoD)
Total Spend:	ODA: £4.13m			Non-ODA: £0.21m
Start Date: April 2015		End Date: March 2020
Outputs					Score
CPS Criminal Justice Advisor (Jamaica)					B
Home Office (ACRO) Support to Digitization of Jamaican Police Records					U
Assistance to Anti-Organised Crime Policing in Jamaica					B
Jamaica Strategic Corrections Partnership Project (DFID)					A+
MoD led Maritime Skills and Leadership Training (Regional)					U
Enhancement of Fusion Centre Capacity (Barbados) in Digital Forensics					A
HO/IEI Deployment to Joint Regional Communication Centre in Barbados					A
CPS Support to Eastern Caribbean Serious Organised Crime (SOC) Processes (esp. Asset Recovery) (Barbados)					A
Border Force Secondment to Caribbean Customs Law Enforcement Council (St. Lucia) and Regional Capacity Building (Trinidad)					U
Support to Guyanese Serious Organised Crime Unit					B
Security Sector Reform, Guyana (FCO)					A
Assistance to SOC Operations in Dominican Republic					B
Overall output score					B
Outcome Assessment: CSSF resourced activity very unlikely to meet the three programme outcomes as currently constituted
Outcome Score: C			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	C	B	C
Risk Rating	Unknown	UKN	UKN

*output/outcome scores

What support is the UK providing?
Across the Caribbean, the CSSF SOC programme provides funding for a range of different activities within the security and criminal justice sectors that seek to enhance the capacity of host governments to tackle the threat posed by Serious Organised Crime both individually and as a region. These activities are intended to improve the stability of the host nations, reduce the threat to the UK emanating from the Caribbean and protect UK interests in the region.

Summary of progress and lessons learnt/actions taken since last review
- Since the last annual review, serious efforts have been undertaken in London to enhance the evidential base underpinning the programme and to draw the various strands of programming together.
- A number of new programme documents were produced and new analysis undertaken. This included the production of a theory of change (ToC) and a new results framework. A Serious and Organised Crime Joint Analysis was also completed, which will guide the focus of further SOC support in the region.
- Quarterly Reporting has been prioritised and is now of a higher quality.
- The recently updated documents have not yet led to more joined-up programming across the region. This is in part because they are not yet fully inclusive of all UK Government activity with some areas of activity not yet included in the ToC or the results framework; in part because ownership of the CSSF strategic direction rests in London, not at post; and in part because they were only recently developed. It is recognised that Hurricane Irma and the resulting CSSF-led crisis response is also a major reason for this delay as effort was diverted to dealing with the crisis.
- The Programme Team recognised the need for additional capacity at post. A D6 Head of CSSF was recruited and will deploy in July. During the year a locally employed CSSF project officer was also recruited in Guyana and greatly strengthened the capacity of the British High Commission to oversee CSSF.
- Departments have recognised the need to improve programme management skills and key programme management staff have attended the three day CSSF programme management training. This has increased willingness and awareness of how to improve CSSF programming but still too many activities suffer from a lack of documentation setting down what they are intended to achieve, why, and how CSSF funding complements departmental core activity and contributes to a coherent UK effort to combat SOC in the region. Until there is a systematic approach to joining up UK work and using CSSF to enhance this, there is a strong risk UK-supported work will not lead to long-term sustainable change.

Summary of recommendations for the next year
- In line with CSSF best practice, and to drive better programme coherence, decentralised CSSF governance within the region should be established under a Local Strategy Board (LSB) under FCO leadership. The LSB should have delegated authority for an approved level of spend. The incoming Head of CSSF should be asked to draw up a series of options for local governance for discussion and ultimate approval at the Americas Regional Board.
- Review and potentially increase locally employed CSSF staffing.
- A Serious and Organised Crime Joint Analysis has recently been undertaken to update UK understanding of threats in the region. This should be used as the basis to refresh the programme theory of change;
- Combined with the above, take advantage of the forthcoming deployment of a SOCNet coordinator and the Head of CSSF Programming to drive a new effort to join up UK Government activity (including that undertaken by non-CSSF spending departments) to combat SOC in the region and then clearly articulate how CSSF can contribute and value to that – particularly through incentivising joint work and long term capacity building;
- Where not currently doing so, all spending departments must provide supporting documentation setting out where, what and why of their CSSF work within a suggested two months of receiving this review. CSSF funding should be withdrawn from those that do not comply. Of particular urgency is the need to have departmental Overseas Security and Justice Assistance documentation (or equivalents) approved and returned to the Programme Senior Responsible Officer (SRO) within one month of the date of this review.
- Simultaneously, the SRO should seek guidance about the correct process for producing OSJAs for the programme as the current approach seems inconsistent with CSSF guidance. The SRO should report back to the Board on his findings within one month of the date of this review.
- Contract gender expertise to conduct a gender review of all CSSF work to identify how the programme may better comply with the 2014 Gender Act within FY 18/19.