Annual Review - Summary Sheet

PROGRAMME TITLE: Peru and Colombia: Serious and Organised Crime
Country/Region:	Peru and Colombia
HMG Partners / (LEAD in bold)	National Crime Agency (NCA) / Crown Prosecution Service (CPS)
Total Spend:	ODA: £2.29m			Non-ODA: N/A
Start Date: April 2015		End Date: March 2020
Outputs					Score
Output 1: Cross-Criminal Justice Sector Coordination					A
Output 2: Reformed Institutions					A
Output 3: Enhanced Tactical and Technical Capacity in Tackling Priority Crimes					A
Output 4: Corruption					B
Overall output score					A
Outcome Assessment: / Outcome 1: Improved coordination between key criminal justice stakeholders – likely to be partially met (B) / Outcome 2: Reformed criminal justice institutions – likely to be partially met (B) / Outcome 3: Improved technical and tactical ability in key thematic areas – likely to be met (A) / Outcome 4: Enhancing Colombian and Peruvian anti-corruption capacity – likely to be partially met (B)
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A/B	A	A	B
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The Peru/Colombia Serious and Organised Crime (SOC) programme aims to reduce the threats to the UK emanating from Peru and Colombia by supporting the criminal justice systems in both countries to make sustainable progress in tackling SOC. The programme is structured to deliver results towards four intended outcomes:

Outcome 1: Improved coordination between key criminal justice stakeholders
Outcome 2: Reformed criminal justice institutions
Outcome 3: Improved technical and tactical ability in key thematic areas
Outcome 4: Enhancing Colombian and Peruvian anti-corruption capacity

The programme complements and, in some cases, builds on other pre-existing SOC support provided by the UK Government. In 2017/18, the programme also began to support SOC activities aimed at directly supporting the Government of Colombia (GoC) to implement the Colombian peace process.

Summary of progress and lessons learnt/actions taken since last review

The programme made important progress towards all four outcomes over the last year:

- Under outcome 1, the programme supported the launch of the Criminal Justice Monitoring Unit (CJMU) in Colombia, and began to design a project for the development of a Delivery Unit at the Fiscalía (the local equivalent of the Crown Prosecution Service) in Peru.
- Under outcome 2, the programme supported leadership training to enable the Peruvian National Police (PNP) to roll out reform initiatives; a process mapping of the Colombia Fiscalía’s investigative processes; and the establishment of the Office of Strategic Analysis in Peru’s Fiscalía, which is producing high-quality analysis to inform decision-making and reform priorities.
- Under outcome 3, the programme supported the training of specialised units in Peru and Colombia on advanced operational practice and protocols, made significant progress towards embedding a financial crime approach in Peru’s and Colombia’s Fiscalía’s SOC investigations; and provided training to crime scene investigators in Peru on enhanced forensic investigation skills.
- Under outcome 4, the programme supported the Office of Institutional Integrity in Peru to review and develop plans to improve their processes and procedures for investigating police corruption.

Summary of recommendations for the next year

The programme should be rationalised to only support activities, which are likely to have a strategic, catalytic, and sustainable impact on the capacity of the Governments of Peru and Colombia to prevent and respond to SOC.

Any training support provided by the programme should be (a) directly and explicitly linked to upskilling criminal justice institution staff to deliver planned reforms or strategic priorities, and (b) designed within and delivered by existing training institutions.

Any future anti-corruption assistance in Colombia should be developed in line with CSSF principles

The programme team needs to develop evidence-based theories of change, one for Peru and one for Colombia, which should then inform the develop the production of country-specific results frameworks.

The UK should dedicate time and resources to engage with the judiciary to explore entry points for UK support.

The SOC programme team should develop a programme level gender strategy.