Annual Review - Summary Sheet

PROGRAMME TITLE: Conflict, Security and Stability Fund (CSSF) – Central Asia Programme
Country/Region:	Central Asia (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, Uzbekistan)
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD), National Crime Agency (NCA)
Total Spend 17/18:	ODA: £3.93m			Non-ODA: £0.15m
Start Date: April 2017		End Date: March 2020
Outputs
Promoting independent narratives, security partnerships and governance models
Strengthening resilience to conflict and improving inter-ethnic and cross-border relationships
Understanding violent extremism and preventing nationalist-driven conflict amongst vulnerable youth and migrants
Overall output score					A
Outcome Score: B			Risk: low / medium

Summary of Programme Performance
Year	2015/16 (DFID projects)	2015/16 / (FCO & NCA projects)	2016/17	2017/18
Programme Score	A+	A	B	A	B
Risk Rating	Low/medium	Low/medium	Low/medium	Low/medium

What support is the UK providing?

During 2017/18, the CSSF Central Asia programme spent around £4m across nine projects in five countries. These projects aimed to: support alternative narratives and countering disinformation from malign influences; strengthen resilience to conflict and improve inter-ethnic and cross-border relations; and address marginalisation through understanding violent extremism and prevent national-driven conflict amongst vulnerable youth and migrants.

Specific projects supported: media plurality and literacy in the region; a collaborative research study on the nature and extent of radicalisation of Central Asian migrants in the Russian Federation; enhanced rule of law reform in Kyrgyzstan; media capacity building in Uzbekistan; improved stability and resource management in Tajikistan and Kyrgyzstan; Tajik-Afghan integration, resilience and reform in Tajikistan; increased resilience of youth for peaceful and inclusive communities in Kyrgyzstan and Tajikistan. The programme also supported development of military ability to engage in international peacekeeping efforts (mainly in Kazakhstan), and efforts to build coalitions around tackling organised crime and corruption throughout the region.

Summary of progress and lessons learnt/actions taken since last review

Strategy & priorities. The UK National Security Council (NSC) Strategy for Central Asia was refreshed in May 2017 and a Joint Analysis of Conflict and Stability (JACS) review was launched in early 2018. Updates were also made to the results framework and theory of change.

Governance. Steps have been taken to ensure that the Strategy Board’s chair and regional Portfolio Manager steer the board towards providing inputs at more strategic, policy and programme levels.

Results framework & theory of change. The results framework was revised to better reflect the programme and streamlined to show greater coalescence around fewer outcomes. Further work is needed on the theory of change in communicating the programme’s theoretical and causal underpinnings.

Uzbekistan. Scoping work was done in Uzbekistan, with agreed decisions to up-scale the UK’s support for Uzbek reform during 2018/19.

Balance long-term funding with space for responsive risk-taking. The programme continues to include multi-year projects for longer-term impact while funding shorter-term projects on reform and alternatives.

Conflict sensitivity. Implementing partners have been requested to report regularly on conflict sensitivity, which will inform programme-level conflict sensitivity. The JACS refresh, noted above, was also undertaken but not within sufficient time to allow its findings to inform next year’s programming.

Gender. A gender audit was recently conducted which identified short-comings in the programme’s gender sensitivity. Limited further pro-active steps have been taken to ensure gender sensitivity is practically mainstreamed in the programme.

Value for money. Efforts were taken to ensure that projects report on VfM.

Summary of recommendations for the next year

Governance: Maintain the revised Central Asia Strategy Board system given its greater effectiveness, including a permanent senior chair.

Strategy: Given the unpredictable environment and potential for further change, the CSSF in Central Asia will need to maintain a degree of flexibility even as this renders multi-year programming more challenging.

Management: Streamline the process to ensure that centrally identified objectives are communicated effectively to the programme team, with versions appropriate for partners to ensure that all elements of the programme’s implementation are strategically aligned and clear on their objectives.

Design: The programme’s theory of change should be strengthened to reflect a greater level of coherence as a regional programme built around its three strands, reflecting greater horizontal symmetry amongst projects (where appropriate), collaboration amongst other allies or partners, and the delicate balance that the programme has done well to maintain between shorter-term tactical projects and longer-term strategic impact projects.

Conflict sensitivity: Build greater conflict sensitivity across the programme. An updated understanding of the drivers of conflict and stability should be incorporated into future programming (e.g. the 2018 JACS exercise) including in Countering Violent Extremism (CVE) / Preventing Violent Extremism (PVE) and the threat that radicalisation poses to regional stability and the UK.

Gender: Include gender sensitivity across the programme by incorporating the findings from the recent gender audit into project- and programme-design elements so that the programme mainstreams gender sensitivity and complies with the International Development (Gender) Act 2014.

Technical support: Greater support on gender and conflict sensitivity is required from London to ensure that the programme has the necessary technical expertise (to ensure that critical cross-cutting elements of the programme are robustly built into the programme’s structure.

Monitoring & Evaluation (M&E): Strengthen the programme’s M&E systems by developing a stronger and more coherent programme results framework that reflects the complete programme’s impact and reflects a strengthened theory of change. This should include access to on-going technical M&E capacity to support these improvements.

VfM: Develop a Value for Money (VfM) framework with clear measurable indicators for economy, efficiency and effectiveness that can be monitored on a consistent basis and that aligns with the programme’s results framework.