Annual Review - Summary Sheet

PROGRAMME TITLE: Eastern Partnership
Country/Region:	Caucasus, Moldova and Belarus
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD)
Total Spend 17/18:	ODA: £3.2m			Non-ODA: £0.37m
Start Date: April 2017		End Date: March 2018
Outputs
Improving effectiveness and transparency and accountability of government security sectors
Countering and reducing the effect of destabilising disinformation
Increasing the space for constructive dialogue on conflict resolution
Reducing the isolation and vulnerability of conflict-affected societies
Overall output score:					A
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A	A
Risk Rating	High	Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme delivers projects in the Caucasus (Georgia, Azerbaijan, Armenia), Moldova and Belarus. The largest footprint is in Georgia, which also hosts the Tbilisi Hub. The programme responds to the Eastern Partnership (EaP) National Security Council strategy by supporting stability, reform and resilience and is split across two strands and four priority themes (a third strand, focused on economic reform, is addressed by the Good Governance Fund which is outside the scope of this review): / Improving effectiveness, transparency and accountability of government and security sectors including by support for reform focused on human rights. / Countering and reducing the effect of destabilising disinformation mainly through the promotion of independent media outlets. / Increasing the space for constructive dialogue on conflict resolution by supporting dialogue mechanisms, inter-community initiatives and confidence-building measures for officials and civil society. / Reducing the isolation and vulnerability of conflict-affected societies by addressing socio-political and economic challenges affecting communities in conflict-affected areas.

Summary of progress and lessons learnt/actions taken since last review

This is a good programme and there is clear evidence of significant value-add in the first full year of the Hub structure. Programme management is of good quality; and the Hub is providing a good service in driving standards. Standardisation of project documents is supporting project officers and improving consistency. All projects have a clear link to strategic objectives and are delivering results effectively; implementing partners are high quality. Last year’s review provided a number of recommendations:

Ensure the level of reporting is consistent across all programmes and seek more impact-focused reporting: The introduction of standardised reporting has improved the consistency of reporting and provided a strong tool for challenge and quality assurance. The Hub and project officers are now driving better quality, impact-focused reporting, with some room for improvement in areas of monitoring and evaluation Monitoring and Evaluation.

Look to develop impact indicators to allow easier tracking of the value of the whole programme: While there is evidence of some work to address this, indicators at outcome level remain too output-focused and specific to individual projects. Whilst a challenge to a programme spread across a broad region and with a modest budget, the Hub should continue to pursue this objective and consider the use of conflict analyses and formal evaluations to produce more systematic evidence of strategic affect at outcome and impact level.

Make greater use of M&E experience in the CSSF network: The review considers there remains room for improvement in M&E. Technical expertise would support this.

Streamline the programme into fewer projects: The review feels that there is strong evidence of a positive trajectory in this area and that all projects have a clear link to the strategic objectives set.

Seek to upscale funding for the 2017-18 financial year cycle, considering carefully issues of scale and where the programme is most likely to make a strategic impact given the limited funds available. This review strongly endorses the finding of the previous review that there are opportunities to exploit both scale and emerging opportunities that warrant additional resources for this programme.

Begin as many projects as possible at the very beginning of the financial year: This remained a challenge during the review year, although the vast majority of projects were able to deliver within the financial year. In the 2018-19 financial year this will be further improved. Moving to multi-year proposals with break clauses may reduce the burden at the design and mobilisation stages of the project cycle and improve continuity.

The review still assesses that the absence of a conflict advisor is a challenge for this programme. This is outside of the programme team’s control and, in Georgia, steps have been taken to monitor conflicts through political reporting.

Carry out a Joint Assessment of Conflict and Stability, and use this and other conflict analysis to ensure programming is effective and does no harm: This had not taken place in the review period but is imminent. The review recommends that the analysis consider producing indicators that will help track conflict dynamics.

Continue plans to deliver gender analysis: A Gender audit has completed recently; though the final review has not yet been published. As a result, this review did not focus on gender in detail.

Continue coordination between the Hub in Tbilisi and spoke embassies, with the Hub mentoring, cascading knowledge and facilitating training: The review team saw substantial evidence of the Hub coordinating with spoke embassies: providing quality assurance, driving standards and promoting knowledge and skills development.

Develop communications strategies for each project: Programme staff were proactive in identifying and exploiting communications opportunities where appropriate and the Hub were looking for ways to improve internal communications.

Summary of recommendations for the next year

This review provides a number of recommendations for continuing development in the following areas:

Resource/budget: the programme should continue to seek additional resources. This review strongly endorses a view that additional resources would enable the programme to take advantage of opportunities presented by scale and provide flexibility to respond to emerging dynamics, both of which could deliver results against objectives.
Strategy and Analysis: Conflict analysis to identify, target and monitor change to conflict drivers in the region is essential in order to support effective targeting of limited resources and to provide greater evidence of impact.

Monitoring and Evaluation: the programme should reconsider the design of the results framework to simplify output-level targets; to increase the relevance of outcome targets to the strategic objectives of the programme; and to incorporate multi-year assessment wherever feasible.

Risk Management: the Hub should consider how to manage project-level risks in aggregate; and whether more targeted, thorough risk management tools in some areas would provide value.

Financial Management: this programme is delivering good value for money, but may consider producing standardised guidance for budget scrutiny to project officers. There is scope to increase fiduciary risk management through the use of independent audits.

Role of the Hub: the Hub is demonstrating significant value by driving standards and facilitating cross-network skills exchange. The Hub should consider how to help project officers to access expertise in key technical areas.